## BB review introduce
Review purpose | 3T Gerber out Review，特别是for 主板 | Version | Remark | Writer | Modify date
BB review 状态更新及检查时间点 | 最迟发板前一个工作日（可以提前查看，并根据内容安排对应事宜） | V0.1 | First release | Wenting Chen | 2023-10-23
BB review 相关各文件的review触发时间建议 | BB OD review：启动时间：concept ,close时间：EVB发版前。 后续每个阶段只针对收到的CR change 进行OD 和 对应设计确认，如没有变化就默认N/A BB review checklist-启动时间：原理图V0.9开始就可以启动（placement 基本上lock了，准备开始走线了 ）。close时间：最迟EVT发版前。后续阶段不再跟踪 BB Simulation review：EVB发版前，EVT发版前，DVT1 发版前 原则上都要pass 。后续阶段不再跟踪 SCH change review：从EVB开始所有阶段发板都需要review PCB change review：从EVB开始所有阶段发板都需要review Test case review：从EVT开始所有阶段发板都需要review BB Issue：从EVB开始所有阶段发板都需要review（包含issue 和risk的确认）
Conclusion判定准测参考 | Issue 比重最大，如果是High RISK，发板review conclusion 即为High Risk。 Simulation 作为过程控制，一般不block 发板，持续优化，如果已确认是大问题，转到issue中并给优先级别判定。 其他review项主要以完成度来判定，如果没有按时完成，就转RISK。
BB issue 判定规则参考 | S1 : Block Gerber out &Solution Not Validated S2 : Not Block Gerber out but Solution Not Validated S3 : Not Block Gerber out &Solution RD Validated 补充说明：RISK 类型的case，都统一先放S3.如果需要升级优先级别，再改状态

## BB Review-XM one page
Project | Stage | OD/Change | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case@Block PCB | Issue@Block PCB | Gerber Out Conclusion | BB issue comment | Solution/Change | platform Vendor review ? | CAD PCB review checklist
Aviator | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Aviator | EVB | Pass | Low Risk | Middle Risk | Pass | Pass | N/A | N/A | Go
Aviator | EVT | N/A | Pass | Low Risk | Pass | Pass | N/A | Low Risk | Go
Aviator | DVT1 | N/A | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Aviator | DVT2 | N/A | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Aviator | PVT | N/A | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Terrain | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Terrain | EVB | Pass | Low Risk | Working | Pass | Pass | N/A | N/A | Go
Terrain | EVT | N/A | Pass | N/A | Pass | Pass | Low Risk | Low Risk | Go
Terrain | DVT1 | Pass | Pass | Pass | Pass | Pass | Low Risk | Low Risk | Go
Terrain | DVT2 | Pass | Pass | Pass | Pass | Pass | Pass | Low Risk | Go
Terrain | PVT | N/A | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Dallas | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Dallas | EVB | Pass | Pass | Low Risk | Pass | Pass | N/A | N/A | Go
Dallas | EVT | Pass | Pass | Pass | Pass | Pass | Low Risk | Low Risk | Low Risk
Dallas | DVT1 | Pass | Pass | Pass | Pass | Pass | Low Risk | Low Risk | Low Risk
Dallas | PVT | Pass | N/A | N/A | Pass | Pass | Pass | Pass | Go
Equator | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Equator | EVB | Pass | Low Risk | Working | Pass | Pass | N/A | N/A
Equator | EVT | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Equator | DVT1 | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Equator | DVT2 | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Equator | PVT | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Prado | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Prado | EVB | Pass | Low Risk | Low Risk | Pass | Pass | N/A | N/A | Low Risk
Prado | EVT | Pass | Pass | Pass | Pass | Pass | N/A | N/A | Go
Prado | DVT1 | Pass | Pass | Low Risk | Pass | Pass | Pass | Pass | Go
Prado | DVT2 | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Prado | PVT | NEW | N/A | N/A | NEW | NEW | NEW | NEW | NEW
Houston | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Houston | EVB | Pass | Low Risk | Low Risk | Pass | Pass | N/A | N/A | Low Risk
Houston | EVT | Pass | Pass | Low Risk | Pass | Pass | Low Risk | Low Risk | Low Risk | Bringup：Flash LED & SOIS ongoing ，low risk Flicker sensor RISK：AP&ADSP design compatible design into EVT PCB
Houston | DVT1 | Pass | Pass | Pass | Pass | Pass | Low Risk | Low Risk | NEW
Houston | DVT2 | Pass | Pass | N/A | Pass | Pass | Pass | Low Risk | Low Risk
Houston | PVT | Pass | N/A | N/A | Pass | Pass | Pass | Pass | Go
Wrangler | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue
Wrangler | EVB | Pass | Low Risk | NEW | Pass | Pass | N/A | N/A | Low Risk | memory layout review not completed
Wrangler | EVT | Pass | Pass | Low Risk | Pass | Pass | Pass | Pass | Go
Wrangler | DVT1 | Pass | N/A | Low Risk | Pass | Pass | Low Risk | Low Risk | Low Risk
Wrangler | DVT2 | Pass | N/A | N/A | Pass | Pass | Low Risk | N/A | Go
Wrangler | PVT | Pass | N/A | N/A | Pass | Pass | Pass | Low Risk | Low Risk
Manaus NA | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue |  |  | Solution/Change
Manaus NA | EVB | Pass | Pass | Low Risk | Pass | Pass | N/A | Pass | Go
Manaus NA | EVT | Pass | N/A | Low Risk | Pass | Pass | Pass | Low Risk | Low Risk | EVB3 NEW camera bringup issue：change PCB & monitor
Manaus NA | DVT1 | Pass | N/A | Pass | Pass | Pass | Low Risk | Low Risk | Low Risk
Manaus NA | DVT2 | Pass | N/A | N/A | Pass | Pass | Low Risk | Middle Risk | Middle Risk | DVT1 camera noise issue
Manaus NA | PVT | Pass | N/A | N/A | Pass | Pass | Pass | Low Risk | Low Risk
Boston | Doc link | BB OD | BB review checklist | BB Simulation | Sch Change | PCB Change | Test Case Review | BB Issue |  |  | Solution/Change
Boston | EVB | Pass | Low Risk | Middle Risk | Pass | Pass | N/A | Pass | Go
Boston | EVT | Pass | Pass | Low Risk | Pass | Pass | Pass | Pass | Go
Boston | DVT1 | Pass | N/A | Pass | Pass | Pass | Low Risk | Middle Risk | Middle Risk | camera power noise issue：change PCB & monitor
Boston | DVT2 | Pass | N/A | N/A | Pass | Pass | Pass | Low Risk | Low Risk
Boston | PVT | Pass | N/A | N/A | Pass | Pass | Pass | Low Risk | Low Risk