## Copperfield (hidden)
Date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
20170401 | C.RAMP | 6.Display/Touch | 5.6 User Feedback | S2 | Closed | Issue：India market When put the “Fail headset” JBL PUREBASS T150A into Moto G5 plus ，there will be some action similar to Ghost Touch. Jira link:https://idart.mot.com/browse/IKSWN-27437 | link | SW/chenwt
20161118 | 7.DVT2 | 2.Power | 5.3 EE DVT | S3 | Closed | Issue:ALT DVT2B发现正面朝下自动关机 Root Cause: Analysis: Solution: Verification: Plan: | link | 肖志浩/Chenwt
20170113 | B.PVT | 1.Platform | 4.Build | S2 | Closed | 下载工位出现概率性不下载（faboot 识别不到USB） | link | xiaozh/chenwt/chenhy
20161101 | 7.DVT2 | 4.Audio | 4.Build | S2 | Closed | GSM buzz in DVT2B units found | link | 肖志浩/李燚
20161118 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | Closed | DVT Mdu30 ：thermal test ,Video recording reach 44.2 degree | link | 陈文亭/吴学敏
20161118 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | DVT EDu14- Surge test (L)，charge 按印度规fail，90V无法开机。需要过120V | link | 肖志浩
20161208 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S2 | Closed | Description :Turbo charger always not charging after charging a little time | link | 陈文亭/肖志浩
20161118 | 7.DVT2 | 2.Power | 5.3 EE DVT | S2 | Closed | ALT Battery current drain out of spec. |  | 陈文亭
20160901 | 5.DVT1 | 3.Charging | 5.2 BB Test | S2 | Closed | Weak 5W charger can not charge | Link | 陈文亭
20161101 | 7.DVT2 | 1.Platform | 5.3 EE DVT | S1 | Closed | ALT & DVT滚筒实验出现 LTE no camp | link | 范立锋/chenwt
20161208 | B.PVT | 7.Sensor | 4.Build | S2 | Closed | 3rd P-sensor CT too low and can not pass APK test | link | 陈文亭/陈怀玉

## Ashley (hidden)
Date | Phase | Source | Severity | Status | George Issue | Analysis&Solution | Owner

## Artura
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2026-05-09 | 4.EVT | 12.EMC | 5.4 ALT | S2 | Open | Issue: EVT 一供 WH208009，AD: -15kV Zone1 Proximity & Front Light Sensor No Function, 实验室反馈重启未恢复。 Analyze: 1. 机器收到校验CQA中：Proximity 闪退, Front Light 不刷新，现象一致，从现象来看像是器件不识别到I2C设备。但是重启后可以恢复。 2. 抓机器Log，给软件分析：IKSWW-203359，分析结果是I2C通讯异常，判断IC被干扰异常导致无法进行I2C通讯，需要下电才能复位（I2C总线没问题） 3. XM实验室尝试复现：Zone1/通话/-15kV 200次暂未复现，但是发现实验室回来这台机器，打Zone1容易触发屏幕Recovery机制。 4. 测量VIO18_PMU，发现reboot过程确实不会下电，只有PowerOff会下电；—— 提交CR给软件，看能否实现reboot过程VIO1.8下电。 5. Vendor 分析，出现这个问题有两种可能：a) 芯片I2C被干扰到其他ADDR；b) 芯片假死无响应; RootCause：高压空气放电，干扰PUD，reboot过程中VIO1.8也没有下电，导致重启也没有恢复，下电重启才恢复。（高压重启可恢复，属于可接受） Solution：1. 实现reboot过程VIO1.8下电。-- MTK确认不能实现； 2. 增加PUD LDO下电方案，增加控制的IO口，需要软件提前确认导入； -- 直接DVT1导入； | link | 廖哲霖 |  |  | 1.SCH
2026-05-11 | 4.EVT | 1.Platform | 4.Build | NA | Closed | Issue: EVT有个板子无法下载，板号NAAA020317 Analyze: 1.Blankflash 的log 发给MTK，待回复。（下载完DA后，无法进入DAmode，拔掉数据线后，板子处于关机状态，没电流） 2.FAE换了 U2001（MT6363））/U2601（MT6375）/U1001（CPU）/U1009(DDR)/U1392(UFS)，发现还没恢复正常。U1392测量底部pad阻抗ok，通断正常 3.按开机键再松开，电流停在200mA左右。说明主时钟已经有了。 4. 硬件测量上电时序，确认时序已经都满足了，也就是板子关键的电都已经上来了。 5.log MTK 分析结果：U1301 初始化失败，返回错误。 RootCause：产线SMT 用错器件，U1301 用错成U1701的器件。U1301 用正确的器件后，ok了。 Solution： SMTowner |  | 文亭 | 敏敏 |  | 6.No Change
2026-05-11 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | Issue: EVT 可靠性有两台机器SIM无作用，重启概率性恢复。 Analyze: RootCause： VCC 电容和中框短路 （绝缘实验临时验证ok，不复现） Solution： 中框DVT1 做避让 |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-04-29 | 4.EVT | 9.Memory | 4.Build | S3 | Closed | Issue: EVT 二供BR157907 128 UFS 尺寸太大，造成连焊。（贴了4pcs 板子） RootCause： 二供 SM38F05190 BWU3AKG16D128G U1392 BIWIN，尺寸11.5*13 VS 一供三星的11*13 Solution： EVT二供试产 及 DVT1 备料临时更换回一供三星memory 长期：1.跟进厂家更改尺寸为11*13情况（可行，但是要2027年才能改好，咱们项目用不上了） 2.项目上将三供pull in ，预计DVT2二供来得及导入验证 |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-04-03 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | Issue: 4/3 front camera 22 pin connect error RootCause： NEW SPEC is NC，Old SPEC is power 。 没有用新SPEC进行设计 Solution：EVB rework 割断连接器上22pin-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来， -- changmf1 done |  | 芳梅 |  |  | 1.SCH
2026-04-03 | 3.PEL | 2.Power | 5.1 Bring up | S3 | Closed | Issue: 4/3 已知DVDD LDO U3161有点问题，EVB2 ，已经rework板子 bringup。EVT 更改进入主线 RootCause：VIN和VBIAS 连接反了，没有识别出来。 Solution：EVB rework 让LDO能正常输出-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来，已提交修改，待导入 --wuxm5 |  | 敏敏 | 芳梅 |  | 1.SCH
2026-04-03 | 3.PEL | 2.Power | 3.Review/Simulation | S3 | Closed | RISK: Display power 和SPK power 的输入端VSYS 过孔只有一个，有风险 Impact：EVB板子不适合 Display 和SPK 最大功率使用，可能会烧毁板子。 RootCause： review没有识别出来。 Solution：EVB rework 让LDO能正常输出-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来，已提交修改，待导入 --wuxm5 |  | 芳梅 |  |  | 1.SCH
2026-04-03 | 3.PEL | 10.USB-C | 3.Review/Simulation | S3 | Closed | Issue：CPU和redriver 之间没有串接电容 in EVB1 Impact：EVB1板子USB3.0 没法工作 RootCause：设计错误 Solution：EVB1 rework for DFC 方案（去掉redriver）--ongoing chenwt EVB2 主板上串联电容 --已更改进板子，待EVB2板子到达后bringup。预计4/8 SW收到板子 |  | 文亭 | 芳梅 |  | 1.SCH

## Aviator
| Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2026-05-18 | B.PVT | 3.Charging | 5.6 User Feedback | NA | Monitor | RISK：ROW ，无线充的DET信号 发现没有下拉电阻，无线充 检测状态可能会不稳定。 发现来源：PRC（没有接无线充电板子的）PVT后期有出现一台机器开机就显示充电图标。分析是因为DET 中断检测到导致判断 无线充电 被检测到。 前置问题的解决方法：PRC样机没有无线充，禁断所有无线充的GPIO及相关功能响应。已经导入主线，从 36.65-11 导入了更改。 前置问题的扩展评估：那么有带无线充的板子，是否也可能存在这个风险？ review 后发现该RISK Impact： 可能1 ：没有无线充 的时候 有极小概率被检测到无线充在位，显示充电图标，实际没有在充电 可能2： 无线充电器拿下来后，可能还会显示充电图标？ Anaysis: 1. DET信号没有外部下拉，内部也不能做下拉（CPU下拉会影响DET拉高，电平不够。 无线充IC默认状态没有上电，所以也不能配置下拉）。所以DET信号就比较接近悬空了，仅有 CPU和无线充IC 默认的连接，下拉能力非常有限。 2. 请无线充IC厂家确认， 有很微弱下拉，小于1uA RootCase： DET信号没有外部下拉，内部也不能做下拉导致 DET中断可能会误触发。（DET是高电平有效。） Solution: proposal 1. SW workaround ：当DET检测到的时候， 通过其他组合条件进行确认再判定是有效的无线充电。临时版本0519 验证ok，会提交进入主线。 待有正式版本后，再确认下。 For 后续长期： HW方案 ，在stack板子上增加一个47K下拉电阻靠近无线充IC端。后面Pike ，Artura 都这样进行更改（Pike EVT修改要改进去，Artura DVT1 要改进去。） ---chenwt tracking | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-05-08 | B.PVT | 3.Charging | 4.Build | NA | Closed | Issue:PRC 样机试产时候，反馈有1台机器，重启后就一直显示充电图标。插拔充电器后恢复。 Impact： 异常出来充电图标 Anaysis: DET信号没有外部下拉，内部也不能做下拉（CPU下拉会影响DET拉高，电平不够。 无线充IC默认状态没有上电，所以也不能配置下拉）。所以DET信号就比较接近悬空了，仅有 CPU和无线充IC 默认的连接，下拉能力非常有限。 RootCase： PRC机器没有无线充IC，所有接口都是悬空。需要将相关部分的功能关闭。 solution: PRC机器 SW上去掉所有无线充的相关信号响应。 36.65-11 导入了更改，验证ok |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-05-08 | 7.DVT2 | 3.Charging | 5.5 Certification | S2 | Open | Issue：CB认证反馈低温0~-20度之间，充电电流达到1.92A,大于电池SPEC的691mA Impact：认证，电池安全 Anaysis: 1. RD复测，常态状态下是654mA，小于691mA 2. 测试过程发现，插入充电器后几秒钟内，会先电流爬坡到4A左右再降低下来到654mA. 推测是这个爬坡过程被拆机到电流，然后判断为fail 3. 发现2 ：开机后的这个4A是SW可以配置的，所以查到哪里的逻辑申请4A电流 尝试优化逻辑来让 安全机制优先级别更高，就有机会优化开机状态下的结果。 4. SW log 分析 4A是SW初始过程中将FCC设配置为5A拉载出来 。 RootCase： 问题1 开机状态 先到4A左右 3-5秒后降到安全范围内。 原因 ： SW为保证可以正常拉载到大电流，先将FCC设为默认5A，然后配置目标ICL，最后将FCC配置为目标电流，低温场景测试，对充电电流要求较低，会触发一个高于电池SPEC要求阈值脉冲电流 问题2 关机状态插入充电器，会先有default 的5V1.5A的配置（非SW上层配置，是 底层配置） 两秒左右就会过去，然后SW起来开始后续配置。 这个点如果认证不放过，就要 看底层是否有机会优化。 solution: proposal 1. 优化初始FCC配置值，将默认最大值与目标值取小作为最终配置值，保证全程拉载电流不超过电池SPEC要求-验证有效，去掉了 4A左右的脉冲。 proposal 2. 关机 充电5V1.5A脉冲QC答复无解，只能优化速度。 修改XBL加载顺序，将脉冲宽度从1.9s改为1.2s同时压低691mA设置到500mA ，来降低其他抖动带来的可能出现的超过一点儿门限的概率。 --待验证有效性后提交修改进入主线，然后安排复测 | link | 文亭
2026-05-07 | B.PVT | 3.Charging | 4.Build | NA | NA | Issue：PVT CQA测试发现，2台机器出现过OTG问题 N4AC420027 4/17/2026 5:10:29 PM UCT pass 。没有抓log ，直接ABA 交叉验证随芯片PMIH0104 （U3700）） QC初步分析IC异常了，更进一步消息，预计要到5月底出完整报告 N4AC4H0005 CR https://idart.mot.com/browse/IKSWW-198501 ，4/28/2026 6:15:57 PM UCT pass 。软件分析是已经检测到时OTG设备，然后电输出，之后枚举数据没有枚举上。 |  | 文亭
2026-05-07 | B.PVT | 3.Charging | 4.Build | NA | NA | Issue：PVT UCT测试发现，主充测试fail，电流非常小 N4AC4C0057 （4/28 下午2点38发现 ，BT是pass的）这台已经更换芯片之后测试Pass了，交叉验证随芯片PMIH0104 （U3700）） N4AC4C0060（4/28 下午2点45发现 ，BT是pass的）这台已经更换芯片之后测试Pass了，交叉验证随芯片PMIH0104 （U3700）） N4AC4E0002 （4/28 下午3点20发现 ，BT是pass的）保留板子 （这个机器OTG复测是pass的） clue： 1 UCT拦截的不能主充的问题，是4/28 下午2点38发现到4/28 下午3点20发现 突然出来3台。 评审会上请产线查这三台的IC批次，以及产线这个时间段有啥特殊性。（整机测试集中性这么明显，可能产线那时候有出现什么我们未知的情况。板级测试查过是pass的，并且没有集中时间），故障IC刚寄出去给 QC 。 需要较长时间才有分析结果回来。 ） 2.log分析第一台，发现是AICL 一直被限制到0，导致没有电流。（一开始插入瞬间有电流，然后被限制下来），推测是PC的AICL相关模块不正常了。 Rootcause： 主充电IC 故障，待产线寄送故障品给QC分析。这是其他项目MP物料。 CT62275/RMA-113099 : #1 failed in C/Tracer as pin QPH1D (177,190) short to QPH1S (176,189). The detail C/T result attached. CT62276/RMA-113100 : #2 failed in C/Tracer as pin QPH1D (177,190) short to QPH1S (176,189). The detail C/T result attached. The failures are indicate of EOS/ESD damage issue. Please review the application and test conditions. If necessary, open CE case for review. |  | 文亭
2026-05-07 | B.PVT | 3.Charging | 4.Build | S3 | Monitor | Issue：PVT 增加UCT站点的FW版本检测，确认是否升级版本成功。 产线反馈有约30%NTF。重启机器测试pass Impact： FW升级是工厂动作，不会影响用户。影响产线的直通率。 Anaysis: 1. 通过log分析，在启动FW检测和升级后100+ms 范围内，就返回读写状态失败，并没有启动真正的FW写入。 2. RD机器测量供电，这段时间内供电电压是稳定的。但是没有抓到复现问题的波形 3.下一步：先飞线，继续压测，尝试抓到故障时候的更多波形做进一步根因分析。 RootCase： 推测：是否供电后，需要等待较长时间IC才能稳定工作？ solution: 1 ： 同时读写状态加上retry 5次的动作（如果失败，下电，再重新上电再读取），来提高成功率。 临时版本提供了， 产线压测30次，ok 。BB 压测27次，ok （确认log 确认触发了retry 的机制，每次触发1次retry 后pass了），所以看起来solution 有效果。 | link | 文亭
2026-04-23 | 7.DVT2 | 20.NFC | 6.Issue | S2 | Monitor | Issue: During Qingdao Wallet field testing, a failure was observed where card payment does not work when the device is powered off (IKSWW-191864 ). Impact： Wallet card emulation tests fail in the powered-off state, affecting offline NFC payment verification. Analysis / Root Cause： When the device is powered off, the NFC power supply BOB experiences a voltage drop, causing the NFC supply voltage to fall below the minimum requirement of 2.5 V specified by the spec. The FMD feature was not enabled. As a result, during the power-off sequence, a vote triggers a BOB reset (RST) action, which further contributes to the BOB voltage drop. Action / Solution： Apply the QC patch to correct the configuration at register address 0x719A,Waiting for QC release patch. | Link | 李果 | 敏敏
| 7.DVT2 | 1.Platform | 5.3 EE DVT | S2 | Open | Issue：DVT2有一条机器出现CapSensor ESD后 无功能-所有通道 ，AD:8kV
| 7.DVT2 | 1.Platform | 4.Build | S2 | Open | Issue：SMT反馈stack 板有锡珠，几乎每台都有，位号Q2603,Q2604,Q2801 solution: DVT2 钢网从1：1更改为焊盘中间加0.2mm间距，不良率 12/172 PVT继续减薄锡膏 | link | SMT yanlin
2026-03-13 | 5.DVT1 | 1.Platform | 5.4 ALT | S2 | Open |  | Link | 敏敏
2026-03-13 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Open | Issue：DVT1二供 EDU14出现一台机器Fail，一台200V Fail，一台250V Fail（实验室标准250V） Anaysis: 1. 两台机器，拆机分析VBUS浪涌管都未烧毁。 2. 测量机器发现USB充电快充/慢充均没有电流，且OVP MOS后端都没有电，判定OVP MOS没有开启。 3. CP-IC U6400是二供南芯，分析发现VUSB SNS的R6401电阻击穿（22Ω），且VUSB管脚对地电阻异常15Ω，判定是浪涌实验中，CP-IC的VUSB引脚先被浪涌击穿对地，然后再烧毁电阻，进而导致芯片内的OVP模块损坏或无法工作，导致充电故障。 4. EVT1 一供400V，二供300V； DVT1一供400V，二供200V&250V, 判定二供CP-IC在Aviator现有架构下可能抵抗能力不如一供； 5. DVT1二供 浪涌测试 采用的机器是复用跌落的； RootCase：二供南芯CP-IC 的VUSB管脚抵抗浪涌能力不如一供。 solution: 1. DVT2 R6401 更换成33R电阻（0613952X37），加大电阻，已和供应商确认50欧以内都OK； 2. 损坏的两颗CP-IC已经给到Southchip分析中； 3. TODO: Rework机器33R，回归测试： 3/23日复测结果，两台Rework二供机器 到33R的均Pass(250V)，但是余量不够； 3/26日复测结果，两台Rework二供机器 到47R的均Pass(400V)，且未出现漏电，判定方法有效。 |  | 廖哲霖 | 文亭
2026-03-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Monitor | Issue：SME tuning 磁吸充电时候发现，死电池的机器，用磁吸充电器无法激活，屏幕没有任何反应。 Impact：Apple Q2.2 磁吸充电器无法激活aviator 死电池的机器。（其他WLC 目前测试都可以激活 ，更新3/17 的FW版本0073之后的结果） rootcause: suspect :1 WLC RX IC 输出电压不稳定，导致主充电PMIC无法稳定走死电池激活流程。 为什么输出不稳定？ suspect :1-1 推测是 WLC 输出驱动力太低 以及 手机瞬态 吃电较大导致的 WLC输出电压不稳定。 （系统耗电，这时候电还没进电池） solution: proposal1: 带SME tuning Apple Q2.2 磁吸充电器 default 模式下的驱动力。 3/30 临时版本FW确认ok了。待SW导入主线后继续跟踪。 | link | 文亭
2026-03-03 | 5.DVT1 | 1.Platform | 5.4 ALT | S2 | Closed | Issue： DVT1 ，实验室一些机器返回分析后，放置一段时间，再开机无法开机，插充电器，没法正常充电。有时候屏幕先亮一下，然后就只有5V80mA左右。 clue：1.之前有一台，插着充电器无法开机，长按开机键几十秒后开起来了，不确认是否同一个问题。 目前针对第二台进行拆解分析 2.第二台机器 N4AC130165 ，屏幕先亮一下，然后就只有5V80mA左右。拆机测量Vbat~=0V ，所以电池死电池了。拆下电池连接器，电池电压0V，死电池了电池本体变形严重，确认电芯异常了，转KP分析。（这台机器经过多轮可靠性，包括2.5米跌落）。 后面又回来两台，都和第二台一样的结果，转KP RootCause：闲军 owner （大概是电池内部防护不够，造成漏液了） solution：闲军 owner（大概概括是更改电池内部保护，DVT2整批导入，DVT2 厂家和 咱们同步验证，看是否ok了） |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-02-11 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S2 | Open | Issue： DVT1产线出现4pcs烧毁VBAT-TVS(FR：4/86)，请软件导入降低电流软件后，3pcs烧毁(FR:3/553) RootCause：从TVS烧毁现象怀疑是Peak电压导致TVS异常开启后短路，电源常电进而烧毁TVS管。 Analyze: 差异对比： - Aviator: SF68D39333(Will)+8845; 烧TVS - Horizon: SF68D39333(Will)+8845; - Urus: PTVSHC2EN4V8UF + 8845; 未出现烧TVS 36.12版本：（进入Homescreen大电流） - 4pcs板子，D3500,D3501均烧毁(FR：4/86)，实测电流在进入Homescreen瞬间有一个7A的值，经实验确认是CPU限频解除导致。 36.16版本：(限制CPU频率，确保没有大电流) - 请软件导入不解除全程限频的措施，截至到2/11出现3pcs烧毁，其中2pcs烧D3500,1Ppcs烧D3501。(FR:3/553) 产线测试波形： - 36.12版本下，产线夹具上测试，3pcs 产线主板 3个板子36次压测，均未烧毁，最高Peak电压抓到4.8V （VBR:4.9V），继续在武汉基带用为准电源压测，也未发现明显异常。 - 36.16版本下，烧毁的1pcs板子产线夹具上测试，未发现故障波形。 | link | 廖哲霖
2026-02-05 | 4.EVT | 3.Charging | 5.2 BB Test | NA | NA | RISK：Vendor 调试时候发现 无线充Vout 飞线出来测试，发现有一个NFC 工作频率的电源纹波。NFC关闭后就没有。 impact：如果真实存在，可能会影响到无线充 通讯解码稳定性。具体待确认 Rootcause： 1. 飞线压到NFC天线上导致，误测问题 |  | 文亭
2026-01-30 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | RISK：Qi 2.2 认证预调试时候SME 发现：前置线圈切换电路的Mos 控制端GS 电压 在低频阶段有大于1V的纹波，有可能会误触发 mos 打开（打开门限是1.0~2.5V） impact： 反复打开关断mos会让功率存在波动，影响的是bpp模式Qi 2.2 认证的 Rootcause： 当前的 S 信号是通过AC（线圈信号）耦合过来，其VGATE是IC内部自举电路基于AC基础上升压的，目前看起来内部有 谐振频率附近的干扰 （频率在低频段128KHZ）。 solution： 在GS之间加一个10nF电容 来进行滤波。 临时验证：实际rework 验证有效果，将原来超过1V的纹波，降低到只有0.3V左右，处于安全区间。 项目上：需要在DVT2 发板上改进去。已提交，待发板时候更改 --chenwt 加滤波电容是否会有负面影响？： SME comment 没有负面影响 |  | 文亭 |  |  | 1.SCH
2026-01-28 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | RISK：Qi MPP 15W CE : SME 反馈 ICL步进 在1A左右突然功率跳变太大，不符合需求。 Rootcause：QC 答复是 QC IC PMIH0104 SPEC范围内的行为，无法确认不跳变。无法从根上面解决（其他竞品厂家也要面临这个问题） solution：寻找其他解决方案 by SME |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2026-01-28 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | Issue：DVT MDu94.A - Extreme Drop Test WH202994 D5 N4AE060004 Post check:No front camera viewfinder:D2/D5 Post check:Unable to find NFC device Rootcause：前置摄像头脱落，结构泡棉问题。
2026-01-16 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Open | Issue: - ANT7 N77&N78 interface Front camera leads camera MIPI error on EVT 3/3PCS Analysis/Root Cause: - The logger shows mipi error. - 翻起前置camera模组头部，干扰消失，模组头部的铜箔从主PMIC屏蔽盖下地，ANT7天线回流产生的磁场干扰从camera模组头部进入到sensor本体。 - Camera deco 接地不良，主板上螺丝孔挖露铜后+ 去掉ANT7 LDS天线，只有ANT N78 MCH 有mipi error, 概率降低50%以下 - camera 模组头部贴铜箔到Receiver后，2台测试ok，改变了天线ANT7的回流路径产生的磁场干扰 Action/Solution： 主板上Deco弹片接地区域露铜并增加过孔，确保Deco接地良好。EVT后期Deco下地弹片检查已镀金； —— DVT1已改入； 去掉ANT7备用 LDS天线 更改camera背面石墨片和receiver连起来，改变ANT7的回流路径，测试2台pass---导入DVT1 二供 Verfication： DVT1 自测三台 pass | LINK | 芳梅
2026-01-15 | 4.EVT | 3.Charging | 5.1 Bring up | S3 | Closed | Issue：SW细节bringup 发现 没有放到TX上的时候DET 信号有时候高电平有时候低电平。（这原本是用来作为放到TX上枚举成功的判断中断） impact:没放到无线充时候，有小概率会意外识别为有无线充？ rootcause：1.外部没有加下拉电阻，导致GPIO浮空 （平台内部下拉电阻阻抗范围太大 10K~50K，不稳定） 2.厂家的GPIO输出电平配置没有按照我们需求配置为1.8V（当前测量是1.2V） solution： 1. DVT1 是SW配置 GPIO no pull +HW 外加47K下拉电阻+FW配置1.8V GPIO输出。 （HW 发版 1/16 已经改入stack 板子） 2. EVT ： 是SW配置 GPIO no pull +HW 没有外加下拉电阻+FW配置1.8V GPIO输出 。这样的情况是，EVT机器当刚关闭无线充时候，有可能会有残留电压，导致GPIO 还继续判断到高电平。 大部分情况是ok的。 长期：后续项目默认Det 信号都增加47K 下拉电阻。 |  | 文亭 |  |  | 1.SCH
2026-01-15 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Monitor | Issue： EVT ALT WH202971 PRC 1:Accelerometer failed functional parametric test,Recovered after reboot:A1/B2(1)-TH/TC 抓log分析 EVT ALT WH203016 APEM testing 1/17 Accelerometer failed functional parametric test,recovered after reboot:A1/A2/B1/B3(1)-TH/TC,B2(1)-post drop,A3(1)-post shake 分析 ：1. 温冲异常在升级A+G三轴正确方向后不复现。 loop3振动完做全部检查时发现1pcs A2 (XY正常，Z保持-79左右)，loop4跌落新增2pcs B1 B2(XYZ值不变化) SW说TCC使用的测试版本太旧，交给vendor去分析。继续跟踪。 2. 和邓玲确认EVT是否还有实验可以复测？需要确认能使用的版本。 |  | 小熊
2026-01-15 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Open | EVT Tumble WH202942 PRC Flicker sensor no function,recovered after 100 tumbles:D1(80) EVT Tumble WH202981 APEM 2:Flicker sensor no function,recovered after reboot:D1(200)D3(60)D4(100)-CR129483 分析 ：问题分析需要抓有效log，TCC 加滚2pcs各100次，不复现，所以未抓到有用的log。先monitor。
2026-01-10 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Monitor | ISSUE：EVT ：TCC ESD 中发现机器自动关机 ，厦门自测发现自动重启1次。 Rootcause：是场干扰模型而非直接击中信号线或者器件。 场干扰故障模型的原因推测：1.这个场大概率是 由于大金属块接地不好导致的场太强 。 2.周围的地贯通速度不足以吸收 当前很强的场干扰。 优化方向：临时加强deco 接地，压测pass solution：1.改变场 ，加强大金属块的Grounding。2.增加 PMIC 本体区域及周围的Grounding，板子多打地孔，特别是贯穿孔（ 要有大孔，大孔附近也要有好的小孔，才能形成贯穿导通） | link | 廖哲霖 | 文亭
2026-01-10 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Monitor | Issue：ESD在CD:8KV下，在Deco区域和侧边出现Flicker Sensor软失效、auto-recycle。 Analyze：1. 厦门摸底机器，已导出Ramdump —— 软件分析是触发了PMIC（PMIC_B_E0） OCP保护，导致PMIC触发RST复位。 2. Deco弹片主板EVT无露铜 —— DOE实验：原始状态 CD:6kV下就复现Flicker无功能；刮开露铜, CD:8kV，AD15kV各打100次均无出现问题。 3. ANT0 Cable 测试CD 8kV下ESD波形，Peak电压有491V，对比Equator ANT0为250V —— Aviator天线小板是新的设计，馈点弹片和下地弹片很近且取消侧弹，相较于Equator天线小板上路径会短一些。 RootCause：1. Camera Deco 两个接地弹片主板对应区域没有露铜, 增大了Flicker板上Deco下地弹片的泄电压力，进而导致I2C干扰。 —— Flicker软失效； Solution： Flicker 软失效： 1. 主板请结构输出Deco对应弹片接地区域(已增加到CheckList) —— DVT1已改入； 2. 增加Flicker弹片过孔下地过孔 —— DVT1已改入； 3. 确认Flicker Sensor Recovery机制 —— 目前已确认有这个功能，现在软件是否打开正在确认。 Auto PowerOff/Cycle： 1. 增加ANT0天线小板过孔下地过孔 —— DVT1 已导入； 3. ANT0主板RF端预留TVS位置，加强下地。 | link | 廖哲霖
2026-01-08 | 4.EVT | 12.EMC | 4.Build | S2 | Open | Issue: 产线报有4pcs机器主板，在4GBT站点出现浪涌管D3500,D3501烧毁； Analyze：1. 和产线TE确认，用的是为准K6206-V20 20V 5A的电源，和之前北京Team遇到的浪涌管烧毁问题一样。 2. 高通SM8845平台开机过程电流大，会超过为准电源的5A输出能力，导致突然有大电流抽电时，电源会顺势加大功率补偿，进而导致电压异常抬升，触发EOS浪涌管导通烧毁。 3. Urus 02版本VBAT浪涌管选用ESD56201D04-2_TR（性能较差，我们已启用），最终选用Prisemi-PTVSHC2EN4V8UF（看Spec参数，和我们ESD56301D04基本一致）； RootCause：产线为准K6206程控电源输出能力和控制速率不够，导致电源异常抬升，触发EOS浪涌管导通烧毁。 Solution：1. 产线增加浪涌防护板；—— 目前产线有1pcs样品，批量至少需要4周，估计要到年后才能上产线。 2. 优化开机电流到5A以下： 目前软件确认是有导入Urus的降电流Patch，但是实测开机电流还是有6A， 已反馈请软件评估进一步优化机会。（工厂build kernel 配置文件没有走perf配置, 走的是debug配置）—— Owner：Jichao Zou； 3. 调整程控电源控制程序，取消VBAT电压调整； —— 修改中； | link | 廖哲霖
2026-01-08 | 4.EVT | 3.Charging | 5.4 ALT | S2 | Monitor | Issue: Alt 3台滚筒 不开机，1台MIL不开机. 故障现象：开机了反应速度也比较慢，关机后，插充电器充电5V/0.3A RootCause：电池连接器松了， 甚至主FPC也松了 Solution：ME |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-12-19 | 4.EVB | 5.Camera | 5.1 Bring up | S1 | Closed | Issue：后置camera SOIS I2C 读写不成功 rootcause：SW i2C 端口设置不成功 Solution：软件setting |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-12-12 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | Issue：前置bringup camera不出图 rootcause：MIPI timming THS-settle(ns) 不满足协议要求 Solution：修改MIPI timming | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-11-12 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | Issue：bringup 发现快充IC插入USB时候能识别到，拔掉USB就识别不到。 rootcause：快充IC的Vbat 和 主系统的Vbat_Plus 没有连接上。（还有B_plus 等网络名接一起，但是VBAT 没有和VBAT_PLUS接一起，由于都有电容，所以不会自动报单端网络。 Solution：EVB ， C6425电容的左侧 飞线到 C3808 电容上端. ongoing EVT 及之后，原理图更改，Vbat 和Vbat_Plus 连接上。 done 长期：checklist 里面专门特别加一条，Vbat 和Vbus 需要确认和主网络连接。（因为这两个网络板子上会多个地方使用，原理图上有很多的网络名，而且基本都有电容导致不会报单端，相对容易漏过。） |  | 文亭 |  |  | 1.SCH

## Terrain
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2026-03-09 | C.RAMP | 13.Discrete | 4.Build |  | Monitor | Issue：OK2P发现2pcs 电容C2620与屏蔽盖SH1002短路造成大电流，F/R 2/3000=0.0066% Analyze: 1.C2620使用器件21014016001，包含村田，太诱，三星三家物料，村田&太诱 高度为0.8±0.2mm/0.8+0.2mm，三星高度为0.8±0.25mm，且三家物料均走上公差。 2.21014016001 实际高度应为1.05mm，而结构建模该料号器件高度为0.88mm 3.C2620处于屏蔽盖边缘，屏蔽盖在C2620附近有个斜坡，器件与屏蔽盖斜坡之间gap=0.14，器件走上限容易干涉 4.OK2P 使用的物料为高度最高的三星物料 Soltion：1.屏蔽盖改模，取消斜坡，增大与电容之间的Gap 2.处于屏蔽盖边缘的C2620等6pcs器件更改为不含三星物料的新料号:SC48E75627 3.屏蔽盖改模前，21014016001,SC48E75627只发murata物料给Terrain，以满足生产需求 | Link | 院长 | 敏敏
2026-02-28 | 7.DVT2 | 3.Charging | 5.5 Certification | NA | Monitor | Issue： CB 认证反馈 2. Q.1测试，电流超了8A （具体代表什么意义待 和battery KP确认） Impact：推测：不能宣称满足Q.1 LPS ，只能宣称PS2 Rootcause：因为电池的对外输出能力越来越大，所以自身不能限制到能pass 8A的这个放电限制 。 （测试方法是 短路充电IC的输入和输出，就是将Vbus 和Vbat 短路 ，多少个充电IC就分别短路多少次，分别测试，用来判断整个系统在异常情况下 外部能抽到的电是安全范围的。标准8A 或者100W 是个认证固定标准） Solution： 两个选择 2.1 尝试正向解决：在OTG场景，监控Ibat ，当Ibat 大于某个值（比如6A ），就关闭OTG （包括OTG 对外输出的OVP mos 管 ） 。 原理上推断有机会可以解决这个case 。需要SW进行逻辑更改 ，请SW评估下是否进行更改以及更改plan @Wei Wei9 Xu 2.2 选择放弃这个项 的符合，宣称不支持 。 负面影响是什么，RD无法判断 ，需要请 认证同事 帮忙多确认下 @Xingxing XX18 Wang@Weiting Wt1 Sun | IKSWW-163405 | 文亭
2026-02-09 | 7.DVT2 | 3.Charging | 5.2 BB Test | NA | NA | RISK : 加州能效测试，临界fail 了TMO要求的70% 的加严标准 Impact：对Terrain项目本体无影响，因为没有NA SKU，作为内部测试参考项，不强制pass。 扩展：Artura 同平台，推测会有面临这个问题，所以需要提前触发给SW 研究解决方案，但是非紧急事件 rootcause：第一阶：关机充满电后，还有5V100mA。这个满电维持电流太高了，一版要稳定过加州能效，在60mA以内比较有机会。 为什么满电后维持功耗这么大？ 第二阶：memory 是否配置低功耗模式？ |  | 文亭
2026-02-03 | 7.DVT2 | 1.Platform | 5.2 BB Test | NA | NA | RISK : MTK 要求这个项目增加SPMI在不同地方进行尝试（CPU，PMIC ，以及PMK 都测试）， 并且增加 glitch 指标。 当前刚完成该测试，发现SPMI 靠近CPU端的Glitch 指标严重超标。 | link | 文亭 | 范南
2026-01-14 | 5.DVT1 | 3.Charging | 5.2 BB Test | S2 | Closed | Issue：BB和SW 测试发现最近的SW版本，手机低电量 1%~2% 开始充电，充几分钟后无线充电大概率异常 ， 故障现象有三种 1. 充电图标一直在，但是充电电量不上涨反而降低最后没电关机了，变成关机充电 2. 充电提醒反复出现 3. 提示位置放偏了 Impact：低电量的手机+moto 15W 无线充电器充电 无法正常工作（充电到2%~5%会停充 或者 出现一些异常提醒 ）。以及推测一些第三方有类似保护功能的TX 也会出现无法工作的问题。 Rootcause： 根因1 ：主充电IC MT6375 检测到 IC端的Vbat=3.6V的时候短时间关闭batfet再打开 -》电池端能吃下的负载瞬断1.5ms左右-》无线充IC输出功率瞬间出现一个大约14W的功率骤然下降 根因2：无线充IC 功率骤然下降-》 MOTO 15W TX 触发 OVP-》TX 主动降 VPA--》TX降频 + 拉满 duty 补功率-》TX IPA 超限触发 OCP 》TX 切断输出》RX 侧 vout/iout 骤降甚至关闭。 solution： Action1：MT6375 batfet转换节点电压 从3.6V改为3.4V （降低可能出现问题的电量比例 ） Action2：无线充开始枚举的时候，如果判断到电量低于10%的时候 就限制无线充功率到10W ,如果判断到电量大于 10%的时候按照15W工作 。 两个Action 在1月28号进入SW主线。 长期：MTK平台建议选择 使用类似的方式，低于10%的时候降低功率到10W 来规避风险。 高通平台目前看PMIC没有类似MTK的这个特性（ 高通PM8350B看到的点是Vbat~=3.05V就已经将batfet 完全打开了） 对应项目最好也再确认下 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-12-22 | 5.DVT1 | 5.Camera | 5.6 User Feedback | S2 | Open | Issue：IKSWW-111442 Vertical streaks appear on cameras 1X-2X (摄像头1X-2X出现竖纹) B2GID:328394128 Analyze: 1. DVT1 样机插联通SIM卡，户外，开NFC，开WIFI（未连接有效网络），预览或者录像时发现有偶发竖条纹。 2. 隔天不复现; 3.拿到样机后，复测主camera天线干扰测试4次，均pass 4.联通注册网络为LTE B1，B3, NR N1和N78 ， 只在这四个频段切换。从天线结构看，N78在camera周围的ANT5和ANT7，按照最大功率26dbm发射测试多次，ANT8 B1 24.5dbm 发射多次也未出现，并未出现异常。B3, N1 在ANT8在，远离camera deco, 远离camera，从理论上不存在干扰主camera的问题。 5.NFC待验证 | LINK | 芳梅
2025-12-22 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Monitor | Issue1：DVT1B ESD 报两台D1,D3机器ANT6 Fail(RX3 B3 B41 B66) ，D4一台 ANT0 Fail(RX0 B28); Analyze: 1. ANT6 ：Tuner NG； 路径：SideKey处进入； Diff：Sikekey音量上按键天线包塑处露金属； 2. ANT0：Tuner NG； 路径：SPK开孔处进入； Diff：SPK口密封胶圈装配偏位； 共同差异是天线TVS换成二供Walsin-TLE1020。 Action: 1. 设计DOE实验判断更换Panasonic ATVS是否有效； 2. 验证新ATVS: TUE10201V06B0性能，是否能完全做一二替代； 3. 请结构判断是否有机会拉齐二供的质量 1）天线塑胶完全包住； 2）确保SPK密封胶圈装配正确； Solution：1. op1：更换性能更好的二供ATVS - TUE10201V06B0 ； op2： ANT0/AN6点位用松下ATVS，其他点位用二供ATVS； 2. MB/SUB板 TVS以及下地电容走线优化，Sidekey FPC增加露铜吸引静电；——DVT2B发板已改入 | Link | 廖哲霖
| 5.DVT1 | 20.NFC | 4.Build | S1 | Monitor | Issue1：产线反馈DVT1 试产中部分中途整机升级的机器中出现不识别NFC,更个stack 板子后可以识别，再装回去也都可以正常识别，直接板测阶段升级软件的机器没有出现过。 Analyze: 1.验证硬件通路是否正常。---从Stack 板测量，开始时候有I2C 信号和NFC_CLK。说明NFC 硬件通路是正常。 2.若SW FWDL流程后，NFC 芯片可以恢复，可以正常工作。 Rootcase： 发送以下的reset指令后，因为一直收不到IRQ, read就会失败，然后就读不到信息， 驱动层面nfcc_hw_check 就不能成功的获取chip type，然后nxpnfcinfo 尝试从驱动获取 nfcc info 的时候 获得的就是0， 然后就不会去 设置 vendor.qti.nfc.chipid. 当前因为涉及到PN560 和SN2260的混用，只有 vendor.qti.nfc.chipid 被设置之后 NFC hal才会真正开始工作。第一次发送 nci_reset_cmd 之后， IRQ 一直没有被拉高，然后即使用polling mode也 read失败 目前从我们抓到的波形以及log看，还是芯片不响应。 Solution ： 在NXP的I2C 驱动这边加一个逻辑，如果probe的时候 nfcc_hw_check 没有成功获取信息， nxpnfcinfo 尝试通过IOCTL获取 nfc info的时候，驱动再次去和芯片交互。 | Link | 李果 | 院长
2025-12-09 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | Issue: 产线出现2pcs Slave 快充测试fail主板，X-RAY无问题， ABA 交叉确认故障跟随 快充IC U2651 。 total 600pcs Analyze: 1. 一供快充IC SC8586A寄给vendor 分析， Vendor 分析结果是IC没有问题 12/18 返回IC，产线安排复测故障不复现，如果按照以往的逻辑判定，这个可能就是焊接性问题。 2. 通知产线如果再发现同样问题，需要抓取log 分析下线索。 Solution： DVT2 没有复现问题，close |  | 文亭 |  |  | 6.No Change
2025-11-25 | 4.EVT | 5.Camera | 5.2 BB Test | S1 | Open | [s1]Issue ：Terrrain EVT 自测天线干扰camera拍照时，EVT1 2台/6台 主camera 被ANT7 N77&N78干扰 Clue: 1. camera模组和FPC远离主板 ok 2. 和天线无关，将主板拆出，camera FPC贴在主板器件上，EVT1和EVT2整机搭配一二供模组都会出现条纹干扰 Root cause: Camera FPC装配后，FPC贴在主板上ANT7的通道上，当ANT7 N77和N78发射时camera 被干扰 Solution：Add copper foil on FL3304 ，Shield the source of interference Verification： DVT1 一供 base 2/ 66pcs DVT1 二供 copper 100 pass | link | 芳梅 | 院长
2025-11-25 | 4.EVT | 5.Camera | 5.2 BB Test | NA | NA | [s1]Issue ：Terrain EVT 自测手电筒亮着时，强制关机，这时候闪光灯会一直亮着，直到开机后，软件初始化再关闭手电筒 Clue:强制关机时未走完整的下电流程，导致没有ENpin 控制的闪光灯驱动IC AW36518 ，长亮着 Solution： Terrain没有实际的用户场景，不做修改。 针对日本SKU有强制要求的，需要使用有ENpin的闪光灯驱动IC 后续项目： 1. 选用带ENpin的闪光灯驱动，继续寻找一颗用于替代AW36518 2. 目前AW36518如果要使用，新的硬件接线方式需要给TX增加一个GPIO控制，并和软件确认闪光灯寄存器设置 | link | 芳梅 | 院长
2025-11-07 | 4.EVT | 5.Camera | 5.2 BB Test | S1 | Monitor | [s1]Issue ：Terrrain wide camera 预览可以看到有竖条纹。 Clue: 1. wide Camera 远离主板竖条纹消失，越靠近主板现象越明显 2. wide Camera 下方有PMIC器件，去掉隔磁片，图像上有非常明显的干扰条纹 Root cause: Wide camera放在PMIC屏蔽盖下，电源干扰到camera sensor，EVT整机camera下方有贴隔磁片在PMIC屏蔽盖上， 但是装配后，未完全覆盖camera头部，导致有磁泄露 Solution： EVT2更改隔磁片贴到wide camera模组上，隔磁片尺寸和wide camera一致，待EVT2整机导入 Verification EVT1 导入次方案后，效果ok EVT2 2供模组依然还有问题。因为一二供模组有差异，隔磁片有包边后，实际有效面积内缩单边0.5mm+ DVT1方案： 结构优化隔磁片，不算包边，需要隔磁片能覆盖住模组底部。手工检查7台ok，2台实测RCN pass | link | 芳梅 | 院长
2025-11-06 | 4.EVT | 6.Display/Touch | 4.Build | S2 | Monitor | Issue: 产线出现2pcs无触屏主板，X-RAY无问题，测量Touch_VCI_3P3无电压，Touch_VIO_1P8开机过程中会有1.8V，5s左右掉电，测量TP所有线路二极体阻值正常; Analyze: 1. 请产线重新刷27软件，没有解决问题； 2. 1#主板更换LDO和PMIC，故障依旧，通过ADB命令回读GPIO状态，没有grep到对应PIN， 3. 1#主板产线自行更换了CPU，不重刷软件，TP电压和功能均恢复正常。 4. 1#主板 怀疑是CPU问题，但是没办法交叉验证（CPU是POP的，EVT没有钢网，产线没办法将故障CPU重新焊接到OK的主板上）。2# 故障主板直接抓Log，软件判断是AP读不到TouchIC的ID，导致初始化流程没有跑下去。且Log中没有看到OCP或者其他的保护类报错。 5. 请产线X-RAY照了下2# 故障机器SPI部分的焊点，未发现明显问题。 6. 2#主板对比测量NG-CPU SPI阻抗，发现CLK MOSI 这两组稍微偏大了点。 RootCase：怀疑可能和CPU有关？ Solution：1. 确认无法交叉验证方法后，2#主板也更换CPU确认下故障是否消除。 2. CPU寄给MTK确认—— 已经请wenting帮忙和MTK沟通，邮件已经反馈了我们这里的分析信息，2pcs主板； 3. MTK反馈管脚IV曲线测试没有发现异常，返回武汉处上板验证，依然不良，已重新寄回MTK处返回台湾ATE进行分析；—— 12/1 更新： 12/19 MTK返回分析报告，判断2pcs CPU分析结果为EOS损坏 link | Link | 廖哲霖
2025-11-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | issue：After 150V surge pulse test,fast charging no function,OTG no function,headset no fuction:D1/D2(Vbus)- 推测：可能1.快充IC的OVP控制模块坏了。如果是这样，有预留串联电阻可以加上电阻进行复测。 Analyze：1. D1机器测量VBUS对地，D2:正向45.5K，反向5.1K，D2：正向 分析：插入充电器，有电压，没电流。插入OTG，看到输出电压只有3V。 拆机测量 OVP 前后的Vbus 电压波形，发现两端电压不等，插入充电器，OVP后端只有1V电压，所以不能正常充电，虽然OVP前端检测到有充电器插入了。 OTG时候，发现后端电压5V，但是接口端3V。 根据以上信息，可以判定，快充IC的OVP控制模块坏了。 根据历史经验评估，OVP模块 坏了，就是浪涌从vbus sens pin 进入，超过了IC的耐受度而损坏了相关OVP控制模块。 解决方向：快充IC的OVP串联电阻，提高这个pin的抵抗力。根据经验以及vendor的信息看，希望加10R~22R之间的电阻。 目前项目上建议直接上最大值22R。 然后尽量小板浪涌管加强接地和走线尽量优化（具体看板子的情况） Rootcase： 浪涌太大，超过快充IC的OVP sens pin 的耐压36V，导致这部分电路烧毁。OVP 模块无法工作导致充电相关都异常，包括OTG。 Solution ：1. 小板浪涌管下地加强——DVT1已导入 2. 快充IC Vbus 侦测pin 预留的串联电阻R2600，从0R改为22R，料号：0613952X33 .---EVT rework 验证，11/24出结果，一台250V Fail，一台500V Pass，结果均Pass（高于200V） DVT 1 原理图已提交对应的更改。 3. 二供两台机器EOS Fail，分析发现一样是OVP控制模块的问题，测量发现OTG可以工作，但是死电池没办法充电，判断还是VBUS SENS PIN损坏导致。（OTG输出时，VCHG有电，OVP模块可以正常工作。死电池时，OVP模块没办法从VBUS SENS PIN取电，所以打不开OVP） 4. 一供250V Fail的机器，分析问题同二供机器。 DVT1 pass | RPA FA link | 廖哲霖 | 文亭 |  | 3.BOM
2025-11-12 | 4.EVT | 3.Charging | 5.2 BB Test | S2 | Closed | Issue：产线反馈，CQA1 有些机器无线充测试fail ，情况2 Analyze: 1. FW 升级成功后，有些机器测试依然fail 。数量不明。（因为被FW升级失败的前置case 给掩盖了） 杨楠的机器证明是这种情况，拆开机器后，弹点上基本上没有压痕。飞线焊接后ok 更多故障机还在筛选返回，预计11/24 会有2台类似故障机器到厦门 ME ， ME分析定位为后壳被顶起，导致接触不好（按压后壳后，可以无线充了）（同批机器切片发现，后壳有顶起 大约0.27 ,更具体数据见ME的报告） Rootcase： 弹片和coil 接触性问题。 推测 是小A壳变形导致的接触不上（可能是边上泡棉顶起来了） Solution ：ME 主导 DVT1 ok | link | 文亭 |  | IKSWW-75804 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-11-12 | 4.EVT | 3.Charging | 4.Build | S3 | Closed | Issue：产线反馈，CQA1 32.3% 机器无线充测试fail Analyze: 1.情况1FW 升级失败，这个对应CR 。拿到两台机器功能都恢复了。 针对这个情况下一步：出临时FW版本来回刷，看下是否可以复现故障。然后分析具体原因和电压波形情况 2.情况2 有1pcs机器可能真有问题， N0TI050112 这台的故障是stack 小板弹片由于首板焊接过导致的问题。 这个已经手写首件，没想到还是拿来装配了。 （这明显外观不良。忽略 ） 。 Rootcase：FW 升级失败：1.1 由于无线充再stack 板子上，所以BT站点测试无法给无线充IC升级FW 1.2目前开机升级FW，是一开电，IC供电电压不稳，就立刻进行FW操作，导致概率性失败，电池电量低的时候fail概率越大 。 （而EVT产线就是不插充电器直接开机的，没有一次插充电器再开机的操作，电量又比较低，因为前面的站点也没测试来卡控电量，恶化了这个情况） Solution ：1.1 FW操作在给电源后，delay 25ms ，然后再进行FW操作。（这样更保险，避免供电不稳就开始操作引起失败）--待SW更改后测量波形确认 。plan 11/25 1.2 站点测试看是否可以双保险，自动化测试，直接执行强制升级命令 并回读FW版本来确认升级成功 ---SW 和 factory 沟通完成，DVT1 正式导入 DVT1 ok | link | 文亭 |  | IKSWW-75804 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-11-06 | 4.EVT | 6.Display/Touch | 4.Build | S2 | Monitor | Issue：产线反馈，出现1pcs闪屏，交叉验证故障跟随主板。（周六反馈CQA1检出来2PCS，产线检出来3PCS，待确认） Analyze: 1. 请产线在白屏状态下调节屏幕亮暗，发现闪屏频率没有改变，调整分辨率也没有改善。感觉和ELV关联性不大 2. 抓Log给软件分析中； 3. 已经请产线寄一台故障机N0TR050117回来分析。 11/10：log软件分析，闪频是触发了ESD Recovery机制，等待周一新版本复测看看 —— 测试30min，无出现闪屏； 4. 通知工厂故障机刷96的版本验证 Rootcase：VTDR的DDIC的ESD Revovery机制需要在HS mode下读取，之前的版本是在LS mode下读取导致。 Solution：1. 产线工厂模式验证了4台故障机刷了新版本，CQA跑了一遍循环，未再复现闪屏； 2. ESD检测模式修改成HS mode改入主线。—— Done | Link | 廖哲霖 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-11-03 | 4.EVT | 12.EMC | 5.1 Bring up | S2 | Closed | ISSUE: VBAT D2751反馈异常，EVT Bringup文亭手头板子大电流，以及芳梅手头一台机器都有出现。 Analyze：1.测量电阻，没看出异常，反向19.85K，正向∞，和正常的比对差不多？ 2.产线去掉CPU 屏蔽盖后故障消失 3.发热点位置在快充IC附近，而且是靠近左下角slave 快充IC附近 Rootcause： 推测：CPU 屏蔽盖有些金属造成短路 和 快充IC大电容 短路造成大电流透过快充IC。非常临界，加热等操作都有可能破坏现象 Solution： 1.ME 主导确认屏蔽盖本体问题和解决。 2. Impact：EVT的机器随时可能会自动关机。 |  | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-10-20 | 3.PEL | 11.Thermal | 5.1 Bring up | S3 | Closed | ISSUE： MCHG NTC 温度读值不对？（AUXADC_MT6375_NTC） rootcause: 双贴了NTC solution：EVT change SCH & CPB& BOM ，remove 1 pcs NTC |  | 德太加 |  |  | 1.SCH

## Dallas
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2026-01-05 | B.PVT | 9.Memory | 5.6 User Feedback | S2 | Monitor | Issue ： "Micron UFS doorbell time out(IKSWW-100968)：问题出现在2台DVT机器，1台PVT机器 Log分析，出问题时，UFS无反应，只有等watch dog time out reset才能恢复，所以QC的增加timeout方法不能解决问题，重点还是需要推动Micron分析原因。 Micron 分析：初步给的结果是 log 看到VCCQ 低于器件SPEC门限的log信息。电压最低到达1.12V ，低于器件SPEC 低门限 1.14V 。 Rootcause：Suspect1：VCCQ 电压低于器件SPEC 低门限 1.14V。 2.但是是推测，不能确认是否是rootcause ，需要micron 继续分析。 Solution： Action1：SW 更改VCCQ电压输出设置，从1.08V~3.04V 改为 1.14V~1.26V ，initial 电压1.2V 要更改才有效 Action2 ：相关的电源 更改LPM mode 为NPM mode | Link | 嘉琨 | 敏敏 | issue 汇总页面 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-11-24 | B.PVT | 3.Charging | 4.Build | S3 | Closed | Issue ：Dallas 故障现象，runin 过后，有的机器插入快充充电器 就出现 反复出现充电图标的故障现象。 插入 USB 和10W充电器，没有故障，可以正常使用。 重启机器后恢复 。 DVT1 RUIN 后的机器出现2pcs （1.27%），PVT RUIN 出现15pcs （2.11%）（截止11/27 统计数据） Rootcause： dallas 电量计从NFG1000A升级到MPC8011B ，主要优势是 MPC8011B的运行内存加大。但是 ，FW设计的时候I2C控制逻辑部分的代码运行空间 从 原来空间 转移到 新扩散的空间中，而新空间的运行速度慢一些， 和 I2C timeout的逻辑 存在逻辑冲突， 存在逻辑漏洞，有低概率导致芯片进入deepsleep模式。一旦进入这个模式会拉住I2C总线，进而导致开机的时候快充IC初始化失败，就出现了接快充充电器插入的时候 反复出现充电图标。 其他线索：目前从fail log 中发现，这种情况下，反复读取电量计后，I2C总线会恢复过来。所以就有了workaround的思路。 Solution： 1 Workaround ：开机的时候对电量计先进行持续读取让I2C总线能活过来，然后再进行快充IC初始化。---plan SW 11/28 进入主线。 2.根除方法：Vendor 将I2C控制代码改回到和NFG1000A 一样的空间，来保证电量计本身不存在这个bug。 2.1 PVT末段的剩余电池，协调厂家过来对电池本体升级后再装机， 并安排压测确认没问题 了---- close 2.2 量产来的电池需要更改过来----ongoing，KP 闲军跟踪中 其他信息：Avenger 也同时出现一样的问题。解决逻辑和dallas 目前安排的一样。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-10-21 | 5.DVT1 | 20.NFC | 4.Build | S2 | Closed | Issue：近期生产线与测试环节出现大量的eSIM概率性掉卡问题。经初步分析，软件层面发现有接收中断（Rx Break） 的异常记录。 CR：IKSWW-60856/ IKSWW-61451 / IKSWW-57936，其现象与本问题一致，但缺乏关键的Modem日志。需要安排重启后进行压力测试，复现问题并抓取Modem日志。 Analysis: 1.工厂环境下的“假性”掉卡：现象：在工厂版本的软件上，执行 -w 命令（恢复出厂设置）后均会出现掉卡现象。本质：底层Modem实际仍能识别到eSIM，但系统UI界面未能及时刷新状态，从而显示为无卡。 2.真实待机下的“真性”掉卡：现象：设备在待机状态下，eSIM会彻底掉卡，无法识别EID。此问题在原有机型上概率约为1-2天出现一次。触发条件：当SIM卡槽1（SIM 1）插有实体卡时，eSIM掉卡的概率显著提升。其触发率遵循：实网卡 > 测试白卡 > 无卡。 根本迹象：通过逻辑分析仪抓取波形发现，在eSIM掉卡前，其通信波形（CLK, I/O, RST）均正常，但eSIM芯片本身无响应，疑似进入“死锁”状态。 临时恢复手段：只有重启设备才能正常识别。此外，实验发现通过NFC向eSIM发送一个复位（RST）信号，可触发Modem重新为eSIM上电并识卡，也能实现恢复。 Root Cause: 经深入排查，问题的根本原因锁定在Modem与eSIM芯片的初始化流程上：Modem复位时，未向eSIM芯片发送必要的 Terminal Profile 指令。由于该eSIM芯片（Thales供应商）默认开启了 UAP（USAT Application Pairing） 功能，此功能若未收到Terminal Profile，会在255个周期后自动关闭eSIM，导致其进入 Mute（静默/无响应）状态。 Solution: 1.SW : 向高通（Qualcomm）提交案例，申请修改Modem底层代码，确保在卡复位流程中必须发送Terminal Profile指令。 2.eSIM : Thales获取默认关闭UAP功能的eSIM芯片或配置文件。 3.HW: 在PVT 2nd 阶段，修改PCB板设计，在eSIM的VSIM供电线路上串联电阻，以隔离来自SIM2的潜在电源干扰。 | link | 李果 |  |  | 1.SCH
2025-10-11 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | ISSUE：case3 DVT1 BT 站点测试 有7pcs（截止10/13）二供主板slave Chargepump 固定fail 在 ACCESSORY_CURRENT_CAPSWITCH_Slave，至少包含：N1DA1D0187，N1DT170182，N1DT170181 N1DA1D0103，N1DN1V0101。N1DA1D0170 和N1DT170148 （10/11 增加） Rootcause： 1. double 确认结果：板子装机，用68W充电器功率到不了68W，只到30+W就重新从0W开始了，这个是slave CP fail 的一种表现。 2.抓log 正向分析--slave CP I2C不成功，初始化时候就开始不成功 3.故障板子N1DA1D0170产线 测量R2837=6.24KR左右，和中值6.19K差不多，地址选择电阻看起来没问题。 【10/27】：1.故障厂家确认可以拦截。现在加入拦截机制，并且要留出一定的margin。11/1 前提供1000pcs ok 物料给到moto 做验证。（目前我们外部设置的地址选择电阻在6.19KR，新加拦截机制检测门限在6.4KR 以上pass。） 2. 根因分析：目前推测是制程问题导致 的 地址选择pin 的电流检测门限偏差（最后等效为 电阻检测范围偏差） 10/28 会和厂家第二沟通会议，待更进一步确认厂家 更深层次的根因。（包括 不同批次的偏差情况，以及后续长期拦截的门限值是否要调整 等相关问题讨论。） Solution：【10/30】：Action 1.厂家确认增加拦截，拦截到6.5KR for这批物料，第一批1000pcs for Dallas，计划 10/30 发出，预计11/1 到达武汉。 2.设计上我们选用4.99KR 1%进度电阻来加大margin （根据供应商的整体数据仿真，最低容许电阻门限在6KR左右，咱们选择小于这个范围的值就没问题），确认不会再出现类似故障。（寄过去的故障品用这个阻值试过也都ok了的） PVT 8+256 的BOM 试产这个物料， PVT试产结果- 301 pcs ，all pass close | link | 文亭 |  | IKSWW-59901 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-09-25 | 5.DVT1 | 2.Power | 4.Build | S3 | Closed | ISSUE：4G BT 站点 shipping mode 电流测试项fail ，retry pass 。IKSWW-51092 ，复现概率极低（2%左右） Clue：0. dallas Vbat 就连着两个快充IC和PM8350B。也就是板级测试执行shipping mode后，只有这些能漏电 1.从故障板子看，测试到的电流有时候小，有时候变动 2. 故障板子拿到后，测试漏电流，底电流正常 3. 故障板子拿到后，测试shipping mode ，电流正常 4. 故障板子拿到后，先操作快充的ADC后，直接测试shipping mode ，Ibat 电流再900~1200uA之间跳变，和产线反馈的故障机的400+uA 和 70uA之间跳变的结果不匹配。 Rootcause：suspect ，4G BT 站点测试后，某个器件没有正常关闭，导致漏电流过大。（而且是波动的电流）---怀疑方向就三个： 两个快充IC 和PM8350B 下一步：1.临时测试包，去掉4G BT站点所有充电相关测试项，压测，看是否会复现问题。 方向2：同步评估去掉shipping mode，看下存储时间。 如果满足不了12个月，考虑参考Houston将出货电量改为60%。 solution：去掉shipping mode，看下存储时间。 如果满足不了12个月，考虑参考Houston将出货电量改为60% IKTM-13379 Dallas remove shipping mode & change storage battery capacity from 50%to 60% | link | 敏敏 | 文亭 | IKSWW-51092 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-10-11 | 5.DVT1 | 5.Camera | 4.Build | S2 | Closed | 5.Camera 4.Build S3 Closed "Issue: IKSWW-54362台报主摄拍照dump。 （3台1100台一供） Clue： 1.均是主摄测试fail，且log均提示的MIPI error Root cause： MIPI cphy参数和目前硬件搭配不是最优 Solution： 优化MIPI cphy参数( 修改后EQ=0x0B， CDR PGM=0x40，CDR Coarse=0x0B)，待软件提供版本给产线。" ---10/13 retest fail ，reopen ，软件参数未提交。 10/15 新参数有效导入产线故障机后验证pass 长期：houston 上的参数到dallas 参数为什么就不生效？ SW主导确认 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-10-11 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | 7. sensor -M-sensor 受到干扰影响 clue：隔磁片规格更改for hac 优化。可能影响到M-sensor 了。 solution： DVT1 1供机器通过优化参数解决了，测试5台都pass了。 |  | 小熊 |  |  | 4.Parameter
2025-10-10 | 4.EVT | 3.Charging | 4.Build | NA | Closed | ISSUE：DVT1 整机AR站点测试 个别机器slave Chargepump 固定fail 在Cap_Switch_Turbo_Acc_Curr_Cap_30W_01_slave Clue： 1.用真充电器68W，可以看到功率是出来了的，没有fail 。共5台 2.Case1 ：其中4台（分析机器是N1DV110139），在使能快充前 控制电源电压后 增加delay 1秒钟 ，4台复测pass 了 3. case2 ：但是还有1台N1DA120231 fail ，现象一模一样（没有cp的电流） 更改测试程序为每次生压后都再次EN，case2 也pass 了。 转入monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-09-25 | 4.EVT | 2.Power | 4.Build | NA | NA | ISSUE：IF 有些板子不良后，需要强制下载才能恢复。 Clue：SW 先主导看，这边只做一条记录。 |  | 文亭 |  |  | 6.No Change
2025-09-01 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | ISSUE："EVT ATT tumble WH195778 1st 6:Cap/SAR sensor Ch2 no function:D8(450)- 0901已返回厦门，分析中 7:Cap/SAR sensor Ch2 no function(Recovered after reboot :D10(500)" 。已恢复 坐压试验 也出了一台SAR sensor Ch2 no function 分析结果一样。 合并处理 Clue：0. 二供机器实验也出现一台450滚出现无作用，重启后恢复了的。 1.机器回来的时候，故障复现。重新开关机依然复现。 2.插入USB后，故障消失 3.装成整机，跌落压测，复现1次。这时候用WIFI adb 查看，发现CH2 没有读值。（所以看起来非门限fail问题） 4. 跌落后又复现了。加热焊接也还能复现。 而且这时候插入USB 无法再恢复了，判断为IC彻底坏了。 5. Houston 是没问题的。 capsesnor没改，可能是其他变化导致的应力发生变化 Rootcause：推测是 IC 被应力破坏，处于半坏不坏的状态。 将这个IC寄给厂家分析内部情况，预计9/10 返回分析报告。 ME 确认dallas 和 houston的结构应力情况。 Solution：建议移动capsensor ，来优化作用到capsensor应力。 Option1 可实现的是往左上角移动，最后移动到屏蔽盖外， DVT1 一供跟踪 DVT1 一供都测试完了 pass，先close |  | 小熊 |  | 分析PA | 2.PCB
2025-09-16 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | ISSUE：EVT二供机器自测，发现1台机器，关机充电后，出现PD充电器会出现fail 。最后不充电。1#机器一直fail 。 另外借了2台机器 ，补充复测了8次左右，2#机器概率性出现2次，重新开机会恢复，不好复现。3#机器一直无法复现。 clue：1. 1#2#机器的log 分析 都是BAT OVP 被触发了，关闭了CP。但是实际上电池电量都基本没电了（小于10%，电量计读到的电压才3.7V左右），快充IC就触发高电压保护，门限是4.8V左右，这不正常。 2. 拆机测量波形，确实有 Vbat 高压出来，Vbus 也抬高了电压，但是Ibus是先下降的。 推测是因为充电电流停下来导致的Vbus电压提升，然后导致Vbat 电压过高。 Rootcause：根因是在二供电池端的OCP值偏低，和SPEC不符合 ，导致的 SGM41606S 触发OCP过充行为而后会连带触发OVP行为，停止充电了。 Solution ：DVT1 二供电池修复 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-08-04 | 4.EVT | 3.Charging | 4.Build | NA | Closed | RISK：PEN current test ，EVT 截止8/26早上 数据看，有一些读值0的情况出现。 出现一次65高数据，复测pass。 概率性出现0值的机器，推测可能是FPC 或者触点接触问题。 需要ME特别关注。 线索：有发现个别机器明确接触问题。 其他机器需要找到机器跟踪，看下是否会复现。 rootcause：TBD solution： 组装部分：DVT1 增加MMI测试，避免机壳没有测试就留到装配。（EVT处于调试阶段，一些机壳没有严格管控就流下去了） UCT 测试部分：DVT1 增加 hall IC的检测，来判断工装笔B是否在位，来进一步确认是否漏装笔就进行测试了。 | link | 文亭 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-08-04 | 4.EVB | 12.EMC | 3.Review/Simulation | S2 | Closed | RISK：ANT 上面 ATVS 的方案 BOM 评审结论：提出验证通过后加二供 咱们只有一次DVT，要如何验证？ 8/4 结论： EVT 先用华新科 主要验证一供（样机 EVT BB申请了6台一供for TCC ESD）。 松下放到二供中的试产，并和邓玲沟通做两台ESD作为备用。（样机要和邓玲沟通好） DVT1 根据EVT的情况来定。 结果是都pass。 |  | 廖哲霖 | 文亭 |  | 6.No Change
2025-08-04 | 4.EVB | 12.EMC | 3.Review/Simulation | S3 | Closed | RISK：主动笔充电相关电路（包括ADC 检测）被打坏的风险 1. ESD期望设计方案：1最优 在机壳外挡住，2.优 挡不住尽量能接地 或者 3.次优放个间接接地（就是笔身周围给出一小块GND，不接触，但是有露出来。） 4.最差就是悬空金属块（当前状态）。 基于ESD 防护， 尽量不要让ESD进入到电路。请ME 帮忙再想想方法，看是否有机会。 2.EVT试产前，用EVB 飞线进行摸底，看加了TVS后，能抗住多少KV ESD冲击。（充电部分和 电流ADC检测部分） action： 1.实体笔 样品，ESD摸底，ESD轻松的就从笔身传递到触点。 所以目前推测的ESD进入risk 是真实存在的，而且较高。8/4 done 2. 采取了很多措施，已经处理的。 主板端EVT 就会导入TVS 来防护两个弹点对应的电路。（电源正极 和 ADC 采集口，分别各加一个TVS 器件在主板）。done in EVT MB PCB 。具体型号优化选择，EVT 发BOM 前完成 --BB 8/8 3.一些否决了的优化方向：笔身金属 在任何一个位置坐间接空气放电的可能性 ： ME 评估 完全没有办法，IP68防水要求，需要用塑胶完全堵死。不能露出任何一点点 导电金属体。 直接接地就更不用说了----目前为止没有可行方案。 ---ME chenjianxi comment ，没有方案。 4. 备用方案1：将主动笔FPC 上增加加强版，然后加两个TVS，再防护一道。 ---ME yuming 评估是这个导致弹片压力增加，有风险，不建议直接进主线。建议作为备用方案。 增加一版V02 FPC。增加加强板和TVS 以及点胶。具体待发板，plan ： --ME/BB 8/8 " 9/1 BB ESD摸底两台数据都打完了，充电和非充电状态下都有打，15kV/18kV压测下，未发现有Fail的状态，目前摸底结果感觉还行，会继续Monitor下TCC的数据 TCC数据：6 台机器，15KV实验完，笔都是ok的。 补测18KV的笔位置ESD实验。 测试手机ok，1支笔fail。厂家分析。手机ok ，close risk | link | 廖哲霖 | 文亭 |  | 6.No Change

## Equator
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2025-11-11 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | NA | Issue ：PRC 售后故障机 356070750758578，不开机不充电 |  | 文亭
2025-11-11 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Open | Issue ：IKSWW-69570 Equator 充电只显示"充电已连接但是不充电“// 新品X70Air DOA申请 clue：第一台IMEI 356070750759253，寄存器看PMIV0102 有些寄存器不对。 该机器重启不会恢复。最后是刷机后恢复了。机器返回武汉，11/11 ETA 武汉工厂 ，shatong2 手上。初步看是可以充电的。 第二台 IMEI：356070750876016 ，11/4 签收，当天反馈充电中但是持续掉电，更换充电器无效，退机。 next ：第一台故障机寄往SW。第二台确认在哪里，以及故障情况。 | link | 文亭
2025-09-28 | B.PVT | 3.Charging | 5.5 Certification | NA | NA | [s1]Issue ： Equator 1725 认证fail，低温下提前停止充电 （一供-2度，二供-10度 。期望值是在-20度+/-3 度） clue：1.log 分析看到，是充电带载电池电压达到4.2V了，走停充流程了。 2.低温下电池内阻看起来很大，-2度之后ATL的内阻258MR，-10度时候CSMOX的内阻458MR。导致的压降很大，一下子就到4.2V了。这内阻正常吗？低温下的电芯内阻曲线如何？---待KP 确认 Analysis/Root Cause: HW根因：低温下电池的内阻会很大，到几百mR，温度越低，就内阻越大，当固定电流下，压降会越大，就会导致提前触发4.2V的低温停充电压。 当前问题1：在-1度左右触发fail的，推测原因是0度以上电流是很大的，电压也很高（带载电压可以到4.5V），转到-1度时候，转换策略会立刻触发判定已经充满（实际电芯电压在3.7V左右） 当前问题2：在-1度这个位置没出问题，继续往下降温，由于限流后还持续充电，温度也越来越低，内阻越来越大，所以电压持续上升，最后再-10度左右（这个值和电池电量有关系）达到了4.2V，然后没有办法继续走完CV 很快就停充了（从log 看到的信息是几秒钟就停了，原因不明）。 当前问题3：当触发充满的状态后，即使温度恢复了，也不会再重新启动充电。就是低温停充恢复机制这种情况下失效了。 当前问题4：插入充电器一瞬间电流很大，然后再变成目标电流。这个会大大加大触发停充的概率 Action/Solution: push_new_image3.zip 主要修改：低于0度的充电电流限制为350mA（ 降低问题2机会 ）。更改FCC来达到一上来的电流不会过大。（解决了问题4）. 前提条件:低温验证不要从0度开始插入充电器测试，要低一些，建议-10度插入充电器，然后继续降温验证。（用操作手法规避问题1） 机器初始电量要低于5%比较保险过。 最多也不能超过10%（越高越可能fail。）这些值是基于厦门温箱环境得出来的结果哈。 摸底by chenwt：这个版本初步验证ok了，低温可以到-21度才停充，-19度恢复充电。 （不触发停充就不会触发问题3） 10/9 认证发出 ：push_new_image3.zip 这个版本给UL 进行复测，根据自测要求 。 反馈测试pass了。 SW 10/9 改进主线 wave1 | link | 文亭 | 李果
2025-09-26 | B.PVT | 3.Charging | 5.6 User Feedback | NA | NA | [s3]Issue ： Equator 关机不充电 问题IKSWW-51939 线索：1.一次QC3+33W充电器故障后，不充电的时候，看到Vbus5V Ibus80mA左右。D+D- 电压3.05V 从这些信息推测：1.CP的OVP是打开了的。这样才有80mA这么多的电流。 2. 补充模拟实验：1 ：正常关机的时候，DP DM 外部强拉3V，再插入QC3+充电器，看一下波形和机器的表现。 | link | 文亭
2025-09-12 | B.PVT | 10.USB-C | 4.Build | S2 | Monitor | [s1]Issue ：PVT 批量发现USB/充电不识别的整机（之前各轮试产未发现） （TCC 4台，工厂2台，预备送媒体机7台，据不完全统计， 不良发生概率在7%左右） 故障现象：无法识别USB/无法快充（可以5V慢充），关机重启故障依旧存在（软重启） Root Cause:1. 误识别成uUSB接口，导致Type-C 识别异常。关键点是这个寄存器及相关初始化流程只在系统VBAT硬上电时候更新一次，后续不会再进行更新。 2.shipping mode的方式有问题导致的概率性PMIV0102 异常掉电，导致下一次上电瞬间检测错误。 Solution: 1. Workaround Patch机制：在开机时候立即读下2b70寄存器，如识别是uUSB，会重新做一次硬开机后再检测一次option接口，确认是否是Type-C 导入用户版本和工厂版本主线--done 2.Equator 项目取消shippingmode，按照60%电量出货来保证一年以上存储时间。（来不及验证更改稳定性，为避免奉献，不导入新的变更） 3. QC 提供NEW shipping mode entry flow ，待正确的导入MOTO 项目（需要开发 及 压测来验证有效性）---SW plan 9/23 ，压测 Plan TBD QC 新的PMIC 需要新的进入shipping mode的流程来保障不会出现该问题，包括PMIV010X, PM7550B, PMIH010X 这三个系列的PMI器件，原因是这三个系列的PMI在进入shipping mode前需要正确的下电配置后才能保证下次上电硬检测是稳健的。而旧的shipping mode流程是adsp直接写寄存器断了电池的电，无法保障PMIC正确完成下电。 NEW shipping mode entry flow 是将配置标志位给到PMK器件，然后由PMK来负责执行所有PMIC的下电流程完成然后再发起断开Qbat 的操作来断电池的电。（特别说明:SM7635/SM6650/QCM6690, SM7550, SM8635 这些平台的SW架构不支持新的shipping mode方案，只能走Workaround方案） | link | 文亭
2025-09-08 | B.PVT | 1.Platform | 5.4 ALT | S1 | Open | [s1]Issue ： M21 Shock Method 516.8 Procedure IV WH196390 D1 NEQR480147 Unable to read SIM Card:D1(26,Bottom right Back Corner)- TA-LotX Tumbler Test WH196385 D2 NEQR480203 Unable to read SIM Card：D2(300) | link | 李果
2025-08-11 | 7.DVT2 | 5.Camera | 4.Build | S3 | Monitor | [s1]Issue ：Equator Rear main camera OTP Validation Test，EEPROM error FR 0.96% 8/900 Clue: 1. DVT2 2供首次出现EEPROM I2C读取error log, 实测不良波形，确认是EEPROM无响应地址。 2. 测量读EEPROM之前的波形，开机时camera i2C平台内部上拉，硬件上在I2C上做了外部上拉，会往VIO上漏电 Root casue: I2C平台内部上拉2.2K, 和外部上拉1.5K（1M clk）互相漏电，这个漏电压会影响兼容性差的eeprom 内部逻辑异常 Solution： 软件去掉内部上拉2.2K，外部上拉改为1K (来保证I2C 在1MHz clk 情况下的信号质量） LL: 改进EEPROM测试方法，开机测量，并关注EEPROM读取之前的供电电压 开机阶段测量camera时序 | link | 芳梅
2025-08-07 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Monitor | issue: equator 地磁精度受接地影响很大，需要调整螺丝的锁付力矩 Equator项目目前地磁在高功率充电下，地磁的角度偏转会比较不稳定。 分析下来，和主板的接地情况关系比较大。 下图标记的③的位置位于充电IC边上，充电时，它会从接地良好的最短路径回流，也就是②和①通过中框回流。 因为螺丝锁的情况及主板的接地差异，导致从②和①处回流的电流值有差异，从而影响到地磁的性能。 我们建议加强如下③的接地，减弱①和②的接地，从而减小地磁在高压充电下收到影响。 也就是在可接受范围内，尽量增加③的锁付力矩，减小①和②锁付力矩。 明天如果有组装，帮忙直接调整一下力矩。 |  | 小熊
2025-08-07 | 7.DVT2 | 7.Sensor | 4.Build | S2 | Monitor | 目前大致情况为： 1. 昨天又找了一台CT超10000的切片分析，看各部分高度是否符合设计 2.周二ME分析了3台13000的机器，都只拆掉了主板，重新按压PUD板的中部，数据就能到5000（这个怀疑是中框上的泡棉是否贴合有问题） 3.再之前，上周ME拆除过10000+机器的屏幕，然后重新装贴中框泡棉，也没有保压，屏幕掩在中框上，CT就正常了。从这点ME认为泡棉问题也不大。最初的100多PCS机器，泡棉是手工装贴，没有治具。可能影响精度。当初有泡棉贴歪（非治具贴）的，外边缘破损（ME认为是某道工序造成，但是排查没有找到具体工序）的。 4. FAE今天会到现场协助分析，看下有没有进展。晚点或者明天更新。 目前，P SENSOR的CT还是高（设定limit 8000，超门限的有约6.5%），并且ME没有找到清晰的调整方向。 今天Vendor那边的FAE会过去武汉现场看一下情况，明天我再和你更新一下情况。
2025-08-07 | 7.DVT2 | 2.Power | 5.4 ALT | S2 | Monitor | Issue：ISSUE: Back pressure automatic shutdown/Unexpected auto power off:D3(NEQE220145)(250N/300N)21:00pm 8/5/2025 D4(NEQE220240)(300)，https://idart.mot.com/browse/IKSWW-30027 Clue：1. 机器带回无法复现问题， 等待软件log分析 2. 单板实验结果待测？ 屏蔽盖内绝缘纸被顶破 | link | 敏敏
2025-08-04 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Monitor | Issue：UCT站点的 OTG测试10%左右不良 （包括后续 模仿数字耳机测试同步也大概率会fail，都是走Host USB 通道） Clue：1.“故障机器”用手工U盘测试，没有问题。测试眼图也没有问题。说明手机本身没有用户使用端的问题。 2. 只有UCT站点有问题，包括USB也有问题。其他站点USB没有问题，推测UCT这个站点环境USB需要比较苛刻的参数。 3. 调整了 Option 8 参数 （host mode 的USB 电平降到最低），故障机可以pass 了。 但是最终DVT2正产末期，还是拦截到2台fail 4.最后这两台fail的机器，手工测试OTG 还是pass。盲调9,10,11 三组参数，还是不能pass 5.SM8750 （Orion 项目）需要类似问题，没有解决。取消UCT站点的OTG测试项，用数字耳机测试项来cover 硬件通道正确性。 rootcause： UCT站点（包括夹具，cable ，U盘）---整机（主板 -主FPC-小板 – USB软参数 ） 合起来的匹配兼容性问题 solution ： 1. IKTM-13189 Equator PAT 增加 OTG 测试 和 数字耳机测试 ，PVT导入， monitor PVT情况（同时先保留UCT测试，确认fail的机器继续往下go ， 看PAT是否可以pass。） 2. 协调一套UCT设备，提供给QC 寻求帮助，尝试寻找可能的优化方案。 毕竟UCT OTG 测试失败是从 SM8750 （Orion 项目）和7750（equator项目） 两个平台的项目第一次遇到。 其他信息：Orion 项目 处理方式是 去除UCT的OTG测试项。 用PAT 和UCT的数字耳机测试项来测试相关通道。（USB host 功能）。 | link | 文亭 |  | IKTM-13189
2025-08-04 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Closed | Issue：UCT站点，USB 不识别率很高 Clue： DVT2 新增加UCT站点的USB连接需求。 拦截的机器再其他原有的站点，目前测试判断没有识别不到的问题。 PC to 夹具的线换成放大线，暂时不能解决 其他idea：是否可以再调整下USB参数？ --RD comment 不建议，其他站点DVT1到DVT2 调整了参数好不容易稳定下来。 现在新增加UCT 站点的需求进来，没法针对性调整，一旦调整，所有站点要重新确认，不排除变差的可能性。 建议维持现状，如果其他站点能继续维持正常 solution： 更改会DVT1的方案，用无线WIFI 链接方案，做UCT站点测试 |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-07-28 | 5.DVT1 | 10.USB-C | 5.4 ALT | S3 | Open | Issue：NEQE140204 USB接口异常， 现象： 正反面插入经常不识别充电，偶尔识别出来有5V充电，但是马上断开。请结构和熊雄接下来看下一步怎么分析，谢谢！ 分析步骤：1. 拆开后壳，不拆usb小板，外面接到另一个ok的usb小板，充电功能，识别口都正常。判断问题在usb小板上 2．拆除usb小板，测量typec口舌片上信号到小板pin不通 3．显微镜下观察到typec口左侧小耳朵和信号pin脱焊 4．按压typec 铁壳时，焊接pin能看到脱焊 Rootcause： typec口左侧小耳朵和信号pin脱焊，导致信号不通。 下一步：交于结构和KP分析.
2025-07-28 | 5.DVT1 | 3.Charging | 5.3 EE DVT | S2 | Open | Issue: 泡水测试后到下一步复用机器实验前，发现显示充电图标 但是充不进去电。Mxc04 WH193926 2nd source lily pad， D1 initial Clue：1.关机充电到开界面前可以充电，而且当系统起来进行判断后就不让充电。 无线充电也类似结果。电池电压，温度，PD协议功率识别，都是正确的。 以上信息推测不是CC1 或者CC2 的问题 2. CID pin 上有0.3V电压，所以看起来也不是CID pin电路问题。fastboot boot mode 可以充电一小段时间（可以用来做临时补电然后抓log用）。 3.Log 给SW分析：给的判断是PMIV0102 的充电状态不变，aicl是0 （意思是否指向说就是PMIV 出现异常了？），充电状态一直是not charging--继续跟踪 4. EXP：长按开机键1分钟来确认是否可以复原。结果是依然fail。（ 9秒和15秒的时候都各自重启一次，之后就开机了） 下一步：信息share给QC，看下是否有什么分析建议。等待回应 这台机器 ：确认 主FPC连接器上有一些导电材料导致 USB NTC 信号对地短路，进而导致USB NTC 温度过高导致保护了不让充电。 进一步分析： 外观看：主FPC连接器端有个 导电材料 ？ 不像是盐水导致，更像是一种生产材料，非外物进入机器。颜色和焊锡很像，银灰色，但又不是实的而是像棉花絮的，碰触就会变形的导电体（有点像导电泡棉的细碎？ ） 其他的：SUB端的一个pin腐蚀了（但是这是个GND pin，不是导致故障的直接原因）。 板子上我没见过这种材料，建议大家及产线进行下一步确认这是什么，以及怎么进入主FPC连接器的。 Rootcause： 确认 主FPC连接器上有一些导电材料导致 USB NTC 信号对地短路，进而导致USB NTC 温度过高导致保护了不让充电。 板子上我没见过这种材料，建议大家及产线进行下一步确认这是什么，以及怎么进入主FPC连接器的。 Solution：TBD |  | 文亭 |  | RPA分析
2025-07-23 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Monitor | Issue; 滚筒180后，上SMART PA无声 分析：从寄存器看，CLK信号未送到SMART PA,重新加热SMART PA 恢复正常 RootCase: SMART PA右下角虚焊 Solution： 结构反馈非大应力区，继续监控 | link | 院长
2025-07-23 | 5.DVT1 | 6.Display/Touch | 5.3 EE DVT | S1 | Open | Issue; no main display:D4(26)-按压连接器可显示，松开不显示。共三台， 分析：屏幕连接器大电流PIN Solder脱焊，测量导通性异常，按压可连通，显微镜下观察到缝隙，分析结果一样 RootCase: 焊盘受外力导致的断开，断开位置结合力不足，焊盘开窗0.45, 实际溢胶后，有效焊接面积0.3mm Solution： 2供Kingwong内部修改焊盘加大覆盖膜开窗，焊盘原设计0.45mm加大到0.6mm,去除完溢胶，有效焊接面积0.45mm, 同一供DVT1数据。 2供封样时间需要等到二供FPC DVT2实验全部合格后，才能启动封样工作，需要项目同采购提前沟通。 | link |  |  | RPA分析
2025-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S1 | Open | Issue: 打完ESD TIS/TRP，D1/D2/D3/D5机器，B20/28有问题,B42一台变差问题，ANT0/ANT1-Fail Clue：返回D1机器，分析 1：ANT7: D1异常Band42机器复测TIS，确认ANT7无异常； 2：ANT0: D1机器ANT复测，发现ANT0异常，无源下观察波形和之前摸底出现Tuner损坏的故障现象一致，cmd切Tuner波形也没有变化，判定是ANT0的Tuner器件损坏； 3：ANT1: D1机器ANT1, 更换损坏的电容后，天线测试TIS依然异常，RF测试传导OK。判定是ANT1的Tuner损坏, 今天天线测试发现SW5通路损坏，判断是从主通路进入； | link | 廖哲霖
2025-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S1 | Open | Issue: DVT1B ESD 报一台机器15kV后capsensor全部无功能，ANT很多通道Fail； Clue: 1. CapSensor I2C地址变了，12->13； 2. 一供机器没有此问题，SAR芯片/TVS是二供； 3. 拆机分析发现电容被击穿，CS0通道直接通过电感下地，影响I2C地址，SAR芯片和通路都没有损坏 RootCase: 天线馈点串联隔离电容被击穿 Solution: 1. 25V耐压电容->更换为50V -> 周一天线确认 2. TVS确认，是否是二供影响(一供没有此问题，且走线先经过TVS) | link | 廖哲霖 | 小熊
2025-07-17 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S2 | Closed | issue:Initial check:Headset no function/OTG no function/USB charging is normal, but fail to connect computer:D4-D4知勇带回厦门分析 Clue: 快充测试ok, 连接电脑不识别口。判断D+,D-有异常。 Rootcause：D4 这台是共模滤波器 FL500 掉件 查看FAEDVT1不良板分析，至少发现7PCS FL500掉件 ME 主导和产线装配沟通，修改装配手法和增加治具。 DVT2 导入 | Link | 文亭 |  | RPA 分析链接 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-07-17 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S3 | Closed | issue：MXC06 WH193914 D1 NEQE1B0126 USB one side no function:D1(225)- clue ：1.CC1 线路 open ，断路点在PMIC 屏蔽盖下边沿底下 layer11，具体看链接截图。 （CC线已经走0.2mm宽度了，但还是断了） 2.WIFI_THERM 这个在CC1 边上的线也断了。 再更边的CID_DET没断（断了就直接没法充电了），另外一边的CC2 也没断，所以可以单面充电。 3. 一供机器没有问题，二供还有另外3台类似故障机器，等待返回后确认。 第二台是：WH193919 D1 NEQE1B0131 USB function intermittent:D1(26,Bottom right Back ) ，现象类似 Rootcause：结构应力太大，导致PMIC 屏蔽盖脱开，并拉动L11 的CC线。（ 推测：二供PCB的抗拉拔力可能比较弱导致出现多台断线。 ） solution： PMIC右下角L11走线都改到L10 & L9 ，DVT2 二供PCB导入修改 |  | 文亭 | 芳梅 | RPA 分析链接
2025-07-14 | 4.EVT | 4.Audio | 4.Build | S3 | Monitor | Issue：MIC2气密性问题 Rootcause: MIC 焊盘镀金，需要更换为OSP Solution: 更改主板和小板MIC焊盘为OSP，DVT2更新器件库 LL:MIC器件库修改为OSP，库里已经把项目中不用的MIC器件库删了，目前器件库里存在的MIC器件库全部为新的OSP器件库。 | link | 院长 | 川叔
2025-07-13 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Monitor | Issue：TCC报一台机器VBAT端EOS-150V Fail，另一台，机器复测后Pass； Clue：EOS走线Review，未发现问题； RootCase: 机器正在寄回，收到后分析 —— D4样机收到后，测试正反OTG都OK，故障无法复现，继续Monitor Solution: 1.DVT2主板，VBAT端浪涌管增加下地打孔；2.继续Monitor 3. 寻找更好的浪涌管，型号: ESD56301D04-2_TR（晓云推荐）—— Prado上有验证过 | link | 廖哲霖 | 文亭
2025-07-11 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：死电池激活场景 ，在电池保护电路还没完全激活开之前，就开始转到5V1.5A快充，电流超过电池的期望3V以下上限电流0.1C 。 可能有安全风险。 rootcause：3.1V 是5V600mA 切换到5V1.5A设置点。 而死电池内部保护后，mos的前向二极管有0.5~0.6V。 补充说明：以前项目没有关注这个转换瞬间是否会有超过的电流，因为这个测试难准确监控到电流，log 也无法记录。 需要再排查下，以及风险如何。 solution：Option1 ：调高转换的电压点（负面作用是：低电量电池 充到能开机的时间会拉长，具体值需要 KP 主导 take CR） option2：电池内部是否可以优化？（ 充电时候默认就直接激活电池？ 需要KP 主导评估，项目上基本没机会，只能长期看） | link | 文亭 |  | IKSWW-19238
2025-07-10 | 5.DVT1 | 7.Sensor | 4.Build | S2 | Open | Issue： CT偏高，和Prado相同的参数，当前CT的max接近12000 Clue： 1.交换前壳组件，不良跟随前壳组件。 2. ME对前壳组件灌胶切片，发现泡棉高度稍微高出SPEC。 RootCase: 前壳组件隔离不良 solution：ME增加泡面厚度，新泡棉机器预计07/16组装，跟踪试产数据 next: 跟踪DF数据 | link | 小熊
2025-07-10 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Open | Issue： 60W充电情况下，地磁输出的方位角度会被干扰，最大可能偏转60度。PRC版本表现很明显，EMEA相对正常 Clue： 1.地磁附近的螺丝孔，锁紧后地磁角度偏转明显，拧松后角度偏转很小。 2.DVT1(V05)版本相比EVT(V04)，ANT增加了BOT面地磁附近螺丝孔的露铜。 RootCase:充电场景下，地磁附近的地通过中框回流到GND。回流电流产生的磁场影响到地磁感应到的磁场，造成精度偏差。 solution：和ANT确认，螺丝孔露铜去掉，回到EVT状态 | link | 小熊
2025-07-08 | 5.DVT1 | 12.EMC | 5.4 ALT | S1 | Open | Issue: DVT1 ESD三台机器CapSensor后CH0无功能，重启后不恢复(硬性故障)；另外也在损坏前出现ESD时无功能，重启后恢复(软性故障); Clue: 1. 分析发现是CapSensor硬损坏ESD机器，熊姐分析发现是在主板SAR芯片附近的100R电阻被打穿，测量阻值为开路，更换后ANT0处功能恢复正常。但是USB处感应失灵，进一步测量发现小板上R806击穿，更换新小板恢复OK； 2. 和EVT对比，发现M802的下地电容被天线DNI了，导致M802处静电直接进入SAR通路，击穿100R和1K电阻； 3. 测量隔直电容，发现没有短路【EVT复测二供Recovery机制时，有一台机器在高压下也出现了隔直电容击穿短路的问题，经核查电容耐压为25V，由于只寄回一台样机，无法确认其他样机是否存在类似问题，因此也在DVT1B导入50V耐压电容】； RootCase: M802下地电容C806被DNI导致静电损失下地通路； Solution: 1. DVT1B 小板C002处手工Rework TVS, C806是否可以Rework待天线确认影响; 2. DVT1B 小板C001/C006已确认更换为50V耐压的电容； 3. 针对软性故障，一二供供应商会确认下Recovery机制，并合入(实测若C001/C806处都加上TVS，打ESD时软失效问题基本不会再出现) | link | 廖哲霖 | 小熊
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Monitor |  QBOOT_BLANK_FLASH_01（9008 SW下载），NTF，FR 3.07% -----SW：志龙 BB 文亭 Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 solution：DVT2 对PCB 上介于repeater 和CPU之间的USB 线路进行差分 90ohm 阻抗管控。 monitor DVT2 结果。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  |  | 2.PCB
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Monitor | Issue FASTBOOT_FLASH_01（ SW 大包下载），NTF，FR 2.42% -----SW：志龙 Open Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 solution：1.DVT2 会特别提出对这段线进行阻抗 90ohm 中值管控。 2.调整FASTBOOT 模式底下的USB参数：Squelch Detector Threshold Adjustment. 静噪检测电压门限调到一个中间值 （112.5mv） option4 monitor DVT2 结果。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  | IKSWW-16177 | 2.PCB
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S2 | Monitor | Issue: EQUATOR DVT1 eBT （板级测试）概率性无法识别 端口,交换站点有时候pass ，不固定。 约7.7% NTF clue：1. APEM 一开始数据还好 0.39%，但是后面的其他3个SKU测试数据看就又不理想了 （15+9+2）/(228+95+13) = 26/336 = 7.7% 2.目前信息：这些fail的站点都是夹具上加了各种延长线和开关，非用户场景，用USB直连电脑 是没有问题。 Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 Solution: 1.DVT2 会特别提出对这段线进行阻抗 90ohm 中值管控。 2.调整所有devices 模式底下的USB参数：Squelch Detector Threshold Adjustment. 静噪检测电压门限调到一个中间值 （112.5mv） option4 monitor DVT2 结果。 其他一些做过的验证：1.建议产线再尝试下加信号放大器的线，并调整下放大器的参数。（产线反馈没有明显改善，看最后的情况看哪个站点需要导入 ） 2. 尝试Option1 将眼图改为最大 ，以及option2 将眼图改为最小。实际结果都不理想，没有明显改善。不适合 3.Squelch Detector Threshold Adjustment. 静噪检测电压门限，从默认的87.5mV改为137.5mV （可配置的最大值） option3 ---结果：故障板好了，但是正常板fail了。所以 这组参数不能批量使用，再优化下参数。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  | QC CR ：7969230 | 4.Parameter
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | IKSWW-16494 [Equator][Factory][CQA1][DVT1] OTG intermittent failure solution：调整OTG 断连门限到最大值，初步压测ok。IKSWW-18561 导入主线后monitor DVT2 |  | 文亭 |  |  | 4.Parameter
2025-06-25 | 4.EVT | 10.USB-C | 4.Build | NA | Closed | Issue: EQUATOR EVT eBT 概率性无法识别 端口,交换站点有时候pass ，不固定。 约10% NTF clue：1.交叉测试夹具和USB测试板，有些变化，但是没法完全解决。EVT2 留下两个板子，一个大概率fail，一个较容易pass的做验证。--TE 2. DVT1 USB 眼图测试pass的参数 V01导入后，对保留的两个板子验证，结果没有改善 --BB&SW done。 3.顶针从细针改为粗针，没有明显改善。 （但是也作为后续主要方案，避免因为细针的干扰因素不好排查）--TE 4. 用USB线直接连接最后夹具和电脑试一下（跳过中间的一些开关测试板）是ok的。 用个人笔记本电脑直连也是ok的。--TE 检查电脑前后端口：有变化，但是无法解决问题。 5. DOE 尝试各种眼图参数，先看下是否对该结果是否有改善。--BB&SW 6. 继续尝试换各种线看下结果 --TE Rootcause: 测试夹具整体环境和板子USB 兼容性不好。（电脑端口，USB线，开关板，板夹具 等加起来的综合影响） Solution:以上确认可以导入的先导入，monitor DVT1的实际数据。 DVT1 还是fail ，重新创建一次问题 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-07-04 | 4.EVT | 12.EMC | 3.Review/Simulation | NA | Closed | Issue: 【自测Risk】使用EVT机器，摸底ANT0-Tuner ESD过程中，发现有概率损坏Tuner； Clue: 1. 之前测试EVT实验室回来的一供D1/D5，二供D4，三台机器，天线没有发现问题； 2. 本周天线那里软件tunner-code ready，找邓林协调了一台没打过ESD的机器进行验证，前测ANT0无源，采用天线常用的B28 B5 B8三个频段的code组合，在ANT0区域打了 ±8kV，±15kV，±17kV三组ESD结果，天线复测无源结果Fail(Tuner切换通路失效)； 3. 走线上由于空间限制，ANT0部分TVS是预留在与弹片同面，而Tuner的天线路径线是在TVS路径上穿孔到背面，经过下地电感后进入Tunner。因为Tunner到弹片的位置很近，下地电感和背面的TVS可能保护效果比较有限，存在Risk； Rootcase：空间限制导致走线不佳，前期布局没有预留第二颗TVS位置； Solution: 1. 关注TCC-DVT实验结果，看是否也会出现Tunner损坏的情况； 2. 尝试直接在Tuner面手工Rework再加一颗TVS，然后加上接地导电泡棉，看能否保护住Tunner； 3. DVT2改板，和天线沟通，天线尝试取消Tunner前端的下地电感，让位给TVS，周末Ruiming会调试，下周一左右会有结果；否则就是走外加TVS改版方案；—— Ruiming已确认无法删除下地电感，走外加TVS路线； 4. 让结构DVT1B先导入接地泡棉，增加小板的接地； | link | 廖哲霖 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-07-02 | 4.EVT | 9.Memory | 5.2 BB Test | NA | Closed | Issue：12GB DDR can not run up to 4.2Ghz，only3.2G Clue：8GB OK. Rootcause: 高通在代码中限制12G频率跑到3.2G Solution: 高通提供patch，8-14号软件包含patch，确认已经跑到4.2G。SI启动测试。 | link | 嘉琨
2025-06-18 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Issue：EVT USB eye test fail Solution：import 0xfd57-0x5-0xfd51-0xa ,test ok . import CR :IKSWW-12700 。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-16 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Issue：（定义为无线充电问题4） EVT2 板级测试 TURBO_CHARGE_OVERALL_STATUS 不良 5/58 Clue: 1.无线充电IC读到的电压电流值异常大（10+A ，70V ），这明显是异常ADC值。（然后导入其他后续的逻辑错误） 2. 5PCS 不良。 有1pcs retry 后pass。 有3pcs 更换无线充IC SC9624后OK，还有1pcs 重复写入FW后pass Rootcase： FW 升级过程异常打断（AP申请dump 寄存器）导致升级fail，并且没有再次触发升级的机制。 Solution： SW 更改FW 升级过程，确保升级稳定性。DVT1 验证 | CR ：IKSWW-10183 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-11 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Monitor | Issue: TCC实验室二供EVT1报CAP-Sensor ±8kV下无功能，重启后恢复；D2 Cap sensor no function(CH0,CH4), recovery after reboot. Clue: 1. 观察到D2机器Intital测试中，CapSenor也有无功能的问题Cap sensor no function(CH1,CH2,CH3)； 2. EVT1二供贴二供厂家的SAR IC，邮件厂家沟通提示公司的驱动可能没有合入软复位模块，已经通知厂家联系对应负责软件同事; 3. 周一收到样机，检测CH1/CH2/CH3无功能，确认是校准参数问题；6/17日刷入校准参数后，ESD测试后，SAR-Sensor参数丢失，软件确认软复位机制还没有合入。此外出现了软失效后第一次开机SAR芯片识别不到的问题，第二次开机OK，已经提交CR给软件分析； Rootcause: 目前推测软件驱动未合入软复位机制可能性较大，另外前测capsensor也有部分问题，推测软件驱动还不完善，进一步monitor； Solution: 1. 检查二供sensor的recover机制；—— 确认6/23日可以完成，DVT前可以导入，已验证； 2. 加强CH0-capsensor部分tvs接地; —— DVT已导入； |  | 廖哲霖 | 小熊
2025-06-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue: TCC实验室二供EVT1报PUD低压下出现无功能，重启后恢复；D4 后测发现 After +8KV air discharge at post check, Proximity sensor no function, recovery after reboot.(2025/6/9,14:00) Clue: 1. 实验室软件版本：user 272版本； 2. 导出LOG结构分析，对应时间点bug report显示功能是正常的，有接近远离状态变化，但是这个时间点没看到打开cqa测试的操作； 3. 使用D2机器，在厦门实验室打ESD ±18kV，200次，无复现PUD无功能故障； Rootcause: 软件定位以及实验，推测是TCC误判； Solution：1. 请邓林安排复测，判断问题； —— 机器复用其他测试，实验室暂无资源安排复测，同时观察到该问题不仅在ESD出现，在微跌等其他场景也有出现，存在共性，目前没有稳定软件版本；使用155稳定软件版本，厦门复测结果OK； |  | 廖哲霖 | 小熊
2025-06-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue: TCC实验室二供EVT1再次报报两台机器低电压下ESD重启/关机：After -8KV air discharge at zone9 (Aging 10 ), Unexpected auto power off,recovered after reboot (2025/6/8 23:09). After -8KV air discharge at zone4(Aging 10), Unexpected auto power cycle , recovery after power on.(2025/6/9,14:54)； Clue: 详细分析过程见后面文档连接 - 更新： 1. 6/17日，软件确认D4机器两次黑屏都是进入dump，并且和modem crash有关，拉modem同事确认，modem crash在TCC所用软件版本中中是已知问题，根源是ipa和modem通信出问题报错，这个问题在新版本中已经fix； 2. 6/18日，再次在D4上出现一次黑屏故障，但是状态是在 非ESD&充电，导出对应时间log给软件同事分析，确认还是modem crash 导致； 3. 6/18日，收到的D1/D3机器，使用modem同事给的软件版本测试ESD ESD +15kV 200次，未出现黑屏； 4. 6/19日，RF/ANT确认，打完ESD后一供D5机器TIS/TRP和正常机器比较无下降；二供D2/D4机器，因为ANT软件还未调通，暗室容易出现掉线，RF非信令测试传导无异常，ANT无源测试驻波效率均无异常。 5. 手动通过adb指令触发ram dump，观察到现象和poweroff类似，黑屏40-50秒后才会进入重启状态； RootCause：根据实验结果以及软件分析，目前判断结论是软件modem不稳定导致系统进入dump状态，进而导致黑屏(实际上没有poweroff)； Solution: 优先考虑改版，预留防护方案： 1. 基带：影响系统重启信号：SM_RESET有预留电阻/电容(10nF DNI),若后期出问题可以贴上；PS_Hold信号CPU端已增加一个0R电阻；PWR_KEY有预留TVS位置; FAULT_N并联器件过多，走线多集中在板中央，暂无方案预留； —— 已经导入 2. 结构：3D VC，结构增加镭雕，加强整片VC在受到ESD冲击时放电通路；—— 已经导入； 3. 后续等待软件版本稳定后，若TCC有资源，提供无panic的软件版本供结构复测 ——— 目前都暂无稳定的版本，最新的稳定版本要月底才能出来，所以等机器收到后先尝试自己复测； 4. D1/D3机器，刷软件给的modem fix后的新版本，提交TCC复测； [7/10] DVT1 一供6台ESD实验未发现问题。 | link | 廖哲霖 |  |  |  | [7/10] DVT1 一供6台ESD实验未发现问题。
2025-06-09 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | Issue：CQA 报一台黑屏，U1000 Disp_rst pin损坏，更换cpu后正常 Clue：总共发现了2台，1台是产线在烧录后发现的，他们再次做离线烧录现象就消失了，还有一台就是机器到了CQA才发现的，ME准备做离线烧录看能不能好，但是离线烧录失败，拆机验证不良随主板，，才把板子送到FAE分析的 rootcause： 黑屏烧芯片的问题，确认到因为屏FPC难扣合，EVT应结构研发需求，都是使用压棒按压FPC，导致FPC有露铜死折风险，露铜区域容易与前壳接触导致短路，有短路烧伤主板芯片风险 Solution： 跟结构的研发核对的是，DVT前壳会挖槽0.8MM避让 DVT也会验证增加FPC预弯折 [7/10] DVT1 400台 CQA 未发现问题。 |  | 廖哲霖 |  |  |  | [7/10] DVT1 400台 CQA 未发现问题。
2025-06-06 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | Issue： WH192420 C1 NEQE080018 Rear flash light no function-间歇性无作用 Clue：实测无作用 RootCase：FPC接触pinw位置接触不良，原因是背胶太小，拆装后无粘性 Solution: 结构增加背胶 |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-06 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | Issue：TCC NEQE080036 SIM 无作用，无线充无作用，cap sensor ch3无读 clue：可以复现 RootCase：无QCN，不是SIM卡，Capsensor CH3参数问题， 无线无作用跟踪到无线充的问题1 Solution: 机器给TCC需要校准，不能调测。cap 参数软件去调试。无线充问题1，刷了修复版本后ok |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue: MIL drop 1.5 WH192393 D1 NEQE080016 Volume(up) button no function:D1(final) Solution:复测结果不明，升级软件后，功能测试ok |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue:MIL drop 1.5 WH192393D5 NEQE080025 Self defined sidekey no function:D5(final) RootCase：早期版本 AIkey 的配置有些问题（两个模块一起配置，导致配置错误） Solution:刷最新版本后OK |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue：WH192390 D1 故障机， NEQE080016 AI key 无作用（ Self defined sidekey no function:D5(final)） Clue：拆机测量发现 AI key 弹片只有1.3V。这个和之前发现的问题类似。 机器版本可能比较旧了 。 RootCase：早期版本 AIkey 的配置有些问题（两个模块一起配置，导致配置错误） Solution:SW修改配置。 刷解决AIKEY的临时版本后，这个机器AI Key 功能ok了，电平也正常了=1.8V |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-06 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue：TCC实验室EVT1一供ESD报D1机器，在CQA前摄开启状态&Charging下，8kV下出现自动关机问题； After +8KV air discharge at zone1(Aging 10),Unexpected auto power off(2025/6/2 10:49). Clue： - 尝试复现：D1/D5两台机器在 zone1 区域厦门打ESD ±10kV/±18kV各100次，未复现；加压对D1问题机zone1区域ESD打±18kV各500次，未复现； - 复查ME设计：前摄被屏幕模组覆盖，模组背面有完整接地铜箔，Rec开缝紧靠金属边框(与中框一体)，整机实验发现zone1静电会优先被边框吸引释放，未发现明显问题； - 复查BB设计：检查AP开关机关键信号(SM_PS_HOLD/FAULT_N/KPD_PWE_N), 均有屏蔽或远离前摄位置，未发现明显问题； - 拆机实验：使用替代机器拆开后壳对Camera模组和REC风险点放电(±8kV)100次，未复现关机； - 故障机Log数据和故障时刻已提CR给软件分析，软件分析结果如下： 软件Log初步分析，判断自动关机时机器应该是在factory mode下打ESD，机器触发了VBUS OVP关机，实验数据不具备参考价值； 1. 标准ESD测试是需要在normal mode下打，该模式下OVP不会直接切断VBUS；在factory mode下电池功能失能，VBUS切断后就会关机； 2. 本批测试错误在factory mode下打ESD的原因分析：第一批机器软件版本不稳定，normal mode下无法打开拨号盘进入CQA，所以TCC采用的替代方案是实验员在打ESD前，首先切换到factory mode初测功能，再切换回normal mode打ESD，最后再切换回factory mode检测功能，手工反复切换，存在误操作风险； 3. 复现：手动切换到factory mode模式，在厦门插充电器在zone1打ESD +18kV ESD，成功复现自动关机故障； 分析log可以看到自动关机前，机器触发了VBUS OVP保护后导致VBUS切断，触发factory kill功能导致自动关机； Rootcase：判断自动关机时机器是在factory mode下打ESD，机器触发了VBUS OVP关机，实验数据不具备参考价值； Solution: - Monitor第二批ESD结果(最快周二晚上打完，跟踪结果) 周二上午和TCC实验员确认，第二批ESD用的软件版本可以正常进入拨号盘，截至周二上午，暂时没反馈自动关机的问题； - 后续Align TCC ESD测试时机器不能处于factory mode下； [7/10] DVT1 一供6台ESD实验未发现问题。 | link | 廖哲霖 |  |  |  | [7/10] DVT1 一供6台ESD实验未发现问题。
2025-06-04 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Monitor | Issue：Rear main camera 64X RCN超标，且有竖条纹 Clue: 1.EVB2 PCBA 测试时 RCN pass,EVT整机fail， EVB2 板子+0603版本 2次测试1次fail 2. 更改sensor setting ， 更换为orion 模组，均无效 3. 使用外供替换更换AVDD，有效且稳定 4. 更改AVDD 上OR电阻为磁珠，输出电容4.7uf 改为10uf， 不稳定，单次有效，多次失效 5. 更改AVDD上 AGND到DGND，无效 6. 更改AVDD LDO输入端为外供电压2.33V，稳定且有效 7. 更改AVDD LDO 输入buck电压2.33 V 1uf 为10uf, 不稳定 8. 翻起电感L4131, 稳定且有效 Root casue: Buck 电源FB 走线在L2层 电感下方，收到干扰，具体可见buck输出频谱波形 Buck电源输出电容值不足（参考设计20uf, 因空间问题只保留了10uf） Solution： 修改buck FB 走线线宽并且避开电感 buck输出端增加10uf电容，因屏蔽盖无位置放置，所以更换AVDD LDO输入电容1uf 为2*4.7uf AVDD LDO输入预留0R电阻，可更换为磁珠，做RC滤波 DVT1复测结果：RCN 30， fail，图像确认有条纹 Clue: 1. DVT1主板干扰频率 2. 更换R4124 为2R， p Root casue: ongoing | link | 芳梅 | 敏敏
2025-06-05 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Issue：（定义为无线充电问题3）有些机器无线充电有图标也有1.5A左右电流进电池，但是CQA测试，无法返回电压和电流值。 Clue: SW主导分析 Rootcase： Solution： |  | 文亭 |  | IKSWW-8971 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-05 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：（定义为无线充电问题2）有些机器无线充电有图标，但是没有电流进入电池。BB 提交CR ：IKSWW-8419 Clue： 0.SW log 的分析是：PMIV0102 的charge state一直没有变，这个是直接读的寄存器。导致走不了充电的流程。 by Xuyf4 1.目前反馈问题的都是整机，而且几乎所有有充电图标的机器都报这个问题，（无充电图标的是问题1） ，不良率接近100% 2. 板子飞线线圈+假电池+EVB屏幕+EVB 主FPC。 3个板子都是ok的。 3. 实验1： 故障机1# ：拆后壳后，故障依旧；拆开小后盖再扣合上，故障依旧；拆开小后盖并修改线圈将线圈引导到手机外部，测试故障依旧。---推测不是TX干扰主板导致的，至少去掉干扰不能恢复。 实验2 ：最后，主板拆出来，线圈直接飞线焊接到弹片上，用EVB的Display +假电池，测试发现问题2 恢复ok了；拆掉飞线，将主板装回机壳中（弹片上有些焊锡），还是ok的。故障机1# 的故障不复现了 推测恢复机制：弹片相关 或者 供电相关 变化会恢复。 实验3：故障机2# ，拆开后盖，扣掉电池连接器，等待5分钟后，再扣合链接器，发现故障恢复了。 结论：故障时候，是PMIV 0102内部哪里异常了，导致只有Vbus有电的时候charge state一直没有变， 要彻底断电后就会恢复正常。 4. 分析Action：1.故障机的PMIV0102 寄存器dump出来给高通分析，看下 寄存器有哪里异常发现。 2.恢复的机器，尝试各种操作尝试复现故障来找到复现路径，尝试找到触发PMIV0102 异常的更进一步的路径。 Root cause : 1.wireless charging process can no go due to PMIV0102 charge state can not change in wireless charging. why 2.PMIV0102 charge state can not change due to PMIV0102 trig OVP （checked by QC by 6/9 ），why 3.插入快充后拔出快充，OVP停留在快充的设定值 10.8V 。 无线充输出是12V ，触发OVP solution：拔出快充的时候，重新设定OVP 为13.2V。临时版本验证ok。修改已导入主线 6/12 。 | link | 文亭 |  | IKSWW-8419 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-04 | 4.EVT | 3.Charging | 4.Build | S2 | Closed | Issue：（定义为无线充电问题1）有些机器无线充电没反应。BB首批5台有2台无反应。 TCC 10台有3台 （A3,A5,A6）， SME 都有发现故障机。不完全统计大概30%左右不良 Clue: 板级测试，无线充IC 读ID都是pass的。 1台故障机：确认ID是对的，FW是对的。故障出现时，TX上面没有指示灯亮（也就是无线枚举都没有成功） 1台TCC故障机D2： 是否装配问题？实验：线圈焊线到主板弹片上测试，故障依旧，推测非装配问题。（实验室的D2机器） SW 拿到一台故障机，实验：更新FW将inhibit 禁用，看下是否inhibit 异常高了导致。 结果：NG 。所以和inhibit 应该没有关系。 是其他问题 SME 拿到2台机器有1台故障机，交给 Vendor 同步分析。 Rootcase： 分析结果1.目前南芯手上的问题1机器确认trim 被修改了（存储着校准参数等信息），导致ADC等数据错乱。导致的无线充fail没有图标。 （这个可以通过SW修复方式修复回来） 2. BB手上的机器升级一次FW后无法再升级。推测I2C地址变动了。这也是trim被改动的一种结果。（不可修复） 问题严重度 ：高 。 solution：1.出临时包，加上修复trim 被异常改写的情况，这个临时小包和大包都准备一下，但是不进入主线（避免将ok的机器也变成NG的风险），仅用来修复故障机。 ---实际验证，发现有些 2.同步准备去掉所有trim相关操作的代码，提交到主线。避免更多的机器出现这种情况（特别是担心出现不可逆的修改，比如SC9624的I2C地址被修改了，就再也修复不回来了）。 6/6 提交修改 https://gerrit.mot.com/#/c/3418718/ 。monitor EVT2 生产情况 （已发邮件和CQA 强调判定方法，待生产反馈，预估13号出结果） EVT2 只测试6台，都是pass 。目前没有更多机器可以测试。先close 了。 |  | 文亭 |  | IKSWW-9596 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-06-03 | 4.EVT | 6.Display/Touch | 5.4 ALT | S1 | Closed | Issue：ALT滚筒测试，两台机器出现无显示的问题 概率2/6。 Clue: 替换SIM-FPC后，两台机器显示OK；测试走线发现ELVSS等Bottom面走线不通，用手轻微掰动Display连接器部分FPC会恢复导通； Rootcase：万用表显微镜下点阻抗，定位最终断裂区在 屏幕B2B连接器左侧焊盘 - FPC出线 这一段，推测折弯区距离焊盘过近，以及屏幕连接器与上支架间隙过小，导致滚筒实验时屏幕连接器不断被掰动，导致连接器左侧焊盘与走线断裂； Solution： 1. 结构分析后，改动钢片外形，B2B位置钢片外伸，SIM卡槽部分钢片内缩； 2. 第二条故障FPC周末寄出给PBH，等待工厂double check下问题和建议； [7/10] DVT1 一供10台滚筒实验未发现问题。 | link | 廖哲霖 | 芳梅 |  |  | [7/10] DVT1 一供10台滚筒实验未发现问题。Closed
2025-05-31 | 4.EVT | 1.Platform | 4.Build | S3 | Closed | Issue：首版验证，AI key无测试界面，测量AI key的电平1.3V Clue :bringup 时ok得。 rootcause：SW 其他模块配置改到这个GPIO得配置了，导致配置出问题 solution ：SW 清理并修改配置部分，临时版本确认ok，CQA有AI key得测试界面 也确认测试ok 。 SW IKSWW-8434 导入改进措施 |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-05-31 | 4.EVT | 11.Thermal | 4.Build | S3 | Closed | Issue： 工厂BT反馈CHARGER_THERM_READING读值错误和BATT_CHARGER_THERMISTOR_VERIFY_STAT数值异常 （读值接近于0度，超出SPEC） Clue : 1.这个NTC 接到PMIV0102 得SMB_TEMP 端口上 （不知道QC SW是否有限制，QC 原理图review没提有问题） 2.反查EVB bringup时候就是这样的读值，只是当时没有识别出来是一个异常 rootcause： TBD 1. SW CR 07888869继续跟踪下是否有机会通过配置来解决。 2. HW CR 07893610 solution ：SW proposal 0 继续debug 看是否能解决 如果SW上明确无法解决得话。---06/03 SW CR 07888869 答复说 不支持这样更改。请换口来实现。 HW Proposal 1 再找一个 ADC 口给这个NTC用。 -----06/03 QC HW 建议 ：PMIV0102 GPIO_06 / GPIO_02 ,(02 目前预留JP 关闭Vbus 用）， 06/04先用GPIO_02 飞线 tuning，结果目前温度不准，测量电平看起来像是内部上拉电阻不对导致分压不对，还在请QC 协助分析 HW Proposal 2 如果proposal 1搞不定，就将不常用得一个NTC 挪过来用给这个用 6/9 update ：detj:DVT1 阶段计划用【SCHG NTC】来取代【MCHG NTC】，同步用【WIFI NTC】来监控【SCHG】和【WIFI】 |  | 德太加 | 文亭 | CR 07893610 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-05-30 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | RISK：特殊版本，关闭SC8541 ，只留PMIV0102 工作。用假电池测试，概率性发现Ibus 不工作 （大概30% ，不稳定） Clue:1.假电池内阻大可能有影响 。 实验1：用电池再试一下是否有概率复现。结果依旧能复现。 Rootcause：启动电压太高导致的概率性fail solution：修改启动电压低一些后，验证ok 6/16 的临时版本。 SW 跟踪导入主线 |  | 文亭 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | RISK： 当前log 看快充68W，两个CP的电流 差异值比较大。 充电性能RISK Clue： 1.目前使用的是临时电池+转接FPC/焊线来提前bringup ，仅能作为参考（内阻不对，影响左右通道的电流分配） 2.目前值是通过log 读取，准确度有问题 3. EVB PCB 仿真看 ，Rbat1 比 Rbat2 小了0.47mR 。和实际测试结果影响看起来是反向的。 （推测偏差结果可能是电池 或者 CP 的特性引起的） 4. 目前的SW版本+houston电池+转接FPC+串联电流检测电阻 测试出来， Ibat 最多差~1A （Ibat1 =5.4A VS Ibat2 =6.4A） 5.这个属性要以实际电池作为最终判定，EVB数据仅供参考（因为和电池的内阻属性相关性也很大） KP给的时间是5/28 equator 电池出来，第一时间寄送给南京和厦门进行确认。 Rootcause : EVB仿真点位有些偏差，按照QC新仿真模型重新仿真数据看左右通道阻抗有偏差 solution： 修改PCB走线。 尽量减少slave CP相关的阻抗，并适当增加master CP的阻抗来尽量平衡。 DVT1 导入。（目前PCB已经修改好并且仿真ok。） 最后优化方向： target ：左右通道Ibat 差值小于1A thermal 结果趋势来进一步判定。 DVT1 机器测试：左右通道Ibus 差值再200mA 也就是对应的Ibat 差值400mA （MAX）。 已符合预期 ，close | link | 文亭 | xuwei | QC CR：7848684 | 2.PCB | DVT1 机器测试：左右通道Ibus 差值再200mA 也就是对应的Ibat 差值400mA （MAX）。 已符合预期 ，close
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：快充时候，log 打印数据和预期是不匹配 Rootcause：可能1 ：PMIV新架构，log打印还需要澄清。 可能2 ：ICL 等充电配置目前有问题，没有如预期配置，所以看起来log 对应不上。 ---需要dump 寄存器给QC确认具体配置值，然后修正配置后dump确认配置对了，才能往下继续测试事宜。 Next action： 1和2 都要同步排查。然后再进入下一个均衡问题确认。 方向1：5/16 QC给的配置，配置后判断还是觉得不对，继续沟通中 （CP 和 Buck 的电流混在一起）） 5/22 QC提供一些配置建议，导入后，看起来比较接近了。（CP 和 Buck 的电流已经可以分别读取了）-分开后的读值是否正确，正在tuning 方向2. 5/16 中午 dump 成功第一份寄存器，发给QC ，待回应。 5/22 QC提供一些配置建议，通过解决方向1后的log 显示 和设置值还是对不上 5/28 快充时候 BUCK charging ICL设置100 （实测电流是100mA）但是log 打印出来BUCK charging 电流是300+ 。PMIV0102的快充DIV模块 实测在2900mA左右，但是 log打印出来是2450mA ,偏差了450mA，问题及log提交给QC ，暂时没有找到根源及提供有效改善方法。 建议SW 从6/3 开始拉QC 例会核对这个问题的分析和解决来加速case解决。 6/13 highlight 给各位领导 ，并重新触发QC CR针对 PMIV CP 电流读值偏差问题。启动邮件追踪push 该case 1. PMIV 快充的Ibus电流已经比较准了，最大电流情况下，误差值预计在100mA左右，可以满足项目需求。 6/20 2 .QC bug ：100mA 的ICL设置时候，内部电流检测倍率不对，是真实值的5倍左右，其他电流档位没问题。 最后临时patch是将读值/5的值再log输出就比较接近了。可以接受，先这样go。具体正式修改，QC会加到高通代码主线中 6/25 | link | xuwei | 文亭 | QC CR：7847941
2025-05-12 | 4.EVB | 9.Memory | 3.Review/Simulation | NA | Monitor | RISK：仿真fail（64%UI， target=65%UI） |  | 嘉琨
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue： 两个PM8550VS PMIC的GPIO ，无线充SW再ADSP 里面初始化配置后直接就开不了机。 Rootcause ：SW主导和QC继续确认原因。--xuwei9 solution： WLC_inhibit 改到CPU 的GPIO口上GPIO125。将WLC_MODE_SEL 改到 PMIV0102 的GPIO08 上，EVT导入 （项目上无法承接风险往下go，保险方案是改GPIO口后继续往下go） Action：0511 已通过飞线将更改后的口rework 出来 初步看符合需求，可以控制了，后续再EVT试产前完成细节bringup 。 负面作用：EVB 板子无线充电默认不能正常工作。 如由需要调试的板子，找Xiamen BB rework。 额外发现：CPU GPIO63 GPIO list 描述是PD 口，实际测量是PU口，需要和QC确认。--HW chenwt EVT 确认OK |  | 文亭 |  |  | 1.SCH
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue： 无线充SW在ADSP 里面初始化配置后 PMIV0102 的GPIO08作为中端口，实际测试无法收到中断 Rootcause ： PMIV0102的GPIO 应该是不能作为中断使用。 solution： 将WLC_DET改到CPU的GPIO63 。EVT导入 Action：0511 已通过飞线将更改后的口rework 出来 初步看符合需求，可以控制并收到中断了 EVT 确认OK |  | 文亭 |  |  | 1.SCH
2025-05-07 | 4.EVB | 3.Charging | 3.Review/Simulation | NA | Closed | RISK：SW 无线IC SC9624 ，在houston 印度工厂量产中，工厂测试发现大概0.15%无线充电无作用，换无线充电IC后OK。（试产约0.07%，所以产线认为可以接受，没有反馈问题） Rootcause : 无线充IC 内部校准参数被改写了，厂家怀疑是咱们FW升级时候有小概率动到校准参数。（但是厂家自己测试无法复现问题） solution： 1.for houson 已经出了版本导入量产（同时加入对校准参数的log 跟踪，以便万一再出现可以抓到细节log确认在什么情况下出的问题），需要较大数量的数据来看是否解决。（预计5/25 出10K左右的结果。） 2.for equator ：备份 PCB 可以兼容的方案CPS4038（老方案，但是会cost up 0.035$），以防万一SC9624的生产良率 无法达到PE能接受的程度。 但是需要在EVT试产前决定用哪个。 PE 主导收集houston 数据。 action : rework CPS4038 的PCBA出来（5/12 到达南京），待SC9624 bringup 完成后开始开发CPS4038 的bringup 。期望在5/20 前完成。 具体待跟进SW进度 Houston验证10K ok， 维持目前SC9624设计 |  | 文亭
2025-05-07 | 4.EVB | 3.Charging | 5.1 Bring up | NA | Closed | RISK：SW 无线充 bringup ，南京有两个无线充调试的板子开不了机。 Clue：1. 说是焊接线圈后出现的故障，但是实际上线圈和板子其他开机相关模块没有任何相关性。（推测是否当时哪里操作不小心短路到哪个电源导致PMIC烧毁） 2.厦门BB 1个板子ok，南京后面用最新版本+第三个板子也ok， 没发现问题。 Rootcause : 1.寄送一个板子到厦门，分析没有漏电，重新刷版本后可以开机，不复现问题。 （不排除是当时SW代码有问题导致的不开机。） solution： keep monitor 没有再报问题 |  | 文亭 |  |  | 6.No Change
2025-03-27 | 3.PEL | 5.Camera | 3.Review/Simulation | NA | Closed | Issue： wide camera 背面有WIFI芯片，S3b 2P2 会干扰camera Clue：1. 在houston 上验证2.2V 会干扰wide camera Rootcause : 13M sensor受到干扰 solution： 预留隔磁片空间 6/20：去掉隔磁片在WIFI最大发射功率，以及正常下载和上传时，测试RCN pass, 去掉隔磁片。 DVT1 monitor | LINK | 芳梅 |  |  | 2.PCB
2025-04-29 | 4.EVB | 1.Platform | 3.Review/Simulation | S2 | Monitor | Issue： SIM卡座有一供HRD和二供Lecton，一二供的物料不可以混搭。供应链需求一二供都需要在FPC厂PBH和kongwing试产，这将会产生4款SIM FPC Clue：1. 厂家物料管控方案 2. ESD的风险管控 Plan： 1. EVT和DVT1 SIM FPC BOM按照一供配一供卡座，二供FPC配二供卡座。哲林确认TVS的贴片方案 2.DVT2试产一供FPC+2供卡座， 二供FPC+1供卡座，若出现ESD或者其他实验fail, 舍弃会fail的搭配 | LINK | 李果 | 廖哲霖
2025-04-30 | 4.EVB | 6.Display/Touch | 5.1 Bring up | S1 | Closed | Issue： 开机fastboot下，插入USB线时，有50%概率会有display先黑亮起后绿屏，如果插着USB数据线，fastboot reboot bootloader 100%会绿屏 Clue：1. 插座USB数据线会出现 2. 按开关机键重启不会出现 Rootcause : 发版的Gerber数据输出错误，原因：工具软件bug问题， cadence未解释详细原因。 Solution： 增加数据输出Datebase 检查。 CAD 增加shorts文件的检查。 BB&RF 调试临时对策： EVB 屏幕和USB数据线或者充电器不可以同步使用 需要使用屏幕的板子AVDD飞线，如bringup notice | LINK | 川叔 | Chenyc4 |  | 6.No Change

## Prado
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
20250430 | C.RAMP | 3.Charging | 4.Build | NA | Open | Ramp Build ,CQA2 ,12pcs can not wireless charge when phone power off. Total/13K ? clue : 1 .Wired charge can work when phone power off and power on .Wireless charge can work when phone power on . 2. Wireless charge can not work at power off but can charge after short press power key . 3. EXP : replace relate components . Q2800 (can not recover) ,U2801 (can not recover ) & U1001 (CPU and need replace memory at same time for power on ,it recover),suspect it is related U1001 issue. 4. EXP : NG U1001 replace to ok PCBA ，result ：TBD 5. EXP : check waveform for fail unit （WLC_DET before and after R2811 & CHRDETB ）to check why it can not work，result ：TBD Rootcause： Solution ： RISK assessment ： | link | 文亭
20250409 | B.PVT | 3.Charging | 5.6 User Feedback | S3 | Closed | DF :BATTMAN-24617 Power Charging issue :wired charger can not charge ,wireless charge ok .PVT NP8N4E0289 clue : 0.Factory test all pass 1 .with factory SW ,and CQA show battery health unknown 2.log check :Slave CP I2C 0x63 can not work . 3. EXP :catch available address on I2C bus 9 （adb：i2cdetect 9） ，result：0x55(fuel gauge),0x60(wireless charge ),0x61 (master CP).only lost 0x63 （Slave CP and not other I2C added） 4. EXP :flash a latest userdebug SW(limit to 30W charging when slave CP I2C can not work) ,it can charge . but with around 27W . test 10 times ok . and check charging curve ok .(30W power) 5. EXP : temp SW that open the power limit of 30W ,change to 68W when slave CP I2C can not work . result:charge to 5.2A Ibus. it means slave CP should work at 0x61 address ,and master REG right take effort into slave CP too . Rootcause： Slave CP SC8541D I2C address jump from 0x63 to 0x61 (HW IC bug) . Factory SW early version block charging in this case to check this kind of item （import from prado DVT2 , SW V2VD35.62/39720a-92145e used in this CR ） Solution ：1. Flash to a User SW and it charging ok ，can charging to full . (about 9 mins slow than MAX power in this case) 2. Factory SW will not block charging in latest version.（import from V2VD35.63-F.2 ）. Just block charging when I2C address jump in factory mode . RISK assessment ：Low risk . more action for other new project : suggest to add an external pull up R (30kohm-300kohm) between addr pin and Vregn of SC8541D to avoid I2C jump when use 0x63 address.(to make the voltage of ADDR stabler) | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | https://idart.mot.com/browse/BATTMAN-24617
20250113 | 7.DVT2 | 3.Charging | 3.Review/Simulation | NA | NA | RISK：MOTO NUDD 磁吸背夹 PCMCR 进入，处于approve 状态中，相关方案的各种事宜分解需要细化清楚 BB相关：1.HALL IC 磁仿真OK， 其他sensor 评估ok ，mag sensor不受影响，不需要两套参数，cap sensor 要启动重新校准。 2. WLC 需要两套参数来匹配（磁吸背夹 吸附 和 没有磁吸背夹，要各自一套参数） 单独增加 GPIO 设计 让AP通知 WLC IC，DVT1B 开始导入到机器中。 被动影响问题：DVT1A和EVT机器 导入这样的FW后WLC 充电会乱掉，怎么处理。 评估ongoing --chenwt ，wanggc6 3.thermal WLC charging 部分，需要两套参数 （磁吸背夹 吸附 和 没有磁吸背夹，要各自一套参数），具体参数需要最终的WLC FW 基本lock 后才能tuning，需要多久时间？目前预估3周是否ok？ | link | 文亭 |  |  | 6.No Change | IKSWV-45596
20250107 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | DF :chagring slow ,total 3pcs NA CDC found . clue : 1 .unit log show Slave CP I2c can not work ，user SW will not charging in this status. 2.this unit factory test all pass Action ： 1.Need fail unit back to xiamen for analysis ，---Jinrong （1 unit will back by Ronli hand carry ) 2. other 2 units Log update and analysis 3.factory test process check : can Factory cover similar fail unit ?---海建，文亭 Rootcause：TBD Solution ：TBD | link | 文亭 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | IKSWV-72264
20241220 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S2 | Closed | Issue ：A+G may can not work after reboot phone . 1unit in NA report this case. Clue :1.Milos can reproduce in some units .at lease 2 units in XM . 2units in shanghai 2.logic wave form check : after reboot ,A+G I3C SDA is low at most time .MTK suspect it is A+G device issue .master can not pull down SDA at so much time. 3. if disable P-sensor ,it can not reproduce (SW debug information ,need confirm) Rootcause :I3C bus error due to IBI function of TDK A+G sensor I3C have some bug that it may pull down SDA line always. Solution :Disable IBI function of TDK A+G sensor I3C | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20241210 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S1 | Closed | Issue: 电话中，离开头部，屏幕无法恢复 Clue: P-sensor CT值没触发门限 Rootcause:此PUD共性问题（MILOS也有）， CT值随时间漂移比较大， Action: 优化算法 |  | 小熊 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20241210 | 5.DVT1 | 5.Camera | 2.Design | S1 | Closed | Issue:前置 Camera马达铁壳不接地，去除铜箔评估 | link | 廖哲霖 | 芳梅 |  | 6.No Change
20241210 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S1 | Monitor | Issue: PUD EVT1---DVT2 CT值偏大 Clue: 泡棉位置和大小对值影响非常大 Rootcause: 1.1硅胶套作用的认知 1.2隔离效果差，材料不合适 1.3 参数 2.材料隔离度的认知：实验设计 Solution: DVT2B 研发验证，PVT 工厂验证 Action: 1. 1.8V增加RC电容，增强电源稳定性 2. PUD板和中框之间改导电胶，解决原来泡棉值大的问题 3. 中框和屏幕之间泡棉减窄，手工验证OK |  | 小熊 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20241205 | 5.DVT1 | 12.EMC | 6.Issue | S1 | Closed | Issue: EDU03 DVT1 ESD d1 SIM卡坏 Clue： 测量SIM卡DATA引脚，二极管挡对地压降为0.9V，正常为0.5V，判断DATA信号被打坏； Root Clue：zone9（ActionKey）前一个区域zone8是SIM卡槽处，且6号引脚是在外侧，推测ESD从SIM缝隙处放电，打到SIM-DATA引脚处损坏SIM卡； Action： 1. 加强SIM屏蔽壳接地(PCB)； 2. SIM卡DATA,SWP引脚，增贴TVS，在DVT1B版本导入验证； 3. SIM_UIM1的DATA/SWP串33R 电阻（0613952X37） CLK/RST/DET串0R电阻（0613952Y66） DVT2 ok | link | 廖哲霖 | 李果 |  | 1.SCH
20241205 | 5.DVT1 | 12.EMC | 6.Issue | S1 | Closed | Issue : DVT1 ESD WH185467 1ST d3 Right louder speraker no function(15kv, zone7, 通话状态）; Clue: 拆机，测量Smart-PA输出LDSP-DM网络阻抗对地0.1欧，判断Smart-PA输出端损坏； Root Cause: 整机Costdown, 删减SPERKER接地泡棉; 先前设计的镭雕放电区，没能成功防住ESD； Action: 1. LDSP-DM & LDSP-DN网络，DVT1B USB板紧急rework 6 台机器，增加TVS进行验证（Presemi PESDMC2XD18VB 18V），月底出结果。；提前Prisemi索样，在DVT2版本全部导入； 2. 天线确认，可以增加泡棉接地；结构确认中框预留导电泡棉预留位置；（DVT1B如果没问题，先不加泡棉0.2元） 3. DVT2版本USB PCB进一步优化TVS放电路径； DVT2 OK | link | 廖哲霖 | 院长 |  | 2.PCB
2024-12-03 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | Issue ： 部分机器快充时候指南针APK 20241105-3Dcompass 1.apk 测试结果会偏转很大（有时候一直转角度不停） clue：1.部分机器会部分机器不会。 和机器EVT或者DVT1 没有直接关系。 2.出现问题时候M-sensor会一直偏移，不会停 3.复现问题偏移过程中，灭屏再亮屏，有较大概率就不再偏移。再碰一下手机，就会继续偏移。---推测这款 APK 和A+G 有关系，而不只是M-sensor，而问题可能出在 A+G的数据而不是M-sensor 4.更换另外一款 指南针APK，确认不复现故障。更加推断是A+G有问题导致的。 rootcause：suspect A+G sensor impact by thermal what is cause by fastcharging. Action：寄送故障机给A+G 的vendor 进行进一步分析 。 solution：proposal ，A+G 更换到手机靠上端比较不热的地方（手机 Y轴靠近上端） DVT2 ok |  | 小熊 | 文亭 | link | 2.PCB
2024-12-03 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue:Barometer 放快充背面，温漂风险 Action：快充同时用气压计场景少，漂移范围可以接受，无更合适位置 |  | 小熊 |  |  | 6.No Change
2024-12-03 | 4.EVT | 7.Sensor | 2.Design | S3 | Closed | ssue 1: Taptap has a low recognition rate Root Cause: A+G sensor is on the low half of the mainboard, making it not responsive enough Action: Move to top part of the mainboard Impact：Camera effect needs to be re-tuned. | link | 小熊 |  |  | 2.PCB
2024-11-04 | 4.EVT | 5.Camera | 6.Issue | S3 | Closed | [s1]Issue ： Prado main camera 客观RCN 测试fail，主观测试fail clue: 1. Camera AVDD2.8V AGND单点接地回路远 Root cause : IMX896 AGND要就近接地 AVDD2.8V LDO输入电源滤波,LDO GND 和 AVDD 输出电源地有压差 Solution: 1 . 修改AVDD2.8V，AVDD1.8V AGND表层接地 2. AVDD 2.8V LDO从2.2uf 改为10uf 3. AVDD2.8V LDO 输入, 输出电源和LDO GND 共地后下主地 LL : IMX896 AGND 接地回路要短。 参考houston布局或者是等prado DVT1的效果 | link | 芳梅 | 院长 |  | 2.PCB
2024-11-04 | 4.EVT | 7.Sensor | 6.Issue | S3 | Closed | [s1]Issue ：和Milos同组参数的情况下，Milos CT=6000，Prado P Sensor CT=39000。配houston硅胶套后，CT=9000 clue: 1. HW设计影响排除，ME差异待拉齐 2. ME设计确认，TP-PSA和Psensor泡棉 Follow Milos Rootcause： 中框和屏之间的泡棉无法防止CT，改用houston DVT2的物料后OK | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-11-07 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Task ：USB 2.0 眼图测试。长线1m测试结果按照短线标准过不去 solution：调整预加重 从10改为11 ，有些优化，基本上擦边pass | link | 文亭 |  |  | 4.Parameter
2024-10-16 | 4.EVB | 5.Camera | 6.Issue | S3 | Closed | [s1]Issue ： wide camera工作时有条纹干扰 clue: 1. Wide camera 抬离主板8mm，条纹消失 2. 用手遮盖镜头，光线变暗时，条纹会变很明显。 Root cause : Wide camera 50M sensor抗干扰能力弱，受到主板上camera下方的电源干扰（VSYS，Vs3_pmic， VBB） Wide camera参数错误，ISP设置4~5X，干扰被放大，和软件沟通的是大概率设置在2X。 Solution: 1. Sw 效果部分集成参数， 增益调整2X（和SW zhangbo54确认ISP增益为2X），贴隔磁片效果可以接受。 2. DVT1主板VS3 ，VBB 避开camera 修改layout。Vsys无法修改。 3. EVT2 装配增加60um隔磁片，RF ok，ANT需要测试，ME已经备料。 LL： 电磁干扰的是camera模组上的哪一部分？模拟转数字电路部分？投影到camera上在哪个区域？ 待做实验验证，不同的区域加变化的电磁场，看效果。是否只和camera模组的AVDD pad 走线区域重合？ | LINK | 芳梅 |  |  | 2.PCB
2024-10-15 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | Issue S3: 死电池激活，WLC 不能自动转入关机充电界面。 Clue：1. WLC 死电池依然能持续激活，充到超过开机电压了3.6V以上，只是系统没有自行转入关机充电界面。 2.有线充电是ok的。 3.测量电压发现 WLC_DET电压不够，只有0.4V VS 期望的1.2V以上高电平。 Rootcause： R2811 电阻和系统漏电产生分压，导致控制电压不够 solution： R2811 从10K 改为1K。（1K 在glory 上面有量产，所以基本上可以确认没问题） ，EVT mems 导入修改 具体rework 实验TBD。 |  | 文亭 |  |  | 1.SCH
2024-10-12 | 4.EVB | 10.USB-C | 5.1 Bring up | NA | Closed | Issue S3: CID no function Clue： 插入设备后，CID GPIO 电平只有1V VS 0.63V以下，所以获取不到中断 Rootcause： GPIO的上拉内阻 和串联的10K电阻 分压比例不好 solution： EVT 串联电阻临时改为1K电阻。（改为1.5K的临时更改验证ok） 负面作用：串联电阻太小，担心MP防护不够高，担心有问题。 DVT1 GPIO 更改到上拉内阻比较大的，预计改到GPIO30 。rework 待验证 |  | 文亭 | 院长 |  | 1.SCH
2024-08-29 | 3.PEL | 1.Platform | 4.Build | NA | NA | Issue S3: EVB 首版验证 不识别USB口 Clue： 1.AP_good 没有信号-》推测可能是没有时钟 2.确认26M 晶振没有震荡-》查找相关。 3.确认 CLOCK IC 使用MT6685LP 没有贴错。-》怀疑 晶振是否贴错及电源是否有。 Rootcause： CLOCK IC 使用的晶振贴的52MHz导致Clock模块无法工作（24M 平台需要使用26MHz晶振）。进而导致不识别USB口 solution： 更改晶振为26MHz，具体型号RF负责 lesson learn ： RF 主导 |  | 文亭
2024-08-29 | 3.PEL | 4.Audio | 3.Review/Simulation | NA | Closed | Issue S2: Smart PA should can not work at EVB Clue： Milos bringup fail & we re-review check same issue in prado （ Smart PA I2S DO & DI connect error ） Rootcause： Smart PA I2S DO & DI connect error solution： 1. get smart PA demo board and wired to EVB for bringup 2. change Smart PA I2S DO & DI to correct connect -from EVB2 lesson learn ：双向改为MISO,MOSI规范命名 | LINK | 院长 |  |  | 1.SCH
[12 empty] | 11.8556 | 9.282

## Houston
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2025-03-24 | C.RAMP | 3.Charging | 4.Build | NA | Closed | Issue： Wireless Charge Test Get Results (Houston IN) ,FR ~0.26% in Dixon . Clue：1. No such case in WHP 2. L2vision test no any data but not just test limit fail （TELL_WirelessChargeTest_GET_RESULTS） 3. BT test ID is 38436 （Asc ii） ，it is 0X9624 ，same as ok unit （WIRELESS_CHIP_ID_TOP_VALUE） 4. Log check Wireless charge IC U2801 FW is right 5.but there is no interrupt from the wireless charge IC to CPU . 6.EXP ：wire out the coil and retest ：fail 7.EXP ：replace of U2801 with a new one : ok 8.EXP： force U2801 FW update ：fail Root cause : wireless charging IC U2801 issue .need vendor get the fail unit & fail board for further analysis. TRIM(IC calibration data ) error after FW update. solution：Vendor change FW update code to avoid edit TRIM data. | link | 文亭 |  |  | 6.No Change
2024-12-25 | 7.DVT2 | 3.Charging | 6.Issue | S3 | Closed | Issue：IKSWV-66067 SM6475 // Houston India // V //The battery cannot be charged to full. Stop @97% Clue：1. india charger +india phone test issue. NA SKU no issue found in same test so far. 2.replug charger and it recover and charge to full. 3.from log: it is due to main charging IC PM8350B abnormal at this time . it show charging ,but no charging current. 4.from log :SW noticed PM8350B abnormal , it happened at about 77% ,and user notice it @97 % when phone closecharge pump. Action : SW add dump REG of main PMIC in temp SW version trying to reproduce and get more information first for rootcause research ,waiting for reproduce Rootcause : TBD solution： workaround :when notice it by disable USB port and enable usb port again or similar action . | link | 文亭 |  | IKSWV-66067 | 5.SW/ME/RF/ANT/Component/MFG/Vendor |  | PCMHOUSTON-25
2024-12-02 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Camera power up fail sometimes -Houston 1.issue 定级 Issue ： camera 概率性不能打开，自动恢复，下次可以打开。runin 数据是这台机器 1/3500 。Total 20台？出现1次？ 测试也有单次出现，自动恢复。正常压测不能复现 等级：软性可自动恢复。 影响：不会影响退机，但有一定的影响用户体验 。 2. 深入挖掘，尝试找到根源清理 。 2.1 runin这台复现1次的机器压测1万次左右，复现问题后的状态抓到了，当前故障也理清，I2C 总线活着，设备也都活着。 2.2 压测复现的log 使能PMIC时候看I2C错误过，但是I2C错误到恢复是几乎一瞬间。 所以现场自动恢复了，复现问题瞬间 不知道具体如何。尝试寻找抓取瞬间I2C错误现场的方法？ ---压测4天没有复现，暂时没有抓到故障 12/9 2.3 如何加大复现概率？：尝试修改脚本，可以离线运行（不连接电脑），次数60万。--- Mingfeng MF3 Yang ¦ 杨明枫 。 然后 HPM协调10台机器进行压测，来看是否能复现？（也用来作为后面workaround 后是否解决问题的验证手段） 3. 是否有解决或者临时解决方法来解决或者降低对用户的影响 可能方案：proposal 继续研究打开camera 时候的PMIC 输出电压的I2C控制接口，争取这边加第二次使能，并且中间加1ms delay。（by Mingfeng Yang 12/9） 方案:加1ms延迟，方案验证通过 | link | 敏敏 | 文亭 | 外部open 的link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-12-02 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Issue：CCT RD复测精度 ，HZ和A 光源 超标准 50% ,其他光源 ok ，共测试8种光源（camera给的标准是 +/-15%） rootcause：推测 1 金机可能不是中间值机器，推测2 算法cover 范围不够导致的。 solution： 1. 通过产线大数据，找到接近中值的机器，重新整理后制作成金机for 后续使用。-------经讨论，金机可以沿用，不更新 2. rework 极限属性的IC到机器上，收集极限数据，然后算法优化来覆盖极限机器。目的是保障极限机器也ok 。这个是优化的新开发流程，paros 没有这一步。 plan 预计12/15 完成相关工作-------抓完6台机器的rawdata，更新了校准系数，验证了PVT NA,DVT2 INDIA,DVT2 NA都可以pass | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-11-18 | 7.DVT2 | 11.Thermal | 5.5 Certification | S3 | Closed | Issue：认证反馈 ，NA SKU 电池NTC 附近温度到达60度后，充电还没有停止。（在电池NTC附近加热电偶进行温度监控） Clue：返回的机器自测pass ，无法复现故障。 rootcause： suspect SW版本比较老怀疑是认证当时有bug solution: 1.更新到最新版本，再次送认证复测 2.同步Action：同步请认证机构打开Battery tracer APP，记录手机温度和电流状态。 万一复现，拍照手机和认证设备上温度和电流的照片，分析数据来判定为什么会fail。 11/28 更新：复测发现 问题1 ：TMO的已经到达58度，Battery tracer APP显示 charging current loading （表示上层通知停充了），但是认证测试的电流表上还是显示有260mA进入电池。 问题2：非TMO的机器，到达62度，电流还是显示-1611 （一直不动，整个过程都是这样，APK似乎出问题了。），这时候夹具上确认到只有120mA电流进入电池，也是判fail。 认证表示 没法提供log ，SW 无法进一步分析。 线索：认证是将电池电芯断开，再电芯和电池保护板之间串联电流计来进行监控判断电流。 12/2 更新：1. 返回的机器 log 捞出来给SW确认判定为pass 。2.对应两台机器，在我们实验室用我们的电流计 和 加热台加热 手机，不会出现11/28 出现的问题1和问题2 。 都是pass 的。 暂时无法理解为什么认证那边测试会fail 下一步: 1. 参考Orion 这周测试 12/6 2. onsite 跟踪测试进一步确认是什么问题导致的？ | link | 德太加 | 文亭 |  | 6.No Change
2024-11-18 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Issue：Build P-sensor cover APK test NTF ,NA DVT2 一供报5.15 NTF。 rootcause：1.分析抖动比较大导致的，solution1 ：加大测试margin 看下改善情况 2.P-sensor 冷启动时候一开始抖动比较大 。 3.测试夹具环境 Display 对CT有一些影响 solution：1.（降低灰卡挡板从22mm改为18mm ，然后将*倍率从0.95改为0.9 ，DVT2 二供全面导入） 2.DVT2最后200+台机器，导入action： 将P-sensor常开并在测试P-sensor前关屏，目前结果 NA SKU 159台都pass。 将这些action都导入PVT ---ongoing （修改12M） 。 然后monitor PVT data PVT当前200台出现1台，继续monitor 数据。 0.6% （3/500） | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-11-18 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | DVT2 ESD WH184180 2nd 11/20 unable to power on;D5(15KV,zone8手写笔孔位置) Rootcause : 绝缘膜没有贴好，ESD从空隙穿过打到FPC上，打坏了hall IC 和 主板 solution：加强厂家对贴膜的管控质量 -ME monitor PVT | link | 廖哲霖 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-10-18 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s2]Issue: WH182655 2nd source EDU14 fail @170V D1 /190V D2 Clue: 1.EVT和DVT1 一供机器 都是pass的（pass 最高电压600V），主要差异器件是快充IC 和 OVP mos 。但是OVP mos 原理上没有直接相关性，所以主要嫌疑对象是 二供快充IC 2.D1 不能充电，但是OTG可以使用，机器漏电21mA / D2 漏电流4mA，功能没有异常。 从以上信息推测，主充电IC模块还能工作，接口识别还ok， 推测故障点在 快充IC的VAC口。拆除IC后主板漏电流正常。证明IC坏了 3. 二供快充故障IC 1# Vendor 第一步确认到 VAC 对GND有漏电，REGN 有些异常。 推测电大概率是从VAC进入。 具体待进一步分析后确认。南芯Demo 上面暂时没有复现到故障。 Rootcause： 二供快充IC SC8541D VAC 端口浪涌抵抗力比较弱导致本体损坏。 下一步： 故障1# IC详细分析，查找浪涌进入损坏的路径。以及 2# IC的初步确认，看是否和1#IC 一样的失效点。10/25 早上提供 。 mona 机器上实测情况含波形抓取（测试条件：插着充电器，浪涌每个电压连续打5次浪涌，浪涌间隔5~10秒 ） ，10/25 早上提供 优化方案 （包括板子修改 或者 器件调整 ） ，10/25 早上提供 demo 上测试条件和 联想测试状态的逼近再复测一下。（CP工作，不工作，开启过程各种状态 浪涌 ） TBD？ solution： serie R on VAC R2743 change from 22R to 100R .Import into DVT2 2nd source .（mems 已经备注） Verify : Temp rework 2 units， test pass . DVT2 2nd source EDU14 ， test pass . | link | 文亭 | 廖哲霖 |  | 3.BOM
2024-11-18 | 7.DVT2 | 1.Platform | 5.4 ALT | S2 | Closed | DVT2 ATT drop WH184222 2nd Unable to power on:D4(1.5m,front) Clue：1. display poewr short to GND 2. change to a NEW display module and it can power on Rootcause : Display module damaged cause power short to GND and cause phone can not power on. solution: ME &KP stracking |  | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-10-18 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S3 | Closed | Issue:DVT1 EDU15 WH182510 1st ,OTG no function,and translater no function,cannot recover after reboot Clue:1.D2- TVS损伤，D+对地68K，D-63K， 问题现象同之前wrangler类似。 2.RD实验：短路5V 到TVS上，不会造成TVS损伤但是短路的同时有浪涌可能会有此现象 3.据实验人员描述这台是测试到Vbus ，D+，D- ，GND 四个短路后的实验后fail。 4. 二供TCC实验无法复现，RD实验参考实验室操作也无法复现。 5.实验室测试方法是先插OTG，再来一根根短路信号出现问题。 实际用户 场景如果有段路，基本上也是配件本来就短路，再插入手机，而这种情况手机会直接软性保护，原则上不会出现故障。所以实际影响很有限 Rootcause：推测是测试中触发浪涌或者ESD并且一直维持5V短路造成的烧毁 solution ：monitor 长期：如果要根除这种实验触发的故障，要更改TVS 型号，选择高电压的TVS，并尽量选择 恢复电压比较高的。（但是对CPU的ESD和浪涌防护会变弱一些）。 所以不太建议更改，具体建议ESD 专家 和vendor 及各地专家沟通下 再说 | link | 文亭 | 廖哲霖 |  | 6.No Change
2024-10-15 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | Issue ：DVT1 ALT WH182695 2nd source： unable to power on:C2(15kv，Zone9 ，耳机孔附近) clue：C2这台故障机（ After +15KV air discharge at zone9 , Headset mic no function, and unable to recover），收到CQA测试耳机MIC功能确实异常 拆出测试SUB板，单独测试HS_MIC_N和HS_MIC_P网络阻抗，均为OL 接入主板，测试HS_MIC_P阻抗为284Ω，HS_MIC_N阻抗为0.9Ω ，VS ok板子 的230kΩ左右 ，确定是codec芯片被ESD打坏 rootcause：中芯国际的WCD9370 比较弱，ESD 直击到耳机通道比较容易损坏。自能尽量增加防护来降低15KV出问题的概率，但是没法确保一定不出现。 solution：1.耳机MIC 串联电阻 从10R增加到100R。DVT2 一供开始导入 2. DVT2 二供优化PCB ，TVS 401 DVT2 都使用中芯国际 的IC 来加大验证数量 DVT2 一供测试pass ，先Closed | link | 廖哲霖 | 院长 |  | 1.SCH
2024-10-14 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | Issue ：DVT1 ALT WH182596 1st source 第二配色 unable to power on:C2(15kv，手写笔孔) clue：样机返回厦门，预计10/17到达 rootcause：1. 主板HALL_INT_S端口阻抗异常，FPC部分VREG_L8E_1p8，HALL_INT_S，HALL_INT_P阻抗异常，确认主板CPU和HALL IC损坏； solution：1. DVT2及以后机器增加绝缘麦拉片 ，确保堵住Hall IC开孔； proposal 2. Hall FPC信号线修改为内层走线，过孔打在焊盘上，并尽可能增大黑胶覆盖厚度面积，在工艺允许情况下增加正面露铜接地区域；---FPC厂家评估无法实现。 proposal 3. 主板TVS根据修改后实验情况决定是否贴；----Hall IC损坏，TVS 不能解决该问题，不走这个方向。 其他项目：应提前审查到导电笔悬空的ESD风险； DVT2 一供测试pass ，先Closed | link | 廖哲霖 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-10-18 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | issue： 产线反馈DVT1 出现2次SIM卡不识别，重新插拔恢复了 action： 产线压测，出现问题不要插拔，直接做飞行模式及开关机看是否恢复，用来判断是否连接器接触不上导致不识别，还是其他原因。 rootcause：插拔过程中 SD 卡座弹片刮到 SIM卡的金属片，导致SIM卡严重磨损。进而导致SIM卡接触不好。 solution：SIM 向下移动0.4mm 来尽量避开 SD卡的刮线。 |  | 李果 |  |  | 2.PCB
2024-08-29 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue S2: P-sensor CT test result:20000~40000 ，Fail（target <3000，deadline：5000) IN EVT DVT1 方案： V2：黑色泡棉+0.03黑色背胶+RX硅胶套+机壳不喷黑（应急生产92pcs） V4：黑色泡棉++0.03黑色背胶+接收区域开孔减小（替代硅胶套作用）+no RX硅胶套+机壳不喷黑（主要生产） V4: 黑色泡棉+0.03黑色背胶+接收区域开孔减小（替代硅胶套作用 ）+no RX硅胶套+机壳喷黑" （期望的比较好的状态，DVT1 一供末期主要方案，包括L-sensor 金机也用这个状态） DVT1 结果：CT 数据在6000~10000 之间，没有达到预期理想状态 DVT1 末期：只能导入临时硅胶套+侧面喷黑方案来降低CT，根据之前的rework 确认 预计CT在3000附近,批量数据 ：200台数据集中在2000~3000，最多不到4000 长期：DVT2 导入修改的防呆的硅胶套，以提高产线装配可操作性（同步PCB修改让位给防呆及检查用） 其他项目：目前的结构设计情况下，需要硅胶套+黑色泡棉+中框侧壁喷黑的方案。 DVT2 目前导入硅胶套后，P-sensor CT已经控制住。 该问题先收敛close ，关注其他问题 | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-27 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | Issue: DVT1 一供50pcs天线干扰camera测试已完成，其中2pcs测试fail, 问题1：一台主摄N77干扰导致预览fail, 问题2：一台Wide wifi 2.4G阈值超标 analysis：1，问题1：主摄N77干扰，因为前置camera石墨片贴着主摄camera连接器 2. 问题2：Wide wifi干扰，log无报错，怀疑测到最后一项从盒子拿出导致，压测150次pass。 Solution：问题1： 结构负责，工厂执行，调整贴装石墨片夹具，保证石墨片到主摄连接器间距1mm 问题2：Monotor 已经执行，暂时没有问题，先close 如有问题再reopen | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-27 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | Issue: ATT drop No power on issue 跌落后概率性不开机 1台 analysis：1.当故障复现时候，测量发现 BB clk 不能输出，但是32K始终有。推断 CLOCK IC PMK6450 或者对应的晶振 有问题。 2.按压晶体后不复现，装成整机加测跌落后复现故障。测量 还是BB clk 不能输出，32K有。 3. 加焊晶体后恢复了。（但是由于 PMK6450 和晶体紧靠着，也会同时受热，所以会一起背加焊到） 4.应力确认这边最大0.2% ，低应力区域。 Root cause： PMK6450 或者 晶体虚焊导致。 Solution：1. PMK6450 和晶体 加大钢网 -DVT2导入 ---BB文亭 -done 2. 预留点胶孔 -DVT2导入---ME jianxi DVT2 一供测试 没有问题，先close | Link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-27 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue: DVT1 一供ESD，6台出现2台前置camera无作用。CQA 和 Moto APP都无法打开，稳定存在，重启也不恢复 Clue：1.重启后直接开CQA 或者用第三方APP 是ok的。但是使用moto APP 切换到前置camera 会自动退出，再进CQA就是无作用，并ramdump。 2.D2机器重新刷其他版本后ok，刷回原来的版本确认也还是ok ，推测 代码哪个关键参数出现错误了（存储在ROM里面的）。 3.当前log没有有效信息，SW 需要添加更多log 抓取的patch，然后重新抓取有效错误。 analysis：D2 软件升级后，恢复。加camera抓去log的patch后，待压测复现问题，抓log D3 TCC 实验室，待下线，加camera抓去log的patch后 抓log rootcause: SW MOTO camera APP 没有定义空指针，导致死循环。 solution: 更改空指针兼容策略，预计 10/11 后开始导入。 DVT2 一供测试 没有复现问题，close | link | 廖哲霖 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-10 | 4.EVT | 11.Thermal | 5.2 BB Test | NA | Closed | Issue： 前摄视频通话温度过高：F: ↑0.11°C/B：↑1.97°C clue： 软件功耗过高： Houston：48.11℃/49.97℃ @ 3.35W Wrangler 48.07℃/ 49.86℃@ 3.35W Boston：无whatsapp 数据，wechat 2.7W 硬件散热不足： 前摄石墨面积↓30%（从215mm²减小到150mm²） Solution： 1、摸底DN 方案收益，收益1C就达到预期 2、DVT1 二供增加DN方案 | link | 德太加 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-10-18 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | Issue：OTG有时候无作用，出现问题后就一直存在，需要重启后才能恢复。工厂和ESD实验都有报，但ESD报的问题无法完全确认和ESD本身是否没有关系。 clue： Chai Lu added a comment - 17/Oct/24 5:29 AMFrom aplogd_0947 logs： CID is ok after connect OTG devices --PASS type c could detect OTG device connected – PASS OTG vbus 5v outpud --PASS 4. The reason is ucsi could not get OTG info Line 26064: 10-15 09:47:52.429 83 83 E UCSI : ucsi_qti_glink_write: timed out for sync_write_ack Need USB module further check UCSI SW issue ，QC 给了个patch ，初测OK |  | 文亭 | 院长 | IKSWV-28598 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-27 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | Issue: IKSWV-23174 3台报主摄拍照dump。 Clue： 1.均是主摄OIS拍照或者AF对焦拍照时出现问题,且log均提示的MIPI error 2.这3台可以录像preview 100% dump 3.跟WIFI无关（工厂测试用WIFI指令控制） Root cause： MIPI cphy参数和目前硬件搭配不是最优 Solution： 优化MIPI cphy参数( 修改后EQ=0x07， CDR PGM=0x47，CDR Coarse=0x09 )，待软件提供版本给产线。 | LINK | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-09-20 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | issue：cap sensor no function 4pcs in EVT 改善rework 机器复测 ，D1，D3，D4，D6 故障机待分析汇总：D1 ，D4 ，D6 确认都是I2C不同，D4 D6已交叉确认IC不良。D1原加焊后ok，但是过后隔天又fail。 D3有其他故障，待分析 其他线索：1.PCB 焊盘没有看到损坏货焊盘掉落 2.IC上的焊盘也没看到异常。3.IC本体没看到明显撞击痕迹，更细节的待vendor 进一步确认。 4.有个确认项”故障IC 和正常IC的阻抗对比确认。（如果有厂家的报告，这个其实就不需要，只是在这前，如果想要初步看下哪个pin 异常，一般也就这个方式） 。昨天 shihai给的信息是D6没有差异 Rootcause：Pin1 bounding crack . due to stress on the component solution： move the cap sensor up 1.5mm . | link | 小熊 | shihai |  | 2.PCB
2024-09-18 | 5.DVT1 | 4.Audio | 4.Build | S2 | NA | Issue S3: L406 PCB package not match Rootcause： 1，DVT1 一供发板前没有进行FL的自检，直接发出去了，PCB一供返回问题L406焊盘没有开窗，临时：处理方式是，让一供 厂家自行将开窗开起来。 2. 然后 范南更新一版PCB和gerber 到服务器上，用的旧的名字覆盖。备后续使用。 实际 DVT1 二供已经用新的制作中。 Solution： 1. HD的板子上是否有FL的库的检查项：还是要检查的，这个比较危险。容易出现没有焊盘开窗而无法SMT的情况 会批量板子报废的！！！ 2. 出现临时处理方案的时候（CAD处理后结果和正式的设计不完全一致的）建议同步CC给主设，这样可以提前和后续工序（比如SMT 等）进行提前沟通，避免后续以为是异常停产导致延误项目。 （中秋假期器件报问题，比较难找到对应的人一一沟通清楚，所以尽量提前sync 好信息） |  | 范南 | 艳红 |  | 2.PCB
2024-08-29 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | RISK : Flicker FOV not good because ID change request Change request： 1. DVT1 ID要求改为类似camera 本体镜头的外观，1.凹面透镜+材料改为 vegas材质 （外观墨绿色）。 X轴 FOV 38，Y轴FOV 49 2. 要改图面透镜+材料改为 vegas材质 （外观墨绿色） 预估 角度还会更小，待有样品摸底，时间TBD Rootcause： solution： 1. 为了区分两种透镜，希望能区分两种机器，增加HWID来做区分，以便后续可以出两个参数来匹配。---chenwt -done 2.9/29 确认按照新打样的墨绿色的，凸面，2.4mm直径方案（材料要用vegas的），已按此准备DVT1 二供及 金机事宜 --xingshengnan-done |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-22 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | Issue S2: WH180780 ，tumble test， D5 cap sensor nofunction （CQA 所有通道一直显示绿色） ，recover after reboot "EVT TMO tumble WH180780 1 out of 5 cap sensor no function,recover after reboot:D5(150) EVT ATT tumble WH180784 Cap/SAR sensor no function:D5(450) EVT MIL drop WH180788 1.5m Cap/SAR sensor no function:D3(post)" clue： 其他两台硬性故障机器，8/28 到厦门 Rootcause：1.第一台软件故障 。2. 结构CH3 板子断裂问题导致，同MIC2 3.capsensor 单体故障。 solution： 1.软件优化2.同MIC2 无作用的修改板子增加一个钢片进行加强 3.单体寄给厂家分析，同时ME 应力仿真值确认及想办法降低形变。monitor DVT 1 一供没反馈问题 |  | 小熊 | 文亭 | WH180780 TCC FA link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D4 -8KV air discharge at zone8(Aging10),OTG no function， clue： D4 OTG is ok ,can not reproduce .安排压测 50枪，不复现 EVT2复现3次，重启恢复， 软件 log 分析，没有ADSP log 暂时没有进一步的结果。 SW有已知的问题：IKSWV-19512 故障发生后，和ESD 测试时的故障结果一样。 OTG和USB都无法连接，Vbus有电，但是USB就是枚举不上。 Rootcause： suspect SW issue 。 Action ： DVT1 ESD 打开ADSP log 后再进行测试，有故障后抓取对应log 进一步确认是否同一个问题。 solution：monitor DVT 1 一供没反馈问题 |  | 廖哲霖 | 文亭 | WH180794 TCC FA link | 6.No Change
2024-08-22 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | Issue S2: EVT ATT tumble WH180784 Headset no function:D4(300)- clue：样机已带回厦门 8/26 Rootcause： 耳机FPC断裂 solution：优化耳机FPC外形和走线 ，import from DVT1 DVT 1 一供没反馈问题 | LINK | 院长 |  | TCC FA link | 2.PCB
2024-09-19 | 4.EVT | 7.Sensor | 5.4 ALT | NA | NA | Issue：1pcs P-sensor no function in ATT drop ，D3 Rootcause：initial fail 。临时rework 装配问题，泡棉装偏了。 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-22 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | Issue S3: ATT drop 1.5M MIC2 no function 5 in 10 unit Rootcause：corner PCB crack （near MAIN camera ） Solution： 1.PCB外形加大0.2往camera，2.top增加一个小钢片用来加强板子。 import from DVT1 DVT1 第一轮ATT drop 没有发现相关问题。 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-29 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue S3: Flicker FOV not very good in EVT ，~65 degree ，target 70 Rootcause： 材料和仿真的不是一个材质，PMMA-CM211-5‰ 均光粉 VS 仿真 NW432D ， solution：1. 打样NW432D ，角度到~80度，性能OK 负面影响：材料的外观颜色会更加浑浊，会影响外观 |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-27 | 4.EVT | 20.NFC | 4.Build | NA | NA | Issue S3: NFC FW 下载校验失败。NTF ~10% Rootcause： TBD solution： SW 改QC 默认驱动，DVT1导入 |  | 李果 |  |  | 6.No Change
2024-08-22 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | Issue S2: EVT ATT tumble WH180784 ，unable to power on:D8(500) （ID：N0QT060208） clue： 1.可以进入9008模式，认到口，但是Blankflash 失败。CPU认到，但是没有跑到memory部分 2.Uart log 确认，DDR 认到，但是没有认到UFS。 三星 8+128 memory 3.拆IC确认 点胶异常 Rootcause： UFS damaged 。 故障样品韩国分析，预计9/14前给报告。 solution：optimize underfill design ，import from DVT1 |  | 嘉琨 | 文亭 | TCC FA link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-23 | 4.EVT | 5.Camera | 3.Review/Simulation | S3 | Closed | Issue S3: houston Flash LED 出光孔位置和结构需要不匹配 clue：1. EVB基带自测闪光灯功能正常，EVT试产产线自测功能正常 2.EVT整机camera测试灯效，发现出光孔和Lens中心点不一致，偏心。 Rootcause： 1.结构需求未出给 2.硬件设计未确认到位。 solution： 1.临时方案： EVT rework 闪光灯板给camera测试Lens效果。 2. DVT1 修改PCB板设计 2.项目长期： 长期： 1）结构EVB根据Lens出光孔输出闪光灯摆放方向图纸给CAD，包含焊盘形状和出光孔标识，并且检查和验收主板设计闪光灯出光孔是否符合Lens出光孔的要求。若有闪光灯不同阶段的更换物料，也同样适用此条。 2）基带负责闪光灯按照结构的要求放置闪光灯，协助结构判断出光孔是否一致。严格遵守BB review 发版检查。 | Link | 芳梅 |  |  | 2.PCB
2024-09-02 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Issue: EVT USB 默认参数眼图 电平过高 solution：调整SW 眼图参数，参考geneva 的参数修改，临时调试复测pass . 相关更改DVT1之前集成 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-29 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | Issue: 自测5台，4台出现 ANT7和ANT8的 N77&N78干扰后主摄像头 1）ANT7 N78 有preview failed和camera error found 2）ANT8 N77 preview failed Clue：log提示后摄MIPI error 实验: 1. 石墨片不动，去掉Inlay, pass 2. 去掉camera石墨片，裹紧Inlay, pass 3. 去掉camera石墨片，去掉Inlay上camera ring，裹紧inlay，pass Root cause: ANT7和ANT8 N77和N78 最大功率26dbm干扰到inlay camera ring和石墨片，两个同时存在就会有fail Solution： 修改石墨片形状，避开后置camera连接器区域， 负面影响：thermal 前置camera 发热较大，有风险。 但是DVT1 还是用这个作为主线 DVT1 二供 导入氮化硼对比测试 。 预计DVT2 thermal MCN 前决定用哪个方案。 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D2 -8KV air discharge at zone16(Aging10),Earpiece and Loudspeaker no function,recovered after reboot.D3 +8KV air discharge at zone1(Aging10),earpiece and loudspeaker no function,recovered after reboot， clue： 安排压测 50枪，不复现 Rootcause： TBD solution：EVT2 不复现 |  | 廖哲霖 | 院长 | WH180794 TCC FA link | 6.No Change
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D1 mic1 and mic2 noisy After -8KV air discharge at zone16（rear camera） clue：can not reproduce ，安排压测 50枪，不复现 Rootcause： TBD solution： EVT2 ok |  | 廖哲霖 | 院长 | WH180794 TCC FA link | 6.No Change
2024-08-29 | 4.EVT | 5.Camera | 5.2 BB Test | NA | Closed | Issue S？: KP camera power noise 测试，主camera测试数据超标4.5（标准4） Rootcause：IMX896 sensor 问题，参考wrangler也是超过4， KP判断pass |  | 芳梅 |  |  | 6.No Change
2024-07-03 | 2.PCL | 7.Sensor | 3.Review/Simulation | NA | Closed | Issue S3: Flicker sensor & A+G sensor reuse I2C bus impact performance clue：1.houston First SOIS+Flicker on SM6450/SM6475 Rootcause：SOIS 占用了SM6475平台ADSP的所有接口 （一组I2C for OIS控制，一组SPI for OIS A+G 数据上传，以及 I2C 的A+G UI通道数据 for EIS）。其他所有ADSP端的sensor只能和A+G UI通道复用I2C. 一些极限场景会同时调用A+G UI 数据和flicker 数据，就会出现总线性能不足的风险（按照SME 的数据计算模式，可以确认同时调用A+G UI 数据和flicker 数据 无法满足 CTS 认证的 EIS 和 AR core 相关认证） 其他同期项目情况：paros 项目 OIS+flicker ，所以ADSP 接口资源够用，不需要A+G和flicker 复用I2C 抢总线。 需要解决问题：1.认证问题：EIS 和 AR core 相关认证 solution：proposal 1. AR core 测试camera 场景默认不开flicker sensor 。 EIS场景（录像？） 使用A+G SPI数据通道获取UI数据，SOIS （拍照物理防抖）场景再配置成 OIS需求数据模式。 ---Need SW camera team evaluate ，ongoing proposal 2. flicker sensor change to AP side。---need SW sensor & camera team evaluate ，ongoing （mey need HW rework base on boston ，waiting SW feedback） proposal 3. houston change main camera to OIS module （similar to paros）--没提上议程，毕竟我们目前的设计有很大的cost down ，如果回到OIS 方案，我们的costdown 就没了，以及会产生一些设计变更。在其他方案不可行的情况下，最坏情况下考虑这个方案。 | link | 小熊 | 文亭 |  | 6.No Change
2024-07-24 | 4.EVB | 1.Platform | 5.1 Bring up | S2 | Closed | Issue S2: SIM detection failed during the SIM bringup clue：1.SIM 波形分析发现 SIM IO/CLK 异常，VCC/INT 正常，RST没有串电阻无法测试 2.卡座飞线出来测试波IO/CLK /RST/INT/VCC 都正常，同时此时验证可以识别到SIM卡 Rootcause：卡座和卡托不匹配，新SIM卡座和老款SIM卡座的卡托不一样（旋转了180度） Solution： 1.临时方案： 将卡托rework 满足EVB调试（Done） 2.EVT PCB SIM卡座旋转更新（Done) EVT check ok | Link | 李果 | 文亭 |  | 2.PCB
2024-07-24 | 4.EVB | 3.Charging | 5.1 Bring up | NA | Closed | 二供快充bringup issue： Issue 1： 大概率 master CP I2c 访问失败。（表现是电流只有20+W） Rootcause： SC8541D的I2C地址选择pin 是E6 ，和BATN_SRP功能复用，链接到电池的C-上，在Vbat链接后200+ms内，就决定了I2C的地址。在扣合电池过程中，Vbat 和GND 大概率会比C-先上电（电池连接器的设计，防止C-先接触上造成其他问题），这样导致I2C是个错误的值（期望值是接地，实际是悬空了） Solution: 将master CP的 E6 和D6 都直接接到GND。 Issue 2： Master 和Slave CP的电流 差异值很大。超过2A以上（68W的期望值是500mA以内） Clue: slave CP的电流非常低，有时候只有1A以下，不正常。 Rootcause： SC8541D Slave 的C2756 多贴了 Solution: SC8541D Slave 的C2756 不贴。 跳贴表格进行更新 Houston 更改EVT导入 | link | 文亭 |  |  | 1.SCH

## Wrangler
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2024-10-29 | D.SHIP | 2.Power | 6.Issue | NA | NA | [s2]Issue:SOC not change ，always 60%-Wrangler aftersale Clue: 1. SW setting SOC to 60% and voltage to 4.2V when fuel gauge not work. 2. reassembly 2 units battery connector and issue gone. Root Cause: suspect battery connect issue.Why ？waiting for fail unit back Solution: | link | 文亭 | 李果
2024-06-04 | B.PVT | 2.Power | 5.4 ALT | NA | NA | Issue: PVT MXC06 Unable to power on 4台 Clue:PMK_VREG_BB is only 0.5V at msm side and 1.2V at PMK7450 2pcs; VREG_SYS_1P8在PMK6450端电压为0V,在PM6450端电压正常，2pcs. Root Cause:PMK_VREG_BB 在Layer11平行屏蔽盖轨迹的地方断开 ； VREG_SYS_1P8在L11层往PMK6450方向屏蔽盖轨迹下断开 Solution: 加宽PMK_VREG_BB 在Layer11平行屏蔽盖轨迹这一段的走线； 加宽L11层VREG_SYS_1P8横向走线(未导入PCB) |  | 敏敏 | 文亭 | Link
2024-05-22 | B.PVT | 3.Charging | 5.3 EE DVT | S1 | Closed | Issue: WH178095 EDu15 Soft Shorts test After OTG 2 ohm resistance Soft Short,OTG no function and data transmission no function(10:37 5/20/2024),unable to recovery after restart.D2 Clue: in OTG mode Vbus is ok but USB not (ADB and fastboot can not work too in USB mode ) Root Cause: sub board TVS on USB D+ damaged （TVS502）. USBD+ is not related to EDU15 test purpose. (short Vbus to GND ,but not D+) suspect the tester mistake short Vbus to D+ . Solution: N/A ,monitor | link | 文亭 | 韩凯
2024-05-09 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S1 | Closed | Issue: user feedback,录像状态下有主摄有异响 Clue:OISVDD电压3.3V高于模组要求的2.8V Root Cause: OISVDD电压3.3V高于模组要求的2.8V，为何回响camera KP分析中 Solution: change LDO to 2.8V output LDO（PN：SC98D62703） |  | 韩凯 | 敏敏 | link
2024-05-08 | 7.DVT2 | 2.Power | 5.4 ALT | S2 | Closed | Issue:MXC06 WH177228 Unable to power on:D1/D2(270） Clue:PMK_VREG_BB is only 0.5V at msm side and 1.2V at PMK7450 Root Cause:PMK_VREG_BB 在Layer11平行屏蔽盖轨迹的地方断开 Solution: 加宽PMK_VREG_BB 在Layer11平行屏蔽盖轨迹这一段的走线 |  | 敏敏 | 文亭 | Link
2024-05-07 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | NA | issue:Charging slow in DF |  | 文亭 | 德太加 | link
2024-04-03 | 7.DVT2 | 7.Sensor | 5.4 ALT | S1 | Closed | issue：Wh176592：DVT2一供ALT India 15kV AD capsensor Ch1 no function Clue1：ch1通路阻值异常，只有100ohm Clue2：参考通道下地电容耐压只有25V Clue3：上支架ANT1 LDS pattern距后盖缝隙很近（天线功率不足需要足够LDS pattern需要足够靠近边框天线） Clue4：R3708 短路 Root Cause：Ch1线路扛静电能力不足，能量从LDS进入冲击CH1 R3708，导致器 件单体短路，检测通路异常 solution： 2、L113 变更为21014050209（27pF，50V耐压） 3、改版主板，线路上增加一个TVS预留位 PVT验证 |  | 韩凯 |  | link
2024-04-03 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | issue: DVT1 2供 ESD Air -8K capsensor no function,recovery after reboot Clue1：上支架ANT1 LDS pattern距后盖缝隙很近（天线功率不足需要足够LDS pattern需要足够靠近边框天线） 厦门和武汉无法复现 |  | 韩凯 |  | link
2024-04-03 | 5.DVT1 | 9.Memory | 5.4 ALT | S1 | Closed | issue: Unable to enter system:D5(270) 3/26/2023, Clue: 1.按power键上电不保持 2. 按压memory 可以正常开机 rootcause: memory 虚焊，点胶不均匀，memory表面有胶水和屏蔽盖粘连，侧面无明显点胶量，转ME优化点胶 |  | 敏敏 | 嘉琨 | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-04-02 | 5.DVT1 | 2.Power | 5.3 EE DVT | S2 | Closed | Issue:DVT LotX tumble Unexpected auto power off:D1（225滚） clue: 1. 不开机 2. 接上假电池(没有开机)，量测B_PLUS(VPH_PWR)电压及VBAT端的电流,VBAT上面每隔1s会有1.45A(MAX)的电流，把B_PLUS(VPH_PWR)从4V 拉到3.574V 3. 加焊后按压还是会自动关机，大概率还是PM8350B本体故障，寄回武汉做PM8350BH 芯片交叉验，问题依旧 4. PM7325有裂纹和破损，PM7325 VREG_SYS_1P8 ，BAB后，PM7325 VREG_SYS_1P8 电压正常，问题依然是不开机，但是由于板子变形严重，分析截止 |  | 敏敏 |  | LINK
2024-03-18 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | issue：DVT1 1st stack WLC 红墨水fail, 第二方案WLC 红墨水fail [s3]Issue ：DVT1 WLC 红墨水实验fail Clue：1. 脱落pin不影响WLC功能，功能检查正常，判断会影响充电性能，用户无法感知。 2. 两次实验，脱落位置不固定，第二页和第三页图示 3. stack板装配后虚空，怀疑在跌落或者震动的时候，stack板晃动导致wlc芯片部分管脚脱落 Solution： ME owner 基带看是否可以优化WLC的开窗，增加焊接面积 |  | 文亭 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-04-01 | 5.DVT1 | 4.Audio | 5.4 ALT | S1 | Closed | Issue: DVT1 ALT 2供ALT跌落碰撞，USB板Speaker信号线串联的L303，L304 脱落 rootcause： 器件在板边，怀疑应力问题？ 另此类器件铜丝绕线到焊盘底部且二供焊盘0.8*0.3，一供0.8*0.4 solution: 1. L303.L304位置向板内移动，支线发版验证。 分析： 1) 结构壳体尺寸正常，未出现撞击的痕迹 2) 二供的焊接面会比一供小，如下图二和图三， 3) SMT工程师分析，二供的焊接正常，不存在焊接问题 4）一供器件焊盘0.8*0.4， 二供的器件设计焊盘0.8*0.3。二供器件焊盘小，会出现图二的问题。 器件实体焊盘如下图四，图五 5）此类器件铜丝绕线到焊盘底部，并且器件侧面不爬锡，SMT工程师反馈之前项目这种设计，线把底部顶起来发生过器件偏移和脱落。 |  | 院长 | 芳梅 | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-03-29 | 5.DVT1 | 6.Display/Touch | 4.Build | S3 | Closed | Issue: DVT1二供组装，3台华星屏幕显示偏绿，KP反馈现象跟随主板 analysis: 1. 现象固定，此主板搭配天马屏幕ok, 搭配所有华星屏幕发绿 2. fastboot下显示ok， kernel 异常，怀疑有参数更改，监控从正常到变绿时，电压，帧率，MIPI clk均正常 3. AP mipi data 测试，相同主板，点白色图片。天马模组MIPI data 波形正常，华星模组MIPI data异常，说明使用华星模组时，AP有对白色图片进行处理。 样机寄送供应商分析： 1.IC bist画面测试，白色色坐标正常。---说明模组及相关设定正常。 2. 删除效果参数，偏绿没有变化。 3. 删除效果参数及校准文件，偏绿恢复正常。 4. 将校准文件重新写入，效果正常。 rootcause: 华星效果参数用错成别的项目，需要重新调试效果参数。DVT2已经导入新参数，目前未报问题 |  | 芳梅 |  | link | 4.Parameter
2024-03-07 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | Issue：front camera RCN value exceed standard analysis: rootcause: crosstalk from display solution: remove to KP yaocf1 |  | 邦邦
2024-03-05 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | Issue：DVT1 CQA test camera0 N78 干扰测试failed , failure 1pcs (测2台)，批量数据待测 rootcause: MainCamera CPHY interfered from thermal graphite film coupled radiation of n78 on ANT9 solution: change the shape of graphite to avoid overlap the main camera connector fromDVT2 |  | 邦邦 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-03-02 | 5.DVT1 | 10.USB-C | 4.Build |  | Closed | Issue: Sub usb Type-C连接器屏蔽壳对地短接的电阻被ANT删除，这6颗电容位按照最初讨论为DCM 贴电容，ROW 贴0R，ANT为兼容DCM和ROW公用天线，直接将ROW 这6颗本来贴0R 电阻 DNS掉 Rootcause ： 此6颗接地位需要和BB/RF一起商定贴片方案及铁壳接地方案，ANT在warroom上提出问题，但未收集到BB和RF反馈，直接修改方案 solution：DVT1 贴0R下地，ANT 优化天线设计， DVT2 因为DCM SKU删除，不需要兼容DCM，DVT2小板删除预留电容位，直接铁壳打孔接地-done lesson learn ；职责划分清楚，兼容部分涉及到更改，需要同步到ANT ,BB ,RF ,若需更改BOM，需要提交给基带进行修改 |  | 芳梅 | 文亭 | wrangler usb typec屏蔽壳接地方式评估 | 2.PCB
2024-02-21 | 4.EVT | 1.Platform | 5.4 ALT |  | Closed | Issue：EVT EMEA P+ESIM， Unable to read PSIM Card ， failure 4pcs （2 Alt, 2 xiamen ant ） Rootcause ：校准数据丢失 |  | liguoa |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-01-31 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue：EVT EDU14 surge test fail on VBAT test point test ，200V fail. clue：B_PLUS short to GND Rootcause ：U1571 PM7350C damaged in surge test surge TVS layout is not best solution：Optimize Vbat TVS layout . monitor DVT1 test lesson learn: add Vbat surge TVS layout in checklist 。DVT1 pass |  | 韩凯 | 敏敏 |  | 2.PCB
2024-01-29 | 4.EVT | 3.Charging | 4.Build | NA | Closed | RISK：add WLC TX function，PCMCR：https://idart.mot.com/browse/PCMWRANGLE-7 Solution：Go with Option1 （1.PM8350B change to PM8350BH bacause PM8350B only support 5V haptic boost but PM8350BH support 10V haptic boost 2.add a loadswitch to get power from haptic boost，3.add TX Modulation and Demodulation component 4.DNI FW update power MOSs because can reuse haptic boost power from Loadswitch）. Change import from DVT1 。DVT1 ongoing ，TX function ok。detail tuning ongoing | link | 文亭 |  |  | 1.SCH
2024-01-29 | 4.EVT | 1.Platform | 4.Build | NA | Closed | Issue ：India P+P SKU SIM2 can't not recognized Rootcause： The VSIM2 power supply design is different in the S21 and S54K Solution：VSIM2 resistor is disconnected inS21 desgin |  | liguoa | 芳梅 |  | 1.SCH
2024-01-22 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Risk ：SC8549D may not able to work ，About 30% on Glory&Aura Clue：1.incoming date Later than 20231222 lot should have problem 2.Wrangler EVT ：E03 35pcs， E05 8pcs firstboard ， E04 30+pcs use Old component ，should not have problem Others ~400pcs ，use new component should have problem. Issue ：india SKU firstboard 1pcs fail/total 3 pcs. sent fail IC to Vendor for analysis Rootcause：waiting for Vendor analysis solution ：change SC8549D to SC8541 from DVT1. PCMCR:https://idart.mot.com/browse/PCMWRANGLE-8 |  | 文亭 |  | glory 无法快充分析 | 1.SCH
| 4.EVT | 2.Power | 5.2 BB Test | NA | Closed | Issue ： power off current leakage 5.4mA clue: 1. fastcharger IC(VBAT2) can reduce 0.5mA maybe charging setting issue 2. charging Patch1 (CP related)： reduce 1mA . so there is other part issue too. Solution:update 310 continuous build,UI power off leakage=274uA |  | wuxm5 | 文亭 | 可能漏电器件汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
| 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | Issue ： camera PMIC bringup fail & Smart PA2 bringup fail Rootcause： I2C address conflict on Smart PA2 & camera PMIC 2 . both are 0x35 Solution：EVB rework ，solution ongoing EVT change smart PA2 I2C （have 4 I2C address option ） lesson：Need to add all the I2C component into Qwiki -I2C map page. and check if I2C address conflict happen when setup ,change ,add 2nd source. --- All Experts remind 1 time at the day before EVB gerber out---platform design owner |  | chenbang |  |  | 1.SCH

## Manaus NA
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2024-04-23 | C.RAMP | 3.Charging | 4.Build | NA | Closed | issue: L2vision wireless charge CHIP ID fail. 1pcs Clue： PAT pass Rootcause：： Q2801 虚焊 |  | 文亭 |  |  | 6.No Change
2024-04-23 | C.RAMP | 3.Charging | 4.Build | NA | Closed | issue: PAT wireless charging fail Rootcause：：1.一部分机器Stack 板子没装。这部分制程问题工厂处理--统计这几天有15pcs Stack 板子没装。 2.有两台机器是stack 有装，但是FW升级一直失败。 Q2803 虚焊 ，具体还有多少台 由产线统计及SMT参数修改解决。 | link | 文亭 |  |  | 6.No Change
2024-04-15 | C.RAMP | 1.Platform | 5.3 EE DVT | S3 | Closed | Issue ：[Factory][TCC][OK2P]TCC AutoCycle Test，The Device can not power on .3 in 12 IKSWU-124341 Rootcause： 1.开机过程中GPIO79判断到高电平后，手机进入9008 导致不开机 2. ANT tuner U100（QAT5655）在超低温下（低于 -30 °c）逻辑异常 导致上电瞬间 DATA 输出高电平 。而该器件QC的温度 SPEC 范围是-30度~85度，我们的实验环境超过器件SPEC。 BB意见：这个是test issue，非用户实际issue，因为 issue 低于-30 °c温度下才会发生的， 而我们手机的工作温度SPEC is -20~60 °c . 其次保险一些就是SW加入 fuse 为固定开机点，不要受GPIO79的影响。（ 不能解决TCC issue，能解决用户万一超SPEC使用遇到的问题。） solution: proposal1.Workaround :Moto SW efuse Boot config to fixed 0100 .（1 unit RD test ok） | link | 文亭 |  | IKSWU-124341 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-04-11 | C.RAMP | 10.USB-C | 4.Build | S3 | Closed | Issue ：type-C port can not work after test (FOD、UCT、L2VISION). ~1% Clue1:power cycle can not recovery,reasembly battery connector recovery. Some component on VPH_PWR error. clue2: plug in Type-C analog headset can recover too. Suspect ：Audio switch control logic issue. clue3 : Rootcause： The Hi-z state of CC_out is not instability. solution: Pull down CC_out by gpio configuration | Link | 院长 | 文亭 | https://idart.mot.com/browse/IKSWU-126081 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-02-23 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | Issue ：[PVT]TCC ALT Test,shake test ,Unexpected auto power off,Power on only after charging.2 pcs loop5 1 time Clue1: log show PMIC PM6150C abnormal UVLO & BOB OCP found. clue2:Power on only after charging clue3 : same unit B1 show PM6150C abnormal LDOs &BOB both OCP (auto power cycle 1 time in loop2 Drop test IKSWU-80251). Rootcause： solution: monitor | Link | 敏敏 | 文亭 | IKSWU-81779 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-12-18 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | [S2]Issue: 产线装配后拍录像/播放竖线 ( ~ 2/300) clue: 拆机重扣之后，故障概率下降很多，十几次出现一次， 交叉模组实验，故障跟随主板 Exp1：Video record, 开WiFi，MIPI log 报错 rootcause: CPHY was interfered by wifi and n78 solution: Tuning CTLE EQ and CDR register |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-01-10 | 5.DVT1 | 8.PCB | 6.Issue |  | Closed | Issue ：Manaus NA DVT2 所有机器无线充电都不能正常工作。 Rootcause：E2001 位置焊盘没有开窗，虽然有钢网，但是E2001 器件贴不住。 导致Vout 不导通。 短期方案：rework 板子，恢复EVT的通路方案（刚好还预留，没有删除） | link | 德太加 |  |  | 3.BOM
2023-12-20 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1 ALT A3(loop5)背跌 不开机 clue: 1.关机漏电流100mA+，无串口； Clue： 1.发热点：从背面看是PM8350B靠左边的位置，这部分是用电端，不是充电部分。（推测是马达，或者显示相关部分电源驱动器坏了），结合第7点情况，推测有可能是显示相关的电源部分有问题，外围器件等可能哪个出问题了。（推测：有可能是外围器件等坏了导致的烧坏IC） 2.确认PM8350B是故障IC，寄厂家QC进一步定位分析（分析具体是哪个模块坏了，以及是否可以看出是否有微小裂纹）；厂家分析结果：电性能烧毁，短路位置150,161,160---指向OLEDB 电源相关 3. 换了新IC屏不亮的问题，排差PM8350B外围的电路是否异常：检查下PM8350B OLED相关供电及器件是否OK（分析来源推测：是否会是外围问题导致IC烧毁？）-- 测量VREG_OLEDB发现对地短路，去掉这个网络上所有连接器件，依然是短路。推测是PCB本身短路，导致大电流烧毁IC。这个网络走线在L12 和L10.以及过孔。 4.板子到板厂时候测试发现短路不见了。寄回板子也是没短路，焊接上正常器件后，开机亮屏 Rootcause： 板子上有某些原因导致VREG_OLEDB对地短路引起大电流，最后将IC PM8350B的对应驱动电路也烧毁。 但是造成短路的具体是什么，目前无法考究，monitor 。万一有类似故障，关注短路原因 Solution：Monitor | link | 文亭 |  | TCC analysis | 6.No Change
2023-12-18 | 5.DVT1 | 5.Camera | 6.Issue | S2 | Closed | [S2]Issue: 主摄Slowmotion出现横条纹 clue: Exp1：新版本U2UAN34.11 OK Exp2： rootcause: SW Issue solution: |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-12-13 | 4.EVT | 10.USB-C | 5.6 User Feedback | S3 | Closed | Issue ： USB can not connect sometimes-Manaus NA Clue ：1.when it happen ，it last for a long time and can reproduce when replug USB on phone 2. it can be recovery by replug USB on PC . 3.it can be recovery with CID pin connect to GND on phone . 4.it is hard to reproduce after phone power cycle. 5. after power cycle, 3 units keep not move ,after 1.5hours ,1 unit reproduce the issue. 6.log ：it is in host mode Rootcause： SW logic error Solution： change SW and recheck ok | link | 文亭 |  | IKSWU-34055 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-11-17 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S2]Issue: EDU03 WH169432 Rear flash light always on , and could not recover:D2/D6(15KV,zone14）, clue: PM6150C BOB short Exp1：Flash 导电泡棉没有接地（盖在石墨上），ME将下接地该区域避让开。 Exp2： rootcause: Flash 导电泡棉没有接地，导致PMIC被打坏 solution: 石墨接地位置区域避让开 | Link | 韩凯 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-19 | 4.EVB | 5.Camera | 5.1 Bring up | S2 | Closed | [S2] EVB3 Main Camera IMX896 Bringup, preview stuck Analysis Exp: 1. IMX896 is OK on boston (SM6450) 2. OV50A with CPHY 1.9Gsps failed on both EVB1 and EVB3 3. IMX896 failed with 0.9/1.9/2.4Gsps on both EVB1 and EVB3 4. smoothly preview under heating board, while stuck preview under cool board 5. IMX896 works well on front and wide camera MIPI path 6. smoothly preview while add extra power supply in parallel with S2B/S3B/S4B 7. IMX896 works well with C1515 removed rootcause: GND return path of PMIC Buck S2B/S3B closes to MIPI CPHY Vias solution: change MIPI traces fanout frome layer 6 to layer 4 | Link | 邦邦 | 院长 |  | 2.PCB
2023-09-20 | 4.EVB | 3.Charging | 3.Review/Simulation | S3 | Closed | Risk：EVB3 simulation ，Master & slave charging patch impedance not match ,delta 3.1mR VS <2mR （desired value） Rootcause： slave battery connector is too far away from charge pump because of RF placement limitation. & No place for double width of Vbat2 layout. Solution： 1. decline width of master Vbus wire to 2mm. & add some coper for Vbat2 . Simulation ongoing ，import from EVT 2. battery have some delta design for Manaus NA （if it is used in Manaus NA only，it shoule be ok . but if reuse other project`s ,may have problem） |  | chenwt |  |  | 2.PCB
2023-09-20 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue ：dead battery Wireless charging fail Clue ：modesel go to 1.2V at about 2ms after wireless Vout on .it cause Vout off. repeat Rootcause： WCHG_DET output high to CPU cause modesel go to 1.2V (current leakage ) . Solution：1. change WCHG_MODE_SEL to PMIC PM8350B GPIO_o4 ,import form EVB3 -EVB3 recheck ok 2. add 10KR on WCHG_DET ,import form EVT | link | chenwt |  |  | 1.SCH

## Manaus DCM (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2023-10-24 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | NA | [S3] Issue： EDU14 WH168701 , D1 After 150V surge pulse test,Cannot charge phone by USB. Clue： 1. RD can not reproduce when get D1 exp: D1 do test again Root Cause: 1. Monitor Solution: TBD | link | 韩凯 | 文亭
2023-10-24 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Monitor | Issue ：Type-C Shell case connect to SUB PCBA GND (JP SKU DCM require Type-C Shell case dont connect to GND） Rootcause： Type-C Shell case fix part connect to middle housing Solution：PCB：sub PCB dont design soldermask under type-C fix part. （螺丝孔） ME proposal 1 ： ME proposal 2： |  | 李果 | 文亭
2023-08-19 | 1.Concept | 2.Power | 1.4 Solution | S3 | Closed | Issue ：storage time with power can not match Docomo requirement. 来源：Manaus -Eng【24夏スマホ】機能一覧表1.0版(Function list)这份文件，① 24 Summer Main specification 页面的157行 A period of 27 months or more must be secured from factory shipment to overdischarge Rootcause： poweroff current around 300uA PCBA +50uA battery=350uA ,can only support 8month storage with power Solution： go with Shipping mode. which is about 50uA PCBA +50uA battery=100uA MAX ,can support more than 27months. |  | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor

## Manaus ROW (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2023-11-10 | D.SHIP | 10.USB-C | 5.3 EE DVT | NA | NA | [s3]RISK：TCC test 5% Nacl 溶液相对容易造成Type-C 腐蚀 Clue：1.XM test 5% Nacl 溶液填满Type-C连接器 很大概率会触发OTG，刚开始周期性触发，最后就一直触发着。 2.对比 QC平台的bronco 项目，XM test 5% Nacl 溶液填满Type-C连接器，就很难触发OTG？ Next action： 抓出CC和Vbus 波形及对应的log，创建CR ，寻找MTK支持一起分析 及找可能得改善方案 Rootcause ：TBD solution：TBD | link | 浩总 | 文亭
2023-08-14 | B.PVT | 7.Sensor | 5.3 EE DVT | NA | Closed | [s2]Issue: chopchop fail when phone deeply sleep Clue1：Latch time locked and not change Root Cause: 1. MTK SCP work abnormal in deep sleep Solution(Work around): 1.Change A+G INT mode to level trigger | link | xiongsn1 | liguoa
2023-07-20 | B.PVT | 7.Sensor | 5.3 EE DVT | NA | Closed | [s2]Issue: CH0 fasle trigger in DVT2 on AW96308 , when holding TOP ant Clue1：Semtech is ok Root Cause: 1. Noise larger than threshold of CH0 due to amplitude too big to meet long distance detection 2.1 IC performance limitation 2.2 ANT Sporton tests require a very long distance for CH0(24mm back) Solution: 1.Vendor optimising with parameter |  | xiongsn1 | liguoa
2023-07-20 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [s3]issue:ALT WH166331 C1 After -1 out of 2 Unable to find NFC device/read SIM Card C1（15kv） Clue1：issue happen only once Clue2：not produced in stress test on vsim1_vcc Root Cause：1、SIMIO1 of NFC IC SN220 damaged solution： 1.1st source +2nd source SIM tray fail , Will do SIM tray ABAB DOE by 7/24 2. Running change with SWP Add TVS in MP |  | Hankai | 李果 |  | 3.BOM
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]issue:DVT2 :EDU03 SIM card insert detected fail,NFC no function(1/6) Clue1：issue happen only once Clue2：not produced in stress test on vsim1_vcc Root Cause：1、Vsim1_VCC of NFC IC SN220 damaged 2、proposal poor grouding that related to P2I which was introduced on DVT2 solution：1、update 3 more clean area of SIM subboard 2、change C414 0.1uF cap to TVS |  | Hankai | 李果 |  | 3.BOM
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue： EDU14 WH165529 ,DVT2 surge 200V fail，OTG &fastcharging can not work Clue： 1.fail unit Log show PD can not work .& Ibus=0 when Ibat =~2A. 2.DVT2 all build with P2I. DVT1 without P2I. Root Cause: 1. MT6375 damaged （replace a new MT6375 ，function,ok）. Proposal 2 ：poor grounding related to P2I which import in DVT2 Solution: ME update 3 grounding more clean area of USB Board after P2I | link | Hankai | 文亭 | 实验汇总表 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue： EDU14 WH165555 ,DVT2 surge 200V fail，OTG &fastcharging can not work Clue： 1.fail unit Log show PD can not work .& Ibus=0 when Ibat =~2A. 2. use 2nd source Surge TVS 3.DVT1 &DVT2 bosth 2nd source Surge TVS test result bad than 1st source TVS Root Cause: 1. MT6375 damaged （replace a new MT6375 ，function,ok）. 2 ：poor Surge TVS cause higher Voltage go to MT6375 Solution: remove 2nd source Surge TVS ，from PVT .BOM change done | 实验汇总表 | Hankai | 文亭 |  | 3.BOM
2023-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | NA | [s3]issue:EDU03 WH164325 2nd NFC unnormal clue: root cause: solution: |  | Hankai |  |  | 6.No Change
2023-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]issue:EDU03 WH164325 2nd SIM card insert detected fail Root Cause：SIM1_INT pin short to GND solution：ADD TVS on DVT2 ,TCC Validated Pass | link | Hankai |  |  | 1.SCH
2023-05-22 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]issue：DVT WH164184 D4After -15KV air discharge at zone9,SIM card is broken. Analysis: 检查SIM接地良好 Root Cause: solution： 1、SIM_IO pin 增加tvs（DVT2导入） 2、SIM卡座接中框泡棉改用导电布 | Link | Hankai | 李果 |  | 1.SCH
2023-04-21 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:TDD Noise Found in EVT Root Cause:1.Receiver Affected by Magnetic Field of GSM-PA which is closed to Receiver 2.1 Multimode RF PA cannot meet the TDD design rules-RF Solution: 1.Add audio switch design for optimization validation | Link | 院长 | 院长 |  | 1.SCH
2023-04-17 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]issue：EVT WH163350 D3 After -15KV air discharge at zone8,Unable to detect SIM Card，unable to recovered Analysis: 检查SIM接地良好 Root Cause: solution：SIM1 IO 串联33R电阻 | Link | 邹仕海 | 李果 |  | 1.SCH
2023-04-18 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S1]issue：EVT WH163344 1 pcs 背压第9点界面异常，第11点时不开机 Analysis: 1.样机未复现故障现象 2.之前出现故障前出现安卓小人界面，怀疑死机导致，SW 抓下log 进一步分析 Root Cause: solution： | Link | 邹仕海 | 敏敏 |  | 6.No Change
2023-05-22 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3]Issue: Cap sensor no function on D2 post Root Cause: Poor SMT soldering Solution:Re-weld to restore normal,SMT optimization | Link | Xiongsn1 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-05-15 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3]Issue: CH1 fasle trigger in DVT1 on AW96308, Semtech EVT ok Root Cause:1. CH1 diff value affected by hand holding bottom of the phone Solution: 1.Vendor optimising with parameter |  | Xiongsn1 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-05-11 | 5.DVT1 | 6.Display/Touch | 6.Issue | S2 | Closed | [s3]SGM Release FCN that mention SGM3837 OLED Driver Frozed,Change to Novatek. Root Cause: SGM3837 出货有0.3%芯片本体损坏，导致整机会在VBAT上有漏电流，供应商数据10mA+ 影响度：量产项目： london na 无影响，London Row 13K , Juno 5K 试产项目：munaus 5G DVT1 1K 主板 , ODM XXX 项目 solution：1. 冻结所有在库SGM3837物料，退货处理。 2. 量产项目主板和机头进行sorting方案，挑选异常 主板方案： MMI夹具上分别测试主板漏电流 和主板+屏漏电流。 Juno 漏电流大于0.5ma的有16pcs/2882pcs=0.555%（16pcs中有12pcs漏电流大于10ma，12/2882=0.416%） 整机待定： 3.manaus 5G 主板sorting方案： 挑出>=0.5mA 漏电流主板 4. 圣邦之后供货初定3K，联想SMT后做sorting。 | Link | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-04-01 | 4.EVB | 2.Power | 5.4 ALT | S3 | Closed | [S1]issue：结构摸底测试中出现电感脱落（没有屏蔽盖） Analysis: 1. 厂家同批次验证，未发现焊盘脱落现象。 2.EVT 麦捷验证，未出现脱落现象。 3.EVT 太诱TMO 跌落中未发现脱落现象。 Root Cause:EVB没有贴屏蔽盖，可能是导致整机应力异常 solution：后续跌落实验室继续跟踪，有问题再重新提出 | Link | 敏敏 | 李果 |  | 6.No Change
2023-04-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S1]issue：EVT WH163330 C2 After +8KV air discharge at zone3/9/15,Drop call-GSM（连接仪器下） Analysis: 实网下测试正常 Root Cause: 可能匹配未调试导致 solution：跟踪DVT1后续实验，有问题再重新提出 |  | 韩凯 | 李果 |  | 6.No Change

## London NA (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2024-01-25 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | issue : London NA WLC can not work after rework stack board | link | 文亭 |  |  | 6.No Change
2023-06-27 | B.PVT | 3.Charging | 5.6 User Feedback | NA | NA | issue :DF charging slow |  | 文亭 |  |  | 6.No Change
2023-04-06 | B.PVT | 1.Platform | 5.6 User Feedback | S3 | Closed | [s3]Issue:abnormal power off during charging, 3 units till now,1 time/month . Clue:MT6363 POFFSTS[0xD]=0x8800 Clue:check vbb quality, Result:.vbb with big margin ,hw low risk Clue:Shut VBB through I2C Intentionally, Result:Not matching Clue:Heavy switch working mode(PFM/PWM) of VBB , Result:No issue Clue:Simulate Vsys and VBB Shut down, Result:Not Matching Clue:Run in 2400 units and check，Result:No Relative issue found Root Cause: 1.VBB Dip and trigger UVLO under extreme High Peak Current. Exp1.1 Force VBB Dip to 2.15~2.5 V@~4.5A，Result: Reproducing 0x8800 Exp1.2 Set UVLO to 2.0V and Draw 4.5A , Result:No Issue Exp1.3 Set UVLO to 2.4V and Force VBB Dip to 2.45V , Result: Phone Working Fine. Exp1.3 Set UVLO to 2.3 and Force VBB Dip to 2.35V , Result:Phone Working Fine. Exp1.4 Set UVL to 2.9V , Result: Dfer Reproducing rate increase 30 times/Month 2.SGM BOB PowerGood Trigger Solution: 1.Set MT6363 UVLO Value to 2.4V from 2.6V, Suggest to import asap and monitor DFer Data. 2.Restart when MT6363 POFFSTS[0xD]=0x8800/0x8000 confirmed in bootloader @charging boot up. | link | 敏敏 | 文亭 | 故障list汇总 | 4.Parameter
2023-04-06 | B.PVT | 1.Platform | 5.6 User Feedback | S2 | Closed | [s2]Issue:London NA unexpected reboot clue: Power off reason[PMIC][0xD] reg=0x40 which mean power cycle due to Long press powerkey 1.Suspect Power key stuck solution: change Key to panasonic 。monitor | link | 文亭 | 敏敏 | 故障list汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-05-08 | C.RAMP | 1.Platform | 4.Build | S3 | NA | Issue ：Pilot ORT 1pcs auto power off@Mxc06 40 tumbles ，D1，https://idart.mot.com/browse/IKSWT-137715 Clue：Log show[PMIC]POFFSTS[0xD]=0x2 ,means some power OCP or OVP. Clue.X- ray 查看之前CPU屏蔽盖风险点，看起来OK,没问题 Clue.故障机 看到气压计本体的盖子脱开了，掉在旁边的受话器磁钢上。（有磁性） Solution: 鉴于这台机器fail一次 ，项目整体的滚筒实验中也没有，风险度较低，monitor。 单体寄给厂家分析， Tracking 厂家单体分析，看是否有更进一步线索。 | link | 小熊 | 文亭 |  | 6.No Change
2023-04-17 | B.PVT | 10.USB-C | 4.Build | S2 | Closed | [s2]Issue: London NA PVT 耳机插拔压力测试，概率性无法识别，重新插拔ok，总不良率：0.4% （5/ 1240 ） SW CR:IKSWT-115443 ，log 判断有插入拔出事件 4/17 chenwt：目前log 分析 及 RD 实验室模拟，这属于连接性问题。 实验过程：先插入耳机，识别好耳机，然后断开一根CCpin 链接，之后就设备就不认了。 （如果再接上这根CC，就会再认到。 ） 这样模拟的log 和 issue 的log 一模一样。 转KP xiongxiong跟踪。 还有DVT2 时候IKSWT-92056 看着有些类似。 DVT2 一例接近100%复现的，log一样。 xiongxiong分析结果是 Type-C 连接器上有一层赃物，但具体是什么，不清楚。 action：PVT 继续确认下故障机，看下是否也有类似的问题。" Pilot 测试都ok，close |  | 文亭 |  | IKSWT-126520 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-03-21 | B.PVT | 12.EMC | 4.Build | S2 | Closed | [s2]Issue:PVT WH162948 D2&D4 TRP fail clue:stress test on ANT spring with tuner code control ，reproduce clue:Ant -> Funer :1.3nH->0R rootcause: 1.Tuner U100 damaged by ESD ，from ANT spring exp: C102 add ATVS ，RD test 4 unit ok with tuner coder 2.P2i destroy the grounding between sim board and usb board in PVT. solution:1.use non p2i usb board | link | 韩凯 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-03-01 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [S1]issue：WH161516- Main band48 No camp - LTE:D3/D4 Root Cause: 1.D3 band48 RX1 of FX6880(Switch PA) damaged、D4 band48 RX0 of FX6880 damaged 2、DVT2 LDS pattern changed in order to pass certification，may increase ESD risk exp：1、change FX6880，result：RF confirmed chip damaged （2023/03/03） 2、add TVS to ANT4、ANT2 result：研发自测ok action :rework 5 unit for retest in TCC ,from 3/9 . solution：add TVS to ANT4、ANT2 ，PVT import PVT reproduce ANT5 1unit fail solution：add TVS to ANT5、ANT7 & more RF component protect . PVT 二供 pass | link | 韩凯 |  | 故障汇总 | 3.BOM
2023-04-03 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S2 | Closed | [s2]Issue: Back camera cannot take pictures clue: rootcause: Not correctly connected after mic seal verification by ME exp: solution: | Link | 邦邦 |  | https://idart.mot.com/browse/IKSWT-116698 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-03-25 | 5.DVT1 | 5.Camera | 5.6 User Feedback | S2 | Closed | [s2]Issue: Rear main camera fail to open clue: rootcause: repaired, DVDD LDO bias short to GND leads to trace open exp: solution: | Link | 邦邦 |  | IKSWT-113215 | 6.No Change
2023-03-21 | B.PVT | 12.EMC | 4.Build | NA | Closed | [S3]Issue:1:PVT NFC test fail rootcause:1.Extra NFC Ant Discreat Component SMT on Stacking Board duo to not in DNS List. 2.Those DNS Part was removed and not adding back. Solution:1.removing DNS Part | link | 芳梅 |  | link | 3.BOM
2023-03-21 | B.PVT | 12.EMC | 4.Build | S3 | Closed | [S3]Issue:1:PVT USB can not used rootcause：TVS507&TVS508 orientation error due change from dual orientation TVS to signal orientation TVS but without orientation mark on build file Solution:1. rework TVS507&TVS508 2、update build filewith orientation mark of TVS507&TVS508 ，done by 3/22 | link | 韩凯 | 文亭 | Link | 2.PCB
2023-03-06 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S2 | Closed | [S2]Issue:1:DVT2 TRP error rootcause： ANT0 tuner damaged Solution:1.add mylar under LDS ，PVT import 2、add TVS on SIM board，PVT import PVT issue reproduce ，reissue it | link | 韩凯 |  |  | 3.BOM
2023-02-24 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:D1 All capsensor no function 2023/2/22 Root Cause： 1.Mylar was sticked uncorrectly，SX9375 exposed to the BTB connector 2.Mylar sticked artificially Solution：Import fixture to locate mylar , ME Planed DVT2 2nd source test pass PVT move capsensor far awar from camera connector | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-03 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | Issue: Temp / Humidity and Temp Cycle ， ALT drop 3units( 3/12) flash led no function. Root Cause: 1.2rd sourcing vendor flash led FPC ，LED SMT poor welding, need fpc vendor PBH improve DVT2 fail too Root Cause: 1. The heightening of the sea ring leads the flash FPC poor contaction, After opitimizing the structure， not find the issue in PVT. | link | 芳梅 | 川叔 | FPC vendor PBH analysis report | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-22 | 7.DVT2 | 4.Audio | 4.Build | NA | Closed | [S3]Issue:[LondonNA][Factory][CQA1][DVT2] When inserted the headset to phone, the phone hasn't recognize the earphone micphone NTF | IKSWT-92072 | 院长 |  |  | 6.No Change
2023-02-22 | 7.DVT2 | 10.USB-C | 4.Build | NA | Closed | [S3]Issue:[London NA][Factory][UCT][DVT2]USB_HOST GET_USB_HOST_MODE_STARTS Fail NTF solution：update test recipe for polling mode and issue not found | IKSWT-91107 | 文亭 |  | MTK CR | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-27 | 7.DVT2 | 3.Charging | 4.Build | NA | Closed | [S3]Issue:[London NA][Factory][BT][DVT2]BATT_CURRENT_CAPSWITCH_CHARGER_ Fail NTF solution: 1.加retry ，每次retry 增加0.1V，并在每次retry 都是Ibus 测试完直接测试Ibat 。 2.低门限放宽一些，从2.5A改为2A | IKSWT-95557 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD WH160481 D6 NKCT130135 ANT :EIS degradation exceeds 3dB, and TIS value out of spec(LTE Main_Band5):D6 final test rootcause：ESD -》ANT0—》ANT0 spring—》ANT0 TVS—》ANT0 Tuner damaged 。ANT0 TVS layout not good enough . Solution: 1. change SIM board layout，import from DVT2 2nd source build，monitor DVT2 2nd source test pass | link | 韩凯 |  | 故障汇总 | 2.PCB
2023-01-09 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | [monitor]Issue:TMO drop WH160497 D6 NKCT130126 Unable to enter camera mode:D6(5) Rootcause ： 1.Unable to enter camera mode/no audio function : U4153 damaged ，should be SMT issue or component issue .(MP component ) 2.Send Unit to Vendor ,monior DVT2 no reproduce | link | 院长 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-30 | 5.DVT1 | 4.Audio | 5.4 ALT | NA | Closed | [S3]Issue:WH160519 NKCT1E0116 Earpiece no function/ Loudspeaker no function/ Cap/SAR sensor no function/No vibration:C1 in initial(before Drop test) Clue:I2C reading audio parts are ok . From log check :capsensor initial fail block audio SW initial Root Cause:1.Capsensor Damaged Solution:1.NA |  | 小熊 | 院长 |  | 6.No Change
2023-02-03 | 5.DVT1 | 1.Platform | 6.Issue | S3 | Closed | Issue: London NA can not rampdump IKSWT-66439 Next A2+ (MT6879V/TZA) / /London NA // T //echo c > /proc/sysrq-trigger,Failed Clue： EVB ，EVT，DVT1 all can reproduce 100% Tesla MP & some PVT units fail too. EXP：Swap CPU with Tesla DVT2 chip ，and issue gone. Issue Follow CPU solution： MTK provide a patch and Solve the issue | link | 文亭 | 敏敏 | IKSWT-66439 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-30 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | Issue:WH160519 B3 NKCT1D0011 Unable to enter system:B3(1)-TH/TC Clue： Rootcause: 4 units all recovered after recharging the battery. Low battery leads the phone can't enter system. monitor | link | 芳梅 | 文亭 |  | 6.No Change
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD WH160481 D3 NKCT130197 NFC NFC no function 1. ESD from MIC3 hole （add from DVT1） -》NFC ANT spring-》NFC IC damaged Solution: 1.ADD TVS on NFC ANT spring DVT2 test ok | link | 韩凯 |  | 故障汇总 | 3.BOM
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD all Cap sensor no function,unable to recover:D2(15KV,zone1)/D4(15KV,zone16)/D5(15KV,zone12) 2:All capsensor no function,CH1&2&3&4 recover after reboot,CH0 unable to recover.D1(15kv,zone4） 3:Capsense(Ch2) no function,recovered after 15min:D6(15KV,zone4） Root Cause: 1.Ch0,Ch1,Ch2 of SX9375 Damaged through Wide Angle Camera and camera ring Exp1: Well Grounding of Wide Camera ,ESD No issue, Same unit, Isolate Wide Camera Grounding ,Reproduced Exp2:Add anti-esd film on cap-sensor area. Result: verifed pass. Solution: 1.Add anti-esd film on cap-sensor area. rd verifed pass. TCC validated Pass DVT2 2nd sourcing test ok | link | 韩凯 | 小熊 | 故障汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-09 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue ESD WH160450 Cap/SAR sensor no function:C1(15KV air） Root Cause: 1.SX9375 damaged Exp: REF_CAP_ANT0_2 shorted to GND Exp: recorverd after changing SX9375 2.ESD Path Analysis ,by 1/16 solution:add TVS on main board (near cap sensor) ，import from DVT2. DVT2 2nd sourcing test ok |  | 韩凯 | 小熊 |  | 3.BOM
2023-01-09 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [Monitor]Issue:build 7pcs can not download clue:remove CPU shielding case SH4309 and ok ,remount shielding case and ok too . R1601，C4411，C4416，C4478 are the High risk point base on the X-ray Root Cause : suspect some cap short to CPU shielding case SH4309 due to shielding case tolerance . Solution：1. ME control CPU shielding case SH4309 tolerance . 2. change PCB to provide more margin space for Risk components ,From DVT2 DVT2 ok | link | 文亭 | 敏敏 |  | 2.PCB
2023-01-12 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue :WH160450 ALS、PS No function A5(5) Root Cause: P-sensor damaged Solution： change PCB outline near P-sensor 。（Y+0.15mm to protect sensor componnet）,DVT2 import ,monitor | link | 小熊 |  |  | 2.PCB
2023-01-09 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue WH160450 No Main display B2(2) B4(3) A5(2) ,recovered after pressing power key repeatedly clue：all recovered, 1 times/4 units from 10 units Analysis:1/20 No available log ,4 units log no match log found in the phone after get the phone 1/31 new log shows，phone sleeps in when fingerprint HBM mode ,that leads no display，it's a SW bug. 2/1 can reproduce the issue at xiamen, phone sleeps in when fingerprint HBM mode ,that leads no display. next action:ALT test ,turn off fingerprint hbm mode Root Cause: NA | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-11 | 5.DVT1 | 5.Camera | 5.4 ALT | NA | Closed | [S3]Issue WH160450 Rear camera viewfinder has noisy points:A1/A2/A6(1)-TH/TC Root Cause: not reproduce in XM。 try to reproduce but can not reproduce |  | 邦邦 |  |  | 6.No Change
2023-01-11 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue WH160450 Cannot charge phone by induction A2(5) ，A1(5) Root Cause: wireless charge coil FPC assembly issue : Spring can not contact to the FPC finger .Assembly issue solution：Assembly issue ，ME tracing assembly quality | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-09 | 5.DVT1 | 1.Platform | 5.4 ALT | NA | Closed | [na]Issue WH160450 Unable to read SIM Card:B5/B6(1)-right Clue：replug SIM card and recovery Root Cause：1.get SW log for recheck 2.tear down phone for short risk check by ME No issue found。 reproduce：drop and SIM tray drop out a little and No SIM，can reproduce ，ME issue . Solution :ME Own |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-09 | 5.DVT1 | 4.Audio | 5.4 ALT | NA | Closed | [na]Issue: TMO drop WH160497 D6 NKCT130126 no audio function/no vibration(25)/unable to detect SIM card(29)/2nd L-sensor no function:D6(56) Root Cause:1.Stack connector damaged lead to failure ,ME tracking | link | 院长 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-08 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]Issue TDD : receiver mode . Root Cause: Up SPK PA Capacitor noise Solution ： change to Low noise Capacitor ,import in DVT1 . DVT1 retest and similar to tundra ，acceptable |  | 院长 |  |  | 6.No Change
2022-12-05 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [s3]Issue: WH159074 TMO Drop 10:Unable to power on:D5(47) rootcause: ：1、high PCB Strain 2、low inductor anti-strain capability, Taiyo Engineering Sample Solution:change PL2301,PL2318,PL2319 to microgate MP inductor,import in DVT1 [s3]Issue 2.1.2 : WH159076 ，ATT DROP， Unable to power on:D1/D14(1.25m),D5/D6/D9/D11/D13(1.5m）,D12/D15(1m) rootcause & Solution: same as WH159074 D5 DVT1 no reproduce so far 1/12 | Link | 敏敏 | 文亭 |  | 3.BOM
2022-12-05 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S3]Issue 2.1.1: build ，NKCN040279 NKCN050156 NKCN040229 not power on Clue：connect J2702 and big current。remove RF DCDC shielding case and ok . rootcause: RF DCDC shielding case short to C2745 & C2744 Solution ：change RF DCDC shielding case from DVT1 -ME 。DVT 1 no issue found | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-05 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: WH159074 TMO Drop 1:Proximity sensor no function,recovered after reboot:D1/D3/D4(14),D2/D5(28 rootcause: suspect no P-sensor parameter optimize , optimize it in DVT1 SW . monitor DVT1 and no issue so far 1/11 |  | 小熊 |  |  | 4.Parameter
2022-11-29 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue: Wide camera power noise rootcause: Low frequency radiation interference from BOB power in light loading PFM mode solution：1.set BOB in forced-PWM mode when camera open, PFM mode when exit camera app. RD Verified Pass 2.optimize BOB VSYS layout， far away from Wide camera module as far as proposable. DVT1 PCB import （PCB change improvement is similar to SW change） | Link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-08 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | [S3]Issue ：EDU03 WH159065 D3 After -8KV air discharge at zone9(Aging10),Mic1 and Mic2 no function,recovered after reboot.(only once not count 2022/12/6 15:09) rootcause: N/A Solution ： Monitor |  | 韩凯 |  |  | 6.No Change
2022-12-08 | 4.EVT | 4.Audio | 5.1 Bring up | NA | Closed | [na]Issue 12/13 SW版本开机后马上自动关机。 rootcause: 报电池温度70度所以高温自动关机。从EVB 到EVT SW 上面 电池NTC 都从 Fuelgauge IC 内部的集成NTC读取而未从我们要使用的 FPC上的NTC读取， 12/13 SW Yuechai 提交的更改 将Fuelgauge NTC读取 切换到产品要用的 FPC NTC读取 。 结构设计上有短路，短路点在小板上 的一个金属压板支架 和备用的NTC电阻焊盘 Solution ：SW 当读取的FPC NTC 大于等于70度，自动切换到Fuelgauge NTC HW 删除SIM小板上备用battery NTC位置，避免结构压板金属件短路 ，From DVT1 |  | 林峰 | 文亭 |  | 1.SCH
2022-12-05 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: WH159076 ，ATT DROP， Unexpected auto power off.D1/D5/D7/D11/D12/D13(1m) rootcause: waiting for unit back to XM [S2]Issue: WH159074 TMO Drop 8:Unexpected auto power off:D4(4) rootcause: SW issue Sometimes press the power button a few times and it will automatically shut down | IKSWT-51733 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-11-21 | 4.EVT | 8.PCB | 4.Build | S3 | Closed | [S3]Issue: Factory SMT build found SMT Stencil not match PCB for SUB USB Board rootcause: 1、In PCB design, the ORGB position was not updated, which led to component position drift during panel assembly. 2、The PCB factory adjusted the data according to its own experience to what it thought was reasonable, but did not give us feedback. The factory directly produces according to our actual output information. The steel mesh and plate do not correspond 3、Data conflict in EVT USB board assembly design solution： 1. Do not paste the offset part. Used for assembly verification of the first version 2. Urgent fabrication of SMT 3. Change Panel design lesson learn : 1. Update in《 PCB 拼板 Step by Step》， to improve the inspection process. 1. During the assembly inspection, check whether each layer is complete; Check that the position is correct. 2. the TGZ file completed by valor assembly will be sent to CAD colleagues for inspection. | link | 太加 | 艳红 |  | 2.PCB
2022-10-21 | 4.EVB | 5.Camera | 5.1 Bring up | S3 | Closed | [S3]Issue: Sois can not work rootcause: Sois I2C Pin Swap （KP output wrong SPEC when design & review） solution： correct EVT PCB SOIS I2C . rework some PCBA for camera team SOIS bringup lesson learn : 1. Vendor change SPEC and do not notice KP，KP didnot distinguish the change from Vendor. maybe KP can optimize vendor design change process 2.Bringup sheet need more detail check point for detail function . |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-10-21 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Issue:wireless can not work on EVB rootcause: suspect Nmos can not open due to no 5V at Vbus of Charge Pump solution：EVB not impact other bringup.rework 1 pcs for wireless related bringup . EVT change Charge Pump Vbus to CHG_VBUS(net after Nmos) | Link | 文亭 |  |  | 1.SCH
2022-10-21 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Issue:OTG can not work on EVB rootcause: Nmos can not open due to no 5V at Vbus of Charge Pump solution：EVB not impact other bringup.rework 1 pcs for OTG related bringup . EVT change Charge Pump Vbus to CHG_VBUS(net after Nmos) | Link | 文亭 |  |  | 1.SCH
2022-10-21 | 4.EVB | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3]Issue:can not find USB port rootcause: Audio switch power =1.8V Voltage is too low due to use VIO 1.8V ,but not Vsys or BOB . solution：EVB rework , remove R4573 ,short bottom pin of C4585 to bottom pin of C305 .(short Audio switch power to Vsys)--ongoing EVT change Audio switch power to VYSY (change MB SCH &PCB )--done lesson learn： 1.EXCEL表的PIN定义，写信号全名，不简写，以免改原理图时误解 2.EXCEL的PIN定义更改后，由更改人通过更改文档提交更改，以免REVIEW环节缺失 | Link | 院长 | 文亭 |  | 1.SCH

## Boston
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | 武汉实验室 失效分析汇总
2024-06-24 | D.SHIP | 1.Platform | 4.Build | NA | NA | [s3] MP产线发现概率性无法下载的主板（IF站点），比例~0.3% 初步判断： SCC8C83981 （EXS00A-CS12311）76.8MHz晶振，使用在几十个项目中，近三年的QC项目几乎都用这颗，没有报相关问题。晶振相关导致不下载故障从2024年5月份开始集中爆出。共性的情况就是都是用SCC8C83981 晶体，推测是SCC8C83981 最近批次有什么参数变化，（有可能还在器件SPEC范围内，因为厂家拿到故障IC给出的单体分析报告是pass的）导致和PMK IC无法很好的兼容工作。 RD分析：PMK IC供电都很正常，没有问题。实际测试XO 晶体本身的波形，发现故障板XO 是完全没法工作起来而不是频率偏移。而XO SPEC提供关键参数目前都看不出异常。 高通也给不了进一步的分析建议，让咱们找XO厂家确认除了 频率指标外还有什么会影响XO起振的情况。 临时方案建议：更换SCC8C83981 晶体批次，跟踪后续情况。更换后暂时没有问题，持续关注。 长期：找XO厂家继续确认还有什么情况会影响XO起振。 | link |  | 文亭 | QC CR：07311754 | 6.No Change
2024-03-25 | C.RAMP | 10.USB-C | 4.Build | NA | Closed | [s3]Issue:IKSWU-111557Boston CQA1不充电、不识别端口 NG，重启后才能pass（包括低电后充电起来的重启） ，比例 4/15000 Clue: 1. Factory 版本测试出现的 。 2. 默认没有ADSPlog ，SW从现有log 无法得到有效信息。 3.恢复的过程包括没电关机了，所以基于此的推测是：机器没电后 内部异常的状态就消失了，可以正常充电继续使用，不会变成砖头机。 exp: 打开ADSPlog ，针对出现问题的机器 以及其他机器共10台，进行压测。截止3/29 验证1300次，未复现。 NEXT：CQA2上追踪 其他建议：产线加入ADSPlog 的批量生产跟踪（这样一旦出现问题，可以获取到有效log，只加在整机端），产线评估中 -TE solution: TBD |  | 文亭 | 院长 |  | 6.No Change
2024-03-25 | C.RAMP | 3.Charging | 6.Issue | NA | NA | [s3]Issue:先放到无线充电盘上，等待5秒左右，插入PD充电器，出现充电图标但是实际没有充电电流的问题 Clue: 1. 时间短或者长都没法复现。 2.插入其他充电器ok （10W充电器，或者QC 充电器）。 exp: solution: | lin'k | 文亭 |  |  | 6.No Change
2024-02-23 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S2]Issue:EDU14 50V surge on Vbus，can not fastcharging (2 in 2) clue1: EDU14 WH172566 2nd source FVCT4J . PVT 1st source is pass. 1. Charging IC Nuvolta NU2115 was damaged Exp: measured surge waveform when broken. Result: surge voltage maximum only 13V, less than IC spec 22V 2.NU2115 analysis by vendor - report ETD 3/6 Exp: Adjust internal OVP Setting of NU2115 , 5 Pcs Exp: 6 More Units to Validate with new setting . Result: pass 3/8（ each unit test twice ） rootcause: surge voltage maximum only 13V, less than IC spec 22V solution:Adjust internal OVP Setting of NU2115（VAC OVP From 14V to 13V； Vbus OVP From 12V to 10.5V ；PMID2Vout_OVP from 12.5% to 7.5% ） （purpose： faster protection triged for surge test）—-verify 6 unit test pass | link | 韩凯 | 文亭 | TCC sheet | 4.Parameter
2023-11-08 | B.PVT | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: +15kV ESD, Flash always on, PM6150C BOB short clue1: flash板接地导电泡棉厚度压实后有1.0mm左右，接触正常 clue2:13M CAM背面贴了隔磁材料， exp：整改未贴隔磁材料机器进行摸底验证 exp：加贴一个tvs，初步验证ok rootcause: solution: PVT test pass | link | 韩凯 |  |  | 3.BOM
2024-01-05 | 7.DVT2 | 3.Charging | 4.Build | NA | NA | [s3]Issue ：4 unit wireless charge can not work after flash SW. （FR：4/200=2%）CR IKSWU-53713 Clue： 1.SW update to FW1.1 and then update to FW1.3 ，so it will update FW twice . 2. Log ：battery capacity are low （only 20+% for these 4 units when issue happen ） 。and then FW=0x 00 3. SW FW update logic：dont allow update FW if FW=0x 00 （to Solve other project issue ：power on with DP insert ，it disconnect DP） Rootcause ： 1.suspect FW update unstable with low voltage battery . 2.When FW updated fail ，it will show 0x00，and can not be updated again base on SW logic now. Solution： 1.change FW update battery capacity limit from 20% to 50% 2.change SW FW update logic ：allow FW=0x00 update again . SW change would be submit from ⅛ ，monitor | link | 文亭 |  | IKSWU-53713 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2024-01-03 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [s2]Issue:Display missing pixel Clue: exp: solution:中框加麦拉盖住底部中框跑道型通孔 | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-12-12 | 5.DVT1 | 10.USB-C | 5.6 User Feedback | NA | Closed | [S3]Issue: USB connection strange B2GID:324037417: unexcepted USB interrupt (Xiangdong`s EUT phone) Clue:1. stress test can not reproduce in test team. 200time USB plug &unplug. 2.Log analysis :some OTG interrupt found frequently. rootcause: LP，Foreign objects entered the Type-C (presumably saline or beverage), causing corrosion solution:NO |  | 文亭 |  | IKSWU-41681 | 6.No Change
2023-11-08 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: ALT, ESD, headset MIC no function clue: dvt1 二供有开始验证中芯的codec，可能与芯片厂变更有关 待确认故障位置 Exp1： Exp2： rootcause: solution: C2718 33pf电容为改TVS，降低概率 |  | 韩凯 |  |  | 3.BOM
2023-12-06 | 7.DVT2 | 5.Camera | 5.2 BB Test | S2 | Closed | [S2]UW Camera with new sensor GC13A2 got line noise Clue: 1. When the module was upright, there iwas no noise, indicating radiation interference. 2. Sticked magnetic shieding film, noise was gone. The radiation source comes from the module projector surface of mainboard. 3. Replaced S5B or set S5B into pwm mode, noise was disappeared. The S5B working mode is affected. Rootcause: Interference comes from S5B. Solution: 1. Stick magnetic shielding film under camera module. (need to verify BB ESD, RF desense, ANT perf, CamKP Mag Simulation) 2. Set S5B into pwm mode when opening camera. (still working with BSP) [Verification] No noise in PVT |  |  |  |  | 2.PCB
2023-12-05 | 7.DVT2 | 8.PCB | 4.Build | S3 | Closed | [S3]PCB from redboard silkscreen layer was broken after cleaning underfill gel clue: 1. problem was not with Compeq PCB 2. Redboard slice the offending PCB and Compeq PCB Solution: Redboard will thicken film of silkscreen layer as thick as compeq's | Link | 川叔 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-11-23 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ： wireless charge ，Irect >Ibus （Impact Qi Certification tuning. Some weak Tx maybe can not work） Clue：1.Ibat *Vbat >Ibus *Vbus （2.77*4.28 >0.78*11.9 ），output poewr >input power .suspect Ibus is error 2.short E1679 ，OK Rootcause ：E1679 impact PM7250B Ibus detection in wireless charging status. Solution：change E1679 to 0R. Import from DVT2 （DVT2 board check Ibus ok 4pcs .DVT2 phone RF check desense ok ） | link | 文亭 |  |  | 3.BOM |  | 9.282
2023-11-08 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: ALT, ESD, Flash always on, PM6150C BOB short clue: flash板接地导电泡棉厚度才0.2mm，而实际flash板到主板屏蔽盖间距有0.58mm Exp1：flash板接地导电泡棉厚度改为0.6mm（result：TBD） Exp2：c1524电容改为0.1uF（result：TBD） rootcause: 屏蔽盖泡棉未接地 solution: 加厚泡棉 | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-11-13 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: EDU03的报告，从OTA的数据看D4 ANT0通路有损伤 clue: Band 71 TRP degradation exceeds 3dB, and TRP value also out of spec. exp: rootcause: solution: improve sub PCB layout，调整TVS位置 |  | 韩凯 |  |  | 2.PCB
2023-11-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S1]Issue: Main Camera preview flicking after ATT trumble 400 cycles clue: 1. camera ois get gyro data fail 2. a+g function fail in CQAtest rootcause: PCB conner broken solution: ME FA |  | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-11-08 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | [S2]Issue: Main camera video record got obvious line noise clue: DVT1A, FR 3/406 exp: rootcause: solution: Increase MIPI VOD parameter |  | 邦邦 |  |  | 4.Parameter
2023-11-08 | 5.DVT1 | 1.Platform | 5.4 ALT | NA | Closed | [S2]Issue: WH169799 MD ALT 2019 DVT1 (Loop1)//ALT kernel panic clue: exp: rootcause: solution: |  | 敏敏 | 文亭 | IKSWU-28732 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-08 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: ATT tumble WH168486, Unable to enter system:D2(400) clue1: ramdump at moto logo processing，log show DDR abort clue2：remove back housing and it can power on（memory test ok in this status）--suspect some component solder crack clue3: slice test , no solder crack found rootcause: unknown solution: Monitor DVT1 / ME confirmed low risk | Link | 文亭 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-20 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S1]Issue: Main Camera preview flicking after ATT trumble 400 cycles clue: 1. camera ois get gyro data fail 2. a+g function fail in CQAtest rootcause: Pads of A+G sensor chipset were cracked solution: ME analyze |  | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-27 | 4.EVT | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue: Insertion mistrigger when stylus closes to the tp area above hall. clue: exp: rootcause: solution: |  | 小熊 |  |  | 6.No Change
2023-10-26 | 4.EVT | 2.Power | 5.2 BB Test | S2 | Closed | [S2]Issue: autopower off on some unit (2 in 7) when charging clue: 1. some unit can reproduce in charging mode （reproduce when SOC =94% ,SOC=100% ,and others） 2. Log analysis: PM: OCP Occured: PMIC: 4; SMPS: 8 . it is PM6150C S8E .suspect S8E in LPM mode when charging EXP2.1 :add loading on S8E found 100mA trig OCP, so it is in LPM mode. 2.2 :SW change it to NPM mode , result TBD （1unit 3days ok ，the other one seems not in NPM mode） rootcause: solution: change S8E from auto/retention mode to auto/NPM under sleep |  | 敏敏 | 文亭 | Link | 4.Parameter
2023-10-16 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Closed | [S1]Issue: UW Camera power noise, RCN value > 20 clue: Short AGND to GND close to UW connector, RCN got pass. rootcause:AGND of LDO is separated, leads to power noise solution: GND optimize & AVDD add 0R |  | 邦邦 |  |  | 2.PCB
2023-09-28 | 4.EVT | 5.Camera | 5.1 Bring up | S3 | Closed | [s3]Risk: The SOIS signal is out of step clue: The SOIS signal is out of step when two sensors on the SE0 simultaneously collect signals. clue: rootcause:SW Own solution:Camera Feedback Acceptable | Link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-08 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: EDu03 WH168449, D2, Flash LED was always on after ESD test on UW Camera ring clue: 1. PMIC damaged leading to VREG_BOB shorted to FLASH_LED rootcause:shot on CAM ring,energy strick the CAM shell to coupled discharge the spring of flash solution: Add TVS On Flash_LED |  | 韩凯 | 邹仕海 | Link | 1.SCH
2023-10-07 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: EDu03 WH168449, capsensor CH2 8KV NG clue: 1. L901 was short damage rootcause: capsensor CH2 sparated from ANT9，remained a suspended metal leading to weak ground solution:1、ADD TVS on the path of CH2 2、change higher voltage capacitor （25V to 50V） | Link | 韩凯 | 邹仕海 | Link | 2.PCB
2023-10-07 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH168459,Cap sensor ch1 no function:D1(25) clue: rootcause: Main board was broken by stress solution: ME Own |  | 小熊 | 邹仕海 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-07 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [s3]Issue ：ATT tumble WH168463, Unexpected auto power off:D1(350/450) Clue：1.it can reproduce in drop .2.Battery connector seems loose （other normal unit seems ok） exp1：wireout Vbat& GND and connect to power supply(without back cover)，RD drop 35 times and can not reproduce. exp2：wireout Vbat& GND from Battery and reassembly phone , RD drop 50 times and can not reproduce 2. This batterty connector is a new part that not MP in lenovo. Rootcause：1.phone power off in drop due to Battery connector contact issue.（connector damaged） 2.Why？ KP and ME analysis -weaker connector Solution： change BAT connector to molex BTB （MP parts） from DVT1 | link | 敏敏 | 邦邦 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-16 | 4.EVT | 1.Platform | 5.4 ALT | S2 | Closed | [S2]Issue: MDU72 ,WH168468, D1 , NB9A040201, 不识SIM卡 clue: no issue in EDu03 ESD test before MDu72 Clue: SIM recognition failure is due to modem crash Clue:Modem crash is caused by the factory's lack of complete calibration. Rootcause:The unit lacks complete RF calibration, resulting in modem crashing. Solution:Recalibrate RF parameters | Link | 李果 | 韩凯 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-10-07 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: TMO tumble WH168459, Unexpected auto power off:D3(125/150/200) clue: same as WH168463, Unexpected auto power off:D1(350/450) rootcause: battery connector deform solution: change BAT connector to molex BTB from DVT1 |  | 敏敏 | 邦邦 |  | 2.PCB
2023-09-08 | 4.EVT | 8.PCB | 3.Review/Simulation | NA | Closed | RISK：Some line layout under shielding case Corner ， may be broken in Drop test Monitor EVT ME Drop test 。 EVT drop test no related issue found ，close | link | 邦邦 | 文亭 |  | 6.No Change
2023-09-28 | 4.EVT | 8.PCB | 4.Build | S3 | Closed | [s3]Issue ： always in Fastboot mode total 13 units in EVT1 build Rootcause： There is some solder added between the bullet of V - and the positioning gold wire, which leads to a short to GND and keeps entering fastboot mode.The SMT process suspects that the opening of the steel mesh is too large, causing too much solder to float onto the positioning wire and causing the short. Solution：EVT2 SMT reduces the steel mesh at the corresponding position. Monitor | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-09-08 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ：3.0V~3.5V battery Wireless charging fail Rootcause： wireless charge stop output due to WLC_Mode_sel setted to 1 when SW detect 3.0V Solution： proposal 1.set WLC_Mode_sel in ADSP when phone power up （over 3.6V）--- -test pass，go with this Option proposal2. WLC_Mode_sel change control logic :default 0 =EPP , 1=BPP ,default not need to set it when SW detect 3.0V -test fail， proposal2 Drop | link | chenwt | 德太加 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-09-08 | 4.EVB | 7.Sensor | 5.1 Bring up | S1 | Closed | [s3]Issue ：FOD bringup fail Rootcause：the FOD connector was 180 degree turned exp： Solution：modify PCB |  | xiongsn | 邦邦 |  | 2.PCB
2023-08-28 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ：dead battery Wireless charging fail Rootcause： PM7250B do not charge with Vbus available only. Need CC logic work fine too. and dc_in_pon can not replace it.(Design in EVB ) exp：use reserved solution （a logic cirruit to pull CC to Vbus with 51KR when dead battery Wireless charging） pass Solution：1. add a logic cirruit to pull CC to Vbus with 51KR when dead battery Wireless charging. inport from EVT | LINK | chenwt | 德太加 |  | 3.BOM
2023-08-28 | 4.EVB | 1.Platform | 5.1 Bring up | S2 | Closed | [s2]Issue ：EVB Boston cannot force 9008 with V+ Rootcause： U1016 orientation error-clockwise 90 degree due to error not clear orientation mark on component Solution：1.turn U1016 anticlockwise 90 degree -EVB rework 2.sync correct orientation identification with SMT Engineer | link | chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor

## Geneva NA (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2023-08-29 | D.SHIP | 1.Platform | 6.Issue | NA | NA | Geneva NA Cannot charge & NTO EWG ID :180574&180463 180574 Analysis ：NTO and can not charge 1.Log found a clue: PM: OCP Occured: PMIC: 1; LDO: 25 it is PM6450的VREG_L25B_3P072 ，output to PDphy of PM7250B and USB power of CPU 2 VREG_L25B_3P072 impedance test： 11KR VS normal 200+KR，suspect some IC EOS。 3. Main PCBA USB DM&DP impedance test： DM is Infinity （abnormal），DP=1MR 。 4. PCBA USB DM&DP impedance test： DM is 11KR（abnormal），DP= Infinity 。 Next action：similar to 180463 ， wating for 180463 check if it is CPU damaged Rootcause: suspect EOS or High DC go into the phone through USB DM pin. and cause component damaged (TVS damaged ,CPU damaged) sent IC to QC for futher analysis. Clue：TCC 3T EOS surge test data ：USB DM DP can pass 45V . it is good next action ：1. monitor QC analysis 2. find ORT unit to do USB DM DP surge test again 3. try to do ESD test on USB DM DP. 180463 is similar | link | 文亭 |  | link
2023-02-27 | C.RAMP | 7.Sensor | 5.4 ALT | S2 | NA | [S2] Geneva5G Polit, ALT loop5, Light sensor功能异常，2台 现象：light sensor参数异常 root casue: 遮光膜开裂 Analysis: 1. 测试暗环境正常。--->电通路正常。 2. 结构拆机分析。----> 遮光膜开裂 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-27 | C.RAMP | 3.Charging | 5.4 ALT | S2 | Closed | [S2] Geneva5G Polit首批ALT测试后, 不充电 现象：不充电 root casue: connector pin crack Analysis: 1. 不充电，不能抓log 2. CQAtest, type-C test, CC pin test PASS 3. 拆机分析主FPC小板端，bat_thm pin翘曲 4. log分析：batt temp检测正常, 无法检测到usb插入 5. CQAtest U盘测试，usb host fail，log上看到可以识别VID, PID, 以及vbus 5V |  | 文亭
2023-02-27 | C.RAMP | 4.Audio | 5.4 ALT | S2 | Closed | [S2] Geneva5G Polit首批ALT测试后Audio问题 现象：Left Loudspeaker no function. root cause: recv装配歪斜 Analysis: 1. log: i2c probe成功，不是之前见到的i2c断线。 2. spk, headset mic正常 3. ME分析 -- recv装配歪斜 |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-24 | C.RAMP | 1.Platform | 5.4 ALT | S2 | Closed | [S2] Geneva5G 量产首批ESD测试后不开机 现象：测完ESD，放置一个小时，换成normal模式开机，2台有1台出现卡死在moto log界面。 Analysis: 1. log分析：安卓没起来，data/misc_de/0/apexdata/com.android.permission/runtime-permissions.xml文件被破坏 SW action: 40次清除log，重启没有复现。 （目前判断不是硬件问题） |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-15 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT EDu03 - ESD Certification Test, headset mic no function, SMIC codec, WH160401 ,1 units from 4 Root Cause: 1.Codec damaged through naked Mic Pin in Audio Jack Exp1: 2 TVS apply on ESD Path . Result: RD test pass (1/1), PVT TCC test failure (1/4). 2. SMIC codec anti-ESD too weak under IC spec Exp2: ESD 2kv directly on IC. Result: FAIL. 3. Geneva ESD protection is not strong enough to protect 15kv Exp3.1: Milan5G 15kV PASS, Geneva 12KV PASS. (Isolation of audio signal and ANT, TSMC & UMC codec pass ESD test before DVT2B.) Exp3.2: HW workaround, add extra TVS on audio path of MB, MDu30 test PASS. Solution: 1. Add extra TVS on headset mic path of MB. | link | 韩凯 | 李果 | link2 | 3.BOM
2023-02-14 | B.PVT | 5.Camera | 5.3 EE DVT | S3 | Closed | 【S3】Issue:DVTMXc03, drops front 100 times, Cannot enter rear 2 camera mode:D1(front), NGVADB0139 rootcause: connector pins solder crack on MB, SMT for further analysis |  | 邦邦 | 锦康 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-14 | B.PVT | 2.Power | 5.3 EE DVT | S3 | Closed | Geneva NA T4P 1台机器开不了机，充电发热 (机器准备做ALT，检查时发现故障） Analysis: PM6150C IC crach, BOB pin short to GND |  | 敏敏 | 锦康 |  | 6.No Change
2023-02-03 | B.PVT | 2.Power | 6.Issue | S2 | NA | [s2]bt crash B2GID:322334682 //Unexpected restart clue: no BT issue leads to unexpected restart. OCP on PMIC LDO19 (UMCP VCCQ2) rootcause: solution: |  | 敏敏 | 嘉琨 | https://idart.mot.com/browse/IKSWT-82029 | 6.No Change
2023-02-07 | B.PVT | 3.Charging | 5.5 Certification | S3 | Closed | Issue: TMO CEC PM fail ,0.31 W VS target 0.3W，CR ：IKSWT-83174 Clue：Pm is the charger input power of power off charging mode （when charging full） rootcause：charger input power of power off charging mode is too high than TMO SPEC. solution：change UFS to low power mode in power off charging mode， Lower down charger input power of power off charging mode（when charging full） TCC retest pass WH161567 ，pm=0.11W |  | 文亭 |  | IKSWT-83174 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-02-03 | B.PVT | 2.Power | 6.Issue | S3 | Closed | [S3]Phone Crash during second restart after skipping SlotB for OTA test , and then Restart failed. Clue:1.Press power key will help to continue the power on process. Clue2:Log shows GP Fault 7 and uvlo Clue3:HardReset or Battery Removed will recover. Clue4:Factory SW Also Reproduce , ~2% Root Cause:1.System Suspend duo to Fault Issue on of PMK6450 which caused by Secondary Power VREG_XO/RF/BB not shut. Exp:Measure Pon_rst_n/Fault_n/PS_Hold when crash reproduced, Result:PMK6450 Trigger Fault_N duo to Vreg_xo keep alive and drop after L17B. 2.BootLoader PSI File issue. Exp:Upgrade newest Bootloader Result: No issue Solution:1.Latest SW resolved Un-reproduced by QC mainline update | link | 敏敏 | 院长 | IKSWT-74127 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2023-01-31 | B.PVT | 2.Power | 6.Issue | S3 | Closed | [S3]FPS of First Vendor Get Hot and Short ，System crash， Clue:Second Source No Issue Rootcause: 1.system crash duo to Vreg_L28B Drop Exp1:log shows TZBSP_KRNL_FATAL_ERR_TYPE Fatal Error type:TZBSP_ERR_FATAL_RPM_ERR )，RPM Trigger Crash 2.Vreg_L28B Drop duo to FPS Module Broken and Short. Exp1.3.0V(VREG_L28B) 400+mA，OCP max=220mA~550mA，voltage drop to 2.4V Exp2.Father Power VREG_BOB Normal Voltage Solution:1. Fix PMIC OCP setting by SW and QC |  | 敏敏 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-01-30 | B.PVT | 3.Charging | 5.4 ALT | S3 | Closed | [s3]Issue: Cannot charge phone by USB: D7 (350) after ATT tumble , WH160949 Clue: PMIC sheilding case solder crack more than 40% .press sheilding case it recover. Root Cause: Batt_thermal Layer9 wire crack duo to ME stress (PMIC sheilding case solder crack ) | link | 文亭 | 邦邦 |  | 2.PCB
2022-12-29 | 7.DVT2 | 2.Power | 5.4 ALT | NA | Closed | Issue: DVT2 ALT WH159234 FVC T2H Unexpected auto power off.A2(1) TrackID: NGVT2H0110 HW: DVT2 SW: genevn_factory-userdebug 13 T1TGN33.7 d5a45-e78dce release-keys AP Log: https://drive.google.com/file/d/1-I8MHqvwROxQwy7XEVP2LI1Nv30weR7U/view?usp=share_link 问题及线索描述： 1. 插SIM卡，灭屏待机，静置2min，自动关机。按power键或者插USB直接开机。 2. 界面信号图标空白，Mobile Data图标反复On/Off，像是不断地尝试注网 3. 不插SIM卡，未出现故障 4. 飞行模式关机，开机再待机，未出现故障 5. 开机一段时间，尝试注网之后，再开飞行模式，待机可出现故障 Root Cause: 1.Unexpected auto power off duo to GP Fault7 triggered which means XO issue from log. 2.Next Step: Check XO -RF Cannot reproduced | link | 邦邦 | 敏敏 |  | 6.No Change
2022-12-23 | 7.DVT2 | 6.Display/Touch | 5.4 ALT | S3 | NA | [s3]LTE B12 Low RX1(DRX) Leve;D20, Initial check:Display Flickering, WH159301 analysis: 观察了是60Hz在严重闪屏，切换到90和120Hz闪屏消失。 怀疑为液晶电荷残留导致。80度加热半小时后，闪屏消失。（和博文沟通，还是ＤＶＴ２之前暴露闪屏问题，已有方案和对策） |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-22 | 7.DVT2 | 1.Platform | 6.Issue | S3 | Closed | [s3]Issue:SM6450 Device unable to boot after anti-rollback version is incremented Root Cause:1.VDD_QFPROM (connect to VREG_L23B_1P8) Power lost when TME checking anti-rollback efuse. 2 :It is difficult for SW to control VREG_L23B_1P8 in TME. Solution:1.workaround:change VDD_QFPROM power supply to an always on 1.8V power(VREG_L21B_1P8 on SM6450 platform), Import in PVT3 SW test ok in Factory | link | 文亭 | 敏敏 |  | 1.SCH
2022-12-22 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | S3 | NA | [s3]ALPS两套屏共用一套参数 |  | 小熊 |  |  | 6.No Change
2022-12-22 | 7.DVT2 | 9.Memory | 4.Build | S3 | Closed | [s3]CQA测试过程中主机dump-IKSWT-54990 Info: DVT2, Samsung 4+128 memory exp1: 交换memory --- issue follow memory ---> 寄memory给三星分析 |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-15 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | NA | [s3] Mdu30,TMO safety 55℃ |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-12-15 | 7.DVT2 | 7.Sensor | 5.4 ALT | S2 | Closed | [s2]Cap/SAR sensor no function:C2(CH2)(15KV), DVT2B ALT WH159234 2nd RootCause: cap short demaged by ESD Exp1: add tvs on path, to be verify by Hank Exp2: monitor in PVT ALT test Solution: Add TVS on cap sensor ch2 | link | 韩凯 | 院长 |  | 3.BOM
2022-12-15 | 7.DVT2 | 4.Audio | 5.4 ALT | S2 | Closed | [S3]Phone Crash during second restart after skipping SlotB for OTA test , and then Restart failed. Clue:1.Press power key will help to continue the power on process. Clue2:Log shows GP Fault 7 and uvlo Clue3:HardReset or Battery Removed will recover. Clue4:Factory SW Also Reproduce , ~2% Root Cause:1.System Suspend duo to Fault Issue on of PMK6450 which caused by Secondary Power VREG_XO/RF/BB not shut. Exp:Measure Pon_rst_n/Fault_n/PS_Hold when crash reproduced, Result:PMK6450 Trigger Fault_N duo to Vreg_xo keep alive and drop after L17B. 2.BootLoader PSI File issue. Exp:Upgrade newest Bootloader Result: No issue Solution:1.Latest SW resolved QC最后一次大版本33.46不复现。 | link | 韩凯 | 院长 |  | 3.BOM
2022-12-07 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Final LTE band 5&band13 TRP/EIS degradation exceeds 3dB After ESD testing Root Cause:1.Ant Holder Changed which easy to affected by ESD. Exp1：DVT2 Units change with PVT ANT Holder, Result: ESD Pass Exp2: Exp1 Change back to DVT2 Ant Holder, Result: ESD Fail Solution:1、Import PVT ant holder 2、naked ant feedback point shrink 0.2mm inner.(0.7mm->0.5mm) 3、Enhance GND of TVS | link | 韩凯 | 李果 |  | 2.PCB
2022-11-28 | 5.DVT1 | 2.Power | 5.6 User Feedback | S3 | Closed | [s3]Issue: Micron 6+256 found VCCQ2 Power Dip in Memory Log. Clue:Micron Memory log shows low voltage happened. 4 units till now Root Cause: 1.VCCQ2 Power Dip due to its Front Switching Power Supply S8E Power Dip when wake-up 2.After Set to PWM , S8E PWM can’t hold the Voltage even when Current stable 3.Switching Freq = 2.0MHz when Dip ,while No Dip when Switching Freq = 3.0MHz Exp Result:Failed Unit work normally in 3.2MHz when Start up and Home Idle. Solution:1. Change Retention Mode to Auto-Mode in Sleep -QC 2.Change 6 pulses in PWM back to 1 pulse during sleep. -QC 3.Modify 2 other Registor - QC No side effect observed. | Link | 嘉琨 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-11-16 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | [s3]Issue:DVT1 some not charging found in Factory PAT,FR 6%. Clue:Recovered after re-assembly Battery or Trigger HW Reset from Power Key. Root Cause: 1. Charging Failure caused by PM7250B initial failed due to unstable power supply when the first Battery connector Plug in. 2. Battery Pack Sensor Signal C+(with 100R in Series) contact first before P+ due to P-,C-,C+，P+ assignment and C+& P+short on Main Board Solution: 1.Remove C- &C+ of battery（change PCB） , Return to P+ and P- Design. PVT import 。PVT ok | link | 文亭 |  |  | 1.SCH
2022-09-22 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:EVT ATT tumble WH156483 1st,No voice. clue:Earpiece no function:D4(450),D11(300),D15-follow mainboard rootcause ：1. I2C line of smart pa damaged in innerlay on corner solution ：1.line expand to 0.2mm 2. optimize Solder Paste to reduce strain， DVT1 monitor DVT1 tested improved ，but still fail 2units ，optimize layout again ，DVT2 monitor No issue | link | 院长 |  | TCCFA | 2.PCB
2022-11-03 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]DVT1 Camera Power Noise Test ,RCN Value: Avg 9.2 ，Min 5 ，Max 13. Root Cause: Camera sensor analog gain 255 was not be correctly write into register Solution: SW corrects setting Lesson learn: check power noise as soon as possible in EVT phase, especially, close loop to check analog gain ect. in register value. | link |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-10-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]EVT1 Main Camera Previous Freeze when Air ESD +8KV. recover after Quit camera Root Cause: 1.1 Camera Module Hung after ESD Strike through Camera Deco. 1.2 Camera SW not stable in Darkness mode. Exp1.2.1:upgrade new sw , Result: Issue not reproduce. Exp1.2.2: Shadow Camera, Issue reproduced. Exp1.2.3:base on Exp1.2.1/Exp1.2.2 ,upgrade to old sw , Result: Issue reproduce. 1.3 Factory CQA SW version is a naked version, No robustness strength for ESD. Exp:Update to User version SW and ESD strike on wide Camera. Result:Not Reproduced. Solution:1.new sw fixed. | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-10-10 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [s3]Issue: EVT 滚筒实验反馈有4台机器开机键无作用。 CLUE：1.锁紧或者松开螺丝，故障可能恢复（暂时没找到锁紧还是松开更容易恢复和复现问题） 2.出现问题的时候，测试开机键测试点，电压1.8V，按下开机键变成0V，松开又回到1.8V。所以推测：弹片接触没问题，上拉电源也没问题。 Rootcause：应力过大，多次撞击导致屏蔽盖频繁拉动内层线路，导致PHONE_ON_N 网络在第8层 有部分断线 补充疑问：以往一般在L9就断了，L8基本没见过。 原因推测：L9 这部分铺地，比较强，力往L8 传递较多。 solution：1.PHONE_ON_N 网络改板走线改到0.2mm宽度-DVT1二供的板子导入更改。 2.同区域的I2S信号4根线一起加粗到0.2mm ，降低其他功能fail风险。 | link | 文亭 |  |  | 2.PCB
2022-10-20 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | [S3]EVT dead battery charging test ，can not charge on with battery cell Voltage 1.9V~2.6V Clue：1. can charge ok with discharged battery package voltage to 0V 2. Cell voltage lower than 1.9V can charge to around 1.9V. higher than 2.6V can charge to power up Root Cause: 1.VPH_PWR drop when PM7250B detect Vbat=3V 2. Cell voltage <2.5V whenVbat=3V ,so package =0V when charger buck stops switching. 3.Due to a design bug in PM7250B, charger buck stops switching for ~150 μs when it transitions from pre-charge to fast-charge state. The battery voltage at which charger buck does this transition is determined by VSYS_MIN threshold which is 3V by default and 3V Geneva NA battery can not support Vbat when charger buck stops switching Solution:change VSYS_MIN voltage configuration to 3.1V | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-09-22 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]EVT TMO tumble WH156479 1st,P-Sensor no function Clue:issue follow mainboard rootcause ：1.P-Senser line on corner damaged in inner layer. solution：1.change line to next inner layer. 2.other rest line expand to 0.2mm DVT1 ok | link | 小熊 |  | TCC FA | 2.PCB
2022-10-14 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | [na]EVT2 wide Camera Previous Freeze when Air ESD +8KV. recover after Quit camera Root Cause: 1.1 Camera Module Hung after ESD Strike through Camera Deco which lead to Previous Freeze. 2.1 8M Camera Module Housing isolated GND duo to Cost Down before(0.x Cents) which lead to Module Hung. Exp:Grounding 8M wide camera by copper and conductive foam($0.05). Result:Not reproduced. 2.2 Camera Deco is conductive and floating from GND which lead to ESD Discharge to Camera Iron Housing. Exp:Remove conductive Deco ,Result:Not reproduced. 3.0 Factory CQA SW version is a naked version, No robustness strength for ESD. Exp:Update to User version SW and ESD strike on wide Camera. Result:Not Reproduced. Solution:1.EVT ESD is an engineering evaluating method. in Real user SW scenario ,issue not happend. Accept it . |  |  |  |  | 6.No Change
2022-09-22 | 4.EVT | 4.Audio | 5.2 BB Test | S2 | Closed | [s2]Risk: EVT TDD Noise Risk Root Cause:Calling sw not ready. Solution:SW fixed and test performed |  | 院长 |  |  | 6.No Change
2022-09-26 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | EVT 眼图调试完成 device mode | link | 文亭 |  |  | 4.Parameter
2022-09-12 | 4.EVT | 11.Thermal | 5.6 User Feedback | S3 | Closed | [s3] Issue:Geneva NA EVB/EVT待机过热问题 Clue： 1. 系统可以正常休眠，休眠电流正常 ，平均9mA，未发现硬件漏电问题 2. 亮屏待机电流高，平均电流超过1.1A，导致发热厉害 （70%的屏幕亮度）,从log看是CPU 频繁重载导致 3. 打开飞行模式后，CPU负载减轻，平均电流降到500mA，发热明显减少 4. 需功耗进一步分解并优化，重点看下modem端 Root Cause： 1. 未导入校准参数，导致功耗异常高，主板发热厉害； Solution： 1. 导入校准参数，亮屏待机电流降到500mA 2. 500mA平均电流，依旧过高，需进一步分解； |  | 林峰 | 李果 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-08-29 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue:Geneva NA EVB HWID incorrect Clue: 0. Geneva ROW have same issue too 1.GPIO38 B band detected as A . (when set pull up with exter pull down 10K , it read high ,VS normal is LOW .) 2.Waveform check : it stop at 1.25V ， so it is high . suspect :Pull up R is about 4.3K VS SM6375 SPEC 20K min （No SPEC in SM6450 yet） 3. change to GPIO 37(HWID 1) ,same issue. 4. change to GPIO48 ,it is ok. change to GPIO113 ，it is ok too. Root Cause: 1. HWID detect error due to Low logic detect error when setting GPIO 37 & GPIO 38 pull high with exter pull down 10K 2. GPIO 37 & GPIO 38 Low logic detect error due to GPIO 37 & GPIO 38 Pull up capability is too high 3. GPIO 37 & GPIO 38 Pull up capability is too high ,Pull up range is 3kohm to 10kohm & Pull down range is 5kohm to 10kohm (QC reply 09/06) Solution: HWID GPIO change from GPIO 37& GPIO 38 to GPIO 48 & GPIO 113 ,From EVT (change done ). further check: need QC comment if there is other GPIOs similar to GPIO37&38 | link | 文亭 |  |  | 1.SCH
2022-08-25 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue:After download adsp.img phone power off Clue: 1.after download adsp.img machine power off,off current is 48uA VS normal is 200+uA 2.after 1 ,then first short press powerkey,no current VS normal current is 170mA 3.Waveform check VPH_PWR Drop and never go back to Vbat when issue happen（suspect shipmode or AFP triged） exp3：short VPH_PWR and Vbat ， then it can power on . 4.Log check :no shipmode mode trigged (after rework VPH_PWR and Vbat to short) ,so suspect AFP triged 5.check BATT_THERM NTC (RT500) & batt_ID R found BATT_THERM NTC no mount on sub pcba exp 5.1： rework RT500 with 100KR and it can power on . （confirm it is AFP triged） exp 5.2 disable AFP function and it can power on too.（no rework HW） Root Cause: 1. phone power off due to batfet close cause ,and cause VPH_PWR Drop （after adsp.img loaded ） 2. AFP mode triged by Low temp caused by RT500 not mount Solution: 1.workaround :disable AFP function in EVB 2. add RT500 into BOM in EVT | link | 文亭 |  |  | 3.BOM

## Dubai+ NA (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2023-01-05 | D.SHIP | 9.Memory | 5.6 User Feedback | NA | NA | Issue ： Dubai+ NA (TMO): NTO After MR0 OTA(IKSWS-176032) ，total 3pcs by 20230105 |  | 嘉琨 | 文亭 |  | 6.No Change
2022-06-17 | C.RAMP | 11.Thermal | 5.5 Certification | S3 | Closed | [s3]Issue:TMO Safety Test, CPU Heavy Loading+Max Volume + Max BrightNess+Charging+White Nosie，Result=53°C >48°C. Root Cause: 1. Top Speaker Over Heating on White Noise. Exp1:Using new Audio EQ ,when SKP Temp < 80°C （Original 90°C）and using 1X1 mm2 Avg Temp in stead of dot temp， Result: TMO Reset. Exp2:Using new Audio EQ ,when SKP Temp < 70°C for back up. Solution:1.Using new Audio EQ ,when SKP Temp < 80°C ，And RCA | Link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-06-17 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue: Tesla some times can not charge in DF (DVT2 &PVT),Recovered after power cycle, 5 users reported. Root Cause: 1.not charge due to cc logic error,and can't detetect cable. Exp1:CC /Vbus Waveform Plot. Result: 1.CC Open 2.CC 5.1K Conclusion:CC Logic in error stats 2.CC Logic error duo to interrupt source masking Exp2: embedded reg plot in User Debug 1 , Result: ISR Mask （mean not support INT now） 3.Int mask duo to int Arbitration issue of system Exp3: Import Patch2 and try , Result:Pass Solution: 1. import patch 2 to main line（I2C INT flow optimize），Validated Pass | link | 文亭 |  | IKSWS-127586 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-07-25 | C.RAMP | 11.Thermal | 5.5 Certification | NA | Closed | Issue:Downloads drops from ~ 2Gbps to 50Mbps Clue1:LV1 52°C Trigger NR CA Off Clue2:LV2 55°C Not Triggered in this case Root Cause:1.NR CA off not correct in Modem Policy Lev1 Exp1:Remove NR CA , Result:Downlink > 5 Min . Conclusion:Pass Solution:Remove NR CA off, DownLink Validated Pass. Issue:Uplink drops observed during test. Clue1:LV1 52°C Trigger NR CA Off Clue2:LV2 55°C Not Triggered in this case Root Cause:1.Uplink trigger in Modem Policy Lev1 Exp1:Remove Uplink Throttle in Lev1, Solution:Proposal:Remove Uplink Throttle |  |  |  |  | 4.Parameter
2022-06-17 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | NA | Issue:IKSWS-129202 Phone battery will not charge B2GID:320148798 my phone will not charge from either the 30 watt usb-c AC charger or the Verizon turbo DC charger in the car Clue：1.HW： NDPA2G0018 2. From the log ，No Vbus detect from the 2 charging IC（MT6375&BQ25960） Root Cause: suspect Type-C connector damaged such Type-C connector liquided or other connection issue Action ：1. check Type-C connector if there is some abnormal 2.Check if there is PRC user feedback same issue ？ Solution: ? |  | 文亭 |  | IKSWS-129202 | 6.No Change
2022-06-17 | C.RAMP | 9.Memory | 4.Build | S3 | Closed | [s3] Issue:Download Failure, FR 0.3%(12/4000) Root Cause: 1. Downloading block by rank1 size check failure duo to write leveling calibration failure. Exp:Force Dual Rank Downloading , Result:Pass . 2. ddr write leveling calibration failed duo to no expected return value from Dram after calibrating command sending. 3.ddr not response duo to WCK（Write Data Capture & Read Data Output CLK，Diffential Pair） not align(Sync/Unsync). Exp3.1: Change Command mode with Byte Mode. Result:Failed Exp3.2: Change Command mode with Normal Mode . Result: Pass Exp3.3: Sync Dram WCK Status before rank detected .Result:Pass Exp3.4: Rank Detection Retry 5 times. Result:Pass 4.Where wck misalignment? Conclusion: WCK Sync Status Abnormal When WCK On Exp:4.1 retry rank detection only DRAM init flow,Dump WCK Status(Sync/unsync) ,result:6/21 Exp:4.2 Setting as WCK to low power mode from high performance mode , Result:No affection Exp:4.3 move WCK On/Off Position, Narrow Down the misalignment code. Result: WCK Sync Status Abnormal When WCK On. Exp:4.4 Ask Micron if any special request/constraint, Result:Not affected Exp:4.5 Any Margin Concern- Discussing ,Result:Not relative 5.Why WCK Sync Status Abnormal? Conclusion: Exp:5.1 Check Dram Controller Reg Difference and change procedure , Result: Dram Controller Reg Changed during ddr boot acceleration in Boot Rom（new feature from other platform but with compatibility issue） Solution: 1.re-compiling DA and Preloader， where reg status fixed in the later init process. rd validated pass. factory validated. |  | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-06-07 | C.RAMP | 9.Memory | 4.Build | S3 | Closed | [s3] Issue:After power off, phone take long time to boot up, FR 3%(55/1759) Clue:ETT Mem Test Pass, Rd & Wr Eye-Diagram Pass. Root Cause: 1. boot up latency due to mr5/8 and ddr rank_size check failure and preloader reset repeatedly. Exp:log Result: show mr5 0x1, rank0_size 0x0000000040000000, abnormal 2. read failure happen on the first check during the Fast ddr lane calibration (Parameters read from UFS after the first full ddr lane calibration) Exp 2.1: Disable Fast K and test. Result: Pass ( 30 units 30 times,1 time failure and not reproduce) Exp 2.2: Retry RX RDDQC, Check if always pass after the first failure. Result: All Pass. Exp 2.3:Check Rx Config Register on the first Fast ddr lane calibration compare to the other times. Result: Quit Different ,Conclusion: bad/wrong Rx Config Exp 2.3.2 Recheck RX Config Register. Result:Rx Config Resister is same ， Revert Exp2.3 Conlusion by Rx Config Normal Exp2.4 Check HT/LT , Result: LT boot up OK. Conclusion:bad rx performance on failed unit Exp2.5 Check 26M CLK, Add 500ms in Mem init and RDDQC(Read Data Q Calibration), Result: No improved, Conclusion: CLK OK. Exp2.6 Check HV/LV ,Result: No Improved , Conclusion:Voltage OK. Exp2.7 Check Power Timing, Result:Power Timing OK. Exp2.8 Lower ddr Frequency to 1600Mbps during preloader， Result:Failed. Conclusion:CLK OK. 3.read failure happend duo to missing of DramCPhy Initial Exp3.1.1:Compare the diffirence between first cali and others. Result: Dram Phy Reset Not executed. Exp3.1.2:Execute Dram Phy Initial Before Fast calibration , Result: No Issue. Conclusion: Issue happend duo to missing of DramCPhy Initial Solution: 1.sw work around:RDDQC retry. no side effect. rd validated pass, Factory Validated pass(60PCS*50times pass) 2.SW Patch:Execute DramCPhy Initial before Fast Calibration. RD Validated Pass. |  | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-05-17 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [na] Issue：Edu 03 ESD test，4/6 OTA Performance Degrade. Root Cause： 1.Tuner Damaged by ESD Through ANT seam in Bottom 2.1 Wasin CES TVS can't stablly protect Tuner Exp:2.1.1 Change Wasin CESTVS to Panasonic ATVS , Result: RD validated, 1 failure of 3. Exp:2.1.2 Add 2 ATVS,Result:failed Exp:2.1.3 Change Wasin CESTVS to Panasonic ATVS,12KV ,Result:Pass Exp:2.1.3 Change Wasin CESTVS to Panasonic ATVS,15KV ,Result:PASS 3. 13% Avg shorter interval(0.1mm) between Conductive Ant and boarder compare with PVT and DVT Exp:3.1 anti-ESD foam cover on the exposured and pad and test. Result: Rd validated , Pass Exp:3.2 enlarge interval by 0.35mm in middle frame, Result: 6/? Solution： 1.Change Panasonic ATVS from Wasin CES TVS.PVT import 2.enlarge interval by 0.35mm in middle frame. ,6/? me running change | LINK | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-05-17 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [na]issue:Edu03 ESD test ,NFC no function after 8k air AD ,D1 units Recover after standing for hours；D2 recovered after battery removed and restart. clue: issue reproduced after esd retest. Root Cause: 1.NFC Ant 330pf 25V resonance capacitor C1352/C1353 broken . 2.Low Capacitor anti-esd performance Exp2.1: Change 330pf 50V cap ,Result:RD Validated Pass Solution:1. Change 330pf 50V cap , 12KV validated pass. 15kV validated pass |  | 韩凯 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-05-17 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | Issue：Edu 03 ESD test，D6 After - 15KV air discharge at zone12 (Aging 10),Cap/SAR sensor ch0 no function, unable to recover route cause：R4509 open solution：add tvs |  | 韩凯 |  |  | 3.BOM
2022-04-29 | 7.DVT2 | 7.Sensor | 5.3 EE DVT | S3 | Closed | [NA] Issue： WH150730 DVT2 EDU03 ESD Test ,D6After - 15KV air discharge at zone12 (Aging 10),Cap/SAR sensor ch0 no function Root Cause: 1.R4509 is open，never seen before Exp1;Send Damaged Resistor to vendor for FA. Result:TBD Solution: 1.Monitor following Test to see if reproduced. |  | 小熊 | 韩凯 |  | 6.No Change
2022-04-29 | 7.DVT2 | 4.Audio | 5.3 EE DVT | S3 | Closed | [NA] Issue： WH150730 DVT2 EDU03 ESD Test ,D1After -15KV air discharage Zone19 aging(10),mic3 no function Clue:Second Source Verification units Root Cause: 1.mic3(AAC) damage through mic FPC stiffener steel and Mic Hole on back housing Info: 1.noisy risky if Mic FPC stiffener steel grounding Solution: 1.Monitor following test to see if reproduced another one . |  | 院长 | 韩凯 |  | 6.No Change
2022-04-26 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3] Issue： WH150801 DVT2 EDU14 Surge Test ，1mA Leakage current is out of spec.D1(180V),D2(160V) Clue1：2nd source charge pump SC8541 verification FVC A2R Root Cause: 1. VBAT Pin of SC8541 which leak 1mA. Info:1.first source TI BQ25960 300V Pass. Exp1.1:Check leakage Current stable？ Result: 5/12 2.Surge Path from VBUS to VAC1 Exp2.1: Surge Signal Measurement ,Result:Surge Peak Voltage 46V>36, 80ns duration. Exp2.2:Add 100nf Cap to suppress peak voltage. Result: No affection Exp2.3:Add 100R Resistor in VAC1 and verify . Result: Pass Exp2.4:Send Failed IC to Vendor for Further FA. Result:Application suggestion provided Solution: 1.Add 100R Resistor in VAC1，RD validated Pass ，TI BQ25960 also Validated Pass ，Running Change | link | 文亭 |  |  | 1.SCH
2022-04-28 | 7.DVT2 | 3.Charging | 5.5 Certification | NA | Closed | [NA] Issue： Safity certification in Shenzhen Sporton , FOD test fail , Root Cause: FOD limit debug for certification Solution: SW FW update for FOD (change to 800) |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | NA | Issue: DVT2 2 PCS Cap Sensor No function Clue：1.Main FPC BTB connector Pin burned in sub board side 2. Cap_ANT1 short to GND after burned Root Cause: ？ Solution: ? | Link | 林峰 | 林峰 |  | 6.No Change
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | Closed | Issue: DVT2 Factory IF fail mostly when battery NTC pin connected in IF fixture , IKSWS-83340 Clue：1.EVT have problem in Wuhan factory but can not reproduce in XM WWTE LAB . So monitor DVT1 Root Cause: Solution: 1. remove battery NTC Pin of IF fixture on DVT2,not impact test |  | 文亭 |  | CR IKSWS-83340 | 6.No Change
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | Closed | [S3] Issue：Issue:Factory IF fail in DVT2 2nd source build ? IKSWS-89240 Clue：0.Phone can't power up after download sw 1.DVT2 1st source build ok 2.DVT2 BB 2nd source component including 8+128 Hynix memory ,SC8541 30W charging IC ,Barometer sesnor ,? 3.6+128 Hynix memory with other 2nd source board fail too (suspect not Memory related) 4. other 2nd source +1st source 30W charging IC BQ 25960 ,result TBD? 5. can download and power on in BB LAB with same PCBA (when first board verify), So it should related factory IF envirenment，Power drop is too large.（Vbus & Vbat） Root Cause:why 实验室复现单台故障的，发现Vbus 有时候会下降比较多，最大的时候Vbat也下降很多。 并且有时候看到电流往Vbat流入（这样会加重Vbus的负载） 分析发现产线IF上电顺序有问题，Vbus 比Vbat早上电。 Solution: 尝试将ICL改为1A，并且disable 电池充电路径提前一些。 2. Vbus 从原来的5.8V 改到6.5V 3.修改测试序列，将Vbat上电提前到Vbus 之前。---实际验证后 三条solution 都加入后，良率上升到95%以上。该问题不block 生产了。 4.产线加上retry ，良率会再次提升。 依此跟踪PVT生产情况再看是否ok | link | 文亭 | 林峰 | CRIKSWS-89240 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Closed | [S3]Issue:DVT1 APM current 13.3mA no meet TMO request(<5mA) Root Cause: 1. p-sensor polling interval time 50ms after awake. proper value=250ms. 1.5mA -SW On-Going 2.Modem cannot be powered off due to RF different designs (0.43mA) 3.Display RST 0.3mA Optimized. 4.TP Power 1.5mA ,Optimized. 5.Display 16M CLK -0.77mA Optimized. 6.Esim Removed 2.2mA Optimized 7.Hall IC GPIO Configuration 3 mA Optimized. Solution: Proposal:1.PSensor Polling interval time optimization. 2-7 according to the root cause 3.32.32 SW meet MTK target(average current=6.93mA,Min=5.77mA) | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Monitor | [S3]Issue:DVT1 MP3 playback current fail,70mA higher。 Root Cause: 1. DVDD_Core Cosume extra 34mA when Mp3 Play. CPU ocupied. 1.1 Why CPU not sleep? - SW 2. Current Not Stable 2.1 Dolby Enabled 2.2 GMS Enable 2.3 Battery Tracer Enable 2.4 TBC Solution: 1.TBD | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Monitor | [S3]Issue:DVT1 Video Playback (local storage) BSP current fail,CD=340mA。 Root Cause: 1.Display Current Cosume 1.1 Fresh Rate Difference. 2.SW configuration or backgournd Service. Exp:Test with Facotry Version 148mA = MTK Demo Phone 148mA. The platform power consumption data is the same as MTK Demo Phone data （W/Display+Factory SW version) 2.1 Dolby Enable -3mA 2.2 DDR Config - SW Solution:1.TBD | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-03-30 | 5.DVT1 | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue:DVT1 Sensor not work after ALT？ 1 in 15+2 in 9 total 3 in 24(only in 2nd mainboard) clue: Root Cause: 1 I2C wire crack at BB shielding case Top left corner 2. PCB over Strain - ME Analysis. Solution: Proposal: 1. Modify Shielding Case Solder Mask to reduce, under validated. 2.Optimize I2C width | link | 小熊 | 李果 |  | 2.PCB
2022-03-30 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1 Vibration not work after ALT 3 in 10 Root Cause:1 VIB_RST wire crack at BB shielding case Bottom left corner （layrer 2） Solution: 1. Change VIB_RST to Layer 3 ，PVT import. |  | 院长 | 李果 |  | 2.PCB
2022-03-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:DVT1 Cap Sensor not work after ESD. clue:Sending Unit to Xiamen. 3/8 Root Cause:1.No tvs Protect for this channel Solution:1.Add TVS on failed channel. | link | 韩凯 | 小熊
2022-04-06 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | [S3] Issue： 2% unit can not work on USB connect （No USB port ），CR IKSWS-84946 Clue 1：power cycle cannot recover but Blankflash and Long time press powerkey can recovery 2.waveform ok onUSB D+D- test point but no signal on Type-C ---Analog switch control problem 3. Analog headset can work ，and after this ，USB connect recover. Root Cause: Analog switch control issue Why ---SW : analysis ongoing---liaohj Solution: SW Analog switch initial change | link | 文亭 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-04-13 | B.PVT | 1.Platform | 4.Build | NA | Closed | [S3] Issue：[Tesla][Factory][IF][PVT]WAIT_FOR_NETWORK_INTERFACE_ARRIVAL_POST_FLASH Clue：实验室复现类似问题，发现这时候，Ibus 一直是0A ，也就是没有抽任何电流， 需要SW 分析下log ，为什么 rootcause：产线设置Vbus 6.5V触发chargepump 默认的OVP最低值6.3V. solution：产线设定Vbus电压到6.2V. | link | 文亭 |  | CRIKSWS-102720 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-02-18 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue: Camera Power Noise Abserved in Darkness in DVT1 units. Clue:EVT not found duo to SW not ready. Root Cause:1.AVDD Power Noise 2.Camera AVDD Capacitor need to fine tune Solution:1.update Camera AVDD Capacitor C4159 to 4.7uF+2.2uF. DVT2 import | Link | 邦邦 |  |  | 3.BOM
2022-02-11 | 4.EVT | 11.Thermal | 5.2 BB Test | S3 | Closed | [S3] Issue： BB test ，CQA battery temp=36 degree ，plug in charge ， battery temp jump to 43 degree 。when 26degree ，jump to 31 degree. clue ：1. Vbus charging current =3A 。plug out charge ，jump back to 36 degree （Vbus current impact battery NTC reading？） 2. When charging with QC charger ，jump is 3 degree （27 to 30） Proposal 1：小板和主FPC 共GND造成的偏移？ Exp1: 小板和主FPC上面NTC拉单独GND，依然有4度的偏高存在。 Proposal 2：ADC 的GND 有干扰，和MTK确认BATON 的参考地是CS_N 而不是GND。 EXP2：飞线NTC- 到CS_N上面，验证有2度左右改善 Proposal 3：SW上面COM_FG_METER_RESISTANCE 默认的75 ，表示补偿了7.5mR。实际上不需要 EXP3：去掉补偿。改为0 。实际验证下来 结合EXP2，基本没有偏移了，温度准确。 Root Cause: 1. HW：BATON 的参考地是CS_N 而不是GND ，有个5mR对地的采样电阻。 2. SW：MTK默认代码加了个补偿值7.5mR ，给电池内部的NTC用的。不符合项目设计。 Solution: 1.SW：去掉补偿。改为0 。DVT1 导入 ---柴璐 ，20220215 提交更改 2.HW：NTC- 改到CS_N，需要更改主板，主FPC，小板。DVT1来不及改，计划 DVT2 导入---林峰 -done | link | 林峰 |  |  | 1.SCH
2022-01-10 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3] Issue：EVT power off current =424uA，too large ,VS normal project 100+uA Root Cause: 1.100uA current leakage on MT6685 Solution:1. MTK will upgrade new version MT6685 , import in DVT1. 2.测试DVT1主板(机器) 5pcs，4pcs power off current= 259uA~275uA,1pcs =325uA,关机漏电流有明显改善 | Link | 敏敏 |  |  | 3.BOM
2022-01-20 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S2] Issue： EDU14 Surge Test WH147427 ,D1 Vbus test 150V,D2 test Vbus 100V ，power off current is more than 1mA. Root Cause: MT6375 damaged （replace a new MT6375 ,power off current go to 0.4mA ，ok） Exp 1: change OVP point from 18V to 14V ,Result:Failed. Exp2:change surge TVS D501 to a better part ,Result: DVT1 Verify. Exp3:change R2701 to 33R from 0R ( R on PD_Vbus of MT6375) .Result:DVT1 Verify. Exp4：add one more TVS near MT6375 .Result:DVT1 Verify. Solution: Proposal 2 :change surge TVS D501 to a better part. Proposal 3: change R2701 to 33R from 0R ( R on PD_Vbus of MT6375) Proposal4 :add one more TVS near MT6375 retest :DVT 1 with proposal 1+2+3+4 pass 2/25 . rework with Proposal 1+2+3 result ，pass 3/1 WH149393 Fix solution ：change surge TVS D501 to a better part ESD56161D24 +change R2701 to 33R from 0R +change OVP point from 18V to 14V . Import in DVT1 already | link | 文亭 |  |  | 1.SCH | FA
2022-01-14 | 4.EVT | 9.Memory | 4.Build | S3 | Closed | [s3]Issue:EVT Units auto boot up after power down on workaround version. Clue:1.No this issue with older sw . Clue:2.Not affect current usage. Closed. Root Cause:1.4 Power for DDR keep alive after power down which lead to reset and auto power on. Solution:1.NA |  | 院长 |  |  | 6.No Change
2022-01-08 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S3] Issue：EVT unit Can't Download on First Board Validation. Root Cause: 1.DDR5 Power Supply VDD2H not enable duo to MT6368 boot config to LP4. 2.Audio I2s Circuit Optimization which lead to affecting the config duo to Shared GPIO Usage，this change Point confirmed with MTK. Solution:1.Enable VDD2H in Downloading Agency Phase, Validated Pass. 2.Recover LPDDR5 HW Config in EVT V03 Version. | link | 林峰 | 文亭 |  | 1.SCH
2021-12-17 | 3.PEL | 6.Display/Touch | 4.Build | S3 | Closed | [S3]VMC_PMU ，power for 16MHz clk can not config to 1.8V yet (default 3V) SW bringup ok |  | 芳梅 | 文亭
2021-12-13 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Risk: Deadbattery wireless charge with QC charger can not work Root Cause:1. QC charger will output 12V，and wireless charge output 10V ，which trig BQ25960 OVP 6.5V Solution:1. FW change ，WCHG_MODE_SEL pull down will output 5V。 FW 1.7 ，import from EVT 2. WCHG_MODE_SEL pull down R 2834 change to mount from EVT . SCH done. 12/13 | link |  |  | change link | 1.SCH
2021-09-23 | 3.PEL | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3]Risk:Battery Connector/GSM PA/Spearker Placement of Dual Speaker Feature can't meet TDD Noise Design Rule. Root Cause:1.Speaker Interferrenced by magnetic field of Ground Current Flow in Receiver Mode. Solution:1.Move Battery Connector to the edge and 90 rotated. Xianjun Feedback that FPC too short to be achieved. 2.Proposal:Adding High Voltage Analog Switch YHM1106(2022/1 MP) ,Cost up 0.15$ EVT TDD test pass | Link | 院长 | 邦邦
2021-09-23 | 3.PEL | 7.Sensor | 1.4 Solution | NA | Closed | [NA] requirement: 气压计 sensor， tdk的20100，目前反馈是spi 可以解掉OTP的问题，希望能把气压计挂到SPI上 ，系统资源是否可以？ Solution:1. 厂家无SPI驱动，不往这个方向评估，close |  | 文亭 | 小熊 |  | 6.No Change

## Milan 5G (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2022-07-14 | D.SHIP | 1.Platform | 6.Issue | NA | Closed | 2 in 23 pcs CPU damaged. 178512 ：Charging too slow。 CPU USB_HS_DM impedance abnomal.CPU damaged by ESD/EOS. 178318：No Turn On. QC analysis result CPU damaged，suspect is EOS/ESD from USB_HS_DM/DP cause it. USB_HS_DM&DP TVS are both short to GND too. |  | 文亭 |  | EWG sheet | 6.No Change
2022-04-06 | B.PVT | 2.Power | 5.5 Certification | NA | Closed | [s3] Issue 1: TMO test ，discharge capacity is too small . 2465mAh . root cause 1 : The discharge capacity test have problem . discharge test form 71% but not 100% ，Log data in : old-power_supply_info（Total capacity is just 71%*5000mAh=3550mAh）,log link root cause 2: external R that caused by the test is too high . 262mΩ(from the test log file by TMO with rework parts log link)-106mΩ(From internal test log file with close phone)=152mΩ （ this cause power off at SOC 16% too earlier than normal one . When it power off, battery OCV is about 3.7V . Which is the real battery voltage . ） | link | 李果
2022-03-09 | 7.DVT2 | 4.Audio | 5.6 User Feedback | S3 | Closed | [s3]Voice Echo found in DF with Car kit audio. Root Cause:1.Audio Car Kit input resistance below 5KΩ，which lead to apply earphone mode echo surpression. Solution:1.Shift Input Resistance Judge Point to 2KΩ ，Validated Pass. 2.Carkit Audio mode params optimized. Validated Pass |  | 院长
2021-12-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Issue:ESD 3/8 units 8KV/15KV auto power off on Second Vendor FPS. Recover after boot up. Root Cause:1.Clk of FPS affected by ESD. Exp:1.add TVS on FPS_Clk , Result:No Issue on 1 units. Exp2.Repeat Exp1 on more units. on-Going Solution:Proposal:1.Add TVS on FPS_CLK. |  | 韩凯 | 小熊
2021-12-10 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue:FVCV29 capsensor ESD ，15KV air，100 times/zone1：Ch1 no function,unable to recovered 15KV zone1:D2 Clue :1 . CAP C502 shorted to the GND Root Cause: electricity discharge through the signal between camera deco and the inlay fleeing into the antenna and damaging the capacitor, causing the capacitive sensor to function Solution: 1、Proposal: ME add black film to cut the discharge path ，12/15 2、ANT 5 and ANT 10 add DNS TVS |  | 韩凯 | 小熊
2021-12-20 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue:MILAN5G USB can not connect sometimes IKSWS-25957 , Get 1 unit N5MV120284 that can reproduce. Clue: 0. NEW cable can not reproduce . some old cable easy to reproduce. 1. when it reproduce ，move Type-C at phone side , it turn ok 2. when it reproduce ，replug cable at PC side ，it still NG 3. when it reproduce ，Power cycle Phone ，it still NG 4. when it reproduce ，replug Battery connector and Cable At PC side ，it still NG 5. swap TMO Main PCBA ，old cable can reproduce，NG 6. swap a NEW sub PCBA ,old cable can not reproduce, ok. 7. Type-C Connector Vendor of this unit is Lecton Root Cause: Type-C connect issue Solution: KP do the further analysis -xiongxiong | IKSWS-25957 | 李果 | 文亭
2021-12-17 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue:MILAN5G 2nd source Ti BQ25890H OTG easily to triged when connect some hub ，report by SW test team Clue: 1.change Boost limit from 1.2A to 2.4A ,it is better (some hub can work ) 2.SGM41542 is ok with 1.2A boost limit . 3.test the current waveform ,SGN41542 is same to BQ25890H 4.there are to many Current burst when a hub is working . 5.different hub have different current burst 6.TI reply they can not change OCP deglitch time (250uS）.it is BQ25890H HW limitation . And OCP setting is = boost I limit. Root Cause: there are big Current burst when a hub is working , and some hub have more big current hurst that trig BQ25890H OCP . Solution: change Boost limit(OCP) to max and add Ibat monitor to make sure Ibat will not Over the battery SPEC 3.5A (monitor Ibat ,if Ibat is bigger than 3.5A ,disable OTG . Import form 20211217 . It can cover more hub . | link | 文亭
2021-12-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue:FVCV19 capsensor ESD ，15KV air，100 times/zone1：Cap sensor no function,unable to recovered 15KV zone1:D2(40),D3(20),D4(70) Clue :1 . CAP C502 shorted to the GND Root Cause: electricity discharge through the signal between camera deco and the inlay fleeing into the antenna and damaging the capacitor, causing the capacitive sensor to function Solution: 1、Proposal: ME add black film to cut the discharge path ，12/15 2、ANT 5 and ANT 10 add DNS TVS |  | 韩凯 | 小熊
2021-12-06 | 5.DVT1 | 2.Power | 5.3 EE DVT | S3 | Closed | [s3] Issue::DVT1 2nd WH145578 fail (unable to power on：D1/N5MT1C0102(after desence)） Clue : Root Cause:1 .L7A short to GND which lead to power on failed. 2.The short-circuit area was found inside the PCB Exp:L7A is still short-circuited after removal IC 3.Why pcb short ? Exp:send to Tripod for analysis,Result:L7 A Short to GND Via on one Point. Solution: 1.Expand Via distance on this point. and DRC the whole PCB to find if other risk exit. | Link | 敏敏 | 李果
2021-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue::DVT1 edu03 WH145517 fail (Unexpected auto power off:C1(8kv air,Zone6),C2(15KV air,Zone6） Clue :1 .Unexpected auto power off:C1(8kv air,Zone6),C2(15KV air,Zone6 Root Cause:FPS signal interference leads to system shutdown Solution: 1.FPS SPI MISO/MOSI resistance from 100R change to 470R 2.FPS CS/RST/INT resistance from 100R change to 1K Test Verification PASS | link | 韩凯 | 小熊
2021-11-04 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3] Issue:DVT1 ATT Drop(WH145506) Cap-sensor CH2 no function Root Cause:1. Solution: 1.ME will change screw holes to optimize structural stress 2.Optimize cap sensor signal line width(0.05->0.2) | LINK | 小熊 | 李果
2021-11-04 | 5.DVT1 | 9.Memory | 6.Issue | S2 | Closed | [s2] Issue:DVT1 ATT Drop(WH145506) Unable to enter system:D6(1m,top),D11(1.25m,right)/Unable to power on:D10(1.25m,back) Clue: 1.The units enters the 9008 mode 2.If memory pressed by external force, it can be turned on. 3.one unit Press Memory Display error and system hanging with blank display. 4.One unit sometime can't boot up ,no uart log,Qdutt sometime abnormal connection. Root Cause:1.Memory signal path broken Exp: Memory Solder Crack from red dye test and cross section Result: PCB inner Via Crack and Solder Crack Observed. 11/10 Solution:1.ME Optimize Strain Design 2.Reserve Memory Underfill Capability on Shielding Case. | Link | 嘉琨 | 李果
2021-10-14 | 4.EVT | 2.Power | 6.Issue | S3 | Closed | [s3]Issue:Unable to power on after Pulse Transient Surge Test on 150V. （1）WH144512 DVT EDu14 - Pulse Transient Surge Test fail 2.After 150V surge test, unable to power on,D3(486uA)D4(14.58mA)(Vbat） 3.Initial Leakage Current:D1(240uA)D2(225uA)D3(220uA)D4(227uA) （2）WH144526 DVT EDu14 - Pulse Transient Surge Test fail 1:Initial leakage current out off spec:D1(230uA).D2(229uA) 2:unable to power on:D1(250V,12.7mA)D2(150V,115mA) Vbat Clue: Monitor DVT build if any failure rate. Result: DVT build Root cause: 1.Surge cause damage of Charger IC and Fuel Gauge which connect to Vbat 2.Charger IC and Fuel gauge have lower anti Surge Capability(6V) then QC PMIC. Exp1. Change a better surge protector(10.5V->8V Clamping Voltage) and layout improved for fuel gauge , Result:10/26-- two machines pass EDU14 test Solution:1.Change a lower Zenar Diode. 10.5V->8V 2.layout improvement for fuel gauge with Solution 1&2,DVT1 (1st RT/FG+1st SGM/Charger) Vbat EDu14 test pass | Link | 敏敏 | 李果
2021-11-16 | 5.DVT1 | 3.Charging | 5.3 EE DVT | S3 | Closed | [s3] Issue:DVT1 EDU14 Second Vendor Verification Unit Vbus 1 unit 190V <200V failed Clue :1 .EVT 2unit ，DVT1 2unit pass 500V 2. The Variant is OVP Second Vendor Root Cause:1.OVP IC damaged Solution:remove SGM Second Vendor OVP from Milan 5G . Done from DVT2 BOM further study for incoming project： add a 22pf cap on OVP voltage feedback pin Verified pass 2 units .but no place to add the cap in Milan 5G. | link | 文亭
2021-11-15 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | [s3] Issue:DVT1 2nd charging IC Ti BQ25890H , input current can not reach 3A. （setting to 3A，test result is about 2.7A ） Clue :1 .Log check :IINDPM occurred . (suspect some Ilimit occurred . but why it occurred ?) 2.setting to 3.25A（MAX setting） , test result =2.8A . setting to 2A， test result =2.2A 3.setting higher Vbus ,Ibus no change . 4.setting higher Ibat MAX to 4A from 3A , Ibus no change 5. Ti reply it is average current limit . Root Cause:1.Proposal:Ibus limit accuracy problem Solution: Keep current setting ，and use higher Voltage for enough input power | link | 文亭
2021-11-09 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3] Issue:DVT1 2nd barometer TDK 20100 pressure deviates from 10K Pa relative to 1st BMP580/Bosch Root Cause:1.Configuration Issue Exp:1.mode config check. Result:Issue Solved. Solution:1.SW bug fix |  | 小熊 | 李果
2021-11-09 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3] Issue:DVT1 2nd charging IC Ti BQ25890H , QC 3 can not work sometimes Clue :1 .D+&D- can not out put 3.3V (similar to the EVT phone that without Dsel 47nf cap) 2. Ic charging type detection it too slow. (similar to the EVT phone that without Dsel 47nf cap) 3. V D+& D- At Charger IC is 3.3V . and 0.983V at USB connect side. --suspect CPU pull down the USB BUS Root Cause:1.Proposal: Dsel Cap is too faraway from pin and wire width is only 0.05mm. Exp1: EVT1 phone rework 1 unit 47nf cap and clue1 &2,result is ok exp2:DVT1 phone ,reowork 1 more wire from 47nf cap and pin. result :ｆａｉｌ exp3 : DVT1 phone , rework 47nf cap closer to pin . result :ｆａｉｌ 2.SW logic control for CPU High Z have some bug（BC1.2 interrupt do not set CPU High Z） Solution: 1. BC1.2 interrupt change to set CPU High Z ---SW change import from 11/12 .temp sw test ok 2.change Dsel 47nf cap closer to IC pin and add wire width in DVT2 for better cap performance. done---wenting | link | 文亭
2021-10-22 | 4.EVT | 3.Charging | 6.Issue | S3 | Closed | [s3] Issue:Charging I2C bus error sometimes(Feature firstly ready on 10/22) Clue: 1.Reproduce 1 time when use 2A OTG , recovered after power cycle （press powerkey for 10S）。When Issue happen no charging status change can happen again：such as USB cannot work，charge Icon not change 2.There are some charger IC I2C reading error before I2C bus error in Log --suspect charger IC I2C reading have some problem. 3.this unit use SGM41542 charger IC. I2C error is I2C error -110 when I2C Bus can not work. 4.Rry to reproduce. Pressure Test. Result: 1 units reproduced. 5.There are some interference on I2C when OTG 2A working. 6.Not reproduced on formal Maximum Current Charging Scenario ,Test by BB and Test Team. Root Cause:Proposal: 1.SDA Signal of I2C interfered. Exp:Add 33pf on I2C SCL&SDA (close to AP) .result : 1 unit can not reproduce in OTG mode. (remove 33pf and it reproduce again ) 2.AGND and DGND not separated in Charge IC Design and Noise coupled to SDA. Solution: 1.Add 47pf +47R on SDA(Close to AP),reserved 47pf +47R on SCL(Close to AP) . reserverd 20R on BTST at charging IC . DVT2 Import. | link | 文亭
2021-09-23 | 4.EVT | 2.Power | 5.2 BB Test | NA | Closed | [NA] Risk： CC SGM7220 current leackage is about 70uA when phone power off . （found by ODM project） Root Cause: VDD is VPH_PWR ，and /EN design to GND . which means the SGM7220 is always on . solution : proposal 1:no change and accept 70uA current leackage proposal 2:change EN to a GPIO 58 (reserved Pull down 0R ) ，from EVT2 EVT V04机器低电流是194mA，比V03降低42mA 。 close |  | 敏敏 | 文亭
2021-10-22 | 4.EVT | 3.Charging | 6.Issue | NA | Closed | [s3] RISK:Charging IC EN GPIO control ，can it work when Battery is very low (System not turn on) Solution:test and check can charge dead battery . so no risk |  | 文亭 |  |  | 6.No Change
2021-10-09 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [s3]EVT Handset TDD -60dB clue: Block the MIC hole，noise disappear Rootcause: 1.Spring on Sub board ? Exp:Check Spring. 2.other noise auido come into mic. EXT: Remover C304,improve to -80dB Rootcause:The 100pf CAP vibrate on GSM max power , the special position Intensifying problem. | link | 院长 |  |  | 3.BOM
2021-10-09 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [s3]Issue:WH144494 Rear flash light lens fusion:A1~A6,B1~B6(2)-TH/TC Root Cause:1.Flash on time set to S level,too long. Exp:1.Re-Config to the right parameter. Result: Solution：1.Fix config bug. |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-10-14 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA] Risk： USB disconnect in GSM900 MAX power with long USB cable for Audio tuniing ，report by Xiaozh1 Root Cause: long USB cable easier to be coupled by RF energy. solution : monitor ,EVT build no issue found . and this is not a user case |  | 文亭 |  |  | 6.No Change
2021-10-09 | 4.EVT | 3.Charging | 3.Review/Simulation | NA | Closed | [NA] Risk：Charging IC NTC design risk ，Vendor review Root Cause: Need to check with Vendor again and get a design for DVT1 build (pull up and pull down R ,and NTC selection ) solution : 1. Change to fix temp design for charging IC。 2. and SW config the thermal protection base on Fuelgauge NTC data |  | 文亭 |  |  | 1.SCH
2021-10-11 | 4.EVT | 1.Platform | 4.Build | S3 | Closed | [S3] Issue ：SOL LED light guide performance not good Root Cause: need to check the phone with ME solution : ME own |  | 文亭
2021-09-14 | 3.PEL | 2.Power | 5.1 Bring up | NA | Closed | [NA] Issue: 1 EVB2 board RT9246 fuelgauge Device ID read error |  | 李果
2021-09-14 | 3.PEL | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3] Issue: RT1715 PD fail sometimes . found by SW Chailu Clue1: 1.I2C go keep low most of the time . 2. power on with charge plug in and it can work 3.Resester reseted found by vendor. Root Cause: I2C SCL keep low cause RT1715 reset . (reset function is open with vendor SW code ）. SW find the rootcause and solve the issue Solution: Proposal 1. disable RT1715 reset buy I2C timeout function . （temp SW checked ok with 2pcs PCBA） Solution2. make I2C keep high when no I2C communication . change import | link | 韩凯 | 文亭
2021-09-13 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [S3] Issue: 2nd charging IC RT9467 bringup found ,the phone power up when no USB plug in sometimes . Clue1: 1.log show power on reason is charger power on 2. RT9467 REGN = Vbat some time (without USB plug in) 3.checked ，REGN will on 500mS when plug in Battery or each I2C reading. Root Cause:1 REGN = Vbat some time (without USB plug in) ，which will cause main PMIC power on then cause phone on Solution: Proposal 1. For EVT temp solution ，Delay 550mS before kernel shutdown ？----SW：Weiwei，huosheng Proposal 2. For DVT1 ，change to Vbus for the mos control ？---BB：Xuemin Exp2： use VBUS replace REGN to pull down CBL_PWR_N,VGS=1.5V can drive the MOS to pull low CBL_PWR,R1:R2=7:3 ，When VBUS=13.2V,VGS=3.96V;when VBUS=5V,VGS=1.5V Close: remove Rt9467 From Milan 5G base on GCM feedback (replace it with BQ25890H from EVT) | link | 敏敏 | 文亭 |  | 3.BOM
2021-09-03 | 3.PEL | 1.Platform | 5.2 BB Test | S3 | Closed | [S3] Issue: Keys can not work in Fastboot mode Clue1: 1.it is ok in normal mode. 2. it is first time connect V+ to PMR735A . 3. Corfu 5G DVT1 meet same issue Root Cause:1. suspect pull 1K to 1.8v for PMR735A GPIO is too large . Exp1. change pull up R form 1K to 10K and it works . (only SM4350 use 1K pull up ,other projects use 10K ) Solution:1. change pull up R form 1K to 10K（R1018） ，done from EVT |  | 文亭 |  |  | 3.BOM

## Yukon (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2021-10-12 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | IKSWR-143124 SM8350// Yukon // R //Phone is OFF. Connect the usb cable, the phone keeps turning off 关机界面的瞬间，插入USB，关机后不会自动进入关机充电界面 1.not a real issue |  | 文亭 |  |  | 6.No Change
2021-09-29 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | [NA] Yukon DF DP issue IKSWR-137479 cable issue change a cable and ok | LINK | 芳梅 |  |  | 6.No Change
2021-10-09 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | 电量计：充电到68% ，关机后，一段时间开机变成56%. IKSWR-139932 高通 case：Case Number 05446277 [View Hierarchy] Action：外加检测电阻用电源侦测一下，看实际电量和UI 偏差到底多少。 10/13 前 Root cause：SW config issue。 Solution： change SW |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-09-24 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH144198 D3 ESD capsensor ，After -8kv air discharge,capsensor ch4 no function and recovered after reboot, 15kV ok. Root Cause:1. monitor Solution: Pilot ok |  |  |  |  | 6.No Change
2021-10-09 | B.PVT | 5.Camera | 5.4 ALT | S3 | Closed | 【故障来源】PVT MXc03跌落试验。 【复现现象】敲击主板的时候图像卡住，重开相机可恢复。测量连接器各个引脚阻抗、连接正常。 【历史线索】产线也有发现几台主摄异常，有发现U1000 和J3150-15印刷少锡。 【推测原因】U1000 MIPI引脚缺锡断裂，震动时断路，MIPI信号终止，CQA图像卡住。 【Next Plan】 1. X-ray查看锡量。=====> 无异常 2. 安排切片查看U1000和J3150引脚是否锡球断裂。===> 发现J3150连接器底部出现开路情况（报告待更新） | Link | 邦邦 | 范南 |  | 6.No Change
2021-10-09 | B.PVT | 1.Platform | 4.Build | S3 | Closed | Issue Description: PVT ROW 8+256 bom wrong Root Cause analysis: PCM CR @ DVT2 after DVT2 BOM released,Manual Changed variant BOM at DVT2，but Lost update ROW 8+256 BOM when PVT BOM released. Solution: Add 8+256 memory configuration variant to schematic files Update the BOM Corrective / Preventive Actions Check released BOM list base on SKU information table （including Memory config ，HWID config ，SKU config） | link | 韩凯 | 文亭 |  | 3.BOM
2021-09-06 | 7.DVT2 | 4.Audio | 5.3 EE DVT | NA | Closed | [S2] uplink has noise when handset calling clue: 1. When charging ,noise dispappear 2. When close calling arithmetic, noise disappear 3. On idle calling mode,no noise 4. On record mode,no noise 5. Volte MODE no noise 6. GSM mode (low power transmit) has noise 7. No noise on handfree mode and no noise when change mic1 to handfree mode 8. No noise before moden node. Next step: 1..Ask qualcomm for help 2.Moden team analyze | LINK | 院长 |  |  | 6.No Change
2021-09-29 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | [NA] Yukon DF Device Rebooted - Stuck in Boot Screen IKSWR-139460 Clue ：1.L5E LDO error in Ramdump log. QC CR：https://qualcomm-cdmatech-support.my.salesforce.com/5004V0000181Vef 2. L5E is RF Power for SDR RF Tracking this case |  | 敏敏 |  |  | 6.No Change
2021-08-27 | 7.DVT2 | 12.EMC | 5.3 EE DVT | NA | Closed | [NA] found 1 WH143148 D1（NYKR270825） After-8KV air discharge at zone3,Display Flickering and Display color change ,30 minute recovery.(11:06 2021/8/26) clue: 1. Root Cause:1. suspect display module damage Solution:1.PVT ok |  | 韩凯 | 芳梅 |  | 6.No Change
2021-09-26 | B.PVT | 3.Charging | 5.5 Certification | S3 | Closed | [S3] TUV certification ：battery output current =5.8A >4.85A of CB in battery spec. testmode : pull current from type-C Root Cause:1. PM8350BH OTG dont have OCP . Solution: add a detection on Ibat to monitor Battery current . when it output >4.85A ,disable OTG . temp SW test ok by BB . TUV retest 4.69A ,<4.85A pass |  | 文亭 |  |  | 6.No Change
2021-08-26 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]Yukon intermittently notice Pluging/out after charger connected. Root Cause: 1.Charger Reset Frequently 2.CC GND Voltage >0.43V 3.Cable GND Mesh Broken ,165mΩ(Spec 83mΩ） 4.2018 Cable Solution:1.Cable Team Own |  | 文亭 |  |  | 6.No Change
2021-09-15 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | [S3] Issue: 2nd micron memory stress test ，3/20@55°C ， 7/20@-20°C auto power cycle. Reproducing:Retest No Issue@55°C， ，5/20@-20°C Clue1: 1.RPM_ERR and AOP Log show some LDOor SMPS fail.-Need RPM expert Double Check and confirm it. Root Cause:1.Memory Power Issue? Exp1.Monitor Memory Power @-20°C. Result:9/17 Exp2.Log Analysis. Result:SPMI Communication Time Out. Exp3.Enhence SPMI Driver Strength. Result: 9/17---with SW RRX31.Q3-50,memory stress test run 24hrs,no auto power cycle happen Solution: 1. Enhence SPMI Driver Strength，Validated Pass，SW updated |  | 敏敏 | 嘉琨 |  | 6.No Change
2021-09-06 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH143213 C1 ESD capsensor ，After -15kv air discharge,capsensor ch2 no function without recovery. Root Cause:1. C204 on CH2 short to GND， change C204 CH2 recovery 2.found crack on C204 Solution: Factory check build process PVT No issue found in build and TCC test. | Analysis link | 韩凯 | 小熊 |  | 6.No Change
2021-09-06 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | Closed | [NA] EUT found 1 charger+cable cannot charge clue：1. it is 45W DVT1 charger sample + cable（without any mark on calbe） 2.swap EXP check :issue follow Cable 3. issue happen when Iubs >3A Rootcause：the cable R of GND is too high causing PD process abnormal(160mR VS 83mR MAX in SPEC ）. solution：No real issue | link | 文亭 | 韩凯 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-09-06 | 7.DVT2 | 2.Power | 5.6 User Feedback | NA | Closed | [NA] found 1 DVT2 unit go dead when sleep ， sometimes 1 day,Need press powerkey more than 10s to recovery. clue: 1. reflash some SW version but all reproduced . 2. 128GB Kioxia UFS exp：The fail is very similar to the Kioxia UFS issue . We update the SW to latest one RRX31.Q3-44 which checked solve the Kioxia UFS issue . monitor the result From 9/10 to 9/15 ，no reproduce Root Cause:1. memory ufs issue Solution:1. chenge SW | IKSWR-130146 | 敏敏 | 文亭 |  | 6.No Change
2021-09-06 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2] DVT2 WH143213 ALT A1这台有出现跌落后P/L sensor no function，重启后P-sensor 恢复，但是L-sensor问题还是存在，Loop5（NYKC2F0130） Clue：Issue：ALS can not go DARK status （maybe light leakage） Root Cause:1. CG tilted(CG翘起) increased ALS reading Solution:ME follow | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-08-20 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [S3] DVT1 Mdu30 Failed on Charging Scenario(7.1°C@back,4.0°C@Front). Root Cause:1.SW Bug and Thermal config fine tune. Solution:1.SW Bug Fix and import New Charging Thermal Config. RD Validated pass. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue: cap sensor can not work on CH0&CH4 after ESD ， recover after charger Plugin. Clue1: D1、D2、D4 failed without chargers，D3 pass with a charger Clue2：recover after charging Root Cause:1. CapSensor Affected by ESD Through ANT. Exp1. take another phone ，recover after quiting CQA texting Exp2. catch log after cap sensor ch0、ch4 no function Exp3:Confirm the detailed recover duration Solution:1. Accept |  | 韩凯 | 李果 |  | 6.No Change
2021-07-19 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3] Issue: DP Eye Diagram 4 lane fail on 8.1Gbps Clue1:Eye Height not enough Clue2:Layout Improved. Root Cause:1.Voltage level not enough or Pre-emphasis Exp1. Fine Tune voltage and Pre-Emphasis Parameter,Result: 8.1G mostly Pass while 1 lane failed a little. 2.Proposal:Parasitic capacitance effect Exp2.Optimized lane and Grounding separation . Result: DVT2 verify. Solution:1.Update Redriver Parameter. Validated Mostly pass 2.Optimize FPC and PCB layout . DVT2 import and verify. | LINK | 芳梅 |  |  | 2.PCB
2021-06-22 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [s3] Power off current =350uA Vs normal project 200-uA Clue:1 NFC boost is on when phone power off 2. Lenovo MP project DOOM =320uA ，Qualcomm phone QRD= 340uA Root cause: 1.NFC boost alwayse on . 59uA ,should be off when phone power off 2. SM8350 power off current is higher than other platform solution : 1.NFC boost EN change to pull down from EVT-B （V03） 2. Yukon Power off current target should be 300~350uA ，monitor in DVT1 factory BT test 3. Base on the DVT1 test data，output shipping keep time limit for Yukon project to PQM. DVT1 testdata：300~350 uA. sync result to PQM yet | Link | 敏敏 | 文亭 |  | 1.SCH
2021-06-28 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue:Camera Team feedback DVT1 unit, RC adjust Value Avg=13, Over Spec 10 . Issue Check: After Test with more Units , We found Yunkon has Same Performance with Sierra . Furtherly seek if any chance to improve R/C adjust performance. Root Cause: 1.Speculation: AVDD Ripple , Result: Not AVDD Ripple. Exp:AVDD Measurement . Result: <19mV ,Best Class. 2.Speculation:EMI ,Result:No effect Exp:Shielding Whole Camera with System Ground , Result:No effect. Exp:Dismantling PCBA and Change Cam Grounding , Result:Worse 6%. Exp:Replace 100pF Cap with 2.2UF after Dismantling. Result:Better but little optimized than Original. Exp:Supply Cam DVDD externally. Result: No effect. 3.Speculation:Camera Thermal Noise? Result:Suspend duo to no available exp. Exp:Cooling help to reduce background noise , and R/C increasing 4.Speculation:Camera Module? Exp4.1:Switch Camera.Result:Suspend duo to no available exp Exp4.2:Replacing AVDD&DVDD ,Result:No Effect. 5.Camera Sensor Exp:Exp4.2:Replacing AVDD&DVDD ,Result:No Effect. Exp:Optimize Sensor PSRR through Parameter Setting from samsung. Result:Better. Solution:1.Replace 100pF Cap with 2.2UF, DVT2 BOM import. 2.Optimize Sensor PSRR through Parameter Setting from samsung. | LINK | 邦邦 | 范南 |  | 3.BOM
2021-07-19 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3] Issue: camera LED torch brightness differ with EVT Root Cause:1. EVT pcb LED CH1 leakage to CH4, CH2 leakage to CH3 2.Async on Capture and light. Exp:1. camera tunning issue,Align Capture and light Timing and adjust light width, Result: 8/3 Solution: 1.SW update | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-08-02 | 5.DVT1 | 1.Platform | 5.5 Certification | NA | Closed | [NA] Issue: ADR test can not read IT3 SIM (一种模拟SIM卡for test ) Root Cause:1. Data line without pull up Solution: 1.ADDpull up 15K，retest pass . Import form DVT2 2. rework 2 more unit for ADR test |  | 李果 | 文亭 |  | 3.BOM
2021-07-13 | 4.EVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3] Issue: RS Pretestfail ，uplink Over 13DB clue1: test 4 headsets with same result Root Cause:1.Audio Switch Modulation Exp1.ADD 1nf cap on headset MIC channel ，after Audio switch （C1817 ） Result: 4dB improvement,Still failed 8dB Exp2: Modify Cap 2.2 nf ,Result: pass(over 15DB margin）on 1 unit Exp3: without Back Cover and Graphite Film ,Result: fail 5DB on 1 unit. Exp4: Modify Cap with bigger value and with Cover and Graphite Film,retest 2 units. Pass Solution: 1.Modify Capacitor Value on Aux Channel. Validated Pass. | LINK | 院长 | 李果 |  | 3.BOM
2021-06-28 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Closed | [S2] Issue:Obvious line noise on 108M image preview in darkness. Root Cause:1.AVDD power noise Solution: 1.Optimize AVDD Power feedback routing,DVT1 Improved 2.Optimize AVDD Grounding on DVT2 |  | 邦邦 | 范南 |  | 2.PCB
2021-06-28 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [s3]Issue:Flash Led can not work 4/300 in EVT. Root Cause:suspect LED CH 3 control impact LED CH 2 Exp: enable LED CH 2&3 at same time by adb command and it can work . Exp: SW version enable LED CH 2&3 both ,but fail . need more check Solution : 1.Change SCH&PCB to disconnect LED CH3&4 （LED driver 1CH can support 1.5A ,we just need 1A each CH ,it is enough .） monitor DVT1 DVT1 no issue so far | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-28 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [s3] Backlight not work sometimes , recover after power cycle .(found by Chenwt) Clue 1 .Log checked : Backlight Driver IC I2C read fail when initial . but Other ICs on the same Bus I2C reading are ok. Can not reproduce solution : close ，reopen it if it reproduce | link | 芳梅 |  |  | 6.No Change
2021-06-21 | 4.EVT | 5.Camera | 4.Build | NA | Closed | [s3] rear camera 2 test in CQA will cause rampdump sometimes Camera2 Kernel panic https://idart.mot.com/browse/IKSWR-100409 clue：can preview ，and video capture fail Root Cause：Speculation:SW issue Solution: temp SW continue build 107 checked ok . close issue . |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-28 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3] Obvious Audio noise in receiver when calling enable. Clue1:400hz and Harmonic, Not TDD. Clue2:No noise with Wechat and Earphone Root Cause:1. Wrong audio path config and noise import by sidetone Solution: Modify audio path config ,temp SW check ok. plan to merged form 7/2 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-22 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | [s3]Dark display 3 in 24 pcs in EVT build Clue: 1. display connector damaged . 2. Backlight IC burned . Root Cause: 1.Display Connector Damaged which lead to IC Burned. 2.Connector is not in the best place 3.ME need one time to adjustment the accurate position Solution: 1.Move connector upper 0.66mm, PCB modified in DVT1. Tracking in DVT1 ，reopen it if issue reproduce in DVT1 build |  | 芳梅 | 邦邦 |  | 2.PCB
2021-06-21 | 4.EVT | 4.Audio | 4.Build | S3 | Closed | [s3] SPK sound weak in EVT CQA test ，100% Root Cause: 1.Smart PA out N & sns N swap Solution: 1.Fix current 32+3 units through Change R4650，R4651 to 0201 0R, done. 2.Fix Smart PA Sch in DVT1 Version,Done Tracking in DVT1 ，reopen it if issue reproduce in DVT1 build | link | 院长 | 文亭 |  | 1.SCH
2021-06-21 | 4.EVT | 7.Sensor | 4.Build | S3 | Closed | [s2] Cap sensor CH3 no function in CQA test ，100% Rootcause： parameter not ready . Solution: change parameter,New parameter tested and CH3 can work. by 6/22 | link | 小熊 |  |  | 4.Parameter

## Sierra (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2021-10-09 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | [na]Issue:some user feedback power drop when Video when battery on 4%. Root Cause:1.Battery Voltage drop to 3.0V. Solution:Proposal:1.3.2V Shut down voltage ->3.4V , 50mA 1% power loss. |  | 李果 |  |  | 6.No Change
2021-07-15 | C.RAMP | 3.Charging | 4.Build | S3 | Closed | [s3]Issue: CQA-BATTERY- USB test result unknown,CR :IKSWR-110537 Clue1: log check 4, BATT_ID_2 = 239720 ， Unknown battery detected, unknown_battery_behavior: 1 Root Cause: 1.Batt_ID pull down R=243K +/- 1%， but reading 239.9K from SW log. SW check ： 240K ~450K .Can not cover this case Impact：phone can not charge and con not power on when Vbat is too low (lower than power on voltage limit) Solution: 1. SW Open limitation to 220K ~450K . Import from 7/19 in to mainline. change : https://gerrit.mot.com/#/c/2012268/ coming project : Yukon change Batt_ID to 100K which SW check is 15K ~137K . Milan5G use 100K too . notice Corfu 5G change to 100K too. |  | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-07-12 | B.PVT | 11.Thermal | 5.6 User Feedback | S3 | Closed | [s3]Issue: USB Connector Temperature Detection 125°C mistriggered found. Clue1:No abnormal signal on NTC found. Root Cause: 1.Speculation:ADC Not stable when sampling. Solution: 1.Notice triggered only after Sampling 3 times each second and all over 75°C. SW release new version and verify. on-going |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-11 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Closed | [na]Anti -water Icon showed when DP insertion in Factory ,recovered after unPlug for 1 Min，0.4% FR. Root Cause:1.LPD Mode Active when only one CC Ra attached in 200ms(Powered Cable without Sink attached). Solution: 1:SW Workaround to re-verify cc status before Show Anti-Water Icon.-SW ，Validated Pass. |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-07-12 | B.PVT | 10.USB-C | 5.3 EE DVT | S3 | Closed | [s3]Issue: DFer Feedback that LPD Triggered when Charged with 120W VIVO Charger. Clue:VIVO 120W has their own protocol and SBU used. Doc link:https://docs.google.com/presentation/d/1n0tqqY8eS7C6cWWbVOopxZkmtI4Qo3L22XRAebT7d2g/edit#slide=id.g4057557fca_0_46 Root Cause: 1.When Charging,CC Detection Triggered and SBU found 45K resistance,which match LPD condition and trigger Notice. Exp:Log analysis. Result:VBUS Shut Down and CC&SBU triggered. 2. SBU(45K resistance) used in VIVO 120W Charging Cable, When no VBUS input,LPD tirggered. Exp:Test Samsung S20 ,Same Issue happened. Solution: 1.Proposal:Accept it. since this issue also found in industry released products. 2.Proposal:Adding uncompatible attachment found in LPD notice context. |  | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-18 | 7.DVT2 | 10.USB-C | 5.6 User Feedback | S3 | Closed | [na]Screen Keep Turn on/off in about 10s when PD Charger Plugged(Display LG 2K Game TV) -Brazil DFer feedback . Clue1. Reproduced in third party Dongle. Clue2: No Issue without PD Charger Plugged. Clue3:No error found in log. Clue4:Verify about 20 different 4K Display/TV in china，Result:Can't Reproduced Root Cause:1.Using LG 2K Gaming Display low speed hdmi port. No Issue with high speed HDMI Port. Solution:1.need user to plug into right hdmi port |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-09 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3]Issue:DP not work when Plug Charger with a 9 in 1 hub. -Brazil DFer feedback . Clue1:No issue with inbox dongle. Clue2:Buy Same Dongle to reproduce. Result:Tahoe using Parade PS5169 Redriver also have issue.Onsemi No Issue. Root Cause: 1.PD Charger Insert and raised up to 9V,Hub Reset occured at 8.6V. 2.PS5169 Redriver shut down data Lane after hardware reset received which lead to DP re-training failed. 3.Speculation: If Plug in PD Charger Firstly and then plug sierra，Hub Keep Reseting duo to 9V3Amode comsume more current and more voltage drop on hub and triger the hub defects,this is reset on 8.6V. Solution: 1.Hub Issue,Accept it. 2.SW Pick newly PS5169 Fix from QC,Issue fixed in XiaMen Dongle when PD Charger Plug Later.But If Plug in PD Charger Firstly，Hub Keep Reseting,Issue Remained. 3.Proposal:SW Workaround - Keep PD Charger working in 5V/3A Mode after multiple Hardware reset received and DP on Position. -It Works but needs SW Evaluation. | Link | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-09 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [na]Issue:DP not work when Plug Charger with a 3 in 1 Dongle. -Brazil DFer feedback . Clue1:No issue with inbox Dongle. Clue2:Buy Same Dongle to reproduce. Clue3:No any error found in log Clue4:No Issue with 1080p Root Cause:1.Speculation-Issue in HDMI Part between 3 in 1 Dongle and Display in high speed. Solution: 1.Change Dongle. | Link | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | issue：display stuck after 15kV air/6kV contact discharge，recoverde by Slide screen clue1：remove deco board testing camera module，appear easily clue2：12kV air not appear when removing the copper foil on the back of the main camera Root Cause：camera mipi data of module shocked when ESD testing solution： |  | 韩凯 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-06-02 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue: QC3+ can not work with 33W Saierkang Charger ,but ok with 33W Kangsu Charger Clue 1. Different Charger Vendor . Root Cause:1. Saierkang charger can not output 6V when 2nd QC 3+ process . The time form 1st QC3 process to 2nd QC3+ process is about 845mS Solution:1. change SW，complete QC3+ process at first process，similar to Berlin. solution import from 6/4 | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-27 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3]Issue:Test Thermal @元神 keep 60FPS，46°C observed. info: Mdu30 Pass. Root Cause:1.High Performance Game Mode. Solution:1.Optimize Thermal Config to meet thermal target. on - going. |  | 林峰 |  |  | 4.Parameter
2021-06-06 | B.PVT | 3.Charging | 5.2 BB Test | NA | Closed | [s3]Issue: 30W charging PD charging current low at last stage Clue:1. Code change at sm8250 baseline: 296 /* This is for burton ONLY – specific to the battery configuration / 297 / Enable float voltage compensation (0x1071) and set resistance to 30 ohms (0x118B) */ 298 err_flag ¦= pm_comm_write_byte(0x2, 0x1071, 0x60); 299 err_flag ¦= pm_comm_write_byte(0x2, 0x118B, 0x0F); Root Cause: AFVC cause this case Solution:1.SW Config, RD Validated Pass. | https://idart.mot.com/browse/IKSWR-101718 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-18 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | [s3]Issue: 30W charging UI100% point test result is 2A VS 0.82A in SW setting. CR：IKSWR-94815 Clue:1. USB charing result 100% in UI VS 90% in Coulomb Counting . 2. charging current jump up for a few minutes when BQ 30W charging switch to PMIC charging Root Cause: 1. SW Not Config Correctly Solution:1.SW Config, RD Validated Pass. | link | 李果 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-28 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [na]Risk:33W Charging full power rate Verification Exp:SW build a Open limitation of 33W and verify. Result: 6/2 BB test done. No issue related power found. | Test summary link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-24 | 4.EVT | 10.USB-C | 5.3 EE DVT | NA | Closed | [s3]Issue:DVT2 Mxc04 ,Can't Charging and Can't Recognize PC. Clue:Tester Enable USB Function though USB Port Damaged Informed. Root Cause:1.Observed ForeignMatter over most of USB Socket Pin Pad.- ME Analysis Solution:1. |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-20 | 4.EVT | 10.USB-C | 5.3 EE DVT | S2 | Closed | [s2]Issue:Mxc04 USB Corrosion 1/4 in EVT. Root Cause:Salt Water in USB Port and VBUS/CC/D+/D- Active in Plugin which lead to Electrolysis effect Solution:1.Import Salt Water ingression detection ,DVT import and Validated 12 units Pass. 2.Proposal:Refer Samsung S20/S21 's mechanism,Enable 2 Level LPD Notice:Vibrating and notice on charger plugin when in LPD Mode. |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-05-12 | 5.DVT1 | 10.USB-C | 5.2 BB Test | S3 | Closed | [s3]Issue: Sierra Current abnormal （+100mA）when plugin A to C cable without PC or charger connected Clue1： There is 56K Pull up Resistor from CC to VBUS in A to C Cable Clue2： No issue with C-C cable which used as standard configuration in 30W PD Charger. Root Cause: 1.constant typec-or-rid-detect-change interrupt lead to extra current drain. Exp1:Log observation ,result:too many typec-or-rid-detect-change interrupt cause current abnormal 2.1 speculation:cc pin pull 56k to ground lead to interrupt ? ，Conclusion:Not Relative Exp2:pull 56k down to gnd, result:reproduce interrupt 2.2 speculation:Added Audio Analog Switch trigger? ,Conclusion:No Relative. Exp:Connect CC Pin to Vbus with 56K in mainboard and remove sub board(Include Analog Switch with CC1 parallel). Result:typec-or-rid-detect-change keep triggered ,Issue Reproduced. 2.3 CC Pin interrupt lead to extra current drain Exp:CC Trigger Source Validation. Result:Pull down resistor below 444K will trigger. Info:125K Resistor 3. water ingression detection lead to CC Pin abnormal Interrupt Exp1:water ingression detection keep triggered when insert A-C Cable but failed to confirm water ingression. Exp2:Flash EVT SW, Result:No Issue(No Water Ingression Detection in EVT) Solution:Proposal:1.Disable Temporarily to help Auto Current Test. 5/18 （Kiev project have same problem ，and Disable LPD with adb command before Auto Current Test ） 2.set long time for recheck to lower down current. (2 mins pers detect and avarage current up 1mA VS 100mA in issue）. | Link | 文亭 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-25 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3] Issue:WH137571, unit A1 Cap sensor no function after loop 5 Clue:1. CH1 no function Root Cause:1. M101 Spring collapse Solution:1.ME Improve | Link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-25 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | [S3] Issue:WH137608,unit B2(1) cannot enter front camera mode and unable to read SIM Card Clue:1. issue happened before loop1 drop test. Root Cause: 1.SIM Card connector PIN cold solder joint 2.camera BTB connector damaged by assembly Solution:1.Factory Improve Process. | Link | 李果 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-23 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | Issue:WH137571, DVT1 ALT loop4 one unit auto power off after drop test Clue:1. drop test in 4 areas（bottom,left,right,bottom right corner）,unit was blank screen,can power on normally without ramdump Root Cause: 1.Battery connector assembly issue.Retest pass after fit connector again. Solution: Assembly improve-owner:ME | Link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-14 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:DVT1A Instant 60mA Current Found. Clue:1.EVT found abnormal current in sleep mode, solved through QCN update. 2 units verified. Root Cause: 1.L5A@S6A used for PCIE/UFS/USB/SDC PHY Consume 200mA Current which lead to extra 60mA@3.8V 2.SPU Consume additional 200mA@0.85V 3. L5A affected by magnetic interference of S7A when CPU Big Core and PCIE works in the same time Solution:Optimize L5A Layout,using Star type Routing for VDD_SP_Sensor. RD Validated 3 pcs ,Pass.Import in DVT2B | Link |  |  |  | 2.PCB
2021-04-11 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue: RS pretest fail. noise value over 15DB Root Cause:New .Analog Switch FSA4480UCX need new parameter Solution:1. SUB1,SUB2 add 100PF /REF,R,L change to 0R / REF,AUDIO_GND add 1NF, Validated Pass. DVT2 Import. | Link | 院长 |  |  | 3.BOM
2021-04-11 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue: -90dB Noise found when in talking/recording mode on Earphone when display off. Root Cause:1.Analog Switch FSA4480UCX 's Power supply Vbob lower down frequency from 40Kto 2K in PFM mode when display off which lead to noise in earphone. Solution:1.Add RC filter(10K+1uF) in Vbob,Noise downgrade to -110dB.RD Validated.DVT2 Import. | Link | 院长 |  |  | 1.SCH
2021-04-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue:charging curve not correct ,need check why it jump to 500+mA from 1.8A . Analysis: Log share to SW , SW analysis ongoing Root cause:SW related . Need solve the bug | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue:When charging ，Battery NTC data is higher than Battery ，Over 46 degree ，impact charging performance Clue：2-3°C Gap. (Ref RIO-H 30W Charging Design) Root Cause:wired NTC additionally heated by Battery Protection Board and Mainboard Solution：Action ：1 checking the battery test data with full speed charging rate.(including Voltage,current,capacity, NTC reading and surface thermal data .) 2.checking if we can have better thermal solution for battery? Not block PCB gerber out. |  | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-04-12 | 5.DVT1 | 3.Charging | 1.4 Solution | S3 | Closed | Issue:SM8250 can not support QC3+（33W charger running change）with 3rd part chaging IC Root Cause:1.Qualcomm announced no support plan on SM8250 duo to software development complexity and high couple with SMB. Solution: 1.SW Develop 33W QC3+ | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-03-20 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:Blank Display when ESD strike on Display,1 of 6,Recovered after power cycle. clue:can't reproduce on failed one. Root Cause:1.Display Issue,Inform risk to Display Team. |  | 韩凯 |  |  | 6.No Change
2021-02-04 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | CR： SIM 2 can not work Rootcause：connector design issue : UIM2 power and GND not connect solution：1. rework UIM2 power and check SIM2 function ok 2.change EVT Main board and main FPC |  | 李果 | 文亭 |  | 1.SCH
2021-01-25 | 3.PEL | 7.Sensor | 5.1 Bring up | S3 | Closed | CR： VIB，SPK，DP，Capsensor...can not work ， Clue：1. share 1 I2C 2.remove Capsensor and ok Rootcause： Cap sensor not power on before I2C Bus work may cause I2C issue. solution：1. change cap sensor power L8C to always on ，need to check SW ok or not 1/27 shengnan 2. EVT change to Singal I2C for capsensor for better |  | 小熊 | 文亭 |  | 1.SCH
2021-01-25 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | CR： Camera No power Rootcause：I2C error (SDA &SCL swap) solution：1. rework LDOs IC I2C -Done 2.change EVT PCB --SCH -Done |  | 邦邦 |  |  | 1.SCH
2021-01-25 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | CR： USB can not work Clue：Main board ok，sub board issue。 Rootcause：OVP GND not connect solution：1. rework the Vbus（short output and input of OVP） 2.change EVT PCB --SCH change done |  | 文亭 | 韩凯 |  | 1.SCH

## Denver (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2021-04-06 | B.PVT | 4.Audio | 6.Issue | S3 | Closed | [na]Issue:Audio Aux Detection Issue Root Cause: When insert the AUX cable, trigger PHP surge protect, and the PHP Impedance test error. The AUX is dectcted as headset. Solution: workaround :When the impedance is dected as 0 ,Change the headset mode to AUX mode. | LINK | 院长 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-03-14 | B.PVT | 7.Sensor | 5.5 Certification | S2 | Closed | [na]Issue:DVT2 units Barometer Test Failed in TMO,Avg Data@4 Group @24units Exceed +/-36Pa. Root Cause: 1.Precision of Reference Calibrator BMP388(calibrated by Drunk8100) over Spec. 2.SMT Thermal Strain Not Released when Calibrated which lead to over calibration.TDK 2.6Pa/Day.ST Pass@5D Standing after SMT Solution: 1.Recalibrate PVT Units for TMO in Chicago Mart. 2.Recalibrate BMP388 with Drunk1000 that calibrated with Pace5000.Done. 3.Sending long Standing Time units,re-calibrate for LE. 4.Hold Standing Time for at least 5 Days from SMT to Calibration for TDK and ST. Go OK2Pilot. 5.Proposal:Furtherly low down Standing Time Solution from Vendor. 5D OK ,Try 3D . 6.Proposal:Import dynamic calibration for barometer.TMO Agree Using Google | LINK | 小熊 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-01-26 | 7.DVT2 | 5.Camera | 5.3 ME DVT | S3 | Closed | [S3]DVT2 2nd source ATT drop, TP no function/cannot enter camera(FR 2/15) Root Cause: 1.TP Signal and SAR_Int Signal Open near Screw post and and under shielding case corner duo to High PCB Strain Exp:1.1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify Exp:1.2. Add More Foam on Shielding Case to reduce PCB Strain. PVT Verify Solution:1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify | link | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-01-26 | 7.DVT2 | 5.Camera | 5.3 ME DVT | S3 | Closed | [S3]Issue1:DVT2 ATT 12 RASS-Tumble WH135516 48M failed (FR 1/15). DVT2 2nd source TMO drop, cannot enter camera(FR7/10) Root Cause: 1.Camera RST Open under Shielding case corner duo to High PCB Strain. Exp:1.1.Reduce SolderPaste on Corner of Shielding Case Solution:1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify | link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-01-21 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue1: Denver DVT1B WH135380 ALT ,P/L sensor no function：B5(4) 1 of 11. Clue:reworked units 6pcs 2nd display+5pcs 1st display Clue2:Can not reproduce Root-Cause:Monitor | Link | 小熊 |  |  | 4.Parameter
2020-12-10 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S2]Issue1: DVT1 ALT ESD ，C2 After +15kv air discharge at zone 9(aging 10), headset MIC no function without recovery.(12/23/2020 18:30) Clue：1.EDU03 6units pass 2. have add TVS and layout is ok. Root Cause: wating for the unit back to XM for analysis，maybe ETA XM by 12/30 Solution:1.No reproduce when get the fail unit。 keep monitor |  | 韩凯 |  |  | 6.No Change
2020-12-10 | 4.EVT | 8.PCB | 5.4 ALT | S3 | Closed | [s3]Issue: 1.Mic2 Drop during TMO&ATT ,⅕ Loop2 ; ⅕ Loop3 2Mic1 Drop During ALT ,1/12,Loop5 Root Cause: 1.unti-pcb strain lower than pcb strain Exp:increasing space between Mic2 and PCB by more solder Paste workable? 2.lower down pcb strain through more support on pcb near mic2 Solution: 1. to add space between mic & PCB through +15% Solder Paste Mask Area from 0.37*0.65*2 to 0.75*0.65 (mm) on both Mics. DVT1 Verify. 2.Add more support on PCB near mic2. DVT1 No issue so far | Link | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2021-01-22 | 5.DVT1 | 7.Sensor | 5.4 ALT | NA | Closed | [na]Denver WH134702 Tumbling on Second Vendor(including PCB Vendor Found) Issue 1: 1:7 of 9 Capsensor no function :D1/D3/D8(100),D4(450),D5(300),D7(500)D9(300) Issue 2:4/9 P/L sensor no function :D1(500),D3(450),D4(400), Issue 3:1/9 Boot Failure. Clue 1:P/L sensor no function：D4 ，I2C wire open ， 2.No Camera Foam Attached and BTB Connector Deattached Root Cause:1.No Camera Foam Attached in Assembly lead to Mainboard Deformed and extreme high PCB Strain occurred. Solution:1.Invalid test,Assembly Correctly and Retest. | link | 小熊 |  |  | 6.No Change
2020-12-14 | 4.EVT | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue1: Denver found Auto Power Off/System Hang Issue on EVT/DVT1 on 10% Reproduce Rate each day. Root Cause: 1.PBS_WD_TO/GP_FAULT2 duo to SPMI Hung which lead to Power Off/System Hung 2.SPMI Hung duo to CPU/RPM Hung 3.CPU/RPM Hung duo to Dip found in S5A which in PFM mode in deep sleep and happened when AP need more power when wake up. 4.S5A Couple with other buck through Grounding under PMIC. Exp4.1:Improving S5 Buck Response Time. Result:100mV improved. Exp4.2:Improving Grounding Path Isolation of S5A . Result:50mV improved. Exp4.1+4.2,No Dip found. Solution: 1.Work Around:Increase S5A by 150mV . 1/4 validated pass. 2.S5A Layout Improvement+Improving S5 Buck Response Time. Validated Pass. | slide link | 李果 |  |  | 6.No Change
2020-12-03 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:Hand-Free Mode Mic -65dB,Spec -71dB Root Cause:1.Mainboard Mic Routing Solution:1.Modifiy Mic Routing,DVT1 Verify. 20201218:updata DVT1: -76dB ok |  | 院长 |  |  | 2.PCB
2020-12-03 | 4.EVT | 1.Platform | 5.6 User Feedback | NA | Closed | [NA]陈文亭机器：遇到一次按开机键开不了机，插QC快充充电器，没反应，SOLLED 也没反应。 clue:1. 前一天充满电，然后放在抽屉里面 2.SW 版本 denver_retail_userdebug_11_RRE31.1_e3622e_intcfg-test-keys_retail_US 3. 电池 断掉一次后故障现象暂时不复现。开机显示电量96%。 合并到 后续总issue里面 | link |  |  |  | 6.No Change
2020-11-24 | 4.EVT | 1.Platform | 4.Build | NA | Closed | [s3]Issue:power off current =240uA ,normal should be 100+uA clue:1. VDD_1P8_SYS =80uA 2.QC release reference design with solution of power off current issue. rootcause： PMK8003 current leakage solution：add 10K pull down on pin5 ，base on QC reference design. DVT1 PCBA test ok |  | 文亭 | 敏敏 |  | 1.SCH
2020-12-01 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA]issue:USB 2.0 eye-diagram test,marginal pass Clue:tune1=default ,marginal pass debug:temp change tune=0x47 ,pass. 0x67 is better. SW change done ，from 12/7 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-05 | 2.PCL | 9.Memory | 4.Build | NA | Closed | [s3] SM4350 will support UFS2.2 物料上会有2.2和2.1两种，需要关注下FW升级问题。 1.针对hynix料，ufs2.2的4+64和4+128都是新料，不存在FW升级问题。 2. 针对三星，ufs2.2的4+64是新料，不存在fw升级问题。 ufs2.2的4+128是目前nairobi上用的2.1的料，需要FW升级，三星不愿意单独区分料号。 3.针对micron，ufs2.2的4+64和4+128都是目前nairobi在用的2.1的料，需要FW升级，micron不同意区分料号。 我先把信息先放在这儿，我们都从各自site看看solution和risk，产线混料风险谢谢 Denver使用hynix4+128 ufs2.2做一供，三星4+128做二供，产线升级fw到ufs2.2。 |  | 嘉琨 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor

## Stingray (hidden)
| Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Department
2019-08-28 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | [S2]Issue: Stingray Black screen making call issue ，after sale Clue: 1. CT higher than 400？IKSWP-105766 CT=600. 2. Factory build CT up limitation is 350 now. Root cause: 1. Proposal: with a screen protector that cause CT higher？ 2.Proposal: Build without a rubber? Solution: 1 .Proposal: New SW calibration algorithm，CT coverage change from 0~400 to 0~654 ---done in MR 2.Proposal: change the CT up limitation to lower Action: change the CT up limitation to lower to get the units CT higher than 200 and check the rubber status. change CR IKTM-5940 :Update P sensor Test limit in JOT station From 0~350 to 0~150 | link |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-20 | D.SHIP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue: 3 units in 13 EWG units, Blank display. Clue: 1. #167400, VINT block damge.#167406,VLOUT3 DCDC damage. #167412,VGL FPC abnormal. 2. No display permanent damage issue in 3T TCC ESD(Edu03) test. 3. ESD and 5 ORTs , No Display Relative ESD Failure. Issue1: #167400 VINT block damge Clue: Get power block from MagnaChip to figure out the relationship among VINT, VLOUT3 and other power source. Root Cause: 1.Speculation:Inrush Current/EOS cause by Hot Plugging Exp1.1:Hot Plugging and Observe . Result: Issue is not reproducible after hot-plugging. Conclusion:NA Exp:1.2:Higher Voltage on Vreg_Oledb Result:Issue is not reproducible after 8V/9V/10V 20us@1Hz pulse charge on VREG_OLEDB(7.6V, the input of DCDC). Conclusion:NA Exp:1.3:Factory Failure Data Collect. Result: similar failure in LDA electronic test. 2.Speculation:User ESD? -> Low Pissibility Exp2.1: ESD after MP . Result:1 Day Return. Conclusion:Low Possibility of ESD Exp2.2:ESD Test Result Summary. Result:13 ESD before MP and 1 ESD & 5 ORT after MP,No Display Relative Issue. Conclusion: Low Possibility on ESD of User. 3.Speculation:Abnormal Loading of Panel Exp3.1: Add load on VINT/VLOUT3 to verify. Result: ?? Issue2:#167406,VLOUT3 DCDC damage. Clue: Root Cause: 1.Speculation:Inrush Current/EOS cause by Hot Plugging Exp1.1:Stress test Hot Plugging and Observe on 1 unit . Result: Issue is not reproducible after hot-plugging. Conclusion:No Conclusion Exp:1.2:Higher Voltage on Vreg_Oledb Result:Issue is not reproducible after 8V/9V/10V 20us@1Hz pulse charge on VREG_OLEDB(7.6V, the input of DCDC). Conclusion:NA Exp:1.3:Factory Failure Data Collect. Result: similar failure in LDA electronic test. 2.Speculation:User ESD? -> Low Pissibility Exp2.1: ESD after MP . Result:1 Day Return. Conclusion:Low Possibility of ESD Exp2.2:ESD Test Result Summary. Result:13 ESD before MP and 1 ESD & 5 ORT after MP,No Display Relative Issue. Conclusion: Low Possibility on ESD of User. 3.Speculation:Abnormal Loading of Panel Exp3.1: Add load on VINT/VLOUT3 to verify. Result: ?? Issue3:#167412,VGL FPC abnormal. Clue: Root Cause: 1.Proposal:FPC Material? SDC Send it to FPC Vendor for FA. Action: 1. Get power block from MagnaChip to figure out the relationship among VINT, VLOUT3 and other power source. 2. Add load on VINT/VLOUT3 to verify. | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-09 | D.SHIP | 7.Sensor | 5.6 User Feedback | S2 | Closed | [S2]Issue:Phone goes dark during calls Clue:1.Try to get the units. 8/23 (VZW will get the units on 8/23?- Syncing)-Ross Clue:Try to Reproduce- 8/26 Tony Root Cause: 1.Proposal:Screen Protector? 2.Proposal:CT>400 Solution: 1.Proposal:User Abuse,Remove/Modify Screen Protector in case of no cover on P-Sensor 2.Proposal:Update Calibration Algorithm on High CT. Before MR 8/30 | Link | 文亭 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-09 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167653 RTT function on the phone is physically off, make an outgoing call it shows up on my phone call, and the ppl on the other line canot hear me properlyl Clue:There is screen protector . RootCause: 1.Speculation: It will increase the CT of the Prox sensor , and more important is that the increases count is unstable because the screen protector is not fully adhered to the 2.5D glass at the edges which is the Prox area. Solution: 1. Requirement for screen protector is to cut off the prox area. other same root cause return unit :FFRP ID 167693 | link | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-09 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | Issue:FFRP 167552 45 - Uninitiated actions Powers off CR ：https://idart.mot.com/browse/IKSWP-101607 RootCause: 1.Speculation: Solution: 1. |  | 敏敏 |  |  | 6.No Change
2019-08-09 | D.SHIP | 9.Memory | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167409 SW-Kernel Panics Clue:Continues ddr error when MemTest. Clue:Samsung Involved, Result:?? RootCause: Why Issue? 1.DDR flip Exp:Log Observation Result: ddr flip Conclusion: R1 Confirm. Why R1? 2.1 Speculation:Mememory Solder Crack Exp2.1.1:ReHeat Memory ,Result:No ddr error until 300 Cycles. Conclusion:May R2 Exp2.1.2:Solder Crack point checking using QDUTT ,Result:on-going Due data?? Solution: 1. | Link | 嘉琨 |  |  | 6.No Change
2019-08-09 | D.SHIP | 8.Mods | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167457 MOD Detect Failure Clues: UI shows “the Moto Mod isn’t lined up correctly. Make sure the connector is clean and try attaching again” when attach Mod. Analysis： Experiment: 1. Measure SPI & CC pins with multimeter ----> OK 2. Measure the waveform of SPI -----> there is some clutter on MISO when CC is connected. 3. Measure BPLUS ----> No BPLUS output when Mod CC is connected. 4. Measure EN pin ---> OK 5. Measure OC pin of switch ----> 1.37V voltage at idle time. It should be 1.8V.---->same 1.37V on normal unit, why? Root Cause: PowerSwitch U710 (FPF2595) is Damaged（Apply new IC to replace and verify BPLUS control---> Verified OK.） Next Step: Send IC to Onsemi for failure analyze EOS ,monitor | Link | 邦邦 |  |  | 6.No Change
2019-08-09 | D.SHIP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167513 01 - Does Not Power On at all Device will not turn on Clue：Blank Display RootCause: 1.Speculation: Solution: 1. PM6150A EOS ，monitor | Link | 芳梅 |  |  | 6.No Change
2019-08-09 | D.SHIP | 4.Audio | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167519 No Mic Audio RootCause: MIC brocken Solution: 1. Audio team owe | Link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-21 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:Field unit:PVT:Stingray: Prox keeps on falsing and waking up during calls on earpiece IKSWP-99509 RootCause: 1.Speculation:Prox Keep bad performance due to High Threshold Setting by calibration 2.Speculation:recheck FFRP ID 167516 HW ： meet 0.3mm Blank card detection design Solution: 1.IKSWP-102131 to correct observed calibration issue | Link | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-19 | D.SHIP | 4.Audio | 4.Build | S3 | Closed | [S3]Issue:Motor Keep Vibrating or no vibration，60%+ failure Rate on AAH4 Batch after over 100K mass production. Clue:Failed I2C：Address High>0.98V ，I2C Adress due to Address Low<0.82V Clue: IC Work normally if 10M Pull Down Clue: Can read chip ID noramly when start up RootCause: 1.AWINIC 8690 work abnormal due to I2C Address shift. EXP1: I2C Control to read chip ID after power on Result: Address form 0xB4 to ox B6 Conclusion: i2c Address shift 2.1 wrong config EXP3： Reset chip register Result : Chip address recover Conclution: wrong config EXP4: One by one config start up register Result:0x36 config to 0x01 (0x21 defaut-Internal 2M Pull Down) after initiating Conclution:: wrong config(0x36 no showed in spec.) 2.2 I2C shift due to Batch difference, AWINIC under investigating Solution: 1.Don't set 0x36(Hiden Register) to 0x01(Disable Pull Down，Default 0x21-Internally Pull Down) SW CR :https://idart.mot.com/browse/IKSWP-101218 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-08 | D.SHIP | 10.USB-C | 4.Build | S3 | Closed | [S3]Issue:Stingray CFC 发现76%直通率，出现问题时是掉口 Clue:1. 换一根 新的C to C 数据线 就好了。 2. shelby ，shelby+ ，RIO 没有问题。 3. 更换USB 2.0 的下载盒子和数据线，有极大改善，到97%+ RootCause: proposal 1：USB 连接器的铁壳比较短，由结构和较短的外壳限位，稳定性比较低。 proposal 2： Solution: 1. 更换USB 2.0 的下载盒子和数据线 2. Quattro 有同样问题，同样的solution |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-21 | D.SHIP | 5.Camera | 4.Build | S2 | NA | [S2]Issue:Stingray 后拍录像播放卡顿异常反馈 ，视频 link Clue:1.video 里面帧在不在？ 2.卡顿出现之后，声音和 视频 是否同步 3. 手机稳定拍摄 背景动态 和 手机 动态 拍摄 静止背景。 4.[‎2019/‎5/‎21 11:48] Shunyong SY6 Xu: 有概率出现录的时候也会卡，大部分是播放的时候卡 5.通过视频观察：停顿时，声音播放，但是画面丢失。（停留在卡顿前画面1S左右，然后跳到另外一个画面，而不是连续画面） RootCause: Solution: 1. |  |  |  | 视频link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-07 | C.RAMP | 2.Power |  | S2 | NA | [S2]Issue: CQA found some units auto Black Display ,CR：https://idart.mot.com/browse/IKSWP-84566 analysis：1.when it happen ,current =30+mA . Need long press powerkey to power on the units. 2. power on current some units more than 300uA . and unstable 3.replace U2400 with a new one , it it ok. 4. fail units retry IF and BT ,it it ok. then go PAT & JOT , it fail again . 5. fail units most reproduce after power on 5 second . ( few need longer) RootCause: 1.U2400 PM6150A damaged on VBAT? 2.Power Supply on Vbat set to 4.35V,and Over Voltage 4.95V Observed on Vbat(B_Plus) when Power Supply on. 3.Proposal:Place board with VBAT on during IF Solution: 1.Power Source Set to 3.8V,and using 2 Phase Power Supply(0->2V->3.4V->3.9V) 2.Proposal:Longer GND Pin in IF&BT. 3.Proposal:Adding 100K between VBAT and GND Pin in BT Fixture. and Connect GND Pin with other Position Column 3.Proposal:Close IF VBAT,Try in Quattro first. | link | 敏敏 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-26 | C.RAMP | 2.Power | 5.6 User Feedback | S3 | NA | [S3]Issue: 1 unit auto power off when make call in China Mobile SIM . Clue ： 1.USE CMCC SIM ,it is ok 2.open the Display module with 90 degree , It is ok. Close the Display module ,it reproduce 3.Not Reproduce. |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-01 | C.RAMP | 2.Power | 4.Build | S3 | Closed | [S3]Issue: Issue 1.Accessory_On_Current_Board_1, True Failure, Clue:April Clue:Several 7.5V 100ms burst on VBAT will reproduce U2400 Failure. Clue:Battery_Off_Current_Board_1 ,1-3Mon 0%, 4/1 - 4/25 0.22%, 4/25-5/7(2 stairs Power Supply 3.9V) 0-0.75%. Clue:1.Accessory_On_Current_Board_1,0-4%,NTF,Small Amounts units. RootCause: 1.U2400 PM6150A damaged on VBAT, QC Feedback:Vddgen on metal layer 4 EOS issue 2.Power Supply on Vbat set to 4.35V,and Over Voltage 4.95V Observed on Vbat(B_Plus) when Power Supply on. 3.Proposal: Place board with VBAT on during IF 3.Proposal:CDM ESD? Need follow up Action - TE liubin Exp1:Longer GND Pin Result: Wait for Pin Arrival . Conclusion: Exp2:Add 100K Between VBAT and GND Pin,And Connect GND to Position Column 4.Proposal:PM1650A Lot? Exp:Analysis Lot Relative, Result:Not Relative, Conclusion:Proposal Drop Solution: 1.Set to 3.8V,and using multiple Phase Power Supply(0->2V->3.4V->3.8V), 1.77%->0.05%, Validated. Need follow up action with more IF site. 2.Longer GND Pin in IF&BT. 0.8%->0.2% 6/10 3.Proposal:Grounding Positioning column |  | 敏敏 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-01 | B.PVT | 8.Mods | 5.2 BB Test | S3 | Closed | [S3]Issue: Mods USB SS Drive Strength level change from 925 mV -100% to 253.6 mV-27%, Data ThroughPut = 51Mbps Clue1: While Shelby Plus finalized 261mV duo to failed on DF when use 219mV Clue2: 5G Mods Fixed on 290mV. Root Cause: 1. USB SS Drive Strength 220mV(0x21) Can Not Meet Minimum Signal Integrity Requirement Solution: 1.Using 265mV(0x23 confirm by 4/9) , Match Shelby Plus Driver Strength Level Data ThroughPut=808Mbps (User Debug SW) -Soak Test on USB SS 0x23 under -30°C and 60°C .Pass -Test Data ThroughPut on 0x23 with User Version- 4/12 | link | 邦邦 | 文亭 |  | 4.Parameter
2019-03-25 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: Cap sensor impact Active pen Root Cause: Both Cap snesor & Active pen Woring Freq 25Khz Solution: Evalute change Cap snesor Woring Freq to 41Khz , there some bug ,need to be fixed Can not use 41KHz ,No time for the SW update. |  | 小熊 |  |  | 6.No Change
2019-03-25 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: Cap sensor Bug when tempreture change too quickly Root Cause: Solution: FW update？, there some bug ,need to be fixed. No time for the SW update. |  | 小熊 |  |  | 6.No Change
2019-03-25 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue: Some times can not power on , Track ID NNBA2K0001 ,NNBA2K0008(DVT2B) Root Cause:suspect 9008 mode issue Solution:Rework these 2 units and sent back to user（CXD Matias ） monitor from 3/26 to 4/4 No problem by 4/22 ，close |  | 文亭 |  |  | 6.No Change
2019-03-04 | B.PVT | 9.Memory | 5.4 ALT | S2 | Closed | [S2]Issue: Unit Stuck on Andriod Logo Screen after Power On. CR : KSWP-69943 1.DVT2B 1 unit failed /183 ,PVT 18 unit failed /319 2.Issue found on IF,Assembly,CQA,ALT Root Cause:1.Sequence of Register Dump Process for Log Error when Error Correction,Known WD Memory Issue 2.PCN Supposed to release on 3/7 but fail to sync with lenovo before 3/12. Solution: 1.Using New Memory with new Ver.78 FW, -DF update and no issue found. 4/4 -Edu12 eMMC Durability Test Pass. 4/1 2. -Build Validation & Rack Test on 4/15 , SMT on 4/9 DF Validate Pass over 10,000Hrs. Go WD. | link | 嘉琨 | 文亭 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-01-23 | 7.DVT2 | 1.Platform | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT2A thermal test camera related fail Root Cause: RC1: camera power consumption & performance need balance Solution: 1.Proposal:SW29.64 import 1st mitigation Strategy for camera ，waiting for TCC retest PQM ,PQA,SW,BB check accept the result 29.105- |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-04 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Unexpected auto power off after ESD CD on MODS area, recovered after reboot. TM display RootCause: Display error 1.Display TE check failed and carry on recover procedure. 2.Display pwr_mode register meet error after power down and on. 3.AP halted after two recover fail. Solution:1. Not reproducible in PVT and Quattro |  | 吉吉 |  |  | 6.No Change
2019-03-08 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: Cannot detect MODS after ESD Front camera(and Front flash) is ON,After +8KV air discharge at zone16 (zap16),The 360 mods I used had the constantly sound of devices connected,Then changed the turbo mods and it completely undetectable in CQA test.I restarted the phone and I found all mods connected normal. Root cause: 1. mods cc signal error. 2. mods detection IC error after ESD Solution: 1. hard to design better |  | 吉吉 |  |  | 6.No Change
2019-03-04 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone stopped at "Android" sreen after ESD testing Clue: After +8KV air discharge at zone16, then check the CQA function at CQA screen,wait for about 30s later,phone auto entered the "Android" screen.Then wait for about 7 minutes,the unit entered to main screen. Root cause: 1. Audio might crash. 2.Could be reproduced without ESD. 3.CQA TEST APP Crash 4.Solved by SW update 29.96 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-07 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone dropped call after ESD testing Clue: After +8KV contact discharge at zone8 (Aging10) , Phone dropped call. When the issue occurred, you can re-call the phone without restarting the phone. Root cause: 1. SW analyse logs. 2.All the call is normal disconnecting, there are no abnormal issues found in the UE side. |  | 吉吉 |  |  | 6.No Change
2019-02-25 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | NA | Closed | [S3]Issue: CR :IKSWP-63410 PPF29.78 Rahul calls suba with phone on his earpiece Prox triggered correctly and display was off for 1 minute while in call over earpiece After one minute of in call, the prox suddenly triggered again bringing the display on and the in call audio route moved automatically to speaker Timestamp of event : 3:22 PM approximately, please check around this time in the b2go attached Suba has also encountered the same issue multiple times on her DVT2A retail SKU as well on the same sw rahul b2go : 305418529 Root Cause: black hair issue Solution:Touch IRink change ： from 2 round hole to racetrack，Improve black Card detection performance | link | 文亭 | 小熊 |  | 4.Parameter
2019-02-24 | 7.DVT2 | 1.Platform | 5.4 ALT | S3 | Closed | [S3] Stingray_TCC_ALT:1 unit auto power off after drop test ，CR IKSWP-53809 DVT2A 1time in Loop3 （total 3 groups of ALT ） ，DVT2B 1time in Loop4 monitor |  |  |  |  | 6.No Change
2019-02-24 | 5.DVT1 | 12.EMC | 5.6 User Feedback | S3 | Closed | [S3]Issue:Kernal Panic - DDR Flip found on NNBV120029,DVT1a on Rack Test RootCause:1.ESD Relative Exp1:Correct ESD Issue Exp2:DVT2A and after Data Exp3:Reproduce 10 times Crash on DVT1A udner ESD ->Result:ESD Relative Solution: 1.DVT2A imported Same Root Cause and Soluton with DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 | here | 吉吉 | 嘉琨 | here | 6.No Change
2019-01-23 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue: DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 Root Cause: RC1: Jtag ESD Risk RC2: Short tisk between Jtag & rear housing . Solution: 1. change to DVT2A units and monitor | here | 文亭 | 敏敏 |  | 2.PCB
2019-01-30 | 7.DVT2 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue: BSP Target 32.1 Hrs，Current 29.8 Hrs. EBL on DVT1A 20Hrs Current BSP on NA version,32.8Hrs | here | 李果 | 敏敏 |  | 6.No Change
2019-01-23 | 5.DVT1 | 1.Platform | 5.3 EE DVT | S3 | Closed | [S3]Issue: MDu44 fail . especial U2400 right bottom corner 1.DVT1B use 2nd PCB 2.DVT1B display easy to separated 3. use 1st PCB ,From DVT2A (remove 2nd source PCB) . MFAL check if there is difference 4.display assembly ok ,From DVT2A Root Cause: 1.PCB Strain 2.ALT Drop Solution:1.PVT function ok . go with no underfill (aligned with PQA &PQM) | link | 文亭 |  |  | 6.No Change
2019-01-23 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2]Issue: 产线装配发现硅胶套装偏导致 sensor 被遮挡的 Action：请整理相关信息关注ME action落实情况，ME Informed to HouXiRong& XianQing | LINK | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-01-23 | 7.DVT2 | 8.Mods | 5.2 BB Test | S3 | Closed | [S3]Issue: An error message appears when restarting the mod Root Cause: RC1: Mods B_plus dont have a good enough discharge path.when the mods restart ,the B_plus should go down and restart to make mods restart . but it dont restart,and it cause mods go into the Flash mode and can not restart Solution: The change point is : add a discharge path for mods B_plus | link | 邦邦 | 院长 |  | 3.BOM
2018-12-26 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: ANT LowB performance degraded after ESD @Calling@Bottom Ant in DVT 2A WH112926 6 Fail/6 units -8dB loss@ B5/B12 Root Cause: RC1:QAT3550 Tuner U200 Broke -Pin CIO，SW3，SW4 -Internal C1 Damage also found RC2:ESD Protection by Varistor not enough Solution: 1.Using ESD128(Infineon) TVS on VR240 , ESD +/-15KV 200 times Evaluate Pass. RSE Evaluate Pass. TRP Evaluate Pass. -Verify one more units for consistency. 2/15 -6 units PCBA reworked and will do ESD Test and TRP Verification in WuHan TCC after assembly. 2/19 -Sample meet PVT requirement. Will Follow Component Qualification Process and Supply. 2/19 | link | 吉吉 | 文亭 |  | 1.SCH
2019-01-23 | 7.DVT2 | 3.Charging | 5.2 BB Test | S3 | Closed | [S2]Issue: shelby 售后不开机主板，分析CC1和CC2 pin 损坏比例较多，评估是否能改善 6150 CC1,CC2 耐压22V，Better than 660 which is only 6V. Iteration:Review |  | 院长 | 敏敏 |  | 6.No Change
2018-10-22 | 4.EVT | 8.Mods | 5.1 Bring up | S2 | Closed | [S2]Issue:Mods DP no display Clue: 1.Mini DP Qualcomm not ready until 11/15 2.DP over Tpye-C can work with no HDCP DP->HDMI Adpator;Aux and DP HW Verified. 3.HDCP Error found,QC feedback that should be TZ issue. HDCP1.x Key and deploy，$0.01,Using new test key ,resolved 4.DP Adaptor over this Channel ,Verified OK. RootCause: 1. Trust Zone Error/No Key For HDCP,Fixed on 12/14 2.Horizental & Vertical Syncronization Signal extact fail，Analogix RD Involved and Digging- 1/7 Solution:1.Source config |  | 邦邦 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-26 | 5.DVT1 | 12.EMC | 5.6 User Feedback | S2 | Closed | Issue: caizhiyi机器反馈原来ok 机器，胜男拆机返工CTP后（P-sensor油墨孔改成跑道型），之后打开蓝牙灭屏后就像自动关机了 clue： 1. 开启蓝牙或者WIFI ，然后进入休眠，自动关机（没有关机画面），都关闭就不会 2. Action：a.拆除LCD 是否能复现？” b.能复现，测量L10A的电压变化，同时关注电流变化，同步找一路参考电压。c.关机状态测量L10A的阻抗变化 3. L10A 外部加电源后，没有问题。 4. 用不休眠的SW版本验证也没有问题。（比如29.35 ） 5. L10A 用外部电源替代，并用电流计查看，有小脉冲电流 ，故障板能到140mA ，宽度130uS 以内。 6. 不开BT或者WIFI，故障板 L10A 外加负载10mA就会掉电 ，另外一个正常板子，外加30mA都不会掉电，再加上BT，WIFI打开也不掉线。 7. 20180106 试用人员又反馈一台 CR： IKSWP-52032，同样是DVT1A机器，现象类似，但复现概率低一些，短时间内不能必现。 Root Cause:1.PM6150 L10A LPM Mode Damaged Action ：Jtag check PMIC 寄存器 Solution:1. use NPM mode for L10A in all mode 2.JTAG Removed （DVT2B removed ，DVT2A change to test point ，done） 3. 3W Routing with GND on FPC ，done 4. Optimized Placement on Receiver Area.（DVT2B ，done）增加GND 开窗保护 5. L10A PM6150 side reserved 1 TVS , 屏蔽罩内无空间在PMIC端加TVS管。L10A在屏蔽罩内已四通八达。 长期事宜： 1. Test case 增加休眠模式 2. 亮屏下用ADB 读取寄存器判定是否ok | link | 敏敏 | 嘉琨 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-22 | 5.DVT1 | 8.Mods | 5.1 Bring up | S2 | Closed | [S3]Issue: 1.DisplayPort Aux Communication Failure,Over 50% Root Cause: 1.Aux Signal Integrity Issue Exp1.1-Clear Log and Start Mods on passed one and failed one on two unit，Log and send to SW for analysis Result:Passed with no error; Failed with all Aux error Exp1.2-Aux-P /GND Wave Form Measurement Exp1.3-Repeart Reading through Aux on failed unit and Passed Unit.Observed the Waveform on Aux P/N from Phone side. Result:Failed unit entering Repeating Read mode,Can't Insert one Read operation Exp1.4-Remove R755Mod,Remove R743Mod,Remove C748 Result:Fail Exp1.5-Remove R756Mod,Short C747mod Result:Fail Exp1.6-Aux n Pull up to L17A using 100K；Aux P Pull Down 100K after Capacitor Exp1.7-Measure Aux P/N ,Observe Waveform after P-N(Math Minor) Reslut:P-N=0 Solution: 1.Sol1.6:Adding 100R after Capacitor on Aux Verified OK,BOM Change in DVT2B | here | 邦邦 | 李果 |  | 1.SCH
2018-12-26 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:SW 反馈有人报Foles通话不容易灭屏的问题（caizhiyi的机器） clue： 1.SW caoyi 告知，手机左手拿着，P-sensor 位置比较容易跑到耳朵意外的区域，导致读值很低，不能判接近。 2. 右耳朵也会出现，那应该是0距离状态下的 Root Cause:1.左耳朵飘出耳朵范围 Solution Action：1.DVT2B 旋转P-sensor 180度，将发射灯更靠近手机中心。（硅胶套同步更改） |  | 小熊 | 文亭 |  | 2.PCB
2018-12-26 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue: Black Card Performance Can't Meet requirement Root Cause:1. Double Holes window on CTP Solution：1.Change Double Hole to Singe Oval Type Hole ,Verify on DVT2B ： Samsung Display PVT 100+pcss TianMa Display DVT2B TBD |  | 小熊 | 文亭 |  | 4.Parameter
2018-10-22 | 4.EVT | 8.Mods | 5.1 Bring up | S2 | Closed | [S2]Issue:Mods Camera not Bring up,Block on Lanes Overflow Clue: 1.AP CSI2 worked with Front Camera 2.APBA Lane2 Signal detected,25Hz/21Hz 4. RootCause: ... RC6.SM6150 CSID Can't Decode CSI Low Speed Data? Exp6-1.Using Front Camera,Wiring to CSI2,Setting Low Pixel Clock Rate ,to Check if no overflow issue on CSI2. Result: Exp6-2:Try to figure out the relation between APBA Clock and SM6150 CSI2 Reading Clock and DSP Codec Clock 1.Different APBA Clock 2.Different SM6150 CSI2 Reading Clock 3. FIFO Status 4.DSP Decode Clock 5.Frame Received(Judge by SOT/EOT Count), 6.Escaped Time when overflow Result: Solution:1.Proposal:Config Muc APBA CSI Clock to match CSID of SM6150 2.Proposal:Config SM6150 CSID to Match each other. | here | 邦邦 | 院长 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-16 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S2]Issue: Factory Download 50%+ can not connect to 9008 (enumerated 9008 with "！") Clue: 1. No Issue with Computer USB 2.Error code:Windows cannot load driver for this hardware.The Driver may be corrupted or missing.(Code 39) 3.Remove TVS no affect 4.USB Suspend found 5.Proposal:Long USB Cable（0.9m+Expander Board+0.6mType-C Cable） 6.PCIE USB Hub 4 Channel ,Validate Pass Root Cause: 1. Issue only happend during 16S duration windows when restart to re-enumerate after provision when 2 or more unit flashing. 1.PCIE USB 3.0 Hub+Moto Driver，Change to USB2.0+Qualcomm Newest Driver 2.0，No Issue 2.1 We import USB 3.0 Function Check in this process. 2.2 Proposal:Unknown Device relative to the driver updation. Solution: 1. Seperate Provision Site 2.USB USB2.0 & Qualcomm Newest Driver,Need seperate USB 3.0 Flip Test. 3.Proposal:Using Delay 35s, Validate Pass. Factory WWTE Issue | link | 文亭 | 林峰 | SW NEW CR https://qualcomm-cdmatech-support.my.salesforce.com/5003A00000t2cYrQAI | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-16 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [S3]Issue:MDu30 Thermal Test Fail-WH111596 Clue: 1.Camera 4K torch，flashlight area overheating 2.wifi streaming with charging，mods connector area over 3℃ 3. Processor loading overheating 4. Gaming with charging，mods connector &metal frame over 2℃-3℃ RootCause: 1.Driver Current Set over Spec in Torch Mode 2.Flow Media Play current drain too big,Charging Current too big. 3.Processor loading is reference only，CPU mitigation not start. 4.Gaming with charging，High Power Comsumption,Charging Current too big Solution:1. Touch Mode Current Fix in DVT1B SW,Validated take effected. 2. DVT1B optimize Charging Current 3. DVT1B import CPU mitigation，target<45℃ 4. DVT1B Using CS CPU for test to eliminate ES High Power consumption DVT1B: All Pass except Data Link over 2℃，It is a reference item. | Link | 林峰 |  |  | 4.Parameter
2018-11-26 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S2]issue:BB test ，P-sensor oil test fail in EVT and Black cardtest fail in DVT1A Clue: Rubber EVT =0.25mm, DVT1A=0.65mm Root Cause:1.Isolite Rubber Thickness need balance between Anti-Oil and Black Card Test Performance. Solution:1.Change Rubber to 0.55,0.65,mm ,Verify on DVT1B |  | 小熊 | 文亭 | test data | 4.Parameter
2018-12-26 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | Issue: caizhiyi机器反馈原来ok 机器，胜男拆机返工CTP后（P-sensor油墨孔改成跑道型），之后打开蓝牙灭屏后就像自动关机了 clue： 1. 开启蓝牙或者WIFI ，然后进入休眠，自动关机（没有关机画面），都关闭就不会 2. Action：a.拆除LCD 是否能复现？” b.能复现，测量L10A的电压变化，同时关注电流变化，同步找一路参考电压。c.关机状态测量L10A的阻抗变化 3. L10A 外部加电源后，没有问题。 4. 用不休眠的SW版本验证也没有问题。（比如29.35 ） 5. L10A 用外部电源替代，并用电流计查看，有小脉冲电流 ，故障板能到140mA ，宽度130uS 以内。 6. 不开BT或者WIFI，故障板 L10A 外加负载10mA就会掉电 ，另外一个正常板子，外加30mA都不会掉电，再加上BT，WIFI打开也不掉线。 7. 20180106 试用人员又反馈一台 CR： IKSWP-52032，同样是DVT1A机器，现象类似，但复现概率低一些，短时间内不能必现。 Root Cause:1.PM6150 L10A LPM Mode Can't meet power requirment Solution:1. Correct NPM mode for L10A in all mode,Validated that no side effect on efficiency. 长期事宜： 1. Test case 增加休眠模式 2. 亮屏下用ADB 读取寄存器判定是否ok |  | 文亭 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-26 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | Issue: DVT1B 火生1台机器不识别快充，需要分析。 clue： 1.关机一段时间后，再开机会回复正常。多次插拔充电器后，又fail 2.Fail 的时候，链接电脑，USB也不能正常链接（提示不正常的设备） Root Cause:1.AP not release USB Channel When QC 3.0 Lead to Pmic fail to intercommunicate with Charger. Solution:1.SW Update according to QC , Which is the same issue with QC3.0 issue under Power off Charging, SW Issue | link | 林峰 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-26 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | Issue: DVT1B high possibility Power off when ESD test Root Cause:1. Jtag signal affected Solution:1.DVT1B Jtag shielded with Copper and isolation film，Evaluated Pass. DVT2A PCB Has been modified . Same Issue with : DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 | link | 吉吉 |  |  | 6.No Change
2018-12-26 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | Issue: DVT1B ESD Evaluate, BT Drop clue： 1.Change SW no affect Root Cause:1.Side Key Fixing Clip Discharge by ESD2.Grounding on Sidekey FPC not Stable 3.Key Signal Affected 4.BT Signal Affected Solution:1.Isolate Side key grounding pad with Clip. Validate OK 。DVT1B test ok （2 round） Action:DVT2A增加绝缘膜贴在侧键FPC上，已通知结构备料 ，DVT2B发板需要将FPC 按键面的露铜去掉。 | link | 吉吉 |  |  | 2.PCB
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:WH111665 1.After +10KV air discharge at zone 6(Aging10),P sensor and light sensor no function,restart recovery. Clue: 点胶和封胶 是否没做好，直接打到P-sensor本体了？ （点胶不完整，打击P-sensor区域，会出现软性失效） RootCause: 1.P-Sensor Affected by ESD Solution:1. SW recovery ,RD Validate Pass 。 |  | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-16 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S3]Issue: Factory feedback SOL LED too dark & sometimes no function Clue: Factory mode & CQA mode with different Lightness . |  | 文亭 | 林峰 |  | 4.Parameter
2018-12-12 | 5.DVT1 | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT1A WH111559 Tumbler 200 times , D1 &D4 front &Rear camera can not work Clue：1.SDA wire open （SCL ok） D1 &D4 2. NFC IRQ，ANT_cap_sensor_CS1_N & REF _cap_sensor_CS1_N,wire open. 3. CPU shielding case seem lift up and SH118 seem lift up too. 4.Press CPU shielding case can recover Root Cause:1. Layer 10 CPU shielding case separate from PCB cause Layer 9 wire open. 2.High Strain on PCB Neck and shielding case Solution:1. enhance Layer 1 shielding case SH118 SMT ,in DVT1B V05 PCB 2:change the layout within this area ,will change in DVT2A V06 PCB 3.Add Foam on Bridge，Validate improved,Import in DVT2A and validate. | link | 文亭 | 芳梅 |  | 2.PCB
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue: 1.Zone 11(Aging10) proximity sensor no function then unable to enter system after reboot,recovered after reset(fastboot -w). 2.Light sensor and proximity sensor no function，recovered after reboot:D5(contact 6KV) 3.+8KV contact discharge at zone 14(Aging10), Vibration no function then unable to enter system after reboot,recover after reset(fastboot -w). 4. -8KV air discharge at zone7(Aging10), Phone unable to enter system after automatically reboot,recovered after reset(fastboot -w). RootCause:1.SW Bug , not happen in latest 2 ESD Test Solution:1.SW Update. Validate Pass |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:Unit 1 +15KV air discharge at zone 6/zone 9/8&10 (Aging10),The phone lock up,recovered after long pressed power key to reboot. Clue:1.System Halt 2.Reproduce ,Log 3.AP or Display Driver? RootCause:Proposal:TX Error? Solution:1.Jtag Removed,Validate Pass. |  | 吉吉 |  |  | 2.PCB
2018-12-05 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | Issue:Unexpected auto power off During ALT Drop Test ,CR IKSWP-42633 DVT1A NA SKU ALT(WH111516)(PA/PSA Anyone） A3(1):Drop right side DVT1A NA SKU ALT(WH111848)(total 9units） A3(1),B4(1):drop back side A4(1):drop left side Root Cause:1.JTAG Short with Edge of Back Housing Hole on bottom. Experiment:DVT1A LATAM L15 Isolate Jtag with film and validate , Pass 12/14 Solution:1.Remove JTAG Connector,monitor DVT1B Validate Pass Same Issue with : DVT1 some user feedback auto power off。 | link | 文亭 |  |  | 6.No Change
2018-12-05 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:The phone automatically reboot,then recovered:D1(contact 4KV) The bluetooth no function, recovered after reboot:D1(contact 4/6KV) Clue: 1.Unplug Side Key FPC and Pull out, ESD Pass 2.Unplug Side Key FPC and Keep in the original Position, ESD Fail 3.ESD Spark found on Key FPC Clip 4.Grounding PCB Bridge ,Shielding Key FPC,ESD Fail 5.Put Film on PCB Bridge,Isolate Key FPC ,ESD Fail 6.Internal Wire? Root Cause: 1.Proposal:WIFI/BT Antenna Strike by ESD ,Verify Fail. 2.Proposal:Varistor may not provide enough Anti-ESD performance, Verify Double Varistor Fail. 3.Proposal:In 03A PCB board, the wire from Anttena is connected to capacitor, but not Varistor first. V04 Modified, Validate Failed. 4.ESD on Power,and Key - lead to fail 5.Side Key FPC Solution:1.Grounding FPC Stiffiner Steel 2. Isolate Key Clip with FPC,Evaluate Pass. | Link | 吉吉 |  |  | 2.PCB
2018-12-05 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:The phone drop call,recovered after call again:D1(Air 8KV) Clue: 1.HandFree Confirmed 2.Proposal:Log Analysis 3.RF Tranceiverin bottom 4.Proposal:Frequency? +2 unit1 Root Cause:1.if Hand Free, TP Ghost Point Issue Solution:TP FW update,Validate OK |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-04 | 5.DVT1 | 11.Thermal | 4.Build | S3 | Closed | [S3]issue: RT516 damaged in DVT1A assembly, fail rate 0.53%= 4/750 Root cause:1.RT516 Crashed When lockdown Side FPC 2.Conflict with Fixture,No Issue after Optimize Fixture in DVT1B Solution:1.Optimize Fixture, DVT1B Validate Pass. 2.Reserve DVT2A Add 2 0402 capacitors to protect RT516,DNP |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-04 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]issue: In TCC ESD test, touch screen no function with large probability,recovered after pressed power key. Clue: Issues appeared when the Display panel faced down, and ESD dischaged on the back frame. 2.Proposal:Touch Screen OK withough ESD? Root cause: 1. TP IC might be interfered by ESD coupling. 2. TP IC is alive when TP no function. 3. TP IC calibration meets problem after ESD test. 4. This issue might be solved by Goodix calibration algorithm. Solution:1.Optimize TP Algorithm |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-12-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]WH111662 A3 ALT Loop2 Drop on left side , P-Sensor No Function. 12/12 Root Cause:1.FPC wire open on strain corner lead 2.FPC foldered in abnormal state Solution: Change FPC GND and Open Area，on-going |  | 小熊 | 文亭 |  | 2.PCB
2018-12-02 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]issue:on Dec/2 WH111848 ALT Loop2 B2:After drop top left corner,P sensor is always in enable status,light sensor is always in dark status, recovered after reboot Clue:Plan :1.PI Get log and check what the status CR IKSWP-44583. 2. Follow up the Loop 3~5 3. tear down the B2 after ALT test 4.SW check how to dump the Register when ALS/PS fail Root Cause:1.SW Bug and Fixed Solution:SW update |  | 小熊 | 李果 | CR link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-11-29 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]issue:WH111516_B4_NNBA120190 After loop2 drop right side,1 units' P sensor&Light sensor have no funciton,but restart can be recover Clue:Plan :1.LOG in CR IKSWP-43026 2. CTP not assembly good 3.Proposal:Try to Reproduce，Can't Reproduce，Monitor others Root Cause:1.suspect assembly issue ：CTP not assembly good may cause rubber moved and cover the sensor . Solution:Monitor Loop 3~5 result,No Issue |  | 小熊 | 敏敏 | CR link | 6.No Change
2018-11-26 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:ALT WH111516 ESD C1 样机Standby模式，+8KV空气放电 ，打TP Lens底部缝隙区域（Zone 3），CQA模式下检查指纹发现Fail，手动关机后不能再开机 Root Cause: 9008 state ，No HW dameged. Not a real issue |  | 吉吉 | 李果 |  | 6.No Change
2018-11-26 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S2]Risk:Mods Factory test plan: DVT1A dont start mods test Root Cause:SW not ready Solution:Inform SW*NPI |  | 邦邦 |  |  | 6.No Change
2018-11-16 | 4.EVT | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]Issue:[Jira iDART] (IKSWP-40058) Can not charge, shows discharging when connecting charger(1user,often)连接充电器无法充电 B2GID:304434411 Clue:14号，ppf29.10版本启动了。目前硬件的相关的可能只有这个。连接了usb没有充电，拔插后拧一下插头才能识别到。另外fastboot 模式也出现识别不到，也是拧usb口才读的到。 Root Cause:usb-c connector 虚焊 Solution: Release FA to Factory&Component,They will follow. | Link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-11-13 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:Sleep Current Drain 27.5mA Root cause: 1.Max3108 6.5mA 2.Memory 6mA 3.Display 1.2mA 4.after SW Merge All upgrate: Base Current =7.2mA@3.8V,Gap:2.2mA 5.Moto Action&Maya: -1.5mA ->5.7@3.8V , Gap:0.7mA 6.Proposal:Boot up with BP-Tool Mode ->System Boot :-0.5mA ->5.2mA@3.8V 7.Proposal: Solution:1.After Fine tuned,5.1mA achieved on DVT1B. | Link | 李果 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-11-13 | 4.EVT | 8.Mods | 5.2 BB Test | S2 | Closed | [S2]Issue: Remove Max3108（I2C->Uart）,Current Drain reduce 6.5mA Clue:1.L19A 2.7V 1mA Root cause: 1.UART Mode Config as Hi-z，improve 6mA 2.Disable Internal PLL, improve 0.5mA Solution:1.Uart Mode Config -SW 2.Disable Internal PLL-SW | Here | 邦邦 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-11-08 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: 1. 1/6 unit D6 cannot boot, stuck at MOTO logo, current leak and heat, after ESD test. 2. 2/6 units D3,D4 cannot boot after ESD test. Root cause: 1.1 D6 Stuck on Moto Logo when boot Due to Cap Sensor Damaged Through CH1 Sensor on Top Left. 2.1 D3,D4 Can't Boot Up Duo to AP Damaged on VDD 1.8V due to Mods SPI CS Pin that Damaged by ESD. Solution: 1.Adding one TVS on this channel and approved by Antenna. Import and validate in DVT1A. 2.Series in 1kΩ Mods SPI CS pin to enhance protection. Import and validate in DVT1A. | Here | 吉吉 |  |  | 1.SCH
2018-10-22 | 4.EVT | 5.Camera | 5.4 ALT | S2 | Closed | [S2]Issue:1/7 unit Front camera fail after ALT WH110271 B2 Root Cause:1. 1. CAM_R_I2C_CLK in Layer 9 break 2. Shielding Case Corner Strain Solution:1.Proposal:Adding Foam - ME 2.Proposal:Solder Open limitation - BB/RF/ME 3.Proposal:Reserve Enhance Shielding Case on Bridge Corner Same Root Cause as A+G Fail, Combined with 1/8 unit A+G fail after ALT WH110272 B2,Closed | Here | 芳梅 |  |  | 2.PCB
2018-11-05 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S2]Issue: DISP_VIO change from L13A to L15A,SW Downward Compatibility ok? Root Cause:1. Camera IOVDD need separate from DISP_VIO 2. Solution:1. follow HW ID to detect EVT and DVT1,L13A change to L15A Compatibility is ok DVT1 a CHECK OK . CLOSE |  | 敏敏 | 芳梅 |  | 6.No Change
2018-10-30 | 4.EVT | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue: Black Screen with 3/15 times during boot up Clue: 1.Reproduce when Assembly in phone ，No issue when place display plat, Found issue on Plat place too. 2.Issue Follow Dedicated Display 3.Hardly reproduce when insert converter FPC. 4.MIPI Test Pass. - new update 5.Proposal:Display Recovery lead to Reboot, Exp:Remove Recovery, No Display when boot sometime. 6.Remove Recovery Machanism，if Boot Up,No Issue. 7.Fix FPC using bandage with Converter FPC, 40 times no issue. - 2018-11-13 8.Assembly back into Phone with good assembly on Display FPC. 20 times no issue. 9. Root Cause: Why Boot up No Display on this display? 1.FPC Slip off Connector lead to Black Screen when shake 2.Proposal:Display Damaged ,Sent 1 Display to Samsung. Should get report in this week. 3.DSI Read Error ，Using TE Recovery instead of Dsi Read Recovery ，No Issue Solution: 1.Adapt TE Recovery ,Validate ok 2.Correct Display Power Down -Validate ok |  | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-30 | 4.EVT | 4.Audio | 5.2 BB Test | S2 | Closed | [S2]Issue:Receiver TDD Noise failed. Clue: 1.Codec affected, RootCause:1.Mic Side Tone Coupling Solution:1.Proposal:Resolve Mic up link Tdd Issue 2.Side Tone Coefficient Adjust |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-24 | 4.EVT | 6.Display/Touch | 5.4 ALT | S2 | Closed | [S2]Issue:1/4 after EVT MXC06 200times WH110432 D4,Display can not work 2/8 after EVT MXC06 200times WH110726 D3,D4 ,Display can not work 1/1 after EVT MXC06 200times WH109891 D3,Display can not work Root Cause:1. Disp_Sctrl Net open , PCB issue 2. Shielding Case Corner Strain Solution:1. Avoid Layer 2 Routing 2.Solder Mask Removed on corner | link | 芳梅 |  |  | 2.PCB
2018-10-24 | 4.EVT | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue:CH1 get stuck when wifi OFF Clue:1.Not occur when WIFI ON 2. Average value getting bigger gradually when WIFI off RootCause:1.CH1 not share the ANT with RF, and no capacitor to Gnd. so Gnd is independent from the system. Solution 1.CH1 add a 39PF capacitor to Gnd , RD evaluate ok, DVT1 validate. | here | 小熊 |  |  | 1.SCH
2018-10-22 | 4.EVT | 5.Camera | 5.1 Bring up | S3 | Closed | [s3]Issue:Rear & Front camera halt sometimes when preview Root Cause: Proposal:SW Issue.1. dvt1a sw OK |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-22 | 4.EVT | 3.Charging | 5.1 Bring up | S2 | Closed | [S2]Issue:Fuel Gauge,No Charging Current Detected Root Cause:1.Proposal:Current Register Mismatch - SW On-Going SW update display config file ,Solved. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-22 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue: 1 of 8 unit P sensor not found in QsensorTest after ALT WH110272 B1. Clue: 1. Change FPC, P sensor still not found 2. Updated software, P sensor still not found 3. P sensor Connector is soldered ok to the mainboard 4. Signal resistor test in P sensor connector on mainboard show normal 5. Test the connection between FPC connector and the bottom of mainboard Root Cause: 1.Why happened? SENS_I2C_SCL in inner layer crack under shielding case corner because of strain Solution: 1.PCB layout to change the force of BB shielding Same Root Cause with A+G fail after ALT，Closed | here | 小熊 |  |  | 2.PCB
2018-10-22 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue:1/8 unit A+G fail after ALT WH110272 B2 Root Cause:1.SPI_CLK in Layer 9 break 2.Shielding Case Corner Strain Solution: 1.Enhance Shielding Case on Bridge Corner ， DVT1B action According to DVT1A S1 result 2.Solder Open limitation - BB/RF/ME DVT1A Proposal 3.Adding Foam - ME DVT1A | here | 小熊 | 吉吉 |  | 2.PCB
2018-10-22 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]Issue:MIC TDD Noise -40dB >-71dB failed. Root Cause: 1.poor Cirrus Mic Anti-TDD , 1.1 Validate ACC+ Shielding Case pass; 1.2 Proposal:Estimate Knowles Mic. Exp: Interposer FPC Sampling to verify. 2.Near field power strength- Antenna 2.1 Proposal:validate Antena Energy Field Modification Solution: 1.Change to AAC Mic in DVT1A, AAC+3Walls Shielding Case 67dB@850MHz ，72dB@900MHz; Cirrus+3Walls Shielding Case 58dB@850MHz 2.Import Mic Shielding Case in DVT1A,Done | here | 院长 |  |  | 1.SCH
2018-10-22 | 4.EVT | 3.Charging | 5.3 EE DVT | S2 | Closed | [S3]Issue:1/4 units Surge Test Fail on 50V Clue: 1. no turn on，PMIC U2000 damaged，vbat leakage current 80mA，USB_IN leakage current 120mA 2. D500 damaged that had 110mA leakage current ， caused PMIC wasn't under protecting when surge test. 3. Surge test wouldn’t cause PTVS18VU1UPA damaged (After 400V, PTVS18VU1UPA was ok), so this D500 damaged may caused by other sources. 4. 4 pcs retest,all pass. Root Cause： D1 reused after edu16 OVP test，D500 damaged by OVP extreme test. NTF issue. Solution： NA Conclusion: NTF issue. | here | 林峰 |  |  | 6.No Change
2018-10-11 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | [S3]Issue: Charging current 1.3A sometimes which should be 3A , Clue： 1. USB on PC can not work when 1.3A charging 2.Connector USB to PC and power on ，it always ok（test 10+ times） Root Cause: 1.SW issue --on going haijian Solution： 1.Fixed by the latest SW version。 | here | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-11 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]Issue: front camera preview fixed on +6KV ESD CD on Receiver Deco Root Cause: 1. Receiver Deco Grounding problem ,Need further check with ME Solution 1.Receiver Deco Short to Metal Housing, RD Evaluate ok,DVT1 Validate Pass. | here | 浦喆 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-11 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]Issue: system reboot in camera preview mode on +6KV ESD CD on Rear Camera&Mods Connector&Deco Root Cause: 1.display te affected（solved by adding 2K Resistor） 2.LCM Grounding not good . Greatly improved by optimized GND. 3.Recovery not feasible Solution: 1.reserve 100pf cap on te and reset,Serial in 2K in TE -Verification ,Screen Freezed ocasionaly and recover after 2s. 2.LCD Grouding Design Optimization 3.Optimize Recovery,Shift DSI Read check to TE Check,RD Evaluate ok. | here | 吉吉 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-11 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: ALT WH10272 Loop1 Drop top side 2units B2(1),A4(1) P-sensor no function ， Clue：1.No Gromet on P-Sensor incase LCD impact. Root Cause:1 .temp ALT units（ME ALT for Display glue verification） No Gromet ，not match design Plan: not ture issue for BB . |  | 文亭 | 小熊 | RPA analysis report link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-10-11 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3]Issue: WH109872 DVT EDu04 Eval - Reverse Polarity fail Root Cause:1.Shotkey Diode Don't Reserved after 3902 Removed. Solution:1.Adding Shotkey Diode - Lab Unit Modification - on-going 2.BB internal Test pass by jump wire 3. the solution had been changed in 48M-V03, will test in DVT1 DVT1A Test pass ：WH111518 ，close | here | 林峰 |  |  | 3.BOM
2018-10-11 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: WH109891 MXc06 滚筒 D3 200次后 cannot not power on（可以开机有电流反应，初判主板导致无显示 ） Root Cause:Proposal 1.Display&Camera Signal in Layer3 around Screw Hole Open. 2.Can't dig further due to unit broken Solution:1.Re route affected signal to keep far away screw - Done Plan:-ME arrange EVT2 2 unit verification ,Monitor | link | 敏敏 | 文亭 |  | 2.PCB
2018-09-04 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S2 | Closed | [S2]Issue:Display Bringup not complete. ELVSS Keep -4.0V Root Cause:1.Proposal: PM6150A not correctly config Solution:1.SW Resolved. | here | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-09-04 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S2 | Closed | [S2]Issue:Display Bringup not complete. AVDD over voltage. Root Cause:1.PM6150A not correctly config , Solution:re configuration PM6150A,Verification Pass | here | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-09-04 | 4.EVT | 8.Mods | 5.1 Bring up | S3 | Closed | [S3]Issue: NFC I2C probe fail Clue: 1.NFC I2C is OK when remove MAX3108, MAX3108’s RST pin is low. 2.MAX3108 VCC has no power supply.LDOEN pin is low. 3.External supply 2.5V to VCC and Pull LDOEN to high,NFC I2C work. Root Cause: 1.Max3108 Hold I2C Bus 2.No VCC power supply for Max3108, Solution:Initial Power Max3108 correctly | link | 邦邦 |  |  | 1.SCH
2018-09-04 | 4.EVT | 9.Memory | 5.1 Bring up | S3 | Closed | [S2]Issue: 1. EVT with umcp cannot download Root Cause:1: There is no LUN in Blank umcp, ufs needs to be provisioned before download. Solution:provision UFS First | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-07-31 | 2.PCL | 4.Audio | 1.4 Solution | NA | Closed | [na]If QUP config to UART,Stingray will have not enough AP SPI for Audio codec. Root Cause: SM6150 not enough AP SPI Solution: 1.use LPI SPI (LPI Qup2)for Audio codec Firmware download , Update 8/8 ,SW can’t realize bridge AP to ADSP. Drop 2.Using I2C instead of SPI to Codec,Update 8/8:need 6.8S loading AOV code.Drop 3.QUP Config to SPI instead of UART. Update 8/8:Mainstream Solution. Plan:Closed. | Link | 院长 | 文亭 |  | 6.No Change
2018-08-31 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S2]Issue: EVT SCH&PCB design battery connector with 5CA9A6MXRG ,but the correct one should be 28014040001 Root Cause: Component Team Not align with ME Team,In-consistence between the PartNumber Solution:1. Carding the Component Selection Flow During Component&ME , Closed. | Here | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-09-04 | 4.EVT | 9.Memory | 5.1 Bring up | S3 | Closed | Issue2:Phone enter 9008(EDL) after download images. QC case number: 03648171 Root Cause:Download issue, miss some download file. Solution:Use moto baseline download tool. | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-08-27 | 4.EVT | 7.Sensor | 5.1 Bring up | S3 | Closed | [S2]Issue:I2C fail to read again sometimes (would happen in 1 hours ,sometimes just in 10 minutes ) Root Cause: SW I2C control issue. Detail need SW update Solution:1. QC feedback some Cord change link Plan： 1. 2 units Stress test 19 hours ok. 2. SW check how this change can solve the Issue | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-08-08 | 2.PCL | 1.Platform | 1.4 Solution | S3 | Closed | [S3]Issue:Not Enough Uart with Flow Control in AP for Mods APBA. RootCause:1.SM6150 AP QUP Limitation Solution:1.I2C Uart Bridge Using Max3108 ， update 8/28 SW Bringup on Demo Pass. 2.I2C Uart Bridge Using FPGA 3.USB Uart Bridge IC CP2102/FTD234 Plan:1.Manage in EVT bring up. Close | here | 邦邦 | 院长 |  | 1.SCH
2018-07-31 | 2.PCL | 8.Mods | 1.4 Solution | S3 | Closed | [s3]Issue:No SPI Port for Mods Root Cause: SM6150 not enough AP SPI Solution: add 1 Switch to solve it Action：Done. Already designed in Stingray and completed development. Update the design diagram here. | here | 邦邦 | 文亭 |  | 1.SCH
2018-05-07 | 1.Concept | 7.Sensor | 1.4 Solution | S3 | Closed | [S3]Risk:Als Design,No Feasible Place for Ambiant Light Sensor on Front Side. Root Cause:Full Display Solution:1.Place ALS on Edge ,2. turn to ALS under OLED ，under evaluation by SME team plan： 8/1 check use AVAGO9307 or AMS 3701 。 9/30 check if we can go with s2？ | here | 文亭 | 文亭 |  | 1.SCH
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [s2]Risk：Stingray P-sensor design ESD Risk Root Cause:P-sensor ESD Risk is high for the current Solution Solution: 1.Non-Conductive Grommet Around P-Sensor 2.Conductive Grommet Around P-Sensor- Update 0.3$,Further investigate Low Cost Conductive Grommet. 3.FPC Grounding Around P-Sensor 4.Folded Copper Shielding refer to Rio-M Plan: 1.Test Non-Conductive Grommet in EVT 2.Test Conductive Grommet In EVT EVT1 test ok ，close it | here | 吉吉 | 文亭 |  | 6.No Change
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S3]Risk:ESD May Damage USB-C on revised shorter metal shell Clarification:1.EVT Validate 2.Pin anti-ESD capability validate on shelby. Only D+/D- Pin have risk while other pins have good ESD durability. Solution:1.Keep Shelby Solution on D+/D- Protection Plan:1.Keep Shelby Solution ,EVT Monitor,Closed. | here | 吉吉 |  |  | 6.No Change
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S3]Risk:ESD May Damage Mods Pin Clarification:1.EVT Validate 2.ESD failure mode analysis Plan:1.Bettery Layout Protection 2.Better TVS with big capacitor and lower clamp voltage | here | 吉吉 |  |  | 6.No Change
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S2]Risk:ESD May Damage Speaker Audio Amp and cause system halt. Clarification:1.EVT Validate 2.ESD failure mode analysis Solution：Add Varistor near the SPK pad and double check if the TVS due to this issue Plan:1. Add varistor near the SPK pad and test the ESD | here | 吉吉 |  |  | 6.No Change
2018-05-07 | 1.Concept | 7.Sensor | 1.4 Solution | S3 | Closed | [S3]Issue:Proximity Design,No Feasible Place for P-Sensor Clue:Stowed Mode RootCause:Full Display Lead to No Space for P/ALS Sensor Solution:1.ME Manage to place it on Front Camera Conclusion:1.Turn to NUD Mangement，Closed | here | 文亭 |  |  | 6.No Change
2018-05-07 | 1.Concept | 1.Platform | 1.4 Solution | NA | Closed | [S1]Risk:Buttonless Design are not mature enough to introduce to Product | here | 嘉琨 |  |  | 6.No Change
2018-04-19 | 1.Concept | 1.Platform | 1.4 Solution | S3 | Closed | [S2->S3] Issue:1.Qualcomm feedback SM6150 Reference Design on 8/13, Update 8/17：Qualcomm Upload on Create Point on 8/17 Root Cause：1.Qualcomm Design Spec Release not follow Schedule, Solution：1.Follow up Qualcomm | here | 文亭 |  |  | 6.No Change
2018-04-20 | 1.Concept | 2.Power | 3.Review/Simulation | NA | Closed | [S2]Chiron BSP 24.2Hours/Latam UMTS, 21.6Hours in China UMTS on 7.0 User Mode on 3300mah. Solution:1.3600 maH now | here | 李果 |  |  | 6.No Change
2018-07-02 | 1.Concept | 12.EMC | 5.5 Certification | S2 | Closed | [S2]Issue:CE FM mode CS/RS (EN55035) test Fail Clue: Root Cause:FM IC demodulate the AM radio Solution:1. Conclusion:Sportan cancel the test item.Closed | here | 吉吉 |  |  | 6.No Change
2018-07-02 | 1.Concept | 12.EMC | 1.4 Solution | S3 | Closed | [S3]Risk:CE ESD Usb Link Fail Verification:on-going EVT pretess ok | here | 吉吉 |  |  | 6.No Change
2018-07-10 | 1.Concept | 8.Mods | 1.4 Solution | S2 | Closed | [S2]Issue: SM6150 Can’t support Mods Projector on Original Architecture Root Cause: 1.SM6150 Only Deploy 1 X4 Lane DSI Solution: 1.Lattice ICE FPGA DP ->My DP Convert Solution - Will Verify on 10/20 if SW ready. 2.Discrete Solution without Lattice ICE,Principle Verified on Demo Pass.Reserve Solution in EVB. -Will Verify on 10/20 if SW ready | here | 邦邦 |  |  | 1.SCH
2018-07-12 | 1.Concept | 2.Power | 3.Review/Simulation | S3 | Closed | [S3]Issue:BSP 7.0 Simulation Shows 23.9Hrs on Latam UMTS Root Cause: 1.No Space on Y+ for Battery because of Camera 2.No Space on Y- for battery because of Mods&CPU+Memory Solution: Narrow down PCB Bridge and expand battery on X+ by 1.3mm 1.Put some low speed Signal on bottom Surface Layer 2.Attach 1 Copper on this layer to shield Value: Benefit 70mA increase up to 3570mah,Cost up $0.04. BSP on Target achieve all day life. | here | 李果 |  |  | 6.No Change

## Sofia NA (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Design Element | Design Element 2 | Department
2020-02-26 | B.PVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3] TOF&NFC do not work sometimes on sofia+ B2B SKU Clue: 1. TOF&NFC share same I2C ，and SCL or SDA hold LOW when issue reproduce 2. issue happen after NFC reset (found by our reproduce)，also found on normal read operation（SW Reproduce） 3. Racer have Same issue . Root cause: 1. NFC FW Issue Solution: 1. Correct NFC FW | link | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-12-03 | 5.DVT1 | 7.Sensor | 6.Issue | NA | NA | [S2] DVT1B Sofia ALS-PS wheel test fail sometimes IKSWQ-39589 IKSWQ-39294 Clue: 1. 90 degree report 103 (device 3 ) & 241 (device 2)while it should be 5000+ Root cause: 1. Solution: 1. | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-11-15 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]PVT sofia NA Display missing pixels,unable to recover. Clue: 1. -15kV AD on FPS area, with display panel facing coupling plate. 2. Not appeared in all of sofia na and sofia plus EDU03 tests before. fial rate 1/68. 3. There is display issue in sofia row, with the same phenomenon. Root cause: 1. maybe display driver IC damaged, waiting founder FA. Monitor PVT 2nd source test |  | 吉吉 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-10-31 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S2] DVT2 Sofia NA ALS-PS no function after ESD ESU03 Clue:1. sensor damaged. INT pin =26R &500R VS normal xMR 2.check with ME the Glue width maybe different with Normal one 3. Root cause: 1. proposal :Glue width is too small . --ME is checking with Factory Solution: 1. proposal :improve the Glue width ,change to the width similar to DVT1 or sofia plus PVT: 2nd source pass. close | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-10-31 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH120786 DVT2 (2 fail/6 units), WH121714(2 fail/4 units) PVT Sofia Plus unit cannot power on after ESD @15KV Air Clue:1.Unit always enter 9008 mode; cannot recover . 2. According to UART log, boot config error 3.CPU bootconfig pins （SPK & REC Smart PA INT 2 pins） Diode parameter abnormal （Fail unit 0.4V VS normal unit 0.6~0.7V ） 4. CPU GPIO_118 short to GND，TOF_RST . checked EDU03 D1&D2 ,same fail. Root cause: 1. Boot Fail due to boot config error that because of CPU GPIO_118(TOF_RST_N) short to GND 2.1 Camera lens deposit is conductive in DVT2, making ESD reach TOF IC unit. exp:Change conductive deposit to non-conductive in PVT,fail. 2.2 Gap exit between lens and lens holder. exp:Red-dye immersion observed. conclusion: The interference between TOF rubber and camera lens is 0.27mm. The Elastic force of TOF rubber is greater than adhesion of clue. 3.1 anti-esd of Camera lens Double-sided adhesive become weak after temperature shock exp:RD Evaluate 2 units. Result:No issue before temp shock but both have issue after temp shock. exp: TCC Evaluate 3 units(factory pressure maintaining units). Result:No issue before temp shock but 1 unit has issue after temp shock. exp:Change adhesive with good temperature performance(PET->PSA).fail. exp:expand lens double- sided adhesive,0.6mm->0.9mm, Result:Rd evaluate fail exp:PET->PSA ; widen adhesive 0.6->0.9mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm , RD evaluate pass. TCC test pass 6/6 units. 2 units ESD fail before thermal shock. These 2 units have been tested MDu52(Environmental / Chemical Susceptibility), which influenced the clue performance. 3.2 Speculation: TOF Rubber too hard? Exp:PET; widen adhesive 0.6->1.1mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm; 60' hardness;RD evaluate pass. camera lens lift up 0.01~0.02mm. Exp:PET; widen adhesive 0.6->1.1mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm; 50' hardness(softer); RD evaluate pass. camera lens does not lift up. Solution: 1. -adhesive change from PET to PSA ； -widen Camera lens double -sided adhesive , 0.6mm->0.9mm； -and thickness change from 0.15mm to 0.2mm； TCC test pass 6/6 units. 2. -PET adhesive(lower cost than PSA)-Lower Cost -widen Camera lens double -sided adhesive , 0.6mm->1.1mm； -thickness change from 0.15mm to 0.2mm； -reduce hardness of TOF rubber, 60 -> 50, running change. RD test pass 4/4 units.(45min 75'C thermal shock, 10 times). TCC test pass, 4 1st sourcing units, 4 2nd sourcing units. | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-10-23 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]sofia some 3rd part charger can not charge(not standard QC 2.0 or QC 3.0 Charger) Clue: 1. waveform check charger output 12V in QC3.0 Authentication process （which should be 5V in normal charger). 2. External OVP open when Vbus get 10.3V ，and the charge drop(PMIC can not get the OVP information) 3. no problem on moto standard QC 2.0 & QC 3.0 charger Root Cause: this 3rd part charger is not standard QC 2.0 or QC 3.0 Charger.it output 12V when phone is doing QC3.0 authentication . Solution: 1. HW：External OVP change to 13.2V from 10.3V (PMIC can get OVP information when Vbus go above 10V.and it can protect >16V Vbus too,which would make PMIC damaged.). HW solution Import from Sofia+ DVT2 and sofia PVT . 2. SW : workaround ：when PMIC get OVP ,SW retry with no QC2.0 or 3.0 support . and charger will out 5V all the time. (New SW can work with New HW units) Other projects impact : it impact platforms with PMI632 or other low OVP PMIC which require external OVP IC. have synced the HW change to Sofia ROW yet . | link | 文亭 |  |  | 4.Parameter
2019-10-23 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: After +8KV air discharge at zone16 (Aging 10 ), fingerprint reader no function,recovered after reboot. Clue: Root cause: Egis sensor dead-loop after ESD. Solution:1. Enhance GND; PVT TCC test Pass |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-10-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH119393 EDU03 In final EIS test, LTE band5,band12,band13 div antenna degradation exceeds 3db, and TIS value is also out of spec. Root cause: 1. ANT DIV tuner damaged. 2. Layout is not the best design. Varistor + 0ohm. DVT2 optimize and monitor. 3. Inlay clue shifts down 0.15mm, making DIV ANT outside. DVT2 optimize and monitor. 4. If still fail in DVT2, change back to TVS128. Low risk No change ,monitor PVT test |  | 吉吉 |  |  | 6.No Change
2019-10-12 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | "[S3]Issue: DVT2 bulit CQA test SX9338 function abnormal: CH0/2 always triggers, CH1 never triggers Clue: 1. Factory SW works well for SX9338 units in Xiamen 2. Function ok when change back to SX9331. 3. Samples for factory and Xiamen download firmware in different way 4. Recheck firmware of SX9338 sent to factory 5. Root Cause: 1. Firmware download wrong because of upgrade fixture in Semtech work abnormally. 2. Solution: 1. Replace the wrong ones to right SX9338 " |  |  |  |  | 6.No Change
2019-10-10 | 5.DVT1 | 2.Power | 5.3 EE DVT | S3 | NA | [S3]Issue: DVT EDu13 - Battery Performance at Various Temperature WH119426 D1 auto power off after 1 hour -10C discharging(run Auto Cycle), the voltage is 3.66V Clue: The discharge time is judged according to the log time, but it fails due to the dislocation of the log time. The actual battery capacity is reasonable. Root Cause: The log time of the software is out of place, which causes the result to fail. Solution: Retest result pass |  | 李果 |  |  | 6.No Change
2019-10-10 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | NA | "[S2]Issue: WH119836 ALT light sensor and P-sensor no function B3( 5） Clue: Root Cause: P-Sensor fall off Solution: ME own further analysis |  | 小熊 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-10-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH119393 EDU03 light sensor and P-sensor no function,unable to recover.D3( +8KV air Zone10, left side of unit) Clue: 1. Not reproducible on other 2 units, with 100 times 15kV AD on zone10 and in calling mode. 2. P/L sensor shares the same voltage source with SAR sensor. Sar sensor functions well. 3. P/L sensor shares the same I2C wires with M sensor and A+G sensor. M sensor and A+G sensor funcion well. 4. No Relative Issue on Previous 6 Edu03 5. Re-Work P-Sensor Sample? Root Cause: 1.P/L sensor fail after cross validation. MB is well funtioning. 2. P/L sensor INT resistence is 98 ohm. Normal one's is infinity. 3.Speculation:Re-worked P/ALS-Sensor?- ESD protection device damage in INT pin Solution: |  | 吉吉 | 小熊 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-29 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]WH119444 Sofia NA SS DVT1B ALT B3(4) Weak vibration. WH119693 sofia +AT&T D8(400) Clue: 1. Fail follow PCBA 2. waveform check it should be inductor PL6502 issue 3. open shielding case and found inductor is glued on shielding case inside. and PL6502 broken Root Cause: Underfill operation problem cause inductor PL6502 broken suggest :ME check glue with BB Solution: 1. change Underfill operation to avoid glue on Inductor PL6502 | link | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-29 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: WH119444 Sofia NA SS DVT1B ALT A5(4) A5:Drop bottom left corner Volume + button no function. Clue: 1. check Sidekey FPC , press V- ,net open to gnd. FPC issue 2.FPC Wire crack (check finger to SMT pad open) 3. 2nd source Helitai FPC. Root Cause: 1. ME own further analysis Solution: 1. ME own further analysis |  | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-29 | 5.DVT1 | 10.USB-C | 5.4 ALT | S3 | Closed | [S3]Issue: WH119444 Sofia NA SS DVT1B ALT B3:After TH/TC USB charging is normal, but fail to connect computer. Clue: 1. can not power on when get the phone . 2.plug in USB and press V- can go into Fastboot mode. But not usb port found. 3. Failure follow FPCA . FPCA issue 4.2nd source Helitai FPC. Root Cause: 1. ME own further analysis,monitor Solution: 1. ME own further analysis,monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-18 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia NA cannot read SIM after DVT1B Tumble Test WH119323 D5(275) Clue: 1. SIM_RESET wire broken.(remove CPU) Root Cause: 1.Inner Layer PCB Delaminated 2.1 Proposal :RF Shielding case pseudo soldering 2.2 High PCB Strain on Shielding Corner. Solution: 1. Proposal : Shielding case SMT improve--SMT Engineer checked SMT is ok. No need change. 2. ME change cpu thermal copper to thermal grease to reduce PCB Strain .monitor test(sofia+ DVT1B )---ME 3. change USIM1_reset wire width to 0.15mm from 0.05 mm in DVT2 V05 PCB--BB-done | link | 李果 | 文亭 |  | 2.PCB | #REF!
2019-09-25 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue:Sofia + NA FPS no function after DVT1B ALT WH119628，A2(5),A5(5) Sofia NA FPS no function after DVT1B ATT Drop WH119363，D10(54) Clue: 1. issue unit & good FPS module, FPS no function; issue FPS module & good unit, normal FPS function. Bad MB! 2. A2 :SPI_CS open to GND, A5:SPI_CS pin R is not stable. D10: SPI_CS open to GND 3.Remove CPU and check :A5 ,SPI_CS wire crack 4.Cross section : BB shielding case right bottom corn :A2 &D10 Via 2-4 crack ;A5 Layer 2 wire crack ; Root Cause: 1.Inner Layer PCB Delaminated 2.High PCB Strain on Shielding Corner. Solution: 1.Remove sensitive line under the shielding corner on DVT2 PCB V05.-done | link | 文亭 | 李果 |  | 2.PCB
2019-09-18 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia NA FPS no function after DVT1B Tumble Test WH119323 D7(150)，WH119323 D5（300） Clue: 1. issue unit & good FPS module, FPS no function; issue FPS module & good unit, nomal FPS function. Bad MB! 2. D7 MISO,MOSI,INT, 3 signal pins on MB BTB connector, no diode character and open to GND. Route broken? 3. D5 MISO, 1 signal pin on MB BTB connector, no diode character and open to GND. 4. remove CPU and check if wires are broken?--- wire broken. Root Cause: 1.Inner Layer PCB Delaminated 2.High PCB Strain on Shielding Corner. Solution: 1.Remove sensitive line under the shielding corner on DVT2 PCB V05. -done | link | 吉吉 | 文亭 |  | 2.PCB
2019-09-17 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ DVT1 DVT MXc03 - Power Cuts Impact Test ,WH118750 D2 , WH118615 D2 ,after right 2500 times:Gyroscope sensor fails Parametric test Clue: 1.WH118750 D2 Gyroscope-sensor channal 0&1 ok , channal dont change. 2. Sofia NA no such failure found so far. Root cause: 1.IC Broken Exp1.1 change a A+G on ok PCBA to WH118750 D2 ,D2 ok . Exp1.2 " Fail IC " on ok PCBA ，fail . So failure follow " Fail IC " 2.1 Speculation:Outer Force Crack? Z Axis not enough air gap 0.17mm? Exp2.1 check if there is some crack on fail IC Result:No Crack Observed , Conclusion:na Exp2.2 Adding more air gap on Z axis. and retest. - guilin/dengling ,date :09/23 2.2 Speculation: IC Issue? sent " Fail IC " to Vendor for further analysis---shengnan Result:No Crack Observed , Conclusion:na Solution: 1. |  | 小熊 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-17 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: Sofia DVT1 build P-sensor some units CT too high ,data? 2/ ? DVT1A, 4/? DVT1B ?/? DVT2 Clue: 1. Re Assembly Display,Disapear 2. Is it a real Issue? Check 6Sigma Distrubution Range.-Xiong 3. Some DVT2B units with high CT really has problem, such as P sensor shielded by glue, FPC gloden finger hided Root cause: 1. speculation: exp3.1: CT high limits units were real abnormal. exp3.2: collect all the test data, limits adjust. Solution: 1. it's not a real issue, CT distribution is a range, and should be adjusted according to the collected data. 2. Real abnormal ones should be reworked. | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-06 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: Sofia+ 2 pcs stylus stylus detected as plug out when full insertion during CQA. Clue: fail follow FPC Root cause:1pcs FPC ，no hall IC on FPC ，FPC Vendor hongxin issue . the other one check :seems same issue now Solution:FPC Vendor hongxin fix this issue |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-06 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [S3]Issue: Sofia+ 3 pcs/50pcs stylus detected as plug out when full insertion during CQA. Clue: 1. issue follow stylus 2. X-ray show magnet distance deviation 0.16MM /-0.15MM compare with normal one 3. 7mm insertion detect, 5mm normally Root cause: 1. speculation: stylus torllerance beyong spec? exp1.1: measure defect unit, result:by 9/9 conclusion:TBD 2. speculation: angular magnet assembly ME own 3. speculation: magnet field strength over spec exp3.1: compare Teslameter reading between normal and defect Solution: 1.WorkAround(9/6 ME Change Dead line),Y+ add more 1.5mm Spacing, Now 2.81mm between Magnet & Hor。Need change Sidekey FPC,FPC Change Confirmed. |  | 小熊 | 艳红 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-09-04 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ unexpected auto power off after ESD(8kV CD) on camera deco. Clue: 1. Flash LED and TOF are high risk component, which are nearest with camera deco. 2. remove Flash spr, issue could still be reproduced. 3. remove TOF and reserve interposer, issue could not be reproduced. 4. Discharge on TOF I2C pins directly(4kV AD), issue could be reproduced, with same fail logs, while could not on RST/INT. Root cause: 1. Camera deco discharge on TOF unit, causing I2C interferred Exp1.1:Adding TVS on I2C,Pass. Exp1.2:change TVS to 18pF or 33pF cap, fail Exp1.3:Series in Resistor 100R, DVT2 Verify Solution :1.Add 2 TVS on I2C ,04B PCB . pass 2.Remove Conductive Camera Deco |  | 吉吉 |  |  | 1.SCH
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118735) :Unable to power on A5(1),B2(1),B3(1) A5,B2,B3:drop back side. Root cause: 1.PMIC Crack，all of 3. Solution:Feedback to ME |  | 李果 |  |  | 2.PCB
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118493) :Unable to power on.A5(4) (Unexpected auto power off first A5:drop back side ,and then after drop right side,can not power on) Root cause: Solder Crack Solution:Feedback to ME，ME Follow |  | 李果 |  |  | 2.PCB
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118794) :Unable to power on.B1(2) Root cause: 1.Pmic Crack Vertically Solution:Feedback to ME，ME Follow |  | 李果 |  |  | 2.PCB
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA TMO drop(WH118494) FVCT11 Sofia NA:Unable to power on.D10(28) Root cause: 1. PMIC Crack Solution:ME Follow Action: |  | 李果 |  |  | 2.PCB
2019-08-31 | 5.DVT1 | 8.PCB | 1.4 Solution | S3 | Closed | [s3] why sofia na using 3+4+3 PCB Layers while sofia row using 2+6+2 which lead to cost up 0.4$-0.5$? clue:Sofia NA PCB design is compatible with Sofia+ NA/row clue:NSMD on Memory and CPU in Sofia Row RootCause:1) PI/SI Simulation not Pass 2)SMD |  | 川叔 |  |  | 6.No Change
2019-08-31 | 5.DVT1 | 8.PCB | 1.4 Solution | S3 | Closed | [S3] Sofia NA 54 Pin VS Sofia Row 40 Pin Root Cause:1.FM+Audio Jack 2.1ME : Ensure Audio Second SPKer on top 2.2 Proposal:PCB Compact Design 3. Sofia Row Reference Sofa NA ,Have some Improvement later. Solution: 0.006$ |  | 李果 |  |  | 6.No Change
20190830 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+Unable to power on- WH118591, B3(5)"B3:after shaker back side." Clue: 1. AVDD of PM6125 is reducing,off current is 0.13mA 2.Press PM6125 ,AVD hold at 1.8V ,and can power on Root cause: 1. PM6125 solder crack 2. ME stress to high on PM6125 Solution : 1. ME use thermal Grease(Old solution is 9X11) on CPU to reduce stress on PM6125 2. Backup : add underfill on PM6125 |  | 敏敏 |  |  | 2.PCB
20190830 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ Unexpected auto power cycle on- WH118591, A3(4),B1(4),B3(5)"A3:drop back side.B1:drop right side.B3:after shaker back side." Clue:1.check with log，shows XVDD_SHUT down，maybe battery is absence or VBAT or B_PLUS short to GND 2.Press all shield case of PCBA with great strength ,not reproduce auto power cycle on 3.Drop the phone from 1.5m height for 20 times,not reproduce auto power cycle on 4.No issue found from DVT1B Root cause: 1.Speculation: Solder Crack Exp1.1:Red-Dye PMIC , Result:No issue found on PM6125 Solution:1. No reproduce . severity low . close |  | 敏敏 | 艳红 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20190815 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [S3]Issue: Sofia+ headset abnoraml when used 02b sub board Clue:1. The mic which striked form sub board is ok 2. The mic hold on the pcb is Root cause: proposal 1 ,ME design no buffer with Audio BOX in EVT causing D501 crack Solution:1. DVT1 ME check gap between Audio BOX and D501 is ok. Action:TCC resubmit 2 D501 ok units double check ----1A pass ，2A fail and D501 damaged . |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20190815 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [S3]Issue: Soifa+ uplink no signal on headset mode used 02b sub board Clue: The mic which tear down from board is ok. Root cause: The mic hold on the 02b sub pcb is blocked off, PCB vender process error. | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: EVT ESD Sofia NA(WH117724) 1）didn't test front side since easy to auto power off while testing it except display area 2）unexpected auto power off：D4(+8KV Air Zone16） Root cause: 1. JTAG is interfered by ESD. In detail, a loop made up of JTAG wire on Layer 9 and Layer 2 is interfered. Exp1.1:Cut JTAG Wire in Layer9 and Test. Result:No Issue. Conclusion:R1 Confirmed. Solution: 1. remove JTAG in Sofia+ DVT1A BR37327, monitor in TCC test. Test pass | Link | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-26 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: TP no function after ESD. Clue: 1. +8kV AD on TP IC area, and -15kV AD on FPS area, with TP facing down. 2. NO INT signal to AP when touching. SPI is well functioning. Root cause: 1. TP enter big palm mode, and filtering any input outside. Solution: Updating TP firmware to V06. Verify ok. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-06 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3]Issue: Edu04 Reverse Polarity Test Fail in EVT WH117718 Clue:1. fail units D501 crack 2.RD units test pass Root cause: proposal 1 ,ME design no buffer with Audio BOX in EVT causing D501 crack Solution:1. DVT1 ME check gap between Audio BOX and D501 is ok. Action:TCC resubmit 2 D501 ok units double check ----1A pass ，2A fail and D501 damaged . | link | 林峰 | 文亭 |  | 6.No Change
2020-06-18 | D.SHIP | 5.Camera | 6.Issue | S3 | Closed | [S2]Issue: can not open flash led during test in the factory sometimes Clue:1. when the issue happens, need to take off the battery. Root , power off b no help 2. Usb_in_mid voltage is 5V ok (VDD_flash),but Flash_led1 0V，no output Root cause: 1. proposal: Sw check the logs 6/21 Exp: SW update ,Result: No SW error find ,Conclusion: May hw issue 2. proposal: PMI632 SW or HW issue ,need Qualcomm support 6/23 Exp: SW update ,Result: 0xd308 shows OVLO Conclusion: May usb-in_mid >5.5V 3. proposal: check usb_in_mid voltage 6/23 Exp: SW update ,Result: max 5.1V Conclusion: may Pmi632 mis-trigger 4. proposal: modify OVLO threshold to 6V 6/24 Exp: Flash ok ,Result: flash led function ok Conclusion: internal comparator mis-trigger 5. proposal: adb shipmode to cut off B_plus ，try to repair NG phone 6/28 Exp: can fix the issue ,Result: no help Conclusion: may PMI632 Vbat circuit error 6. proposal: May PMI632 Vdd_Gen issue which leads to VIB & flash no function ,try to check sleep leakage 7/3 Exp: ,Result: 1 poweroff leakage 103mA，1 poweroff leakage104mA Conclusion:PMIC VBAT current leakage 103mA,Qualcomm make sure it's VDD_Gen issue Solution: 1. 产线操作方法管控降低不良率： 组装电池完成后，扣上电池连接器，然后完全拔掉，过1s后，再重新扣合上电池连接器 昨天产线实验数据： BE17线Sofia+ 1750Pcs，不良2Pcs，F/R:0.11% BE02线 sofia na， 1000pcs，不良0Pcs，F/R: 0% 从数据上看有挺大的改善。 2. 简化不良机修复方案： 不良机可以通过放电到自动关机后，再放置2小时，使电池过放保护，达到VBAT断电，之后再充电，开机。这种方案不用拆机，减少人力和物料消耗。 怀玉这边有安排试了 7台不良机如上操作，闪光灯可以恢复正常。 短期方案如上，请车间从成本和人力上选择最合适的方案，建议是2种方案搭配用。谢谢了。 | LINK | 芳梅 | 怀玉
2019-07-29 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S2]Issue: Unexpected auto power off- Sofia+(WH117750）B3(1) Clue:1. It can be turned on normally.but Display abnormal 2. The log shows can't read the ID of display, and advise me to update SW Root cause: 1. proposal: update SW to the new version Exp:SW update ,Result:OK ,Conclusion:Maybe SW issue Solution: SW ,Closed | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
20190830 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia auto power power off 1 time , WH118417 D4,D10 （TMO Drop） ，top side drop Clue:1. Can not reproduce Root cause: Solution:1. Action: |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-29 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: Unable to power on-WH117715 (sofia na) A6（4） post shaker inspection. IKSWQ-4345 Clue:1. always Auto power cycle ,check by chenwt 8/1 .SW checking log (power about 28S and then power cycle) Root cause: 1.Speculation modem or wifi block problem EXP1: SW erase modem and can power up 100+s ,and then power cycle . It should modem block problem 2 Speculation:Solder Crack. Exp2. Red-Dye done ,but no issue found .PCBA damaged. Solution: Action follow DVT1A ALT . DVT1A ALT no such issue found | link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-08-01 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue: Loudspeaker noisy. Sofia Na EVT ALT WH117715 ,B1(1) B1(1)： Root cause: 1.Audio AMP Boost Broken(because of damaged boost inductor). 2.Boost Inductor laminated duo to partially glue between inductor surface and shielding case in drop test. Solution: 1.Feedback to ME to Check Glue Process. done B2(1)： Root cause: 1.Audio AMP Boost Broken(because of damaged boost inductor). 2.Boost Inductor laminated duo to partially glue between inductor surface and shielding case in drop test. Solution: 1.Feedback to ME to Check Glue Process. done | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3] Issue1: Front & rear main camera no image (Display Blank,unstable) ALT WH117715B1(3),B2(4) ,A1(5) Issue2: Front & rear main camera no image (Display Blank,unstable) ALT WH117750(sofia+)：A2(4) after drop Clue:B1:(N2SR010084) ,A1:(N2SR010083),A2:(N2PZ080020),B2: Not in hand Clue: Front & rear main camera reuse a mipi switch U5000. Clue:Reproduce by Frozen U5000 Root cause: 1.Proposal:U5000- CSI2 MIPI Solder Crack/U5000 VREG_L12A Solder Crack EXP1.1: Reflow B1-U5000 ,can not reproduce by now. EXP1.2: Reflow A1-U5000 ,can not reproduce by now. Exp1.3:Cross Section Sofia+ A2 :F6 pin solder crack ,E6,A6 Partitial crack. Solution: 1. Sofia+ Glue U5000 ,Sofia NA TBD ,DVT2 no glue tracking 2.ME:Add Groove in Shielding Case---recheck WH18735,A4(5), U5000 solder crack . --solution2 can not solve Sofia+ issue. Sofia NA TBD ,waiting for DVT1B test | link | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: L-sensor no function after ALT EVT ALT Sofia NA(WH117715)，A1(5),B1(5) A1：Can not reproduce Clue: LCD module is tilted Root cause: Solution: B1：reproduce Clue: ALS can work, but reading data in Qsensortest is very small. The reading in office is only 10lux and the normal ones are 300lux. Root cause: ALS area is covered by rubber Solution: 1.ME confirm no LCD module tilted issue in DVT1A 2.ME Evaluating not use rubber |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: P-sensor no function after ALT EVT ALT Sofia NA(WH117715) ，B 3（5），B4（5） B3：Can not reproduce Action： TCC for red dye test,unit broken，close. B4： Can not reproduce Clue:LCD module is tilted(checked by ME Guilin) Root cause: Solution: 1.ME confirm no LCD module tilted issue in DVT1A |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3] Issue: rear main camera not work after EVT Tumble Test WH11717, D4 Clue: 1. Main Camera I2C resistor abnormal. Should be wire crack Rootcause： 1.rear Camera can't work duo to I2C_SCL crack in inner layer under shielding case corner because of pcb strain Solution： 1.Remove L9 wires in this area ,Sofia Plus DVT1A Verify 2.Change L9 wires in this area to Width no less than 0.3mm,Sofia Plus DVT1A Verify 3.Feedback to ME if any approach to reduce pcb strain，Done | link | 邦邦 | 艳红 |  | 2.PCB
2019-07-31 | 4.EVT | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3] Issue: wide& rear main camera not work after EVT Tumble Test WH11717, D5 Clue: 1. Main Camera I2C resistor abnormal. Should be wire crack Rootcause： 1.rear Camera can't work duo to I2C_SCL crack in inner layer under shielding case corner because of pcb strain Solution： 1.Proposal:Modify Layout ：remove L9 wires in this area ,by 8/5 2.Proposal:Modify Layout ：change L9 wires in this area to Width no less than 0.3mm,by 8/5 Duplicate with WH11717,D4,Closed | link | 邦邦 |  |  | 2.PCB
2019-07-31 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S2] Clue: Front & rear main camera reuse a mipi switch U5000. Root cause: 1.Proposal:U5000- CSI2 MIPI Solder Crack/U5000 VREG_L12A Solder Crack Action： Cross section will be done ，Plan TBD Solution: 1.Proposal:Glue U5000 2.Proposal:Reduce PCB Strain Duplicate of Issue1: Front & rear main camera no image (Display Blank,unstable) ALT WH117715B1(3),B2(4) ,A1(5),Merged &Closed | link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-31 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]7/31 TDD Noise Found in EVT Root Cause: 1.SPK Coil Couple by Electro Megnetic Interference Exp:Isolate and Loop Back SPK Coil P/N and Test . Result:Noise heard. Conclusion:R1 Confirmed. Exp:Move SPK out of Phone, and Observe .Result:No Noise . Conclusion:R1 Confirmed. 2.1 Long Distance from Battery GND to PA Exp:Modify GND Sink Point closed to PA. Result:Pass ;Conclusion:R2.2 Confirmed. 2.2 Proposal:GND around SPK Exp:Eliminate GND Around SPK , Cancel Due to R2.2 Solution: 1.Change GND Sink Point closed to PA.RD Validated Pass. Monitor TDD Test on Sofia Plus DVT1A Units. (V03a PCB) | Link | 院长 | 川叔 |  | 2.PCB
2019-07-30 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: EVB test , phone shoutdown when test ,face up ,Without charging Clue: 1.can not reproduce With charging 2.face down ok Root cause: ESD couple through Jtag connector with ground plan because a backhousing hole. EXP: cover this hole ,RD retest pass. Solution:DVT1A there will be not a hole above the Jtag . |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-29 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Unexpected auto power off-WH117750 (Sofia plus NA) ：B3(1),A4(2) Clue: https://idart.mot.com/browse/IKSWQ-3900 B3:drop right side. Units broken for TCC other test,can not try to reproduce. Clue:1.SW log check ：1 user power off found , but No useful log found.(very little log add in the SW now) Root cause:Proposal 1.SW issue Solution: 1.Waiting for Android Q SW and recheck in DVT1A A4:drop top side.Units broken for TCC other test,can not try to reproduce. Clue:1.SW log check ：1 user power off found , but No useful log found.(very little log add in the SW now) Root cause: Proposal 1.SW issue Solution:1.Waiting for Android Q SW and recheck in DVT1A |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-30 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: Unable to power on- WH117750(Sofia plus NA) A6(1),B6(1),A5(3)after drop Issue1：B6:drop left side. Root cause: 1.Internal Reference Voltage Regulator AVDD Abnormal which lead to unable power on 2.PM6125 Crack observed duo to PCB Strain Solution: 1.ME Follow Issue2：A5: drop Top side. N2PZ080004 can be power on, not reproduce 8/1 by chenwt Can't Reproduce. Issue3：A6:drop back side. Root cause: 1.PM6125 Crack duo to PCB Strain Solution: 1.ME Follow | link | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-26 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | [S3]Issue: EVT build sofiaNA found 4pcs Display abnormal ,failure follow Main PCBA Clue: 1. Blacklight Driver inductor Or Diode damaged (3pcs inductor ,1 pcs diode ) 2. Check Backlight circuit: 1).The inductor PL5300 1.1A typical, 1.3A max, The inductor choose is oK 2). sofia can't support display module hot-plug, if battery on , then plug display module, may lead LEDA(VBAT) short to GND, there will be a very big current, damage inductor or diode 3). poweron without display, the power VSP 5.5V /VSN -5.5V/VIO 1.8V/LEDA 24V etc are always on, then plug display module, more power signal may short .need SW to modify 4) Check Blacklight Driver setting : 5) LM3697 has OCP( set at 1 A (typical). it'a hardware action. But it's not useful for the short of Vout_LEDA to GND 6）LED String （LED_K1 /K2/K3）short Detection is not work , the short decection can't report active， need sw to check, it may occupy system resources 7. RD found 1pcs fail in assembly display module when unit power on . ---Longhai Root cause: 1. Proposal:Display Abnormal due to PL2500; PL5300&D5300 Damaged. 2.Proposal:Power Supply Grounding lead to big current 3.Proposal:Power Supply Grounding due to Hot-plug with battery Solution: 1 .Proposal:产线管控,拒绝带电插拔 ,Factory Informed. DVT1A Monitor 2.Proposal:SW update,shut off power supply to display, when without a display module.(DVT1A cost down display LDO , L9A can't close),SW Imported.DVT1A Monitor 3.Diode PMEG4005AESF 0.5A typical /0.71 max，Change the Diode to Rohm RB161QS-40， 1A typical. PMEG4005AESF 0.5A typical is not enough for HBM mode ,DVT1A Import and Monitor No more fail found ，close | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-24 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: Phone auto power off after ESD at rec deco Clue: 1. There are 3 parts that could be affected by rec deo second ESD: P sensor, LCD, receiver. 2. After removing P sensor, issue reproduced. 3. LCD recovery well fuctioned. 4. Receiver not GND to MB or middle frame. 5. Add conductive foam to enhance recevier GND, issue not reproduced. 6. This part of GND design is involved in EVB, but not be carried on in EVT. Root cause: Receiver not GND to MB or middle frame. Solution: Add conductive foam to enhance recevier GND. rework test ok . import in DVT1A monitor |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-22 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: P sensor no function(permanent) after ESD at rec deco Root cause: rec deco sencond discharge on P sensor IC Solution: Proposal 1: cut rec deco edge to keep away from P sensor IC; add discharge tip to LCD metal plate. Validate Pass. but will cost up too much . ME go with Proposal 2 Proposal 2:cut rec deco edge to keep away from P sensor IC; add discharge tip near LCD metal plate.(0.5mm shorter than proposal 1 ) Risk :can not rework ,just can retest in DVT1A . Test pass | Link | 吉吉 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-12 | 3.PEL | 11.Thermal | 5.2 BB Test | S3 | Closed | [S2]Issue: EVB ：When in charging mode ,Battery NTC report about 45 degree ，but Battery module real temp is 30 degree. Clue: Vbus OVP heat when charging , maybe impact NTC detect. Root Cause: 1. Vbus OVP heat when charging impact NTC temperature Solution: 1. change Vusb OVP IC to main board from DVT1 ----chenwt Battery NTC close to battery cell actual temperature. | Link | 林峰 | 文亭 |  | 1.SCH
2019-07-12 | 3.PEL | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue: There is noise on the board when Display on,EVB board+EVB Display module Clue:1. remove Display ,no noise. It maybe Bias current working noise. or Backlight driver noise. 2.The noise only exist when use 2p8s panel,when use 3p6s panel is ok. Root Cause: 2.SW setting is wrong for 2p8s panel:OVP set to 24V,which leads TI LM3697 output some noise (5Khz to 10+Khz ,not fixed) . (TI LM3697) . issue in EVB Display module , not real issue Solution: 1. No need to change , sofia display module is 3P6S , the voltage of LEDA is 18V , 24V OVP is ok waiting for an analysis link and then close---chang fangmei Done | LINK | 芳梅 | 院长 |  | 6.No Change
2019-07-02 | 2.PCL | 1.Platform | 1.4 Solution | S3 | Closed | [S3]Issue: Sofia NA Cost VS Sofia Row,8$ Gap. Passive,Dll 0.56$, Sensor Gap 0.1$,PCB Gap:1.77$ RootCause: Passive ,DLL Gap 0.56$ 1.1 Cap Sensor LDO, -0.0176$ 1.2 FPS LDO ,-0.0176$ 1.3 Cap Selection(BB), -0.087$ 1.3 Buck Boost ，-0.1$ 1.4 Total Gap left : 0.34$ 1.5 Proposal:RF Cap: 100pf , etc ? 1.6 Proposal:RF Bead , ? 1.7 Proposal: RF Cap Sensor Gap 0.1$ 2.1 M-Sensor & A+G , Same Solution ,0$ 2.2 Cap sensor: A96T346($0.25) vs SX9331($0.43) (Gap: +$0.18); 2.3 Psensor:MN58406($0.3)+26005($0.29) vs VCNL36866A($0.32) (Gap: -$0.27); Sensor Gap Should be -0.09$, GCM Issue PCB Gap: 3.1 Design Gap Proposal:PCB Mainboard 10层2阶 - -20% ， -0.3$ , Drop Due to NA+Row more Complexity 3.2.1 GCM Negociation Gap 3.2.2 Vendor Selection 3.1.Main PCB $1.13 $1.96 $0.83 3.1.1 Jack on MainBoard 3.1.2 27W Turbo 3.1.3 3.2 Main Flex $0.26 $0.71 $0.45 3.2.1 3.2.2 40 Pin VS 54 Pin ,1pin/1 cents 3.2.3 Same Vendor , Vendor Price . 3.2.4 3.3 Prox sensor FPCA $0.00 $0.25 $0.25 3.3.1 Need Confirm. 3.4 SIM/SD Flex VA $0.05 $0.00 -$0.05 3.4.1 3.5 Side Key FPC $0.00 $0.44 $0.44 3.6 PCBs AND FLEXES, OTHER $0.25 $0.09 -$0.16 Solution: | Link | 李果 | 小范 |  | 1.SCH
2019-06-26 | 3.PEL | 12.EMC | 5.1 Bring up | S3 | Closed | [S3]Issue: EVB SIM can not work: RootCause:1. No VSIM 2.NFC power supply design issue cause no Vsim output to SIM card Solution: 1.NFC change 2. Reserve 0R for Vsim because there maybe not NFC in some sku. (will be done by RF) |  | 李果 |  |  | 1.SCH
2019-06-26 | 3.PEL | 12.EMC | 3.Review/Simulation | S3 | Closed | [S2]Solution Risk: Doha DVT issue: GPIO97 config to INT function will cause CPU can not sleep . QC case：04068560 RootCause: QC SM6125 problem ,QC reply other Designer face the same problem , No solution From QC by 6/27 Solution: change AUD_DSP_IRQ_N From GPIO97 to GPIO 45 before Sofia NA EVT Gerber out. |  | 文亭 | 院长 | change link | 1.SCH
2019-06-26 | 3.PEL | 12.EMC | 3.Review/Simulation | S3 | Closed | [S3]Solution Risk: USB OVP 2 ball input and output , 3A charging current ok? Solution:check with Vendor ， the test data show it is ok . |  | 林峰 | 院长 |  | 6.No Change
2019-05-29 | 2.PCL | 4.Audio | 1.4 Solution | S2 | Closed | [S2]Design Risk: Nomad Uplink performance . Clue:Nomad=4.3 >4.0 , Test Pass. No Risk. RootCause: 1.Mic Uplink noise lead to nomand loss Exp1.1: Rioh test result 2.1 Audio Codec Ground and Earphone GND Voltage Level difference Exp2.1:RIO-H Nomad Failure Issue FuPan ， Result: 82nH Inductor connect to Noisy GND , Conclusion: Noisy Audio GND lead to fail. EXP2.2: A40 Grounding design check , Result:EarPhone GND loop back to Mainboard. Conclusion:Audio GND and Earphone GND should be the same voltage. 2.2 Proposal: TDD noise algorithm duo to high TDD Issue 2.3 Floor Noise due to Sub PCB design Solution: 1.Separate Audio Ground ,Validate Pass,No Risk. | link | 院长 | 文亭 |  | 6.No Change
2019-05-15 | 3.PEL | 9.Memory | 2.Design | S3 | Closed | [S3]Design Risk:Upper limitation and low margin in DDR Routing Impedance Clue:Micon 4+64 Pass Simulation Root Cause: 1.Impedance control can't be with good margin due to distance between layers. 2.Thickness Locked to 0.716mm duo to Cost Balance. Solution: 1.DDr Eye-Diagram to validate -BB/SW 2.QC SI Simulation -BB/QC 3.EVB H/L T Stress Test. - BB 4.QC Can Fine Tune 1p by SW DDR REG Fine tune. if failed. waiting for recheck and then close---Dongjiakun |  | 嘉琨 | 院长 |  | 6.No Change
2019-05-17 | 2.PCL | 2.Power | 1.4 Solution | S3 | Closed | [S2] Solution Issue: PM prefer Sofia NA BSP Target=72Hours@50th but currently Sofia BSP=56.1 @50th Root Cause: 1.BSP Output Solution: 1.PM Sync the Actual BSP. |  | 李果 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-29 | 2.PCL | 12.EMC | 1.4 Solution | S3 | Closed | [S2]Solution Risk: Pesnsor/REC Deco ESD RootCause: 1.Rec Deco Floating 2.P-sensor Closed to Deco Solution: 1.Proposal:Extend Rec Deco GND more close to Display Shielding Can. EVT Verify. EVT test fail ，new issue list，DVT1A go with reserved solution |  | 吉吉 | 李果 |  | 6.No Change
2019-05-17 | 2.PCL | 7.Sensor | 1.4 Solution | S2 | Closed | [S2]Solution Issue: Use I3C A+G that cost up 0.2$ Root Cause: 1.No SPI Interface support in SM6125 lead to use I3C 2.HIFI AR Core Require High Speed Data Bus. 3.Moto G Support HIFI AR Core Requirement to support Google App. Solution: 1.Keep I3C Design | Link | 小熊 | 李果 |  | 1.SCH
2019-05-17 | 2.PCL | 7.Sensor | 1.4 Solution | S3 | Closed | [S2]Solution Issue: Discrete P-Sensor Solution totally Cost up 0.5$ Root Cause: 1.Discrete P-Sensor Cost up 0.3$, CTP Cost up 0.2$ 2.Narrow Gap on the forehead suggest by ME&SME 3.Normal 3in1 P-Sensor Can't Fit. 4.FPC Can't Afford enough space. Solution: 1.Using Laser Hole through 2 Layers , Meet Requirment. |  | 小熊 | 李果 |  | 1.SCH
2019-05-17 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [S3] Issue: EVB build always enter 9008 mode Clue:9008 can blank flash ,but can not enter fastboot mode root cause: GPIO118 pull high to L9A ,cause the Boot mode incorrect. solution:1. DNP R5006 for EVB build -done 2. EVT sch delete R5006--done |  | 文亭 | 邦邦 | SCH change link | 1.SCH
[S3] 1.4 pin 版与2 pin 版的利用率 （方正使用2pin可以提高） 2.打孔的数量 3.贴片效率 4.打板的数量，华为4次，oppo 2次 ， 影响他的交付， 5.混搭大板和小板 5.阻抗线低于40um的，LDK，355D，射频要求45um以上，285.

## Nairobi (hidden)
Report date | Phase | Block | Source | Severity | Status |  | Doc | Owner | Assistant | Sheet | Change? | Department
2020-08-20 | D.SHIP | 1.Platform | 5.6 User Feedback | S3 | Closed | [S2]Issue:Game performance, Asphalt 9 high quality Display setting, FPS=22fps ,VS 30FPS of Redmi K30 Clue:1.CPU big core almost not work ,just Small core working. Vs Redmi K30 Big core working more. 2. GPU working with full Frequence and usage . Vs Redmi K30 not full frequence . 3.Display module resolution:Nairobi ：2520*1080；Racer 5G：2340*1080 ；Realme X50：2400x1080 ；Redmi K30 ： 2400x1080 suspect: 1. CPU block the performance exp1：lock CPU CLKto higest always ，no improvement 2.GPU get too much work to do and too heavy .can not work well exp2：change Display setting 2.1 Use Sofia Display , issue gone . 2.2 setting Nairobi display resolution to 1920*864 on SW , issue gone . Root cause：SW didnot set Display Physical size ,and then Game make too much loading to GPU ,lead to FPS drop. solution: Temp ：Set Display Physical size to 67*157mm in SW platform code , issue gone |  | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-28 | C.RAMP | 9.Memory | 5.6 User Feedback | S3 | Closed | [S3]Issue:Second Vendor Micron 6+64, TombStone Issue found on 1 DVT1 unit from DFer. clue: 1.Total 661 pcs produced in 3T , Plan on 7/20 shipping request 2K. Hynix is first vendor . 2.Memory FW 106 Root Cause: 1.UFS communication issue found through Log. Same symptom on Racer. 2.Micron confirm that FW 106 has one ufs timing compatible bug with QC SM7250(Though meet JEDEC）, fixed in FW 109 and verified workable. 2.1 Shift Back this unit from BJ for furthur FA. 2.2 SW judge the severity . 6/30 Solution:1:Using new FW 109 Memory in the following production . |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-22 | B.PVT | 7.Sensor | 4.Build | NA | NA | Issue: Build PROX_SENSOR_UNCOVERED_RADIO :CT too large ,over SPEC Clue: 1. CT OVER SPEC issue follow LDA module (front housing+p-sensor+CTP) 2. 1 unit component Vendor checked component is ok. Root Cause: suspect 1 : assembly issue. Solution ： | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-17 | 7.DVT2 | 11.Thermal | 5.5 Certification | NA | NA | Issue: Thermal ,RF power limited in certification. Clue: 1.High temp test fail （should be Thermal config limited RF power) Root Cause: Solution 1： |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-22 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | Issue:ESD，PVT ATT SKU WH127075 ，D2 1：The charging LED is always on after 15KV air discharge:1台 Zone 13 Clue: 1. Zone 13 ：face down ，upside 2. SOL_LED work sync with it Power input VREG_BOB. suspect PM7150L damaged Root Cause: PM7150L damaged . Solution ： ME follow the glue quantity between front rim and front housing |  | 文亭 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-22 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | Issue:ESD，PVT ATT SKU WH127075 2：unable to power on after 15KV air discharge：1台 Zone1 Clue: 1. a Root Cause: P-sensor power(L10A) abnormal impedance（ 660R） Solution ： ME follow the glue quantity between front rim and front housing |  | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-19 | 7.DVT2 | 4.Audio | 5.5 Certification | NA | Closed | Issue: VZW ,EN55035 ,CS fail Clue: Root Cause: Solution 1： change Volume. changed by adb and retest pass |  | 院长 | 李果 |  | 4.Parameter
2020-06-17 | 5.DVT1 | 7.Sensor | 5.5 Certification | NA | Closed | Issue: DVT1 AR Core certification fail: calibration fail. Clue: 1.calibration including camera & A+G sensor 2.A+G sensor should be Invensence (2nd source which only build in DVT1 unit) 3.Depth camera change in DVT1, the test phone are with old depth camera. Root Cause: Over limit, need calibration to decrease raw_data into threshold (Same as Racer) Solution ： Use adb command to calibrate A+G before AR Core test. | link | 小熊 | 邦邦 |  | 4.Parameter
2020-06-10 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: PVT EDu03【WH127058】 light and proximity sensor no function:D1(NNIE430147) (15KV, Zone1） Root Cause:P-sensor INT abnormal ，Component damaged Solution 1：ME follow the glue quantity ( 0.33mm->0.5mm) | LINK | 小熊 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-23 | 5.DVT1 | 9.Memory | 4.Build | NA | Closed | [s3] Issue:Factory rework Umcp &CPU ,PCBA go into 9008 dirrectly and can not download （3 pcs in 3pcs） clue:1.Blankflash tool log show UFS initial fail ;2.uMCP is KM5V8001DM-B622 （didnt rework other memory） 3. AB swap(uMCP )， fail follow uMCP; 4. rework 1unit with hynix MEMORY，not reproduce （ODYSSEY use） 5. non-secure phone，IFlash No Bonding with CPU and Memory ; 6.FW Status latest ;7.new ic ，while racer used too but not qualified Root Cause: -Why Memory Can't Download after Blank Flash? 1.1 Memory Damaged? Conclusion: Exp1.1: Failed Memory ReBalling and Welding back to Original Board and another new Board ; Result:Both Failed Exp1.2：Samsung FA ; Result：FW OK,User Data UECC Error, Redownloading and Aging Test Pass. Exp1.3 :Verify Issued Memory that sent back from Samsung; Result:Test Pass. 1.2 Welding Issue？Conclusion1.2:TBD Exp1.2.1 Cross Section,TBD; Exp1.2.2 Remove CPU,and Measure Impedence of each Memory Net on Failed Memory,TBD Exp1.2.3 X-Ray ;Result:No cross welding Exp1.2.5 Reballing Failure Unit and Reflow Oven,TBD 2.1 Over Temperature during Maintain Lead to Damage? Exp2.1 Check Temperature and Duration During Maintain if over Spec;Result: No Feasible Repairing Heating Temperature of Memory in industry. Exp2.2: Check IF Station Data,Result:No Issue Exp2.3:Flash Bootloader ;Result:Pass with Memory Issue reported Exp2.4.1:good unit,Heat and remove Shielding Case;Result:Failed. Exp2.4.2:Re-Flash and Boot Successfully.Welding Back Shielding Case,Result:Boot OK. Exp2.5:Good Unit.Heat and remove shielding Case,Result:OK Exp2.5.Heat Memory directly for 100°C-320°C@50~100°C Step @<30S ;Result:OK Solution:1.Heating Temerature Control , 320°C ，<30S 2.Factory Evaluate MVA increase 0.041RMB | link | 嘉琨 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-25 | 7.DVT2 | 11.Thermal | 5.2 BB Test | S3 | Closed | [Monitor]Risk:Nairobi Thermal on 5G Scenario Clue:Heat Feedback on WeChat Video Talk and Teams Meeting etc.when 5G working on both Downlink and UpLink,5W+.Over 45°C when long time used. Clue:Mdu30 Pass ,Except 5G Scenario duo to lack of 5G Environment in WuHan TCC. Potential Root Cause:1.No 5G Thermal Standard &Lack of 5G Environment in WuHan TCC 2.Raw Thermal Config without 5G mitigation Precaution Measure: 1.5G SW mitigation , Solution confirmed,fine tune done on 5/28,Monitor |  | 林峰 |  |  | 4.Parameter
2020-05-20 | 5.DVT1 | 6.Display/Touch | 4.Build | S3 | Closed | [Closed] Risk:liberty Backlight damaged issue Clue:DVT1-DVT2 no Issue feedback. Run in 100 units，No Issue. Clue:Exp: PVT Run in 1000 , Monitor 6/? Potential Root Cause: 1.Temperature,Over Heating on PM7150L or Switching Inductor? Exp:Run in on 50 °C and Low brightness/High Brightness Switch stress test, Result:No Issue 2.OVP &OCP when Mode Switching? Exp:Signal Measure,Result:OVP Set 38.5V,OCP 1.75A,Vsw=58V,0.5S@30V,Function Normal@several Times ,Will Keep More Stress Test. 3.4X5 Leds VS 3X6 Leds？ Exp:After 1,2, Than Verify 3X6 , Result:TBD 5/26 4. Isat of Inductor？ Exp:Nairobi Inductor 1.2A, Current Drain=0.8A@Full brightness of Display ,Result:Meet Requirement Cost: Murata 280% > Samsung 200% > MicroGate 100%(1.1 Cent) Precaution Measure:1.SW Import Soft Start both on Power on and Wake up , 2.Set OVP 20.5V,OCP 1.05A ,RD Verified OK RD Verified Pass. DVT&PVT&MP Run in 2595pcs ,CQA Verified Pass, No Risk & Closed. | LINK | 芳梅 |  | liberty tech review link | 6.No Change
2020-05-25 | 7.DVT2 | 10.USB-C | 5.6 User Feedback | NA | NA | [S3]issue: Nairobi Thunderbolt USB port detect fail issue(SM7250) 。 具体issue：Nairobi 5G项目，在部分电脑 雷电口可以识别USB， 部分电脑 雷电口不能识别USB。（目前测试 Lenovo 2台T470S ，还有1台T480电脑， 都有问题。 只有1台T490 电脑ok.） SW QC CR：Case Number 04621321 Clue: 1. SM7250平台的Racer 5G 同样的表现 2. SM7250平台竞品手机情况： realme X50 ，readme K30 ，发现同样fail的问题， 故障波形一致。 3.有台T480电脑（liuyc20的电脑）原来不能识别，更新电脑的雷电口驱动后可以识别。 Rootcause： SM7250 平台性 和 电脑 雷电口 的兼容性问题 solution: 待QC分析 | link | 文亭
2020-05-15 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [Monitor]Issue: Adaptive brightness mode，brightness shows 0%,screen flash sometime Clue： 1. Backlight current=(hal/4095)*CABC duty circle*25mA，brightness 0%,hal=19，Cabc duty=79% ,backlight flash. hal=19, backlight current= 0.0916mA/sink， hal=34, backlight current= 0.166mA/sink， 2.enable CABC(0x1D951=0x1), set 0x19D49=0x0c(PMIC Digital Accumulator bit-width selection14 bit to 15bit) and 0x1D952=0x0, set CABC=79%, hal19/34 ok , but Hal=29/48/67/72/91 backlight duty not stable, screen flash Root Cause:1.Limitation of PM7150L under Low driving current with CABC , Exp:find which parameter leads backlight flash : when backlight flash, cabc duty circle stable(test the waveform from display and use signal generator set CABC), hal value stable(adb log hal value per 10ms and adb set hal value ), but the backlight wled duty not stable ,it means the current changes。 CABC duty circle change to 96% or disable CABC ,backlight duty is stable hal=19/34. 2.CABC Compatibility Limitation of PM7150L? Exp:Check with QC, QC confirmed known issue on PM7150, Solution:1.Set 0x19D49=0x0c(PMIC Digital Accumulator bit-width selection14 bit to 15bit) and Disable CABC on Low brightness<=200, SW Work around ,Version effected | LINK | 芳梅 |  |  | 4.Parameter
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03[WH124614]Kernel panic;D3(15KV zone6） Clue：1.Cap-Sensor No Function 2.Duplicated Root Cause: 1.Cap sensor ATVS VR100 damaged duo to EOS . 2.Speculation:ATVS Rated Voltage Margin not enough Exp:Change a Stronger Part,DVT2 Imported and Test Pass. Solution ： VR100 change to LXES03AAA1-193(Rated Voltage: DC 4V,AC+/-25V ->DC 6.3V AC +/- 80V) , DVT2 Imported,DVT2 EDU03 WH125964 pass | link | 李果 | 小熊 |  | 3.BOM
2020-05-11 | 7.DVT2 | 7.Sensor | 4.Build | NA | Closed | [Monitor] Issue: Build found some M-sensor surface scratches monitor SMT process from5/11 by NPI | link | 小熊 | 怀玉
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03【WH124662】 light and proximity sensor no function:D4(15KV, Zone3） Root Cause:P-sensor INT abnormal （35R to GND） ，Component damaged Solution 1：ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，DVT2 EDU03 WH125964 pass |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-15 | 7.DVT2 | 7.Sensor | 5.4 ALT | NA | Closed | Issue: DVT2 ALT WH125967 D4,D5 P/L sensor no function Clue： 1.CQA Psensor can not enter, Lsensor no data Root Cause: 1.Speculation: P/L sensor crack issue.(same AS issue found in DVT1).ME follow |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-15 | 7.DVT2 | 7.Sensor | 5.3 ME DVT | NA | Closed | Issue: DVT2 ATT WH125966 D2 cap sensor no function Clue： 1.CQA All channel unknow ,reboot can not recovery Root Cause: SW issue Solution ： Fixed ,from 5/15 |  | 小熊 | 文亭 |  | 3.BOM
2020-05-15 | 7.DVT2 | 4.Audio | 5.3 ME DVT | NA | Closed | Issue: DVT2 ATT WH125967 D4 headset no function Clue： 1. report checked All MIC no function with headset 2. MIC analysis show ALL mic ok . SO it is headset downlink issue. Root Cause: Sub board crack (area near headset jack) Solution ： ME follow |  | 院长 | 文亭 |  | 3.BOM
2020-04-29 | 5.DVT1 | 3.Charging | 4.Build | NA | Closed | [s3] Issue: Build BrdTest Station,"TURBO_CHARGE_CONNECTED" Test Fail, Retry pass,NTF. Fail Rate:10%? CR: IKSWQ-90483,SW: QPN30.13 Clue：1. most of fail PCBAs are VZW SKU. Exp：Stress test with 2PCBA to check if it can be reproduce--Can not reproduce by 0507 chenhy4 2.Fail log:charging type SDP,Pass should be DCP Exp：check USB D+/- waveform when issue reproduce 3.retry pass without shutdown power or moving the board Root Cause: 1. Speculation:Contact issue? Can not reproduce in DVT2 so far ,monitor DVT2 VZW build （FROM 5/14） By 0515 no issue found ，close | link | 文亭 | 怀玉 | https://idart.mot.com/browse/IKSWQ-90483 | 6.No Change
2020-05-08 | 5.DVT1 | 4.Audio | 5.6 User Feedback | S3 | Closed | [Monitor] Issue: Background Noise observed on V07 PCB during Car Audio charging & Aux in mode ， Clue :1. follow up Main PCBA. V06 No Issue. Root Cause: 1.HS_REF is ground well but still was Affected by MainGround that mainly used as Vbus Power Return Ground. 2.HS_REF was Shift to Layer5 from Layer 7 duo to R&L Crosstalk Audio Ground Optimization Solution:1.Recover Audio Routing as V06 Version on PVT&Risk Buy, done 5/9 | Link | 院长 |  |  | 2.PCB
2020-05-06 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [Monitor] Issue: HeadSet Downlink TDD Background Noise observed on V07 PCB Clue :1. follow up Main PCBA.V06 No Issue. Root Cause: 1.HS_REF is ground well but still was Affected by Layer 4 MainGround that mainly used as RF GSM PA Power Return Ground. EXP1.1 Connect HS_REF to GND on sub board and recheck issue gone. 2.HS_REF was Shift to Layer5 from Layer 7 duo to R&L Crosstalk Audio Ground Optimization Solution:1.Recover Audio Routing as V06 Version on PVT&Risk Buy, done 5/9 | Link | 院长 |  |  | 2.PCB
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT1 EDu03【WH124642】[NNIA1C0043 /D4] 2. -15KV air discharge at zone15(Aging 10),Cap sensor CH0 unknown Clue：1.直接用ROOT权限操作CAP SENSOR IC，IC可以正常输出各实际状态 2.自测碰到三个通道都unknown的状态，应该是权限问题(Permission)导致 3.在同平台smith在4月29日有修改权限配置，应该是HAL层不同导致。但之前的项目Sofia等都不需要配权限 Root Cause: Linux访问文件都是需要配置好权限的，目前这些节点都是root用户权限，对于上层进程而言，这个权限比较苛刻 Solution 2：SW更新，让它们属于同一个group就可以了，同group的就没有这个权限问题 | link | 小熊 | 李果 |  | 3.BOM
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue:DVT1 EDu03【WH124642】[NNIA1C0043 /D4] 1. +15KV air discharge at zone13(Aging 10),proximity sensor/light sensor no function,unable to recovery Root Cause: 1.proximity sensor/light sensor INT abnormal （100R to GND），Component damaged 1.1 glue quantity too low? Solution 1：ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，monitor duplicated to EDu03【WH124662】P-sensor issue |  | 李果 | 小熊 |  | 3.BOM
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03[WH124614]Kernel panic;D2(15KV zone6） Clue：1)P-Sensor no Function 2)Cap-Sensor No Function Root Cause: 1.Kernel panic and P-sensor/cap-sensor no function duo to VCC of P-sensor shorted 2.P-Sensor Damaged by ESD duo to glue width under spec(0.38mm observed <0.5mm Spec) Solution: ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，monitor reproduce in EDu03【WH124662】. duplicated to EDu03【WH124662】P-sensor issue |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-15 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] DVT1 Issue:Edu03 ESD Test，cap sensor function normally on D4(NNIE130086) on 4/15, but no function after reboot Clue： 1.Remove VR100 on CH2 and the cap-sensor returns to normal Root Cause: 1.Cap Sensor CH2/Addr affected by VR100(ATVS LXES03AAA1-154 abnormal impedance), Sending to XiaMen & Later to Murata Japan for further FA (zto:640106156044) 4/16 Exp 1.1:Stress Test 800 Times @Zone13@2Units, Can't Reproduce. Exp1.2:Try Infineon TVS ESD103, Result: TBD Exp1.3:V/I Test Shows Leakage Resistance ~79Ω Exp1.4:Stress Test 600 Times on ANT Directly,Can't Reproduce. Monitor. 2.Cap Sensor Enter RD Debug Mode when Pull Down Exp2.1:Reproduced on Semtech DemoBoard @Pull Down 20K , Semtech America explain It is RD Debug Mode Entry. Exp2.2:Isolate ANT by spraying Paint，Result:TBD Solution:1.According to Result of Exp1.1 and Exp1.3，Exp1.4，Turn to Monitor reproduced ，EDu03[WH124614] ,duplicated to EDu03[WH124614] capsensor issue | link | 李果 | 小熊 |  | 4.Parameter
2020-05-07 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3] MDu30[WH124618] FVC E1D，QPN30.19 ,20W 充电器,无热管,Speaker位置增加散热膜，display 2nd IC display 90HZ 场景验证（充电下,wifi streaming 手动设置） 1）Camera photo front 42：44.6 2）LTE data call at Max power front 38：39.7 3）Game with charging back plastic 42:51.6 4) Processor loading front 40：42.8 Toot cause ，Thermal config issue ，correct from 5/13 |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-11 | 7.DVT2 | 7.Sensor | 4.Build | NA | Closed | [s3] Issue: Build TEST L2AR Station,M-sensor fail，DVT2 10% (13/130)，NTF Clue：1. can not reproduce with manually test (6 in 6,By huaiyu & Online ME Liuxiang) 2. other sensor NTF too. 3. When issue happen the USB port is connected but Network &ADB can not work. 4.L2AR test with Vbus power but not Vbat. change to power by Vbat ,issue gone Root cause：suspect Vbus power not enouth for the test. solution :change to power by Vbat from 5/12 . monitor | link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3] Issue: EDu03【WH124662】 1）the phone lock-up,restart to recover：D1(6KV contact，zone7） Root Cause: should be ramdump issue. monitor in New SW from 30.23 |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-05-06 | 5.DVT1 | 2.Power | 4.Build | NA | Closed | [s2] Issue: Build CQA1,In CQA app, check battery information, find battery level jump,CR: IKSWQ-91703 Clue：1. NNIA1C0039 issue ,other can not reproduce 2.Fail log:temperature jump too .t=25,-40,39 in one second! 3. Fail log:Battery remove and then Battery inserted after 2 second! Root Cause: 1. NNIA1C0039 1 unit issue, not common issue. reassembly sub board and recovery . should be connector assembly issue. | link | 李果 | 文亭 |  | 6.No Change
2020-04-26 | 5.DVT1 | 2.Power | 5.4 ALT | NA | Closed | [s3] Issue: WH125660 A5，B1 auto poweroff 1 time Clue：Ramdump show it not poweroff but ramdump too Root cause ：same as IKSWQ-89850，a QC bug . found in ESD test too IKSWQ-85825 Solution:fixed in SW 30.22 . monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-26 | 5.DVT1 | 2.Power | 5.3 EE DVT | NA | Closed | [s3] Issue:EDU13 WH124523 Power ：battery performace Run local video less than 5 hours （~=2.7 hrs） Clue：1.sofia plus more than 5 hours 2. Nairobi power log show average current is 1.8A.3.Battery capacity checked no problem（70% of 25 degree）. 4. Problem ： D1 NNIA110016 standby current is about 0.2~1.2A，abnormal Root Cause: 1. D1 unit current abnormal(+0.2~1.2A） ,RF calibration parameters lost and the modem has been restarted 2. Recalibrate RF parameters and the current is normal Solution: 1.Recalibrate RF Parameter |  | 李果 | 敏敏 |  | 6.No Change
2020-04-24 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3] RISK:WH124577 ESD :In final TIS test, LTE band7 main antenna degradation exceeds 3db, and TIS value is also out of spec on D4(NNIV120109) on 4/24, Clue： Root Cause: Sending to XiaMen ANT for further FA 4/24 ，Will Open after Ant Check 针对这台B7的问题，ANT暗室同样可以复现。 结论如下： 1． 我们提供工厂的TuneCode都是偏TX的，所以RX相对差。 2． 我们提供tunecode都是基于EVT机器，和DVT1的机器比，天线性能偏移掉了。 在问题机上，我们update新的code以后有源和无源数据都是合理的 |  | 李果 | 林峰 |  | 6.No Change
2020-04-26 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | NA | Closed | [s3] Issue:Thermal WH124559 Game with charging plastic 42:59 Clue：Stale data，NA & Close Root Cause: |  | 林峰 |  |  | 6.No Change
2020-04-13 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:DVT1-1 P sensor CQA test can enter but no reading 4/40pcs Clue: 1.log show phone in FAR(0) state 2. restart phone, test ok 3.can reproduce sometimes 4.Seperated I2C . 5.Reproduced once on Stress Test on 1 unit @Stay Still@Change Light Frequently@overnight. Root Cause: 1.Interupt keep low by P/ALS through Log lead to Test Fail 2.P/Als missed receive Int Flag Read duo to ADSP didn't Pull Up in first few mili seconds in sleep mode. 3.Why ADSP Missed Few Seconds Pull Up，Coworking with Qualcomm Exp3.1:Register Comparison , Result: Canceled Solution:1.Workaround 1,ADD Int Flag read when phone wake up . Drop According to S2，S3 2.Workaround 2,ADD INT flag read and do ISR in ESD recovery loop (1 time per 8S), Imported 3.Workaround 3,Add External Pull Up Resistor ，Done on DVT2 ,Monitor | link | 小熊 | 文亭 |  | 3.BOM
2020-04-23 | 5.DVT1 | 2.Power | 5.2 BB Test | NA | Closed | [s3] Issue: sleep current abnormal （25mA）after open and close camera APP clue:1. remove all the camera module ，PCBA sleep current is 25mA too Root Cause: 1. AXI port Resource Request，No Vote Mechanism to exit and Continually Occupy resource which lead to AP can't enter Sleep mode. Solution: 1. Adding Vote Temporarily。Verified OK-SW 2.Furtherly Check with QC |  | 邦邦 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-23 | 5.DVT1 | 1.Platform | 5.6 User Feedback | NA | Closed | [s3] Issue: 2 PCBAs go into 9008 always ,From RF debug clue: 1. have current leakage (1#100 mA ,2#300mA) 2. can blankflash but go into 9008 again 3.S4A impendence abnormal. 1#=13R ,2#=4R 4.remove CPU and S4A impendence ok 5.S4A is close to Vbus on main connector Root Cause: 1.CPU (related to S4A part )damaged. 2.suspect: connect Main fpc to Main board when main FPC and sub board connector toPC already(with 5V power) cause short the S4A to vbus. Solution: connect the Main FPC to Main Board when sub board not connect to PC or chareger. | link | 文亭 |  |  | 6.No Change
2020-04-13 | 5.DVT1 | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]4/12 DVT D1 After +15KV air discharge at zone 13(Aging4),No Main display 1.Grounding OK. Root Cause:1.Display Affected. Sending to XiaMen for further FA 4/14 Solution:1.Dispaly damage, and KP further FA |  | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-17 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: CQA P-sensor No Value，ALS Stuck，Restart ok Root Cause: Share Same Root Cause with Intrupt hung. Solution: SW Fix |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-17 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: Factory SW FB :NAIRO_IFLASH_DVT1_005_894.xml.zip PS can not enter . Clue:SW poblem,NAIRO_IFLASH_DVT1_004.xml.zip is ok. Root Cause: SW Power config issue Solution:SW change https://gerrit.mot.com/#/c/1536341/ |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-15 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: L2站点有发现，ALS/PS rawdata偏小， 重启后依然fail Root Cause:麦拉遮挡PS 孔--by Huaiyu Solution:Factory own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-15 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: CQA PS 正常，ALS 一直dark，不变化， 重启后依然fail Root Cause:ALS 校准bug有关(重新刷机可以解决)--by Huaiyu Solution:SW own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]DVT1-1 ALT(WH12455) A6(5) Magnetometer no function Root Cause:1.M-sensor crack 2.M-sensor too close to board edge Solution:1.V07 PCB change M-sensor far away from board edge ,done。 monitor | link | 小熊 |  |  | 2.PCB
2020-04-10 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:EVT EDU14 WH124347，surge test fail ，D1 &D2 Vbus At 150V&100V fail（unexpected auto power off at plug in the power） clue： 1.first project to use Will TVS for surge. other project use NXP TVS for surge Rootcause: 1.New Part WILL SF68C56226 Edu14 surge Test Verified failed. solution: Change back to NXP 48014320001（Used in all in-house project） 1. BOM change done 2.DVT2 SCH change done. 3.DVT2 and PVT material ok. further Project Action：parameter test ：WILL fail unit VS WILL OK unit VS NXP unit （sub board test wave ），done 。 Will D18 performance is similar to NXP 18 ， verity it in TCC and D18 pass . | link | 文亭 | 林峰 |  | 3.BOM
2020-04-13 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [S3]DVT1-A(V07) Magnetometer placement change cause SW parameter update Root Cause:1.M-sensor crack 2.M-sensor move from BOT to TOP on mainboard Solution:1.SW parameter compatible by HWID。 2. HW of Japan SKU reserve 2 placements for M sensor to make SW compatible. | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-03 | 4.EVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3] Issue:EVT CE CS Pre-test Failed, Over 15dB@4.5MHz@UpLink Root Cause: 1.CS Uplink failed due to Audio Ref Signal not balanced and Echo Suppression Algorithm Take Effect. Solution: 1.Fine tune Coupling Capacitor and inductor on Ref on newest audio configuration. RD Validated Pass. Sporton validated Pass |  | 院长 | 李果 |  | 1.SCH
2020-04-06 | 4.EVT | 11.Thermal | 3.Review/Simulation | S3 | Closed | [S3]Overheating risk are on speaker Root Cause:1.SPK Heating Solution:1.Add Graphite on SPK Box.Test Pass. ~0.15￥，No Volume loss |  | 林峰 |  |  | 4.Parameter
2020-04-14 | 4.EVT | 1.Platform | 5.2 BB Test | S3 | Closed | [S3] 1 unit NNIV040046 can not power on sometimes. unstable clue: 1.SW check it is related to a SW debug function D+ short to gnd will run EDL mode ，then release D+ will enter 9008 2.test R between D+and GND it is ok sometimes 3.copper for mmw ANT cover USB test point 4.remove the copper can not reproduce for 5 times test. Root Cause:1.thermal copper for mmW ANT cover USB test point causing D+ short to GND . 5. Impact VZW SKU(with mmW) Solution:1.change copper ? 2.add a glue to cover the USB test point?(checked can not move the test point) ME tracking | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-04-07 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [na]Issue:EVT CQA Report Rear Camera Record Stuck,FR：4/53=8%（IKSWQ-80124） Clue： 1.Follow Mainboard 2.Only happen in RF connector SMT in wrong direction 3.when in flymode there is no issue Root cause：1.MCLK Signal dispear after few seconds when camera start up. 2. Multiple invoked in Clock module and Modem module on GPIO25/MCLK 3.GPIO25 Detection invoked when RF Calibration Fail duo to Connector wrong direction 4.Modem Code share Racer 5G GPIOI25 Config which is not used in nairobi Solution:SW Re-Config GPIO25 - Verified Pass. | link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343， A6(1) Flashled always on ， including power off mode. clue：1.Light unstable when knock the phone around Flash LED. Rootcause： 1.Flash LED on due to spring M1811( Flash LED2+) and M1813(WLED_CAM) short which caused by cracked registration mast 2. ME furtherly analysis solution: ME Follow 1.ALT after 4/20 remove the registration mast. 2. change registration mast to bigger from DVT2 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，No Turn On ,A1 Clue:1.Turn on after changing Display. but PCBA cannot power on when unit arrive in XM 2. Main FPC： B to B pin deformed，can not assembly well ，may cause pins short when press B to B （will heatup when plug in charger）,when connect main fpc ,can not power on ,disassembly main fpc,it can power on . 3. Main FPC change to a good PCBA , 1 time it can not charge and heat up on the connector,1time it can not power on . So the Main FPC should be damaged physically Rootcause：1.Display module Broke（but it should be broken when disassembly） 2.Main board VREG_S4A_1P8=0.8V,Resistance of VREG_S4A_1P8=1.2Ω,normal value is 2.1KΩ ,suspect charging with the damaged main FPC cause Main board damaged. 3. Main FPC damaged when assembly 4. ME ：FPC didnt assembly well cause main FPC damaged. ( B to B pin deformed) Solution: ME tracking DVT1 build if the FPC assembly bad. BB monitor | link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-30 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop5，Display DIM:B6(1) Rootcause：4/2ME can not reproduce，waiting for KP check |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-31 | 4.EVT | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue：EVT WH124356 ATT11+WH124357 ATT12 ，D1 ，not turn on（when unit arrived XM ME） Clue：1.enter fastboot mode but shut down within 5 sec. 2.can Blankflash ,and enter fastboot mode and not poweroff ,but when flashall,phone reboot ,it will reproduce failure again. 3. it show low battery voltage in charging mode. Rootcause： check the Battery Voltage=0 . swap a good battery it it ok. move to KP for battery analysis DVT1 ：ATT11 WH124550 D10 & ATT12 WH124551 D10 same fail ，battery issue |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-17 | 4.EVT | 7.Sensor | 5.4 ALT | NA | Closed | [S3]Issue：EVT RD ALT*2round evaluation，ALS/ps fail 3 in 6 (including 2 in 6 sol LED fail too) Rootcause： ME middle housing deformed causing P-sensor component damaged and LED damaged too. solution: ME own. ME action 1. ：enhance housing strength by adding metal at the corner, will implement in DVT1 white color build； ME action 2. move P-sensor up 0.2mm |  | 小熊 | 文亭 | test result | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-31 | 4.EVT | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue：Nairobi 目前的SW 关机状态下，短按开机键 屏幕会闪一下,CR(IKSWQ-79283) Clue： 时序测试：现短按开机键时，mipi输出后，背光亮起的时间有差异。短按是mipi数据输出60ms后，背光开始输出，长按开机键，mipi数据输出500ms后，背光开始输出. 希望SW 分析 Rootcause：SW reply 结合代码走查，发现了个code的BUG,预计解决 by 4/2 check ok with SW 4/8 |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，No Turn On ,A1 Clue:Main FPC connector deformed. Rootcause： assembly issue Solution: ME Own 1.correct Allsmbly in DVT1. 2. checking if need to change Main FPC for better Allsmbly |  | 文亭 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop1，Cannot enter front camera mode:A2(1) Rootcause：ME FA B2B Issue ，should be assembly cause connector damaged 4/2 | link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ATT drop WH124356， Proximity sensor and light sensor no function:D1(27,T,1.25m),D3(12,B,1m),D4(45,T,1.5m) Rootcause：ME middle housing deformed causing P-sensor component damaged,same as ME evalution test. ME own the issue tracking | Photo link | 小熊 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ATT drop WH124356， Cannot enter rear 4 camera mode：D1(3,F,1m),D3(21,F,1.25m) Rootcause：Macro camera fail. B to B connector dissasembly.ME own the issue tracking | Photo link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop2，unable to power on after top right corner drop:A1(2) Rootcause：DISPLAY FPC在近主板B2B的弯折区有严重变形，并且display module的B2B 边框区域有明显塌陷，图片已上传GD 主板没有问题，更换display module后可以正常开机。ME&KP own the issue tracking | Photo link | 林峰 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]Issue：EVT ALT WH124343，loop2， P/L sensor no function after top side drop:A1(2),B5(2) Rootcause：-sensor component damaged,same as ME evalution test. ME own the issue tracking | photo link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-26 | 4.EVT | 5.Camera | 3.Review/Simulation | S3 | Closed | [S3] Risk：Ringlight driver hotplug risk when assembly rear hoursing. Clue:Ringlight driver always output Vbat -0.3V on WLED_CAM . it may short to Flash LED2+ when assembly. will it be a issue? Evaluation: 1. Very Low chance to misassembly rear hoursing .we can not reproduce. 2. Eval Test Vbat=3.8V , manually make WLED_CAM short to Flash LED2+ ,LED current <500mA， Driver ok. Risk close . No change needed for this item |  | 院长 | 文亭 |  | 6.No Change
2020-03-26 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，B1(1) No display Clue:1.手机可以开机，无显示 2.拆解后，没有发现明显Display B2B翘起，在重新扣合B2B后，显示恢复正常 目前看到的2台机器，FPC弯折区都有明显往一个角度弯折 Rootcause： suspect Display module issue , KP own the further analysis |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-17 | 4.EVT | 10.USB-C | 5.2 BB Test | S3 | Closed | [S3]issue: 10.1.1 Nairobi EVB USB 2.0 eye test fail Clue:USB phy tuning have 4* 8 bit register X0,X1,X2,X3 QC default parameter :0xA1,0x43,0x2E,0x03 solution: parameter tuning to: 0xA1,0x03,0x27,0x03 .Test pass . SWchange parameter from 03/17 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-03-05 | 4.EVT | 8.PCB | 3.Review/Simulation | S3 | Closed | [S3] Issue：V03 FPC outline not match ME requirement ，found by FPC vendor Rootcause： 1.get wrong V02 PCB 2. didnt complete ME check process before gerber out Solution: 1.Update V03 FPCgerber lesson learn :1.Need CAD update the Milestone PCB if it is updated. 2.need ME check before gerber out |  | 邦邦 | 艳红 |  | 2.PCB
2020-03-05 | 4.EVT | 8.PCB | 3.Review/Simulation | S3 | Closed | [S3] Issue：V03 sub ，panel and audio jack overlap （0.09mm*0.05mm） Rootcause：Panel check before Audio jack change done. Solution: EVT build :push audio jack before reflow ,and 100% check smt status after reflow DVT1 :Panel change before Gerber out (V04) lesson learn : 1.audio jack PCB liberry design with panel cut out . it can cut the overlap area berfor gerberout automaticly. 2. Panel check must be completed after all PCB change done. |  | 艳红 |  |  | 2.PCB
2020-03-05 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue： Camera control pin on PM7250 Voltage =3.8V ,not 1.8V (total 5 pins) Rootcause：PMIC MV GPIOs can config to hight voltage ot low voltage (1.8V) Solution: SW change PMIC MV GPIOs setting to Low voltage -done |  | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-02-27 | 4.EVT | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3] Issue：Receiver Pads placement do not match ME LDS design Rootcause：1.Recierver Pads placement do not match ME LDS design 2.why review and design not match? TBD---zhihao Solution: PCB04&05 Phone :PCBA remove GND spring , ME add a copper to connect REC pin.--ME own PCB06 change Pad placement to match ME design. -done |  | 院长 |  |  | 2.PCB
2020-02-26 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3] Issue：Deepsleep current =20mA+ @ 3.8V,over spec about 15mA on EVB-B V01 PCB Rootcause： 1.VREG_S4A_1P8=14.6mA @ 3.8V,over spec 12.73mA due to mmW config. not ready 1.1 after calibration,VREG_S4A_1P8 down to 2.1mA 1.2 flash SW which add mmW config.,VREG_S4A_1P8 down to 3.8mA 2.VREG_BOB=1.8mA @ 3.8V, over spec 1.3mA due to cap sensor not enter sleep mode. 3.VREG_S4C_S5C_0P75=2mA @ 3.8V,over spec 0.5mA,this is power for an on-chip memory of SM7250 Solution: 1.SW optimize 2.Deepsleep current of V04 PCBA=5.05mA @ 3.8V(all sensor disable),meet target |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-01-10 | 4.EVT | 1.Platform | 5.4 ALT | NA | Closed | [S2]issue: EVB WH123730 MDu66-Eval Product Bend Test not power on ,D4 Clue: WH123730 D4: 1.Vbat=3.79V, can not charge up, with a power supplier no big current, 23 mA with powerkey pressed . 2. PMIC shielding case seems been reworked 3. reheat PM7250&PM7250B by Chenbang ,no improve. Root cause: 1. SMT issue ，fail board before assembly Solution: 1. None | link | 林峰 | 文亭 |  | 6.No Change
2020-01-10 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]issue: EVB ALT WH123729 not power on A3 (Loop3). Other units fail too after some days. Clue: A3: 1.Vbat=2.78V ,can not charge up, can power on with a Good Battery ,but suspect no charging current into Vbat（Can detect turbo charging） . No IC crack found. 2.testmode check Battery temp=-40 degree C，suspect NTC problem Root cause: 1. NTC dropped （same as other fail units） 2.NTC ME design issue Solution: 1. Change NTC placement in EVT，ME Confirmed | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-01-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Risk: FPS soft fail after ESD. Clue: Because of ME design limit, FPS module GND is very weak, and no metal deco. Probable Cause: 1. FPS driver deadlock after ESD, cannnot response to AP's command. Precautionary Measures: 1. Add 100ohm series resistace on FPS signal routes. Verify ok on sofia. 2. Independent LDO power for FPS. When AP knows the FPS ESD error, auto power cycle the FPS module. Verify ok on sofia. EVT ESD test tracking |  | 小熊 |  |  | 6.No Change
2020-01-10 | 4.EVT | 12.EMC | 5.4 ALT | NA | Closed | [S1]Risk: No solution for ANT ESD protection. Clue: 1. ANT is exposed at the gap of inlay. 2.Murata A-TVS ESD protection performance is weak. 3. Infenion's TVS has better ESD protection performance, but with large harmonic. ESD128 -20dB, ESD 103 -40dB. Root cause: ANT tuner and SP4T will be damaged because of no protection. Solution: 1.ATVS EOL on 2021.9 | Link | 李果 |  |  | 6.No Change
2020-01-07 | 3.PEL | 1.Platform | 3.Review/Simulation | S3 | Closed | [S3]Issue: Jtag pin wrong Root cause: copy racer sch but replace connector with sofia parts Solution: 1. EVB-B wire out for bringup---done ，bringup ok 2.EVT change SCH refer to sofia sch---done 20200313 V04 PCB checked ok by Wangxf14 |  | 吉吉 | 文亭 |  | 1.SCH
2020-01-07 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | [S3]Issue: Macro camera bringup fail Root cause: Mipi design, CSI3 Lane0 P/N swapped. Solution: 1. rework to swap Lane0 P/N by flywire for bringup ok 2. Correct connection in EVT sch 20200312 V04 checkedok | Link | 邦邦 |  |  | 1.SCH
2020-01-07 | 3.PEL | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: A+G 上电时有个51mA VDD脉冲电流 Clue：MISO 和 电流脉冲有周期性出现，可能有关系 Root cause: PIN2/3(connected to GND) sink current Solution: PIN2/3 connected to VDD/VDD set to NPM mode at power up | LINK | 小熊 |  |  | 6.No Change
2019-12-03 | 3.PEL | 4.Audio | 5.1 Bring up | S3 | Closed | [S3]Issue: 1.1.1 Nairobi Fastboot fail after Blankflash in EVB-B build，about 50% units fail SW QC CR ：04388408 ，ongoing ---王小峰 Clue:1. 按开机键后VBAT 电流从几十mA到200+mA变化，未掉电 2. log ：fail after QSEE load ，可能安全建制部分有问题导致系统触发reset 3. log ：PM: OCP Occured: PMIC: 2; LDO: 8 推断可能 Vreg_L8C有问题 Analysis： 1.memory power ok ，没有看到掉电 ---学敏 2.bootconfig ok，去除所有bootconfig相连器件，依然fail--chenwt 3.加焊CPU和memory 1pcs，依然fail--chenwt 4.测量系统复位信号： PS hold 维持1.8V，没有低电平输出. SDM_RESIN_N 这个一直有信号输出在reset CPU的样子，570ms一次。--chenwt 5.check Vreg_L8C ，U4504 M-sensor ，U4503 barometer，U4502 A+G--chenwt 5.1 remove A+G ok 5.2 Vreg_L8C 外加1.8V 可以起来。 电源6705B上看到最大瞬间电流在 26mA左右。 Root cause: Vreg_L8C is in LPM mode. but A+G cause a bigger current rush Solution: 1.Sw check Vreg_L8C config is in LPM mode ， change to NPM mode. Done by 1/2 2. check A+G current when power up.----shengnan xiong 后续分析借鉴：不开机相关log可以查看关键字OCP看是否有线索。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-12-03 | 3.PEL | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3] case ：From Chicago John Gorsica： in talking to CTO audio team (Marley integration), have learned that Qualcomm's software implementation expects a separate bus for the EC (echo canceller) reference signal. Our original plan was to use I2S TDM mode to send this data over a single I2S bus. This team has requested that a second I2S bus be routed from LPI GPIO121-124 to AIF3 on Marley. Action：EVB，no change ； change into EVT with Racer solution --SCH change done |  | 文亭 | 院长 |  | 1.SCH
2019-12-03 | 3.PEL | 4.Audio | 3.Review/Simulation | NA | Closed | [S2] QC BB review：Recommend use normal GPIO MI2S instead of LPI MI2S for 3rd party codec. LPI MI2S may met jitter issue for 3rd party codec. We have CR2547793 for LPI MI2S 48kHz jitter issue, pls check with audio sw for CR status. QC SW answer： will solve the problem in about 2 months. Action： no change. Close . reopen it if there is issue found |  | 文亭 | 院长 |  | 6.No Change

## Tahoe (hidden)
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Department
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 试用机PVT ，wangqifu的机器，试用一段时间后，OTA SW 然后发现有时候充电慢。 售后一台机器报功耗高，暂时合并分析（接口信号异常了，qifu的机器概率性测试到异常，售后的一直测试到异常） Tahoe power consumption abnormal （After sale），IMEI 354001150843951 Analysis Clue:1. Vbus ，USB D+ ，CC1，CC2，SBU output are abnormal. This cause AP can not sleep always ,it sleep out too often. Clue2：R between CC1& USB D+ =900+R when plug in type-C cable(no charger connected ) Root Cause: suspect PM8150B damaged EXP1：sent the phone to Wuhan factory and replace PM8150B with a new one ,then check if it is ok ? have sent out the phone | link | 文亭 | 敏敏
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 售后2台故障机报充电自动重启和充电慢问题 clue: 1.354001150743953 充电时自动重启，插电脑检测不到手机 D+:827Ω，D-:398Ω； 354001151119179 有时偏慢，有时充不进电，有时电量无变化 D+:372KΩ，D-:820Ω； 2.怀玉 在武汉拆机分析发现CPU端阻抗异常，TVS 阻抗也异常 Action：EOS测试失效的机器，TVS 和CPU 也都坏了，比较拟合，EOS？ Solution: | TCC 摸底测试link | 文亭
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 售后1台故障机报充电速度慢 clue: 1. USB D+和D- 插入充电器时没波形。 关机测量对地阻抗异常，在1K R 以下 。正常是几百KR 2. 拆机直接测试主板测试点对地阻抗，D- =2.2R ，D+ =800+R ，异常 3. 测试小板D+、D-对地阻抗，10KR左右， 也是异常的。而线路上对地只有TVS器件。推测TVS器件也异常了。 Root Cause: 怀疑是EOS导致。 那EOS来源是什么？机器的防浪涌能力如何？ Action：TCC 增加 tahoe 对USB2.0和CC pin 的防浪涌能力摸底测试 ，60V fail，很高的抗性。EOS测试失效的机器，TVS 和CPU 也都坏了，比较拟合。 为什么还是会坏？有啥改进机会？ Solution: | TCC 摸底测试link | 文亭
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s3]Issue: Linxee claim 2 pcs new devices freeze and reset during charging. clue: 1. Linxee 借用试产机 及 购买量产机器用来做DP to HDMI cable 产线测试，一台手机会和上千条cable 适配。 2.有2台新购买手机（总共买3台），第一次测试，测试到没电后，插充电器充电，然后开机发现就死机重启。 机器走售后流程中。 3.试产机器也有1台出现问题，故障机USB无法认到，Bug2go log 分析应该是USB识别不到导致的 watchdog 重启。 建议分析硬件USB相关，转寄XM机器。 HW 分析：故障同上，USB2.0的主板段 D+ D- 阻抗异常，而且推断是CPU端异常；小板段也是异常，推测是TVS也异常。 Root Cause: 怀疑是EOS导致。 那EOS来源是什么？机器的防浪涌能力如何？ Action：TCC 增加 tahoe 对USB2.0和CC pin 的防浪涌能力摸底测试 Solution: | CR IKSWR-55445 | 文亭
2021-03-01 | D.SHIP | 2.Power | 4.Build | NA | Closed | Tahoe： 原始issue：Tahoe EVT板级测试 test 出现概率漏电流异常，800uA左右 。 正常关机没有复现issue。 分析：非正常关机导致，漏电流电源确认是PM7150L的AVDD电源（内部电源），提case 给QC ，QC答复是PM7150L（或者PM6150L）申请 系统19.2M时钟后没有正常关闭导致一直耗电 。----RD Wu Xuemin，NJ SW xuwei9 解决： QC 给了个patch，尝试在我们这种工厂关机流程中去关闭19.2M时钟的申请，然后DVT1 SW ok了（包含了QC给的patch），之后产线测试都没有再反馈了。该问题close。 扩展Issue：整机端是否有类似问题？ （Ibiza项目板级有问题，暂时没解决，直接扩展整机摸底测试，发现也有类似问题。） 整机测试：发现整机端也有这个问题。 （当然整机端和BT端，SW不太一样，开机程度也不太一样。）-----来源 ：SW MFG Luguo，RD Wu Xuemin Tahoe项目回退确认BT 情况：发现QC给的patch 集成之前的版本，10/12 就已经问题不复现了。 而9/29的EVT版本有问题。 中间的变更可能是解决BT 测试 漏电流问题的关键。（反推可能patch并没起作用）-----来源 ：SW MFG Luguo Ibiza 和 Denver ： Issue：测试一直都有这个概率漏电问题（早期EVT还有板子漏电问题，可能覆盖了一个试产阶段，DVT解决板子漏电问题） 后来原来以为参考tahoe增加patch 后就ok ，但是一直没有办法清除，一直怀疑是patch 及修改方法不对。 但从目前结果看，这个patch 有可能并不能解决这个问题。 Action： 1. Ibiza 不同SW修改方案的再次验证（可能是QC会重新给patch？可以也扩展到tahoe看下效果）。---- SW，SW MFG 2.寻找 Tahoe 9/29~ 10/12这段时间 factory SW版本的变更点，用来找解决这个case 的重要线索。----NJ SW，SW MFG 扩展涉及范围：今天增加测试的结果 PM8150L tahoe （测试结果：故障概率复现） PM7150L Nairobi （测试结果：故障概率复现） PM6150L Denver，ibiza ，Kiev（测试结果：故障概率复现） PMI632 的 Sofia NA和 PM6150A 的 Quattro ，（测试结果：故障不复现） 所以初步总结：LCD背光用到QC PMxxxxL 方案的机型应该都有同样问题。 Solution： SW 更改产线的下电时序，保障LCD来得及关闭 背光部分。避免该问题。 导入截止由SW 和 PQM 决定。 |  | 敏敏 | 文亭
2020-12-17 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | CR：IKSWR-35501 photo mode-The flash is on to take pictures, and the phone is automatically turned off Clue：Low voltage battery+DP+Camera+Flash ，auto power off Rootcause solution：change Flash current from 2.4A to 1.5A ，recheck ok | link | 芳梅 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-12-17 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | DP compatible issues | collection | 邦邦 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-12-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3]Risk: ALT ESD C1 +15KV Zone3/4/6/7/8 auto power off，adn enters the system crash interface. recovered after pressing power key clue: 1. Root Cause: Solution:not reproduce |  | 李果 |  |  | 6.No Change
2020-12-02 | 5.DVT1 | 1.Platform | 5.6 User Feedback | NA | Closed | [s3]Issue: there are some phone freeze and dark screen problem inDF clue: 1. Root Cause: SW Solution: | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-11-23 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3]Issue: Mdu30 , 1.LTE data call fail clue: 1. Pass last test, Retest Pass. Root Cause: Solution:PVT Retest Pass. |  | 林峰 |  |  | 6.No Change
2020-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | "[s3]Issue:Edu03 , DVT1 test WH132624 ,D4,After +8KV air discharge at zone6 (Aging10),the phone drop call(2020/11/20 11:02) Clue: 1. zone6 is upper side 2. just happen 1 time in DVT1 total 4 round test. (16 units) 3. real net phone call Root Cause: Solution:can not reproduce ,monitor PVT。 PVT not reproduce |  | 李果 | 韩凯 |  | 6.No Change
2020-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | "[NA]RISK:Edu03 , VT1 test WH132624 ,D1&D2 After -8KV contact discharge at zone18 (Aging10),the phone Unexpected auto power off Clue: 1. zone18 is camera deco ,middle 2 cameras (upper 2 cameras is Zone17) 2. D1 Rear camera(and Rear flash) is ON , D2 Front camera(and Front flash) is ON 3.WH133310 have same issue too . (total is pass ,because it is high voltage test and recoverable issue) Root Cause: Deco 的接地不好导致 Solution: 1. 主板上有预留加强接地方案，但基于目前属于软性可接受范围，故综合cost平衡，暂时不导入增加导电布方案。 PVT Retest Pass. |  | 李果 | 韩凯 |  | 6.No Change
2020-11-23 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | "[s3]Issue: Mdu30 ,SPK 最大功率fail 。 Root Cause: 1. SPK 石墨偏上贴了。2.石墨片偏小些 Solution: 1. SPK 石墨往下贴一些，并且石墨片加大。 手工验证 往下贴 改善1.5度，再加大后总的改善2.7度。 PVT导入 PVT test pass |  | 林峰 |  |  | 3.BOM
2020-12-10 | 5.DVT1 | 1.Platform | 5.2 BB Test | NA | Closed | [na]AnTuTu Performance- 1.Tahoe Total Score 60W （61.5W Best ） VS IQOO5 Pro 66W - @12/2 2. Tahoe GPU 24W+ VS IQOO5 Pro GPU Score 27W RootCause: 1.CPU/GPU Config to Performance Mode, increased to 63W . - SW 2.Speculation:GPU Optimize , Supposed to increase 3W . Exp:Consulting QC for help.- Result：GPU OverClocking only effective on AA chipset.Not fitful on AB/AC due to fuse. QC is not willing to provide OverClocking Patch . 3. more power CPU and bigger DDR5 and bigger UFS 3.1 Memory, 12+256 Memory + SM8250-AC Exp:Build 4 pcs for testing. 12/21 Solution: 1.Set CPU/GPU to Performance Mode Score ： 630000 （Best） 2. Set GPU supper performance forSM8250-AC，mode ，Score ：670000（Best） |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-23 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [na]Issue:Audio headset Downlink TDD Noise was audible. Root Cause: 1.1 Href Signal in layer 7 Affected by Grounding Layer 6&8 in which Big Current Pass through 1.2 Big Current Path on Layer6&8 duo to different Grounding Via placement in Whole PCB Layers compare with Nairobi. 2. Audio Signal in the surface side of Battery in which big Power Noise exit. 3.Href in MainFPC route on the side of L Channel. Exp:change Href in the middle of L&R, RD Validated ok. Solution: 1.seperate Href Signal from main RF PA power path, DVT1 import and verify 1.1 Optimize Layer 11 Grounding 1.2 Switch Audio Signal Fan out Position on Connector to far away from Battery Connector. 2.back up Href signal routing on Layer 2, DVT1 import and verify 3.Put Audio signal on the other side of FPC. DVT1 import and verify 4.Swap Audo_L&HREF in Main_FPC ,PVT Unit validated Pass.uplink:-75dB (Spec -71dB) ,Downlink:No Noise. PVT test pass | LINK | 院长 |  |  | 1.SCH
2020-11-23 | 5.DVT1 | 1.Platform | 5.2 BB Test | NA | Closed | "[s3]Task: Tahoe Antutu Score test SM8250-AA =58W;SM8250-AB =59.6W;SM8250-AC =61W 竞品 : SDM865 Android R 的竞品就看到 1+的机型 8T，SM8250-AA （从CPU主频信息倒推）memory 是 12GB+256GB，跑分59W pass 提升机会：Android Q 竞品 IQOO5 跑到66W，GPU到达27W VS tahoe的 23W+ ，有一定提升机会。 SW 寻求提升方法中 | link | 文亭 | 林峰 |  | 6.No Change
2020-11-23 | 5.DVT1 | 7.Sensor | 1.1 OD | NA | Closed | "[s3]Risk: Tahoe Add 1 Dock which may impact M-sensor Evaluation: M-sensor simulation checked pass. can accaptable. Tahoe+ need more check for this case, Risk(maybe tahoe+ need this Dock too?) |  | 小熊 | 文亭 |  | 6.No Change
2020-09-27 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3] Issue: DVT EPr02 Eval - eCompass WH131414 测试结果为 10°，目标是5°，暂停，等待确认结果 Root Cause:1.parameter related Solution: tune done,RD self test pass .TCC DVT test pass WH132626 |  | 小熊 |  |  | 4.Parameter
2020-11-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 ,2nd round test , 2units can not power on Clue: D3 failed point is near P-sensor&SOL_LED ,D4 failed on the chin. D3： Root Cause: 1.SOL_LED of PM8150L short to GND which lead to fail to power on. 2.Sol_LED Strike by ESD through 0.5mm width Glue Area Solution: 1.Add one TVS on Sol_LED,BOM Changed. RD Validated OK. TCC Validate ok WH133310&WH132624 D4: Root Cause: 1. LEDA of PM8150L Damaged which lead to power cycle issue. 2.LEDA Strike by ESD through Display Edge. Solution: 1.Add one high voltage TVS on LEDA ,BOM Changed. RD Validated OK. TCC Validate ok WH133310&WH132624 | link | 李果 | 韩凯 |  | 3.BOM
2020-10-09 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 2/8 units unexpected power off, recovered after rebooting Root Cause: 1.System auto power off due to FPS Striked by ESD. Exp1.1:Disconnect FPS Con, Result:Not Reproduce. 2.CPU Affected by ESD Through SPI of FPS Exp2.1:Disconnect SPI Signal one by one. Result:MOSI&MISO Matters. Exp2.2:Replace ESD Block Resistor 100R with 1K. Result:Pass. Exp2.3:Replace ESD Block Resistor 470R on SPI MISO &MOSI line and import in DVT 1build Solution: 1.Replace ESD Block Resistor 470R on SPI MISO &MOSI line and import in build. monitor 2. replace ESD Block Resistor 1K on RSR,CS,INT line. in DVT1B BR 40462 ,Test pass | link | 李果 |  |  | 3.BOM
2020-10-29 | 4.EVT | 10.USB-C | 6.Issue | NA | Closed | [s3]Issue: SW test ，Connect Jiewang（500G） mobile hard drive to the OTG cable phone does not recognize,IKSWR-11737 clue: 1.change This OTG cable to a hub ,it it ok 2.Racer turbo(SM8250) can not recognize too. but other projects can recognize 3. test by our OTG and hub + our 1T&2T hard drive ,they are ok,can not reproduce. 4.both USB 2.0 &3.0 OTG header test fail on this mobile hard drive Jiewang（500G） Root Cause:no signal issue found. Action 1.1: SW analysis no result Action 2: HW, eye diagram test (host mode ) USB2.0 pass， USB3.0 host fail at 5G Far End Total Jitter at BER-12 (CTLE ON) -5.9 %. Solution:keep current status. no change . |  | 文亭 |  | IKSWR-11737 | 6.No Change
2020-10-22 | 4.EVT | 2.Power | 5.3 EE DVT | NA | Closed | [s3]Issue:sleep current 8.6mA , can we lowdown it? clue:高通的参考数据4.7-6.7，我们现在关闭sensor后8.6mA Root Cause: 1.Action 1: RRT31.13 版本分解各个模块耗电 2.breakdown 数据看，除Memory 容量差异样（6G VS 8G），主要在VREG_S4A_1P8 上存在3.3mA Gap，QC上的数据应该只测了单路SM8250 PX3， Solution: VREG_S4A_1P8 功耗相对其他平台看，数据接近的，属于正常范围，将修正BSP target | Link | 敏敏 |  |  | 6.No Change
2020-10-29 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [s3]Issue: Tahoe TOF calibration fail issue 2%~3% clue:ToF I2C probe failed Root Cause: Power on frequence dont meet Spec Solution: SW change Power on frequence to 5ms delay , temp SW check ok, import in SW mainline with 5ms delay from 11/02 lesson learn： add power and I2C frequence check in TOF BB test。 need to provide a design With margin | Link | 邦邦 |  | IKSWR-12689 | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-27 | 4.EVT | 2.Power | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 1/8 unit can't power on ,15KV Air Discharge on chin. clue1:PMU Damage 2:leakage current of AVDD of PM8150L is 340uA,normal is 1.5uA 3:press power key,REF_BYP of PM8150L no output 4:AVDD leakage current and REF_BYP output of PM8250 is all normal Root Cause: 1.PM8150L Damaged 2.Speculation:Floating VDD_BOB Affected by ESD which lead to PMIC Damage. Exp:Test more 2 unit on SubBoard but not reproduced. Solution: 1. Add 1 cap on VDD_BOB Terminal. - Done 2.Reserver 1 Resistor on Mainboard in next version. DVT1A test pass |  | 李果 |  |  | 1.SCH
2020-10-09 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 15KV Air Discharge at MIC3 ,System auto power off clue 1: 6 units (2units TCC+4units new drivers) 15KV +200 times/unit ,Result :Pass Root Cause: 1. SW issue Solution: 1.Monitor DVT1 TCC test pass |  | 李果 |  |  | 6.No Change
2020-09-27 | 4.EVT | 2.Power | 4.Build | NA | Closed | [na] Issue: BT test ，IKSWR-6070，[BRDTEST] BATTERY_OFF_CURRENT_BOARD_1 Fail ，800ua VS target 300uA ,Retest Pass，NTF。9/21, 11.9%; 9/22, 14.1% Clue1:Attaching Display and Power Cycle 100 times. No Issue. 2:open kernal uart log and remove display ,power cycle over 100 times,no issue 3:leakage current is from AVDD_BYP of PM8150L,640uA Root Cause: 1. Speculation: Device Config and initialization issue solution：SW change . import in DVT1 SW . close . can reopen it if it reproduce. |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-27 | 4.EVT | 9.Memory | 5.4 ALT | S3 | Closed | [s3] Issue: ALT WH131408，B6 ，unable to read memory card initial and recovers after TH/TC in loop2 but the same failure repeats after TH/TC in loop5. A4(5), B3(5) Loop5 can not read memory card. A2(0) unable to read memory card initial and recovers after TH/TC in loop2 Clue1: Tear down B6,No SD Card solder issue found. Clue2:2 initial failure found, but recover Clue3:SD Strace <60mm. Root Cause: 1. SW analysis log ，https://idart.mot.com/browse/IKSWR-6840, ---log invalid（时间不匹配） EPr03 - Memory Card Compatibility Testing pass，including 21 different Tcards close 。will reopen it if it reproduce |  | 嘉琨 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-10-10 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA]Issue: some LPD mis triggered isuse found ， clue 1: no issue in Without redriver boards Root Cause: 1.should be Redriver impact it EXP1:remove redriver and checked ok: EXP2:ADD pulldown R on SBU to check LPD limit :300~400KR . EXP3:check Redriver Aux on Hi_z config : 80~160KR. lower than LPD limit ,causing the issue. Solution: 1.remove LPD function on SW |  | 文亭 | 院长 |  | 1.SCH
2020-09-23 | 4.EVT | 6.Display/Touch | 5.2 BB Test | NA | Closed | [na]Risk:DP Signal eye height 98.6mV in worst case(850mV and 3.5dB Pre-emphasis , not meet 104mV spec in No Redriver Solution. Clue1:with Redriver,Eye Height=145mV(Cost Up0.8$). 2:with 1.6m extension cable,DP link ok in No Redriver Solution Root Cause:1.Insertion loss of FPC and PCB Routing with 5.9dB loss Exp1:Test More Display ,9/29 Exp2:Measure the accurate Swing Voltage between 600mV and 850mV to detemine the margin. Solution:1.Sub Board using No Redriver go first and keep verify the risk level in the following. Product Team raise PCMCR to add USB3.1 and DP1.4 , Need Add Back Redriver. Closed. | Link | 芳梅 | 邦邦 |  | 4.Parameter
2020-09-27 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3] Issue: DVT EPr04 WH131416 After making a call, the screen turn off,cannot recovered by itself root cause: parameter related ,need tuning by 9/30 ,not blocking PCB solution:SW change . done . self receck ok by 10/13 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-23 | 4.EVT | 11.Thermal | 4.Build | S3 | Closed | [s3] Issue:thermal ，在正常CQA 闪光灯打开时温度过高 ,手在靠近闪光灯的时候烫手，请怀玉帮忙看一下是否可以调整 Root Cause: 默认电流300mA.超过标准的200mA左右。 Solution:1. SW tuning torch current setting |  | 林峰 |  |  | 4.Parameter
2020-09-23 | 4.EVT | 11.Thermal | 4.Build | NA | Closed | [s3] Issue:thermal ，在正常CQA检验过程中手机温度会比其他项目温度高 Root Cause: 1. can not sleep .more power . SW not very stable , will refer to TCC thermal test data |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-27 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [S3]Task: USB 2.0 eye test ， devices mode test done and pass | link | 文亭 |  |  | 6.No Change
2020-09-23 | 4.EVT | 6.Display/Touch | 5.2 BB Test | NA | Closed | [s3] Issue: DP Audio no function Root Cause: Audio get information that it is HDMI ，so audio output with HDMI. config it to DP output ,it will ok. need to find out why HDMI information report to Aduio. Solution:1. SW workaround changed ,and SW checked ok. mainline SW check pass 9/27 |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-23 | 4.EVT | 10.USB-C | 5.2 BB Test | S3 | Closed | [s3] Issue: OTG output 1.6A loading ，有0.7V的纹波，频率160KHz左右。 1A 时是400mV左右，和其他机器类似。还可以接受。 Root Cause: Solution:1. |  | 文亭 |  |  | 6.No Change
2020-08-20 | 3.PEL | 5.Camera | 2.Design | NA | Closed | [s3]Risk ：TOF FPC上 Xshut pin 直连到VDD（2.8V），是否有风险 Root Cause: 结构空间只够5个弹片，Xshut 评估有机会FPC上直接拉高来省掉一个pin，达到5个pin的目标。但是FPC上没有留上拉电阻，而是直接接到2.8V。后来追查结构上空间也非常有限，很难加 电阻在FPC上，除非万不得已 实验:1. ST L3 demo 板上直连Xshut 和VDD ，接2.8V电源，发现只有5UA漏电，可以认为没有漏电问题，可以接受 2.裸片IC单独2.8V供电，对地电流约为0.7mA，Xshut对VDD短接后，对地电流为微安级，在可接受范围内，风险等级低 solution： keep design |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-06-08 | 1.Concept | 11.Thermal | 2.Design | NA | Closed | [s3] Issue:thermal ，目前布局热管对不上POP 的CPU。 需要确认下如何处理。 Root Cause: -受结构限制问题 （特别是中框件不能动） Solution:1. 布局或结构中框调整，让热管尽量靠近CPU热源 风险低 | ME link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-16 | 4.EVT | 1.Platform | 5.1 Bring up | NA | Closed | [S3]Issue:SIM2 不识别 Clue:1.SIM2通道有正常信号访问 Root Cause: 1.软件采用的初始NV 数据直接参考Racer，导致无法识别. Solution：1.SW调整NV ， 可以识别. |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2020-09-10 | 4.EVT | 1.Platform | 5.1 Bring up | NA | Closed | [S3]Issue:无法Provision Root Cause: 1.SW直接采用Racer上的UFS3.0，Memory Type 设置不对，我们使用的是UFS3.1 Solution: 1.SW正确配置Memory Type |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor

## Shelby (hidden)
Date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Department
2019-01-17 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | Closed | Issue:Can't Power On with Leakage Current in After Sale ,12/20 units of not power on . 0.0x% RootCause: 1.USB_CC;PM660 ,Pin27 ;VOL_UP;PM660A,Pin97 2.USB Vbus(5V) Closed to CC1,CC2 3.CC1,CC2 Maximum Voltage =6V Solution: 1.Accept the failure rate. 2.SM6150 CC1,CC2 upgrade to 22V 3.TCC Evaluate More units - 2019/4/30 |  | 敏敏 | 吉吉 |  | 6.No Change
2018-07-17 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2] Shelby P-sensor :can not power on when LED current set to 150mA Clue: RootCause: 1.LDO OCP 2.Wrong Configuration Solution:1.Right Configuration | link | 敏敏 | 小熊 |  | 4.Parameter
2018-07-05 | D.SHIP | 7.Sensor | 5.6 User Feedback | S2 | Closed | [S2]Issue:User Feedback that Black screen when talk RootCause: 1.P-Sensor TMD2725 has bug on calibration, It occurs when IR of Sunlight transition when Calibrate. 2.Easier triggered on high gain 4X ，Normal 100mA,2X,or 1X is ok on golden eagle,houdini Solution: 1.SW Work around to void negative P Value. 2.Change Gain to1x for better margin（LED current from 20mA to 80mA to match performance requirement） | link | 文亭 | 小熊 |  | 4.Parameter
2018-06-26 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | "[S3]Power users roam to China and found Shelby had a short battery life. Clue: 1.Using VRZ Sim 2.Ask another Power User who are roaming to china,Battery Life is normal,He closed the data link. 3.Houdini also have GMS issue Root Cause: 1.Proposal:4G connecting not stable because of the compatibility of network service. -Try 3G manually and try. -Observing the Signal connecting status 2.Proposal: VPN was blocked because of Chinese Government Policy Issue,GMS(Google Service) keep trying connect to Google Service and cause extra 7 Hours battery life dropped which is found in Houdini too due to WakeLock Service don’t release . -setting ->battery->Slider down to check if GMS have abnormal battery drain percentage 3.Proposal:VPN Usage will cause extra 10 Hours Battery life Dropped which can be reproduced. -setting ->battery->Slider down to check if VPN activated 4.Proposal:other APP that keep connecting -setting ->battery->Slider down to check if some APP have abnormal battery drain percentage 5.Proposal:User in low signal strength Area which cause searching with maximum power,maybe low possibility in china -Observing the Signal connecting status Solution: 1.Normal issue 2.Normal Issue 3.Normal Issue 4.Normal Issue 5.Normal Issue. Closed |  | 李果 |  | BB Analysis | 6.No Change
2018-04-27 | C.RAMP | 7.Sensor | 4.Build | S3 | Closed | [S3]Als no function Clue:Connetion Bad RootCause:Spring Contact Issue,ME Analysis OK2Ramp Pass，Closed |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-04-27 | C.RAMP | 8.Mods | 4.Build | S3 | Closed | [S3]1 unit found Missing Pixel with Mods Projector Clue:1.BT Pass,2.With Projector Mods Fail Root Cause:1.Solder Joint on AP DSI4&5 |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-04-14 | B.PVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2] Issue:ALT WH105378 A5 loop2 Magnetometer sensor no function Root cause: 1.M-Sensors Crack by cutting force Observed on FPCA 2.M-Sensor was cut by Sharp Edge in the Slot 3.M-Sensor need glue more Solution 1.Expand Glue on M-Sensor 2.ME Expand Slot 3.Proposal：SOP Improvement Merge to 2018-3-29 Edu02 Issue ,Close | link | 小熊 |  | ME Analysis | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-03-29 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue:DVT3 Edu02 Magnetometer sensor no function Clue: 1.Magnetometer Sensor no function also found during Assembly 2.EDu02 on FPCA samples 10pcs checked Pass by Hongflex. 3.PVT IQC Sort FPCA,No Failure Found. Root cause: 1.FPCA Damaged. Nothing to do with Edu02 2.Some 3 of 5 M-Sensors Crack Observed on FPCA 3.Proposal:M-Sensor Crashed with the Pocket Edge during Abnormal Assembling: -Owner:NPI liuyulong Solution: 1.Proposal：Assembly SOP Improvement –Owner：NPI Liuyulong 2.Proposal：Enlarge the M-Senosr Pocket as below for more space for M-Sensor–ME Ethan 3.M-Sensor need glue more Plan: 1.Assembly Issue Analysis，Focus on Side FPCA Assembly in PVT, To see if failure found in JOT –Owner:NPI ，On-Going 2. Enlarge the M-Senosr Pocket more space for M-Sensor –ME Ethan ，Done，Solution Run in Change in MP directly. 3.Glue M-Sensor - ME Ethan/BB | link | 小熊 |  | BB Analysis | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-03-28 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S1 | Closed | [S3]issue：Media volume maximum, when rear camera take picture ,there are some vertical line. clue：Audio smart pa and rear camera avdd 2.8v ldo use the same B_plus power supply, Root Cause:1.Smart pa consumes large current , so B_plus voltage has a big drop which belows 2.8V， AVDD ldo putout is not stable ,this causes the issue happen Solution: 1.Cirrus Enable Surge Current Threshold，Verify Pass，SW imported | Link | 院长 |  |  | 4.Parameter
2018-03-08 | 7.DVT2 | 8.Mods | 5.1 Bring up | S3 | Closed | [S3]MyDP I2S Bring up SW Own |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-03-15 | 7.DVT2 | 9.Memory | 5.6 User Feedback | S3 | Closed | [S3]QC CR：03374129 moto CR：IKSWO-65523 issue： Kernel panic while streaming music and using BT headset B2GID:301816190 1 time clue： QC log analysis show： This issue is happening due to memory corruption. issue is only once so far. Lets keep this in monitoring state. moved the case to h/w CE to help further as device needs for PTE/foundry team investigation. QC reply ，BT issue ，RF take this issue。 |  | 威姐 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-03-15 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]CR IKSWO-71285 One Unit Haptic feedback has stopped working / Audio Lost B2GID:301980855 Clue:1.Log show I2C issue,new type 2.Re-Boot OK 2.DVT2a HW Version Root Cause: Solution: Plan:1.NTF,Monitor |  | 院长 |  |  | 6.No Change
2018-03-12 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Samsung Display White after ESD Zone 16 Clue:1. RootCause:1.EMI Conductive Fabric on LCD Driver Area Introduce the ESD Energy 2. ESD Energy Flow Through Sensitive Area of LCD Driver Solution:1.Better conductive EMI Conductive Fabric to GND 2. Using Anti-Static Film to Block the ESD Energy through Sensitive Area ,DVT3 Validation Pass. |  | 靓仔 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-03-09 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [s3]Soft ESD Failure on Second Vendor TianMa D6 Unit,Reboot OK （8KV Air discharge） Clue:1.Zone1- P-Sensor/SPK no function ,Reboot OK 2.Zone1 -System Halt ,Reboot OK. Root Cause:1.Codec Affected by ESD through SPK Solution:1.Move TVS Position to the SPK Terminal, Evaluation Pass. Antenna Eval Pass DVT3 Validation Fail， Keep Original Design |  | 靓仔 |  |  | 3.BOM
2018-02-26 | 7.DVT2 | 8.Mods | 5.6 User Feedback | S3 | Closed | [s3]DTV app shows signal low when inserts usb with wall adaptor. Clue:1. Root Cause:1.Charger Detection Invoke USB while it is used for Video Steam Solution:1.Disable USB Invokation in these scenario Plan: Support SW, SW solve it | Link | 邦邦 | 文亭 & 李果 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-02-26 | 7.DVT2 | 8.Mods | 4.Build | S3 | Closed | [s3]60% HDK Projector test Fail on DVT2B Clue:1.Projector Mods OK 2.Slim Port Routing is ok 3.Eye diagram OK 4.DP Link error ok 5.Fine Tune Drive Strength ，No Improvement Root Cause:1.DSI MIPI Lanes Set to 2 ,It should be 4 Lane. 2.Some Cable can't supoort 1080P stablly. Solution:SW Lead 1.Configure right 2.Config to 480p Plan:1.Validation with other Factory in Brazil | Link | 邦邦 | 院长 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-02-12 | 7.DVT2 | 9.Memory | 4.Build | S2 | Closed | [S2]Issue:1. Shelby_IF_QBOOT_BLANK_FLASH_01_true fail In DVT2A EMEA &Brazil SKU . Clue:1.Erase DDR ,Can't reproduce 2.heat Unit 1 memory about 100，200,300 degree，can't recover 3.heat memory up to 400 degree ，Recovered 4.Found Dirt under memory after Take it Down，Re solder the same memory ,recovered. 5.Heat Unit 2,Can't recover 6.Red dye 1 unit no abnormal found 6.Detached Memory,Check Signal ,one CPU Address line open Root Cause： 1.CPU Address line Solder open 2.Why solder open,SMT investigate Solution: 1.SMT investigate Plan: 1.Cross Section Unit 2 . 2.investigate other 2 units 3.Raise SW SR to Qualcomm | Link | 威姐 | 邦邦 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-02-12 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Epr04 test fail in DVT2A Root Cause: P-sensor gain is too high Solution:1.change gain PLDRIVE to 20,build a new config (tested in XM ok) Plan:1. retest in Wuhan TCC with new config by2/24 Verification：1. new WH104491 test pass at 2/23. will check with SW chaoyi change into: OCW28.41-BECKHAM-SHA1 |  | 文亭 |  |  | 4.Parameter
2018-02-12 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]-6KV contact discharge at zone 16(Aging 10),Mods function intermittently, recover after restart. -6KV contact discharge at zone 16(Aging 10),Mods function intermittently, recover after restart. Root Cause:1. CC pin ESD Suppression Not enough Solution:1.change CC pin TVS to larger capacitance and retest with improvement. Evaluation Pass.DVT3B Validation Pass Plan:1.DVT3B Validation |  | 靓仔 |  |  | 3.BOM
2018-02-09 | 7.DVT2 | 6.Display/Touch | 4.Build | S2 | Closed | [S2]Power off when Import TianMa LCM Root Cause:1.Power sequence mismatch between First Vendor Samsung and Second vendor TianMa Solution:1.Fine tune Power Sequence to meet both of them Plan:Verifing |  | 芳梅 | 院长 |  | 4.Parameter
2018-02-12 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Risk:Cap Sensor I2C Risk Root Cause: Solution:1.Reset SCL When Error Found Plan:1.SW arrange Pressure Test |  | 院长 |  |  | 6.No Change
2018-02-11 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3] 1.Some Unit Cap Sensor function not stable 2. CQA Test Cap Sensor Fail Clue:1.Happend when Wifi Scaning each 70S. Root Cause:1.Wifi Scaning Mode 2.Cypress FW filter Solution:1.Cypress improve filter,Far away need 6S Response time，DVT3 validation Pass | link | 小熊 |  |  | 4.Parameter
2018-02-11 | 7.DVT2 | 8.Mods | 4.Build | S3 | Closed | [S3] DVT2A,3/2600, Mods Projectors still can't work Clue:1.1 Unit can’t reproduce 2.Change Anx7805,can’t recover Root Cause:1.ANX7805 I2C error .2.ANX7805 Reset Sequence issue 3.U5041 C4&C5 Solder Joint by X-ray Solution:SMT Lead-Solder Paste Resize ,DVT2b No defect found Plan: | Link | 邦邦 | 院长 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-01-08 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue:1.Cap Sensor Detection distance cannot match ANT SAR requirement in DVT1B units Root Cause：1.Cypress Solution may not meet requirement 2.Antenna Pad Too Small,3.loading capacitor too big 4.FW Parameter need fine tune Solution:1.Reduce Loading Capacitor-Done 2.Proposal:Increase Ant Area ,Dropped because of schedule impact . 3. Fireware Parameter fine tune. Best Performance now.but not stable. 4.Using Psensor to resolve Front Detection 5.Back side set as 10mm | link | 小熊 | 森森 | link | 4.Parameter
2018-01-18 | 5.DVT1 | 8.Mods | 5.1 Bring up | S3 | Closed | [S2]Issue: Harsu Mods can't work Root Cause:1.CSI2 P/N Swap ，DVT2A Revised 2.SW do not ready Plan:1.Support Jon Bring up 2.Pressure test. | Link | 邦邦 |  | Link | 1.SCH
2018-02-03 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S2]U5040 Solder joint Root Cause:1.Proposal:Soler Paste Over Volume Solution:1.Fine Grain Stencil Plan:Give Advice to SMT on Stencil Grain | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-01-15 | 5.DVT1 | 9.Memory | 4.Build | S3 | Closed | [S3]Issue:1.DVT1B Second Vendor 4+64&4+32 Hynix memory build . 17pcs can not flash in IF . clue:1.Blankflash Success , 2.Fastboot mode failed , Root Cause:1.Qualcomm SW Driver Issue Solution:1.4G Weak DQS Pull Up Patch-SW | Link | 威姐 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-01-04 | 5.DVT1 | 11.Thermal | 5.4 ALT | S3 | Closed | [S3]DVT2a Tianma display compare result in Max brightness，+2.5℃ > samsung display Clue:1.Decrease Brightness ineffective RootCause:The power consumption of Tianma is higher than that of Samsung Solution:1.Adding Graphite under Driver IC Plan: control the power consumption of Tianma display,DVT2B tracking--onwer: KeyPart | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2017-12-18 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | [S3]Issue:Remove the Charge,charge icon not disappear Clue:1.Only happen on AICL Closed Root Cause:1. PM660 Issue 2.Same as 98 Solution:1.Qualcomm feedback no solution except enable AICL mode. | Link | 林峰 |  | Link | 6.No Change | 1.BB
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Usb Fail 3 units D2：After ±8KV air discharge,The computer can not identify the UUT,can not recover. D3,D4：After -15kv air discharge,The computer can not identify the UUT,can not recover. Root Cause:1.D2-D4 Usb Analog Switch Damaged 2.Rohm 1pF TVS request by purchase team can't meet Requirement 3.Easy to striked by ESD due to Type C Connector tongue piece protrude Solution:1.Using Better TVS on DM/DP,Eval 10pF Pass，Verify on DVT1B，DVT1B Pass-2018-1-12 ，ALT Fail 1 unit -2018-1-16 2.Reserve Additional TVS closed to USB-C Pin on DVT2 3.Reserve 2 0R Resistor on DM/DP Done 3.TVS Closed to USB Port 4.2 TVS （Switch+Port） | link | 靓仔 |  | link | 3.BOM | 6.Display
2018-01-08 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue: can't boot in low temperature environment (-10C°） Clue:1.battery capacity drop to 0%, so can't boot up 2.Sencond Vendor Battery is OK. Root Cause：1.Qualcomm Fuel gauge Algorithm issue,ESR+Rslow>2ohm under -10°C Solution:1.Fine tune ESR coefficienct,Evaluate OK Plan:1.Gathering Battery Discharge data and to check with Qualcomm to possition the issue. | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-01-29 | 7.DVT2 | 8.Mods | 4.Build | S2 | Closed | [S2]Issue:1.DVT2A Build Projector Failed Root Cause:1.I2C read 0X42,and then Fail to Write 0X02 due to clk bit halt on 6th bit due to I2C Arbitary mode 2.The Rising of V1.0 Power of Anx7805 affect the CLK during 1us. Solution:1.Retry Reading IO expander-Verify Pass. 2.Initial IO expander first, Presure Test on Projector Open Scenario ,Focus on Vibrator and Audio.- Pass | Link | 院长 | 敏敏 | Link | 4.Parameter
2018-01-17 | 5.DVT1 | 12.EMC | 5.5 Certification | S2 | Closed | [S2]Issue:CE ESD Usb Link Fail Clue: Root Cause:Usb Data Transfer interrupt by GND voltage drop when ESD Solution:1.Proposal:Separate Signal & Changing GND with Shielding GND 2.Proposal:Separate Shielding GND with Cable 3.Better TVS with bigger Capacitor- Sporton Verify Pass Plan：1.import S3 in dvt2a and monitor Closed |  | 靓仔 | 森森 |  | 3.BOM
2017-12-25 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue:Vibration/Earpiece speaker/Alert speaker function intermittently during ALT Root Cause:1.I2C Abnormal lead to Function intermittently 2.Anx7805 I2C Abnormal lead to this issue. 3.I2C abnormal when Anx7805 Pown Down and V1.0 Power Supply exit. Solution:1.Using independent GPIO to control An7805 1.0V Power 2.Modify Power on/off Sequence to avoid Power down and V1.0 Power supply exit at the same time. 3.Reset IO expander U5401 when I2C crash. Plan: 1.Monitor in DVT2A | Link | 院长 |  | Link | 1.SCH
2018-01-16 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue:Alt test after ESD,GamePad Mods keypad no input Clue: RootCause:1.ANX7805 Usb Port Damaged 2.ESD Proect May not enough Solution:1.Optimize ESD Protection，DVT2A imported Plan:Monitor DVT2A Test Status | Link | 靓仔 | 邦邦 | Link | 2.PCB
2018-01-08 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S3] NTF BT ：DVT1B AMPS_MSMGPIO14_INITIAL_LOW_STATE fail Clue： Root Cause：1.Power Sequence Issue Solution：1.Initial C-Wire first，and start to test Plan：Verify on DVT2A | Link | 邦邦 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2018-01-08 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S2]DVT1a 2 units（total 1500pcs） JOT AMPS_NO_LOAD_CALIBRATION_STATUS fail clue：1.SN: NS9A110077 change U710/U711 to a new one retest pass by liguoa 2.SN: NS9C120127 is under analysis by Xianhua 3.No Signal When Calibrate 1A 4.Same Issue on Houdini RootCause:1.276 ,280 exceed 1-255 range Solution:Replace 220K compensation Resistor with 620K Plan:1.Replace 220k compensate Resistor with 620K , 2.Verify in DVT2A | Link | 李果 |  | Link | 3.BOM
2018-01-08 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:DVT1A Power Consumption exceed 2mA,Failed at Standby Mode (6mA while BT/WiFi is on) Clue: Root Cause：1.Mods Anx7805 IC 1.0V Power Supply is not shut down. 2.This IC share the same Power Source with WIFI/BT,Enable Pin share the 3.3V Power Supply on Anx7805 Solution:1.Using Seperated GPIO as Enable. Plan:1.Import Solution1 in DVT2A and verify | Link | 敏敏 |  | Link | 1.SCH
2017-12-25 | 5.DVT1 | 1.Platform | 4.Build | S2 | Closed | [S3]Issue:1.DVT1a U5040,U5041 Solder open issue ，SMT suffered failure rate of 0.5% Root Cause:1.Cold Pad Design lead to Solder Open Solution:1.Expand Solder Paste 2.using cold pad design 2.Reseve Glue Design on this IC by fine adjustment hole on shielding case Plan: 1.DVT2A Verify | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-11-15 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]Issue: Ps/ALS sometimes not work after 1.2M drop . reboot ok . Clue:1. ME found that Position Over limit Root Cause:pop pin connect shortly open when drop ,recover after a short time. cause p-sensor work abnormal Solution：Proposal 1. ME check design Proposal 2. SW evaluate recover method at same time. Plan: 1.Follow up ALT DVT test result 2.Push Software Insert Recovery Mechanism 3.Push ME Analysis or Improve Spring Contact Stability DVT1A ，1st ALT ok ，follow up DVT1A 2nd ALT | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-06-20 | 4.EVT | 9.Memory | 5.2 BB Test | S3 | Closed | [S3]Risk:SD trace is too long (130mm length,More than limitation 77mm) Conclusion: keep good pcb layout，protect the signal, keep equal tace length. Verification:EVT Test, 1.4ns, 0.96ns , Risk Turn to Issue. Issue:SD card Interface Signal Integrity Fail, 200M Mode ;Clk,Data,CMD Rising Time/Falling Time Exceed 1.4nS,Creteria <0.96nS. Clue:1.200M Sandisk sd card ,SDR104 ,No Speed affection 2.100M （No Brand）Copy fail temporarily,Signal Integraty OK,low down clk to 50M ok. 3.Modify IO Driver Capability,can't meet. Root-Cause:Trace too long Solution:1.Optimize Routing,Less Gounding to lower down parasitic capacitance 2.Lower Down Clk when Data Error rate like P2,or Houdini | link | 威姐 |  | link | 6.No Change | 1.BB
2017-12-27 | 5.DVT1 | 8.Mods | 5.4 ALT | S3 | Closed | [S3]Issue:ALT WH103118 B1 can not power on with turbo charge mods. RootCause:1.Analog Mux Damaged lead to can't power on 2.Proposal:maybe caused by ESD/EOS Solution:1.Optimize Mods Pin ESD Routing in DVT2. Plan:1.Monitor | Link | 邦邦 |  | Link | 2.PCB | 1.BB
2017-12-27 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:Edu16 Charger Overvoltage Test 1/2 Fail Clue:1.D2, After 11V Charger Overvoltage test, the charge current changed to 1.5A（Initial 500mA ），can be recovered by restart, the test stop Root Cause: 1.It is not a OVP Issue,2.Why Trigger 1.5A Charging Mode is a SW Issue Plan:Support SW to Analysis. | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Unable to power on D1：After -15KV air discharge,power off,unable to power on Root Cause:1.LCD Damaged lead to fail to power on 2.Wrong Grounding Foam Position lead to ESD Damaged(Conclusion by Display zhuanghuajun) Solution:1.Enlarge Conductive Foam and Graphite Keep out Area ,Verify 1 unit evaluation pass Plan:1.Evaluation Thermal Side Effect. | link | 靓仔 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Display Missing Pixels D5：After-15KV air discharge,display missing pixels. Root Cause:1.Wrong Grounding Foam Position lead to ESD Damaged(Conclusion by Display zhuanghuajun) Solution:1.Enlarge Conductive Foam and Graphite Keep out Area ,Verify 1 unit evaluation pass Plan:1.Evaluation Thermal Side Effect. | link | 靓仔 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Display
2017-12-12 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:Cap Sensor Sensing Fail Clue:1.2 Channel Fail,Value 2000-5000 ,Normal value is 0. Root Cause:1.Antenna Switch output capacitance affection lead to sensing failure Solution:1.Add 82nH Inductor to cancel this affection Plan:1.Antena confirm the inductor affection,2.NA Sku keep run for data. 3.Latam Sku add 82nH inductor.4.Reserved inductor in DVT1B,Will determine the final solution after solution verification pass. | Link | 小熊 |  | Link | 1.SCH | 1.BB
2017-12-04 | 4.EVT | 8.Mods | 5.2 BB Test | S3 | Closed | Issue:The eyes height is fail, compare with Eagle it is fail too. Rootcause:1.Maybe due to the MDK to increase the length of lines. Plan:1. Check if there are some opportunity to improve the pcb layout. 2.Check if can test without MDK 3, Refer to the Mydp test result which using the same lines. | Link | 威姐 |  | Link | 6.No Change | 1.BB
2017-11-22 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：4 units boot up failure after ALT Root Cause: 1 VREG_OLEDB Abnormal result in Boot Failure 2 OLEDB_EN Abnormal result in VREG_OLEDB Abnormal 3 PCB delamination under Mods result in OLEDB_EN crack Solution&Verification： Solution 1:Wires on 9th Layer Keep away from Mods Conn Verification 1=DVT1B Verify Plan： 1.Mods Connector Changed to original version,Low risk | link | 文亭 |  | link | 2.PCB | 1.BB
2017-12-03 | 4.EVT | 3.Charging | 5.6 User Feedback | S3 | Closed | [S2]Issue:Shelby EVT2 can't compliant with Xiaomi 10W Type-C Charger. Clue:1.Factory Software 2.Moto 30W Charger is ok . 3.Verify Xiaomi 10W Charger OK(Include Low Voltage) 4.Compliance test is ok Root-Cause:Need issue confirmed Plan:1.Need to reproduce issue ,Proposal 1):Using 4X Extended USB Cable 2).Using repeater 3)Using USB Cable without D+,D- | Link | 林峰 |  | Link | 6.No Change | 1.BB
2017-11-27 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Risk: Flash Thermal Evaluation fail at 1.5A which exceed LED's Junction Temperature , and will damage flash led Clue: 1.factory flash calibration set flash current 1.5A(cool)+0A(warm)/ 0A(cool)+1.5A(warm) 2.Ibis use the same LED Flash,No defect in Factory,After sale 2.Thermal Evaluation result: Flash can work at 1.2A(cool)+0A(warm)/0A (cool)+1.2A(warm)/0.75A(cool)+0.75A(warm) Root Cause:1. Solution :1. Flash positive add vias 2. Flash positive enlarge copper paving Plan:1.Verify on DVT1A Same AS Ibis（simulation data） ，monitor | LINK | 芳梅 |  | LINK | 2.PCB | 1.BB
2017-12-01 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:WH102567 ESD Fail，Unit Can't Power On Clue：1.Restart Fail 2.disassembly and find no grounding for display module. Rootcause:1.Display damaged Plan:1.KP zhuanghuajun Analysis. 2. grounding display module in DVT1A . | Link | 靓仔 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-12-25 | 5.DVT1 | 12.EMC | 5.5 Certification | S3 | Closed | [S3]Issue: EN301489 RS Pre-test fail Clue：With this solution 1，#8#9Failed, Using Letv cable Pass -2018-1-13 Root Cause:1.Mic Bead cause the unbalanced which easily affected by RS 2. Solution:1.Remove Mic Bead, Pass ，2.Add 2 1.5nF Capacitor on Mic Channel and R&L to System GND,Pass | Link | 院长 |  | Link | 3.BOM | 1.BB
2017-12-29 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue:Vibration/Earpiece speaker/Alert speaker not work sometimes (function intermittently at 12/28) ,found by SW Yongbin. more units were found Clue:1. Log show I2C fail. 2.SMT suffered Solder open failure rate of 0.5% on U5040,U5041 Root Cause：1.Anx7805 cause I2C Abnormal 2.according to A5 cross section ,it should not related SMT issue Solution:1.Refer to <[S3]Issue:Vibration/Earpiece speaker/Alert speaker function intermittently during ALT> Plan:1.Same issue with another one ,combinate | link | 文亭 |  | link | 1.SCH
2017-11-15 | 4.EVT | 3.Charging | 5.4 ALT | S2 | Closed | Issue:EDU04 WH102186 fail Root Cause: 1. U550 Damaged by MosFET breakdown in over reversed polarity Voltage. 2. U550 reversed polarity Voltage SPEC is -0.5v/2A, and measured Voltage is -0.382V/1A ,-0.432V/2A in SPEC. 3. TCC retest 5PCS ,all pass. The design is available,only 1 PCS damage maybe cause by other reason.(etc. wrong test condition/ component single defect） Monitor in the next test. DVT1A pass | Link | 林峰 |  | Link | 6.No Change | 1.BB
2017-11-09 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | Issue:Synaptics Need 3.45V LDO Root Cause: SPEC requirement Solution：1. 3.45V LDO use On 2. change power input of 3.45V LDO from VBAT to OTG power 5V boost . Done 3. Choose 3.5V LDO for second source availible Plan:DVT1 Verify NO FOD in shelby | Link | 礼森 |  | Link | 1.SCH | 1.BB
2017-11-27 | 4.EVT | 12.EMC | 5.4 ALT | S2 | Closed | Issue:DVT EDu03 Eval - ESD Certification Test After +10KV air discharge at left side crevice in zone 16（Aging 10），Cannot open rear and front camera and vibrator no function,can't recover. Clue:1.LCD Grounding is not good Root Cause:Cap sensor damaged . No ESD protection now. (ANT TVS DNP in EVT because no sample) Solution&Verification:1.Mount ANT TVS，DVT1 Vefify Pass Plan：Monitor |  | 靓仔 |  |  | 3.BOM | 1.BB
2017-11-13 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | Issue:Unable to power on Clue:A3(1),A5(1),B1(1),B5(2) Root Cause:battery plug incorrectly Action： Factory correct it in coming build monitor 2nd ALT test result ME own | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-11-22 | 4.EVT | 10.USB-C | 4.Build | S2 | Closed | Issue:EvT2 can not recognize network in xiamen enginner lab Clue:1.Wuhan Fixture OK but Xiamen Fail 2 ADB can't Connect 3.EVT1 OK Root Cause:Limited Margin due to TVS used in USB D+,D- are 10pF Solution：Using New TVS with 1pF Capacitance |  | 威姐 |  |  | 3.BOM | 1.BB
2017-11-13 | 4.EVT | 3.Charging | 5.4 ALT | S3 | Closed | Issue:EVT1st ALT Charging abnormal Clue:A4(3),B2(3) RootCause:Cause by Low Temperature, Analysis:Log Provide to SW for analysis； Battery Power low to 50% easy to cause power off in -10℃ Solution： 1. charge to 100% and make sure battery >50% during ALT test ,verified ok. | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-11-10 | 4.EVT | 5.Camera | 5.1 Bring up | S2 | Closed | Issue:Andriod CTS Camera test item PIP(picture in picture) Failed Root Cause:1.Rear Camera & Front Camera Using the same CSI0 Data Channel 2.Share Same Reset Signal Solution:SW Disable parallel cameras for CTS test， NO need to change HW CSI design | Link | 芳梅 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-11-09 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | Issue:Noise when insert type-c earphones Root Cause: 1.Mic Bias 25Hz Switch Solution:1.Mic Bias constant open,Evalation OK Plan：DVT1A verify, Verify: OK | link | 院长 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-11-08 | 4.EVT | 9.Memory | 5.2 BB Test | S3 | Closed | [S3]Issue: Alternate Operation Fail Root cause:1.Variant BOM can’t invoke Alternate Part 2.Alternate Part need same Symbol and Cells name. Solution:1.Develop tool to solve it . |  | 芳梅 |  |  | 6.No Change | 1.BB
2017-10-23 | 4.EVT | 8.Mods | 5.2 BB Test | S3 | Closed | Issue:Mods I2S Tx no out RootCause:I2S Tx ，Rx Switched in front of MUX input Solution: 1. Short TX,RX, -liguoa---I2S verified OK 2.Switch TX ,RX on EVT-2 -liguoa - Done Verification:Verify on EVT2 | Link | 李果 |  | Link | 1.SCH | 1.BB
2017-12-21 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S1]Issue:With the charger can't turn it off,Will be automatically power on Clue: Root Cause:Mobile phone input ALT special instruction(fastboot oem off-mode-charge 0) Solution:Eliminate the instruction( fastboot oem off-mode-charge) | link | 李果 |  | link | 6.No Change | 1.BB
2017-12-16 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S3]Issue:SDA Pin of a MOD connector short to GND Clue: Root Cause: The mod connector short circuit Solution:DVT2 will change the old connector Plan: | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-10-27 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | Issue：Power Consumption Airphone :29mA RootCause: 1.Mods ANX7805 :20 mA 2. Cap-sensor :1.1mA 3. TP: 4mA Solution： 1.10/25 SW has been modified---weiweij 2.Because there is no firmware version cause, need to get the phone debug. Will follow blaine cap-sensor solution.-----caoyi 3. wil be optimization when get the formal TP ----liguo/yongbin Update Airplane 4.1mA 10/27 | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-10-12 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S3 | Closed | Issue：金手指厚度做成0.3mm，Spec is 0.2+/-0.02mm RootCause：some DFM mistake confirmation between CAD & Hongflex Solution： 1.grinding thinner 10pcs by hand- fanlf/liujjg 10/13 done 2.Hongflex re make the sample (10/12) chenwt |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.BB
2017-10-12 | 4.EVT | 7.Sensor | 4.Build | S3 | Closed | Issue：There is not U6160 in BOM(FPC2050 ,side FPS driver IC) RootCause：SCH Variant BOM affected by old Info Solution：1.EVT board only not SMT U6160. chenwt Done 10/12 2.Soler FPC2050 by hand for SW bring up . Chenwt 10/16 3.update BOM generation process,adding variant review step .fangmei 10/16 | Link | 芳梅 |  | Link | 3.BOM | 1.BB
2017-06-16 | 3.PEL | 8.Mods | 5.2 BB Test | S3 | Closed | Issue：EVB Mods Bringup suffer much RootCause：1.Clock&CS of SPI Swapped 2. M-PHY I2S Rx Missing 3.SPI Switch Signal LPI can't work Solution：1.Swap clock&cs 2.jumper wire 3.replace LPI-GPIO with GPIO | Link | 李果 |  | Link | 1.SCH | 1.BB
2017-06-16 | 2.PCL | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk: SAR sensor design， Cap sensor can support 3 ANT？（1 up +2 down）？How to design it？ Evaluation:Change IC from SX9310 to SX9324. More compatible for High Path capacitor（From 100pf to 200pf，same cost）？ Conclusion:1 Cap sensor can support 3 ANT （3 Bottom ANT） | link | 小熊 |  | link | 6.No Change | 1.BB
2017-07-25 | 2.PCL | 3.Charging | 5.2 BB Test | S2 | Closed | OVP design check,Moto has added OVP IC, Keep monitor |  | 靓仔 |  |  | 1.SCH | 1.BB
2017-08-15 | 3.PEL | 10.USB-C | 5.2 BB Test | S2 | Closed | Risk：Usb Eye diagram may fail because of Type-C connector on FPC | Link | 威姐 |  | Link | 6.No Change | 1.BB
2017-08-01 | 1.Concept | 10.USB-C | 5.2 BB Test | NA | Closed | Risk：IBIS Swiwming Water Proof Fail 2017-8-28：IP68 Canceled on NPI，turn NA Solution：Reserved ADC on CC1 for anti-water research ,Research it on EVT | Link | 威姐 |  | Link | 6.No Change | 1.BB
2017-06-20 | 1.Concept | 11.Thermal | 5.2 BB Test | S3 | Closed | Risk: Thermal design check . there should be high thermal Risk ,need further check Evaluation: Conclusion：It is fine according to the latest Thermal Simulation | link | 林峰 |  | link | 6.No Change | 1.BB
| 1.Concept | 1.Platform | 5.2 BB Test | S1 | Closed | Design：Key Design to compatible with Option C1，Option C2，Option D，Option E before 9/5 Conclusion: Design Changed | Link | 森森 |  | Link | 2.PCB | 1.BB
2017-08-28 | 3.PEL | 1.Platform | 5.2 BB Test | S1 | Closed | Issue：LPI GPIO can't use，Need xx more GPIO conclusion: Add IO Expander | Link | 文亭 |  | Link | 1.SCH | 1.BB
2017-06-16 | 1.Concept | 8.Mods | 5.2 BB Test | S2 | Closed | Risk:NEW MODs connector SMT RISK( Can pass Build and can pass ALT) Conclusion: here | here | 李果 |  | here | 6.No Change | 1.BB
2017-07-03 | 1.Concept | 10.USB-C | 5.2 BB Test | S2 | Closed | Risk:Type C ，switch control logic is correct？ Conclusion: It is ok | link | 威姐 |  | link | 6.No Change | 1.BB
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S3 | Closed | Risk:M-sensor placed on side of battery ,some Assembly risk Evaluation: 1. check with AKM porformance . 2. can we put it on main PCB?（base on new stacking） Conclusion:Place in the middle of Side Key FPC | link | 小熊 |  | link | 2.PCB | 1.BB
2017-06-20 | 1.Concept | 3.Charging | 5.2 BB Test | S2 | Closed | Product Design:Charging solution 20W？27W ？ charing IC solution is？(Impact thermal and placement) Conclusion: 27W Adpater +20W charging rate (not big switch solution) . Thermal risk is high. Any chance change to 20W Big switch solution？ Charging Solution back to 15W because of cost - 2017-8-1 |  | 林峰 |  |  | 6.No Change | 1.BB
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk:Barometer design ：ME requirement is for IP68？ Conclusion:check with Bosh that no IP68 phone MP with Bosh Barometer .Barometer can not work because the air can not go into the phone. Next Action: Any solution for air to go into phone but water can not go into it? Cost? IP68 Cancel on NPI -2017-8-23 | link | 小熊 |  | link | 6.No Change | 1.BB
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk:P-sensor ，How to design it in Notch phone？ Conclusion:Camera+SPK+P-sensor+camera,P-sensor on Flex ,now is ok. needed further tracking if there is any change | link | 文亭 |  | link | 6.No Change | 1.BB
2017-08-02 | 1.Concept | 10.USB-C | 5.2 BB Test | NA | Closed | Risk：FPS option 2-3 may have ESD risk Evaluation： Conclusion：Solution Canceled | Link | 靓仔 |  | Link | 6.No Change | 1.BB
2017-06-16 | 1.Concept | 4.Audio | 5.2 BB Test | NA | Closed | Risk:Use typeC For earphone interface，How to design FM（ANT） ？ Action:1.Inform Risk to RF,RF Own -Done 6/16 | link | 院长 |  | link | 6.No Change | 1.BB

## Quattro (hidden)
Date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Department
2019-12-16 | D.SHIP | 9.Memory | 6.Issue | S2 | Monitor | [S2]Risk:WDC Memory may exceed erase endurance specification which may lead to no turn on Clue1:Roburst2 have several No Turn on issue in EWG and DF due to UFS issue Clue2:P/E Cycle(Programing or Erase Cycle) limitation should under 1M, For Roburst2 UFS, Low Risk under 200K ;Mid-Risk <-250K; High Risk <=300K Estimated Average P/E Cycle=P/E Cycle Counter+71%x Initialization Counter ≈ 71% Initialization Clue3:For UMCP， the initialization Counter Coefficient should be low than 71% duo to bisc4 INAND New Generation Tech. WDC will feedback the coef by 12/20(CHN) Clue4:For Stingray,Initial Assessment P/E Cycle≈ 154K ( From 2 Stingray and 2 quattro Power Cycle Data).More data with more accurate estimate on-going ,12/20(CHN) The risk is true,we still need more data to have a more clear view. Root Cause： Why no turn on? 1.All Free SLC Block used for improve write operation was wrongly erased after initialization by Firmware due to they are wrongly recognized as "Not Erased" even for erased block,After exceeded endurance Specification,it will lead to no turn on . From WDC FA on R2. Why those opeartion issued? 2.1 Those operation will be triggered after VCCQ Power Down in Sleep mode or HW Reset issued. From WDC FA ,It is known issue 2 months ago in WDC. 2.2 Why Free Block was recognized as "not Erased"? UFS FW Design Logic error issue Solution: 1. Correct memory FW 1.without erased all free block operation; 2.enable a new SLC(6% memory capacity consumed) and update,by OTA or by service center , WDC will release solution by 12.23 |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-22 | C.RAMP | 2.Power | 4.Build | S2 | Closed | [S2]Issue:Display Flicker during Charging after Patched for Flicker when Loud Speak. Clue:Only when Battery Fully Charged Root Cause: Why Display Flicker when Charging? 1.Input Charging Voltage Ripple 200mV Observed and ELVDD 120mV Ripple observed when Charging to Full battery Capacity, TianMa Display Need 5mV . 2.ELVDD Enter Force Boost Only (0xDE70=0x80) ,No Issue under Charging with Original setting 0x00(Boost Only Mode and Boost+LDO mode Dynamic Switching) duo to when input Voltage Transient over 200mV-300mV， Pmic Will Enter Boost+LDO Mode with low ripple(7mV). . Why ELVDD Force Boost Only（0x80）? To solve issue when Loud Speak(0.7% Failure Rate) 3.0x00(Dynamic Boost&LDO mode) have issue Switching when Voltage Transient over 200mV-300mV that happen during Loud Speak which lead to over 5mV Ripple 4.1 TianMa Display Only Accept 5mV Ripple, SDC Display accept 50mV due to AVC Tech. 4.2 0x81 mode consume extra 20mA Power current. Solution: 1.When Charging , Set 0xDE70 as 0x81（Force Boost +LDO mode，Extra 20mA Power Consumption,Acceptable under Charing） When not Charging , Set 0xDE70 as 0x80 (Force Boost Mode, No Extra Power Consumption) HW Validate OK. SW Release 7/26 | Link | 敏敏 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-05 | C.RAMP | 2.Power | 5.6 User Feedback | S3 | Closed | [S3]Issue: 7/5 SW summary User Feedback that Shut Off Suddenly when using DouYin, Camera Capture with Music Background or Duo in Low Battery Status. Clue:Stingray 4.6A, Quattro 29.59 6A, Quattro 29.45 5.5A RootCause: 1. Shut Off Due to Supply 2.8V over 3ms on PMIC. Exp:VBAT_L2=2600mV(deglitch=8mS) or IBAT_L1=6000mA(deglitch=8mS), it will trigger BF fault and cause BATFET open. 2. 2.8V over 3ms on PMIC duo to High Power Consumption in Audio Smart PA.Over 7.5A maximum Current Observed in DouYin APP. 3.1 BCL Setting From 5.5A to 4.5A. 3.2 High Audio Smart PA Gain Setting. 30% bigger Current Drain than Stingray. 29.59 have 9% Bigger Current Drain Than 29.45 Solution: 1.Enable Smart PA Low Voltage Protection, 50ms or 5ms Release time, HW Verify OK. KP Audio team check 5mS not impact audio performance , SW will merge this change . by 7/10 Under Pressure Test and DFer Validation | link | 敏敏 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-07-05 | C.RAMP | 5.Camera | 5.6 User Feedback | S3 | Closed | [S3]Issue:29.59-2 Thermal Camera Test, 1°C Higher than 29.49 ,but in test Tolerance. Clue1:59-2 : 42.9°C @15Min ; 29.49 41.9°C@15Min ，39.6°C@10Min Clue2:Camera Power 3% increased observed. Root Cause:1. Power Consumption 900mA+@Camera Preview, While Z6 Pro with Same 48M only 600mA 2.Camera Team investigate. Solution:Monitor. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-06-14 | C.RAMP | 10.USB-C | 5.2 BB Test | S3 | Closed | [S3] Issue: Quattro Compatibility Test with M14（ThinkVision new generation Display）10% Display Low Resolution 640X480， about 1-2/10 Failure rate. Clue: 1080p normally Clue:External Adaptor with M14, No Issue Clue:Change Another Cable , No Issue. Root Cause: Why Low Resolution? 1.EDID Read error Exp:Log Analysis. Result:EDID Read Error . Conclusion:Phone side can't read EDID. Why EDID Read Error? 2.Aux P/N Signal Transaction Affected by OTG Vbus Sink Current Exp2.1: Observe Vbus Waveform, Result: Aux Read Time slot in VBUS Sink Current. Conclusion: Aux P/N Affected by Vbus sink current. Exp2.2:Delay Aux Reading by 5S , Result:No Issue , Conclusion: Aux Reading avoid Big Current can resolve issue. Why Aux P/N Signal Affected 3.1 Aux P/N in Cable Bad Common mode rejection Exp3.1.1:Verify Black Cable and white cable on differential interference. Result:Aux P and Aux N have different differential interference. Conclusion: Cable Matters. Exp3.1.2: Compare Black Cable with Standard Cable. Result:Aux N is more close to Vbus than Aux P which lead to different Common Mode Rejection. 3.2 OTG Output big Ripple duo to Vbus Power Exp3.2: Measure WaveForm,Using External Loading . Result: 0.65V Ripple@200KHz (Target <0.5V Ripple) when Current drain greater than 900mA (OTG enter PFM Mode) Observed. Conclusion: Big Ripple Observed when Current great than 900mA. Why Big Ripple? 4.OTG of PM6150A Enter PFM Mode and unstable Exp4.1: Switching WaveForm Observation Result:Big ripple when enter PFM mode. Conclusion: PFM mode Alter lead to big ripple. Exp4.2:Change 4.7UF to 10uF on MID_CHG, Result: 0.2V Ripple@800K ,Acceptable. Conclusion: Increase capacitor on Mid_CHG can solved this issue. Solution: 1.Set EDID Read Fail retry Delay to 4S -SW Need CR - Recommend 2.Modify Type-C Cable, Twisted-pair Aux P&Aux N. - ThinkVision Team - Not Recommend 3. Change C2412 to 10uF ， Cost Up $0.003 - Baseband - Recommend , Bom Changed | Link | 芳梅 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-06-14 | B.PVT | 6.Display/Touch | 5.4 ALT | S3 | NA | [S3] Issue: Display Missing Pixel after ALT Drop Estimate to drop this issue ,Due to wrong Test Method-Tear Down Crack Display cause Abnormal PCB Strain. |  | 芳梅 |  |  | 6.No Change
2019-06-14 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3] Issue: Display FOD visible after ESD Clue: ESD at zone15, LOGO LIGHT area. Recovered after 2 minutes automaticly. Clue: Root cause: 1.LHBM Reg Affected, 1. Panel Abnormal , TE Lost, Panel Recovery Triggered and Recovered. Solution: 1.SW recovered and NTF 2.Close LHBM 1.Close LHBM |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-06-14 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:[S3] 1.P sensor no function after ESD, with permanent damage. （EDU03） WH116676 1 unit fail 1/6 Clue: 1. ESD at zone 1, front camera area. ME Status OK. 2. In 8 TCC tests, 42 units in total before PVT, no this issue. 3. 8 more PVT units Zone1 ESD pass .then these 8 PVT units stress test pass(100 times +15kV AD and 100 times -15kV AD on zone 1), 5 times strengthen test. Root Cause: 1.P sensor IC VDD is damaged, with low impedance. With about 100mA current, IC heats. 2. Receiver deco 2nd discharge. Solution: 1.Low Risk :Accept 2.modify Grounding conductive fabric （make a path for Receiver deco 2nd discharge）,ANT Approved, Runing Change. | Link | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-06-04 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2] Issue 2: [Quattro] [Factory] [CQA1] test result:P-sensor is at Near status all time. Rootcause： 1.Near status caused by high CT due to Rubber cover the IR LED cause reflection 2. DVT2B Rubber dimensions：Out of tolerance 3. Wrong Rubber Design due to incorrect Vendor Spec Solution： 1. use MP tooling Rubber that within tolerance ---PVT import 2. change the rubber design ,here ---Pilot Import 3. change threshold to increase 50% margin.---PVT import | link | 文亭 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-31 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | S3 | Closed | [S3] Issue: sometimes Motoaction can not work outdoors IKSWP-89083 clue：1. When the IR channel data is too high，Pdata will increase and fluctuate. Root cause： 1.Moto Action suspend due to P-Sensor report Near status(Pocket Mode),Observed from Log. 2.Low Threshold observed as a result of low noise calibration which triggered by wrong P-Sensor Data under normal crosstalk value. 3.Innormal P-Sensor Data reproduced after P-Sensor quit sunlight Mode. (Sunlight Mode is to solve correct response under outdoor IR enviroment,by setting Pdata=0 and Report Far Status). 4.Why P-Sensor output a wrong data when quiting sunlight mode? Can not reproduce by Vendor RD. Solution： SW Working Around. 1.Optimize Low Noise calibration :using Average data without Peak and Valey data to calibrate. 2.Optimize Low Noise calibration : Do not calibrate when IR channel is higher than 1oooo 3.Debounce Trigger ,Only when 4 continuesly valid data compare to originally 1 . validated on temp patch. 4.Set lower sunlight mode to level 1 which is easier to enter (original is level3) , validated on temp patch. 5.Low Down 5mm detection distance(20mm Near,25mm Far) to increase threshold to 180,120（MPS=2）. DF Validate Pass. | link | 文亭 | 小熊 |  | 4.Parameter
2019-05-31 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | [S2]Issue: 40℃高温关机充电4 hours，充入电量未达标准3.9V Clue1:从log分析，高温充电下，充电thermal机制启动，充电电流降到300mA，Quattro 电池4000mAh，电量大，充电速度太低无法满足需求. Clue2:thermal config 调整，最低充电电流提到700mA，自测Pass，实验室测试临界pass，与预期不符，从log分析，充电误进USB模式，导致充电电流只有500mA Clue3：经过实验室压力测试，关机状态下，常温或高温下，都有概率会进入USB模式，开机不会 出现fail的概率和USB cable线插入的速度有关，慢速插入时复现概率高 Clue4：测量fail时出现的波形，关机下，系统先进bootloader，再进kernel，初始化完成后，亮屏充电，发现在bootloader下做充电状态识别时，会有异常波形出现，导致无法进入BC1.2之后的QC3.0协议，在后续的kernel mode 继续以异常的状态持续充电 Root Cause: 1.bootloader模式下，充电状态识别容易出现异常（尤其是慢速插入时），而开机状态，充电识别初始化在kernel层完成，在kernel层的充电识别初始化，未发现问题 2.Proposal:Moto Bootloader solution： 在进入Kernel后重新做一次充电状态识别，可以有效排除慢插的影响，确保系统识别正确的充电类型 经多次压力测试，OK | Link | 林峰 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-29 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: DVT2A unable to power on after ALT complete Clue: 1. leak current: 15ma when power off 2. the voltage of DVDD(PM6150) is 1.5v ,the normal voltage is 1.8v 3. B_PLUS is 1.654V,the normal voltage is colse to vbat voltage. root cause: 1.PM6150 is damaged after ALT 2.The corner chipping already propagate to the active circuitry area, so it do affect the function 3.High PCB Stain due to abnormal Test Method that Tear Down Display. Solution: 1.Monitor next ALT. | here | 敏敏 | 院长 |  | 6.No Change
2019-05-16 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S2 | Closed | [S2]Issue: DVT2A Quattro Thermal Failed 4.3℃ on Camera Photo Clue: 1.DVT2B re-test on camera 43.1°C,improve 1.2°C. Root Cause： 1.Camera Fine Tune Not Fixed and power consumes more 2.Thermal config Triggered but failed to mitigate the surface temperature. Solution： 1. HW: CPU heat spreader Expand 2. Active photo off @Back Therm>40°C 3. MAX backlight 100%->95% @ Quiet therm>45℃ 4. turn off log 5.Turn off WMP(Thermal Log APK) PVT Validate Pass | here | 林峰 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-29 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3]Issue: standby U510( USB DP ss mux) current leakage 0.6mA Root Cause: U510 pin 18 EN is pulled up to L7C which is always on , when EN=H，U510 active current is 0.6mA. solution： Change the power supply to L17A which is used for USB PD. L17A could be powered off if there is no usb or dp device. |  | 芳梅 | 李果 |  | 1.SCH
2019-04-29 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S2]Issue: DVT2A ALS Angular in Y axis is only 25 degree(Standard=33 Degree?) Clue: 1. Test in Vishay show ALS angle in Y axis only 25 degree 2. if no silicone case, 27 degree in Y axis solution： By adjust LCD brightness response curve | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-06-07 | B.PVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: Quattro No turn on issue after ALT drop-Link Clue1： U2400 Pin solder Crack in DVT1B & DVT2A Clue2： U1600 Pin solder Crack in DVT2B Clue3 : all no turn on issues happened after display crack. Clue4:No issue in Tumbling Test. Root Cause： 1.U2400/U1600 issue Exp 1.1: current observation. Result: Conclusion: U2400 abnormal 2.U2400/U1600 solder crack Exp 2.1: red dye test. Result:U2400 solder Crack found by red dye test.Conclusion: U2400 solder crack. 3.U2400/U1600 weak solder joint. Drop Exp 3.1 Cross section failed one .Result: by 6/18 Exp3.2 Cross section normal one. Result:Solder Joint Normal .Conclusion: No Issue. 4.Proposal: ME change lead to high PCB Strain Exp 4.1: Harder Thermal Pad . Result: Failed too . Conclusion:Harder Thermal Pad also failed. Exp4.2: .TBD 5. No Sealess Assembly display in position lead to high PCB Strain after display crack and removed for analysis. Exp 5.1: keep original display until ALT drop finish(loop 5) result:Function and Red-dye no Issue . Conclusion:Drop test without Sealed Display lead to Extreme High PCB Strain that cause Memory and Pmic Solder Crack. Solution： 1.add underfill in U2400 & u1600,optimizing underfill cost . 2.Remove underfill | Link | 林峰 |  |  | 6.No Change
2019-05-06 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | NA | [S3]Issue: FOD self test fail, but can recover withou rebooting Clue:1. -15KV air discharge at zone 11(Aging 10),Fingerprint Self Test fail, then return to the previous menu,after executing the “Fingerprint performance Test“ test item,then run "Fingerprint Self Test" item.it can be pass 2. Sensor is alive. AP SPI port is well functioning. Solution: 1. SW asked vendor for help. 2. Update SW, PPH 29.29 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-27 | 7.DVT2 | 11.Thermal | 5.6 User Feedback | NA | Closed | [S3]Issue:User Feedback Quattro Got Hot using 65W Type-C Charger（T480 Note Book） Clue:Test 65W , Issue Can't Reproduce in XM SW,XM HW,BJ Thermal Root Cause: Need confirm Issue first. |  | 林峰 |  |  | 6.No Change
2019-04-29 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2]Issue: DVT2A P-sensor TCMD unstable Clue:1. JOT Fixture may impact the test result ----ENG chen Huaiyu /WWTE Tang Muzong 2. SW DVT2A_04 get the data different per test , should be some problem ---SW Huangjq9 solution： SW&WWTE Own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-29 | 5.DVT1 | 10.USB-C | 5.4 ALT | S2 | Closed | [S2]Issue: DVT1B ALT-WH115686 ， A1(3) A1:TH/TC,USB charging is normal, but fail to connect computer. Clue： DM,DP common mode filter open , replace it and remove TVS on DP ,it is ok. Root Cause: -Why TVS&CMF Damaged? 1.External High Voltage on DP Exp1:Apply 9V on TVS with 1A Discharge Current. Result:TVS Damaged Observed. Conclusion:TVS and CMF damaged on DP duo to High Voltage over 9V Exp2:Draw Vbus Log and Pivot out. Result: Continues Voltage over 9V found . MAX=12V 2.Proposal: SW Issue? Drop Exp:Observe Normal One VBUS. Result:Under 5.5V . Conclusion: Not SW Issue. -Why over 9V voltage on DP? 1.Vbus short to DP due to Bad USB Cable or Bad Charger or Water Ingression Exp2:Mark ALT USB Cable and Charger , Observe the following ALT Test. Monitor if new failure. Result:the third failure happend Exp:Using Charging Monitor test the Calbe and Charger. Result: Heat found between Cable and Charging Monitor. Conclusion: Charger Broken duo to USB Cable Short found. -Why Over 9V on Vbus ? 1.Proposal:Charger supply Over 9V duo to D+Or D- short to Vbus Exp3:Short D+/D- with tweezers . Result:Vbus go 10V-12V. Conclusion: NA -Why USB Cable Short? Artifical USB and Plug Plastic perished and all fallen off. Bad cable solution： 1. Using New Cable & Charger in latest ALT of Quattro. 2. Discuss with TCC Lab to use reliable USB Cable in ALT Test. | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-10 | 5.DVT1 | 1.Platform | 4.Build | S2 | Closed | [S2]Issue: Factory IF QBlank Flash Issue ，1-3% NTF (Unknown Device,) Root Cause: 1.Soft Reset After Provision lead to multiple channel conflict. Solution: 1.SW Optimize Soft Reset by Adding 1S Delay between Provision and Bootloader Flashing. | here | 文亭 | 小范 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-22 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S2]Issue: DVT1B ALT WH115309 ，Not turn on after ALT loop 5 (6 in 12) Clue：Cross section， not abnormal found between DVT1A & DVT1B Root Cause: 1.U2400 PM6150A Solder Crack Found , Confirmed by MDU44 2.High PCB Strain Lead to Solder Crack Exp:Add Bucket Holder ,Result:6/12 Failure -> 1/10 Failure ，Conclusion:Significant Improved. Exp:Add Harder Thermal Pad on U2400,DVT2A Validate Pass Exp:Under Fill U2400,Result:DVT1A Validate Pass. solution： 1.Add Bucket Holder 2.Add Harder Thermal Pad 3.Backup:Underfill U2400, DVT1B ALT Pass. | link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | NA | [S3]Issue: TP no fuction - recoverable Clue: 1. +8V air discharge at zone 3(Aging 10),touch screen no function,press the power key 10s times later power off,press the power key to reboot recovered.(4/15 10:55)(Front camera(and Front flash) is ON ) 2. Zone 3 is the bottom side of display. Root cause: TP keypart own |  | 吉吉 |  |  | 6.No Change
2019-04-10 | 5.DVT1 | 1.Platform | 4.Build | NA | NA | [S2]Issue: Factory IF QBlank Flash Issue ，1-3% NTF (Unknown Device) Root Cause: 1.Proposal: Moto Multi-Downloading Tools +USB3.0 Issue? (No Issue feed back from other vendor of QC SM6150) Exp1:Using Qualcomm Multi-Downloading Tools + USB2.0 Tools Resource:PI Align with SW on requirement -IMG include UFS provision,reset and blank flash in PBL mode Solution: NPI own ，BB monitor and support |  | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-24 | 5.DVT1 | 5.Camera | 5.2 BB Test | S2 | Closed | [S3]Issue:DVT1A Quattro tele camera OIS_VDD and GRO_VDD are swapped Root cause: OIS_VDD and GRO_VDD are swapped in camera module 2D drawing. Impact: All units before DVT1B Tele camera OIS cannot work（Not including DVT2A）. Solution: change the OIS_VDD and GRO_VDD in DVT2A sch Action : 1.Notice PI & HPM DVT1a&DVT1B units Tele camera OIS cannot work 2. rework units for china team bringup OIS 3. mail how to rework the units for chicago team . 4.optimize 2D drawing Lesson learn : optimize 2D drawing requirement with Camera Module Vendor . Such as add power voltage requirement in 2D mapping ,Add current requirement for each power in 2D Drawing . etc | link | 邦邦 |  |  | 1.SCH
2019-04-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3] Issue: P sensor no fuction after ESD, recover after reboot Clue: 1. SW version is 29.15 2. P sensor could get no fuction without ESD, just covered by finger. Root cause: 1. P sensor fuction bugs in SW 29.15 2. ESD recovery works well in SW 29.16. 3. TCC re-test P sensor fuction after update SW 29.19. No issue this time. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-22 | 5.DVT1 | 7.Sensor | 6.Issue | S2 | Closed | [S2]Issue: DVT1B, NqTL1Q0095, fail to open every camera Clue: No data read from A+G sensor in CQA test Root cause: 1. Camera software combines A+G sensor in its algorithm, if sensor is inactive, camera will fail to be launched. 2.Question:Why A+G Failed? persist.img data have been erased, sensor can't download their parameter and stop starting. Reflash persist make sensors all work normally | link | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone drop call after ESD Clue: 1. +8KV air discharge at zone 12(Aging 10),Dropped call.(4/15.14:25-14:35)(In a call) 2. zone12 is bottom side of battery door. Root cause: Unreproduciable after 200 times +-15kV AD, with phone keypad hidden Unreproduciable in DVT1B 2nd EDU03 test, WH115370 |  | 吉吉 |  |  | 6.No Change
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: System stucked after ESD Clue: 1. +8KV air discharge at zone 11(Aging 10),Picture jammed,press the power key 10s times later power off,press the power key to reboot recovered.(4/15 10:55-11:05)(Rear camera(and Rear flash) is ON ) 2. Zone 11 is the right side of battery door. Root cause: Unreporducible after 200 times +-15kV AD Unreproduciable in DVT1B 2nd EDU03 test, WH115370 |  | 吉吉 |  |  | 6.No Change
2019-04-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: DVT1B +8KV air discharge at zone 10(Aging 6),Drop call,picture jammed,restart cannot be recovered, Re-pair Bluetooth headset recovery Clue: 1. zone 10 includes cap sensor ant, div ant and bluetooth ant. 2. From DVT1A to DVT1B, bluetooth ant's GND inductor(2.7nH) is removed. 3. Another new unit could reproduce this issue. Root cause: SW Issue, IKSWP-79280 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-24 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:DVT1B Display go black when calling with DVT1B ，7 pcs Root cause:1.P-sensor Rubber change in DVT1B Exp:Temp parameter check ok by 4/4 ,Done Solution: 1.Provide BAT to update new Parameter. 2.SW ready by 4/8 PPH29.9 Lesson learn : need to follow up Change impact .P-sensor Rubber change impact Factory build and TCC test ，when the change was confirmed need to change SW in time for them .（for User too） | link | 小熊 | 文亭 |  | 4.Parameter
2019-04-05 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | Issue:Quattro DVT1A FVC L1A MXC06（WH114507）D3, alt camera no flash RootCause:Proposal: Proposal:1.48M （rear main camera）Connector Release， Lead to CQA rear 1 viewfinder torch on flash ledTest Failure 软件逻辑上用camera id识别camera关系，48M的camera id正常为0，连接器松动，初始化失败，id 0被分配给其他的Camera。所以在rear 1 viewfinder torchon中看到的是其他camera的图像。 经验证，该机器flash LED自身功能正常。 2.Why Connetor Loose？ Solution: 1.ME Own |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-24 | 5.DVT1 | 5.Camera | 5.2 BB Test | NA | Closed | [S3]Issue:Quattro DVDD Ripple when work，（哪个camera？什么情况下面出现） Root cause:Camera Current Drain Solution: DVT2A Reserve 1 LDO. | link | 邦邦 |  |  | 1.SCH
2019-03-24 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:The video was stucked(Picture jammed) during ESD testing Root cause: 1. SW bug(IKSWP-73588) Solution: SW version update |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-25 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S2 | Closed | [S2]Issue: DVT1A Tianma Display Flicker found under gray Scale. Root Cause: 1.Tianma Display can't endure 5mV dynamic ripple of ELVDD. 2.ELVDD Power Ripple 5mV when Power Mode Switching on non PSRR mode. Solution:1.SW set 0xde70 register to 0x80,force ELVDD circuit work at boost only mode. | Link | 敏敏 | 院长 |  | 4.Parameter
2019-03-20 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: DVTA ALT WH114449 A1 ，Auto power off 1time in loop3(1 in 12) clue: 1.after Loop4 ，it always power off after drop 2.Press Top PM6150 Shielding case ，Reproduce case 3.remove rear housing ，reproduce （so it is PCBA issue） 4. remove PM6150A Shielding case ，Reproduce 5.remove PM6150 Shielding case ，can not power on 6. this ALT units were built with temp shielding case ，which can not protect PCBA well. 7.Measure power (primary power Vreg_BOB=0V ,So PM6150A do not work completely ) Root Cause: 1.U2400 PM6150A Solder Crack Found , Confirmed by MDU44 2.Temp shielding case have weak protection Solution： 1. Update New shielding Case , 2nd ALT Test good , Mdu44 for double check pass too 2. Backup solution:underfill for DVT1B 2nd ALT&tumbler ---linfenga | link | 文亭 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-19 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Not turn on after tumbler test WH114467,D1&D2 （2 in 5） Clue: 1.D1 &D2 Power on current 110~130mA ,can go into 9008 mode with V+ key,but can not download. (should be memory issue) 2.found Shield case is too weak ,and more than 25% unsolder 3. D 1 press U1600 then can turn on Root Cause: 1.U1600 Memory Solder Crack due to Tumbling, Confirmed by Mdu44 2.Temp shielding case have weak protection Solution: 1. Update New shielding Case , 2nd tumbler test(With correct shielding case) pass 2. Backup solution:underfill for DVT1B 2nd ALT&tumbler ---linfenga | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-19 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: Front camera preview fixed after ESD test. Recovered after reopen camera app. Root cause: 1.No GND for front camera 2.After grounding, issue not reproduce. Solution: Add Grounding area. After enhancing GND, this issue is not reproducible in DVT1A 2nd ESD test. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-19 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: P sensor no function after ESD test. Recovered after reboot. Root cause: 1. Air gap around P sensor IC. Solution: 1. need SW recovery ,Tracking 2. ESD recovery works well in WH115318 |  | 吉吉 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-18 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:P-sensor no function Clue: Root Cause: Rubber skewed ME will be in charge of this issue. |  | 小熊 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-01-09 | 3.PEL | 1.Platform | 3.Review/Simulation | S3 | Closed | [na]Simulation:High Strain on BGA4 0.43%,BGA3 0.58%（pixworks&Audio codec ） Root Cause: 1.PCB Strain 2.Drop Crash Solution:1.Monitor DVT1 ALT ， Red-Dye Data & tumbler test result 2.Reserved DVT1B underfill ，need to check how to build DVT1B | here | 林峰 |  | Simulation | 6.No Change
2019-03-01 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [s3]DP over Usb-c didn't work on AR Prototype of nReal（若太科技） Clue:1.Work on DP Display RootCause: 1.USB SS&DP Coexistance Config? Exp:Get USB+DP Hub to verify the co-existance 2.Not Fit with This AR(Need Customization) |  | 芳梅 | 邦邦 |  | 6.No Change
2019-03-20 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Closed | [S3]Issue: DVTA Factory IF 9008 and fastboot mode can not get USB3.0 clue:it is ok when board Power on Root Cause:Switch power L7C not turn yet in Fastboot mode and 9008 . Plan: 9008 mode ：not support USB 3.0 on Quattro Fastboot mode ：SW issue ,Yuecai solve it at 3/21 ,will submit into DVT1B SW by 3/26 |  | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-03-18 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue:No Main display after Shaker right (WH114449 B3 loop1) Clue: Root Cause: 1. can't turn on caused by side-key FPC Dome invalid. ME will be in charge of this issue. |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-02-27 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3]Issue:Display blink some time ，Worse with Adaptor FPC Clue: change mipi 1.09 G from 1.14G ,improved . but fail too with Adaptor FPC Root Cause: Pw8368 insertion loss 1.EMI filter impact? Exp1:Replace EMI with 0R Resistor 2/28 No improvement 2. Pixelworks Insertion Loss? Exp2-1:works under normal mode is ok with Adaptor FPC, but the hardware bypass mode fail. 2/28 Exp2-2: Compare the mipi signal Waveforms，hardware bypass mode is much worse than normal mode 3/1 Exp2-3: mipi Impedance in the px8368wm =100 ± 20%Ohm, but the mainboard PCB and display panel mipi = 85 ± 20%Ohm Exp2-4: Pixelworks Vendor can't putout the Insertion loss data Exp2-5: Compare the MIPI waveforms before and after Pw8368, the loss makes the MIPI quality bad 3.SW Configuration on MIPI Signal Integraty, Exp3-1:.MIPI Drive Strength Increase to 0xFF(default 0x88) ，no improvement 3/1 Product Team Reject this feature due to MEMC not remarkable |  | 芳梅 |  |  | 1.SCH
2019-02-27 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue：Board ESD Evaluation Display easy to go dark Clue: The system is well functioned. Root Cause: 1. No ESD recover strategy in current SW version. 2. No TE signal after screen blanked. Panel IC died. Solution: Pixelworks FAE may provide ESD recover version if possible. Product Team Reject Pixel Work due to MEMC not Remarkable. No this issue in DVT1A PCBA, but need to sheild JTAG connector. |  | 吉吉 |  |  | 1.SCH
2019-02-27 | 4.EVT | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3]Issue：USB 3.0 SS ，flip test fail ( 1 side can work ) RootCause: SW Config Solution:SW re-Config |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2019-05-16 | 7.DVT2 | 3.Charging | 4.Build | S3 | Closed | [S2]Issue: 40℃高温关机充电4 hours，充入电量未达标准3.9V Clue1:从log分析，高温充电下，充电thermal机制启动，充电电流降到300mA，Quattro 电池4000mAh，电量大，充电速度太低无法满足需求. Clue2:thermal config 调整，最低充电电流提到700mA，自测Pass，实验室测试临界pass，与预期不符，从log分析，充电误进USB模式，导致充电电流只有500mA Clue3：经过实验室压力测试，关机状态下，常温或高温下，都有概率会进入USB模式，开机不会 出现fail的概率和USB cable线插入的速度有关，慢速插入时复现概率高 Clue4：测量fail时出现的波形，关机下，系统先进bootloader，再进kernel，初始化完成后，亮屏充电，发现在bootloader下做充电状态识别时，会有异常波形出现，导致无法进入BC1.2之后的QC3.0协议，在后续的kernel mode 继续以异常的状态持续充电 Root Cause: 1.bootloader模式下，充电状态识别容易出现异常（尤其是慢速插入时），而开机状态，充电识别初始化在kernel层完成，在kernel层的充电识别初始化，未发现问题 2.Proposal:Moto Bootloader solution： 在进入Kernel后重新做一次充电状态识别，可以有效排除慢插的影响，确保系统识别正确的充电类型 经多次压力测试，OK | here | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor

## Andy NA (hidden)
Date | Phase | Block | Source | Severity | Status | Andy Issue | Doc | Owner | Assistant | Sheet | Change?
2017-12-21 | C.RAMP | 12.EMC | 5.6 User Feedback | S1 | Closed | [S1]Issue：SPK Degrade Clue:1. Root Cause:1.Cause by ESD? Solution&Verification: Plan: FuPan: |  | Yangwla |  |  | 6.No Change
2017-04-24 | C.RAMP | 12.EMC | 5.4 ALT | NA | Closed | [NA] OK2Pilot ESD Fail,SPK Noise Issue:ESD Fail on Zone1 -15KV on Alt ,1/2. Root Cause:Find that Conduct Foam Grounding not good ,100Ω，out of spec 3Ω Solution:Press Conduct Foam on FPC to ensure the grounding，and then Assembly on back Housing. Verificaion: Verify ESD 4 pcs on 4/27：WH100063-Pass Research 1:Further Diving on Bead Effect -yangwla Research 2:ESD TVS Part Near by Contact Pin Research - yangwla | here | Yangwla |  |  | 3.BOM
2017-03-22 | 7.DVT2 | 11.Thermal | 5.5 Certification | NA | Closed | [NA]Issue:TMO Thermal Pre-Test Fail ,Gap 5°C Root Cause:Can't Meet TMO Standard Solution: Waiver With TMO Plan: 1.TAM Dialog with TMO on this case by TBD | here | Liguoa |  |  | 6.No Change
2017-04-13 | B.PVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3]Issue:Sku2 EUT with second source Charger,CE 301489 RE test has 2.1dB margin,FCC 15B RE has >3dB margin Root Cause:Andy NA EUT Dvt2 A ,Assemble parts mix with first and second source,impact the RE Level Solution:Use the First source assemble parts Plan: Andy NA EUT must guarantee that has no Mix and Match of the first and second source of assemble parts | here | Yangwla |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2017-02-27 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3] Sensor No Function found in ALT . Issue: Andy NA DVT2B Alt 2pcs fail:Sensor no Function Root Cause: P-Sensor Solder Short between IC & interposer board Solution:PE Lead (eminent change SMT line which with SPI ) Plan:PVT SKU2&3 use new samples for control run . | here | Chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2017-02-17 | 7.DVT2 | 12.EMC | 5.3 EE DVT | NA | Closed | After +15KV discharged at zone9(camera&flash&MIC2),Mic 2 no function:C2 | here | Yangwla |  |  | 2.PCB
2016-01-03 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [S1] ESD Fail,SPK Degrade Issue:ESD Fail on Zone1 -15KV on Alt ,1/2. | here | Yangwla |  |  | 1.SCH
2016-01-05 | 5.DVT1 | 7.Sensor | 5.3 EE DVT | NA | Closed | P - sensor anti-fog test, at the same time arranged SKU1 and SKU3 SKU1 fail, but SKU3 pass | here | huangls |  |  | 4.Parameter
2016-12-29 | 5.DVT1 | 8.PCB | 5.4 ALT | NA | Closed | ALT/AT&T -Boot up Failed | here | Liguoa |  |  | 2.PCB
2017-01-23 | 5.DVT1 | 12.EMC | 5.5 Certification | NA | Closed | Andy CE Certification RE Test Failed | here | yangwla |  |  | 3.BOM
2017-01-11 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | Bad 5W（1A)） charger issue. change SW and pass | here | wuxm5/Chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2016-11-22 | 4.EVT | 12.EMC | 5.2 BB Test | NA | Closed | Issue:RF Buzz Noise Condition:NS Cancel ，Mic_GND Connect to Pmic_GND Result: -46dBV/-48dBV | here | Xiaozh1 |  |  | 2.PCB
2016-11-29 | 4.EVT | 12.EMC | 5.2 BB Test | NA | Closed | EVT ESD Fail,P-Sensor No Function | here | yangwla |  |  | 2.PCB
2016-11-29 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | Andy EVT Edu14 surge Failed | here | Xiaozh1 |  |  | 1.SCH

## George NA (hidden)
Date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2017-05-31 | B.PVT |  | 4.ALT/DVT | S3 | Closed | [S3]Issue:psensor no function in ALT loop5 -Chenwt RootCause: PAD crack were found on Both PCB & Module .There may be some crash during assembling since silicon rubber case assembled well and no obvious deformation observed. Solution: Monitor to see if it happened twicely. | here | chenwt/Lvgl
2017-05-31 | B.PVT |  | 4.ALT/DVT | NA | Closed | [S2] DVT2b ESD Fail,Headset Pop Noise Issue:ESD Fail on Zone15, PVTA&PVTBEval Pass Root Cause:1.Codec Damaged by ESD through SPK Solution:1.Move TVS closed to Signal Pin Plan: Update ESD Design Rule with high priority -yangwla | here | yangwla
2017-05-20 | 7.DVT2 |  | 4.ALT/DVT | S2 | Closed | [S2] DVT2b ESD Fail,SPK Noise Issue:ESD Fail on Zone1, PVTA Eval Pass but PVTB Re-Test Fail 1/4. Root Cause:1.Codec Damaged by ESD through SPK Solution:1.Add 2 TVS on SPK Channel 2.Switch Semtech Part nearby contact Pin with will part ,Eval 4 pcs with Pressure Test Pass Verificaion: Verify ESD 4 pcs on 6/1 ,Pass | here | yangwla
2017-04-28 | 7.DVT2 |  | 2.Build | NA | Closed | [NA]Issue: Cap Sensor Detection Partially Fail on BT Root Cause: 1.No update issue belongs to CQA Software Issue .2 No output issue need to furtherly Analysis Solution: Update Cap Sensor Configure Data Avoiding Trensient Response Pending Verification:Pass | here | xiongsn1
2017-04-28 | 7.DVT2 |  | 5.Certification | S3 | Closed | [S3] Issue:EN301489 ESD Failed on Data Link(Phone to PC) -Yangwla Root Cause: PC Side USB Module Affected. Cable shielding Issue.Andriod big version update on usb Data transformation which cause the data verification capability S3 down and the procedure easily affected by ESD. Solution: 1. Improve Cable Shielding ,Cert Pass | here | yangwla
2017-04-20 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] George NA DVT2A MDu30 Thermal Test,game+charge,Front side 44.2℃ VS 42℃ Issue: Pass B standard(45℃） but fail in A standard（42℃），quality update a stricter request and block it. Root Cause: cost down solution cause 1℃ up （42.9℃ DVT1B），and charge current mitigation not available for DVT2A test (44.2℃） Solution: update SW mitigation solution by controlling charging current. Plan: Self test pass，and submit to test on 4/26，test result will output on 4/28 | here | Linfenga
2017-04-20 | 7.DVT2 |  | 4.ALT/DVT | S3 | Closed | [S3] George NA DVT2A XM99620 1pcs(Loop5) no turn on Issue: no turn on Root Cause: PM8940 U1205 Joint Crack by Strain, Solution: Under Fill U1205 Verification: Pass | here | chenwt
2017-04-19 | 7.DVT2 |  | 4.ALT/DVT | S3 | Closed | [S1] after ALT(for EDU06) ( loop3 1pcs D2,Loop5 1pcs D10) No signal Issue: LTE No Camp Root Cause: U5500&U5600 Solder Crack Solution: 1.Glue U5500&U5600 2. Single strech Shielding Case Plan: https://docs.google.com/spreadsheets/d/11us2BUCEQluIthHAMDMPdh_TdoCEyoipaotpBndCfr8/edit#gid=0 | here | chenwt
2017-04-17 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] Can not power on after ALT(for EDU06) ( loop4 TH/TC done ) D7 Issue: VPH_PWR short to GND. C2110 component issue. remove it and the phone ok. Root Cause: PE lead the fail analysis Solution: PE lead Plan: TBD | here | chenwt
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Issue:ALT DTF test ,3*Loop5 ，1 pcs no power on Analysis/RootCause:From cross-selection Analysis,U1205(pm8940) had cracked on the board side of solder joints Solution/Verificaiton:ALT and tumbler test were pass until now. Plan:FolS3 up the next ALT and tumbler test,if the same failure happen, add underfil is the available backup solution. | here | Linfenga
2017-03-25 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Thermal materials cost down solutions risk Issue:Decrease half size of copper could cost down ￥0.2，the temperature should rise 0.5-1℃； Analysis/RootCause: LTE Data call(15dB） fail，RF correct the measure method after align with TCC because the wrong measure method cause big different data between DVT1A and DVT1B. Solution：the retest result was pass after update measure，and the cost down solutions could been accepted. Plan: DVT2A had imported the cost down solution which could save $0.27. | Link | Linfenga
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Red Dye test After ALT, Found MCP functional solder had partial crack but function was ok Verification:ALT and tumbler test were pass until now. Follow up the next ALT and tumbler test,if the same failure happen, add underfil is the available backup solution. | here | Linfenga
2017-04-17 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] MSM_therm not correct (EDU08) Issue: MSM_therm too S1t . more than CPU Root Cause: R1208 not mount Solution: R1208 change to 0R from DNP Plan: change From DVT2B ,done. Retest with rework units by chenwei ,ongoing.WH99980 ,pass | here | chenwt
2017-04-13 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] LCD damaged Flickering after ALT ESD here Issue:1/2sets Zone 3: air discharge -15KV fourth times, top display flickering, and can not recover.LCD damage. Root Cause: housing resistance, the value is 21.6ohm, while spec should less than 1ohm.ME checked that this lot housing resistance abnormal while in the process Solution: OK housing lead in. And built in DVT2A Golden units and latest Black units. Plan: ESD test will be done in XM99841(golden,4/16) and XM99784 (black,4/20) update:XM99841 Pass and XM99784 Pass | here | pengsp/chenwt
2017-03-15 | 5.DVT1 |  | 2.Build | NA | Closed |  | here | chenwt
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Thermal DVT1a failed Issue:1.WCDMA Voice Call 1.2 °C while no charging 2.Wifi Stream (Front 0.9°C ，Back 1.2°C) while charging ,here Solution：1.Decrease PA Power 2.Charging Rhythm Modification Verification：Dvt1b Pass | here | Linfenga
2017-03-15 | 5.DVT1 |  | 2.Build | NA | Closed | [NA]Isuse:sensor Vision test limit need update Solution:Delta limit need to change from 580 to 300( refer to Andy),and folS3 up DVT2A test DVT2A check ok ，close | here | chenwt
2017-03-07 | 5.DVT1 |  | 3.BB Test | NA | Closed | Cap sensor noise Place Cap Sensor IC as Closed as Possible to Sensor PAD,Shielding Sensor Line Ant had confirmed performance is ok . DVT1B PCB change：Place Cap Sensor IC as Closed as Possible to Sensor PAD,Shielding Sensor Line | here | Linfenga
2017-01-16 | 4.EVT |  | 3.BB Test | NA | Closed | discharge on low voltage battery the sample don't charging on low voltage battery，but normal voltage battery is ok sw problem,charge is ok after sw update charge is ok after sw update |  | wuxm5
2017-01-16 | 4.EVT |  | 4.ALT/DVT | NA | Closed | ALT issue: After loop2 post drop inspection, phone heat up: B2 1.off current more than 500mA 2.EOS problem.Not happened then in the next ALT test. | here | chenwei24
2017-01-13 | 4.EVT |  | 2.Build | NA | Closed | Board Test Issue:2 PCS Board Fail 1.Vr1421 TVS damaged;（0.5mA current increase） EOS damage from FA report of vendor: 2.U1205 PM8940 chipset damaged;(MPP2 pin damage) 3.Not happened then in DVT1 build need vendor analysis report. | here | FAE

## Option
Project | Project | Phase | Source | Block | Status | Severity |  | Issue | Analysis&Solution | Owner | Department |  | Design Element | Design Element 2
Andy NA | 0.Andy NA | 1.Concept | 1.1 OD | 1.Platform | Open | S3 |  | [S3] Issue: Clue: RootCause: Solution/Veirification: Plan: | here | 小范 | 1.BB |  | 1.Route | 1.1 ESD
Ashley | 0.Ashley | 2.PCL | 1.4 Solution | 2.Power | Monitor | S2 |  |  |  | 文亭 | 2.RF | RF | 2.Part | 1.2 Strain
George NA | 0.George NA | 3.PEL | 2.Design | 3.Charging | Closed | S1 |  |  |  | 李果 | 3.Antenna | ME | 3.Pin | 1.3 EMC
Copperfield | 0.Copperfield | 4.EVT | 3.Review/Simulation | 4.Audio | NA | NA |  |  |  | 林峰 | 4.ME | Display | 4.Net | 1.4 TDD
Shelby | 1.Shelby | 5.DVT1 | 4.Build | 5.Camera | [5 empty] | 嘉琨 | 5.SW | Audio | 6.Parameter | 1.5 Thermal
Stingray | 2.Stingray | 7.DVT2 | 5.1 Bring up | 6.Display/Touch | [5 empty] | 敏敏 | 6.Display | Antenna | 6.Parameter/Sequence | 1.6 Current
Quattro | 3.Quattro | 4.EVB | 5.2 BB Test | 7.Sensor | [5 empty] | 小熊 | 7.Audio | SW | NA | 2.1 Selection
Sofia NA | 4.1.Sofia NA |  | 5.3 EE DVT | 8.PCB | [5 empty] | 院长 | 8.Charging | NPI |  | 2.2 Position
Sofia Plus NA | 4.2.Sofia Plus NA |  | 5.4 ALT | 9.Memory | [5 empty] | 芳梅 | 9.Sensor | CAD |  | 2.3 Compact Design
Nairobi | 5.Nairobi |  | 5.5 Certification | 10.USB-C | [5 empty] | 德太加 | 10.Camera |  |  | 2.4 Polarity Mark
Denver | 7.Denver | B.PVT | 5.6 User Feedback | 11.Thermal | [5 empty] | 廖哲霖 | 11.FPS
Tahoe | 6.Tahoe | C.RAMP | 6.Issue | 12.EMC | [5 empty] | 范南 | 12.Connector
Sierra | 8.Sierra | D.SHIP |  | 13.Discrete | [5 empty] | 川叔 | 13.Battery |  |  | 3.1 Pin Mapping
Yukon | 9.Yukon |  |  | 20.NFC | [5 empty] | 艳红 | 14.Build SMT |  |  | 3.2 Pad Stack
Milan 5G | A.Milan 5G | [8 empty] | 韩凯 | 15.Build Test
Dubai+ NA | B.Dubai+ NA | [9 empty] | 16.Build Assembly
Miami | C.Miami
Geneva NA | D.Geneva NA
London NA | E.London NA | [12 empty] | 4.1 Topology
Manaus Row | F.Manaus Row | [12 empty] | 6.1 Initial Sequence
Manaus NA | G.Manaus NA | [12 empty] | 6.6 CSI/DSI Configure
Boston | H.Boston | [12 empty] | NA
Wrangler | J.Wrangler
Houston | K.Houston
Prado | L.Prado |  |  |  |  | Comsumer Impact | Milestone Imact | Fix with Plan | Have Plan to Fix | Severity
[6 empty] | Y | Y | Y | Y | S1
[6 empty] | Y | N | Y | Y | S2
[6 empty] | N | N | N | N | S3
[6 empty] | Block Gerber Out | Solution Validated(Y/N) | Severity
[6 empty] | Y | N | S1
[6 empty] | N | N | S2
[6 empty] | N | Y | S3
S1 –1.Impact consumer, 2.Program blocking issue, 3.Must fix prior to ship S2 – 1.Impact consumer, 2.But have plan to fix, 3.Manageable risk S3 – 1.low risk of getting field returns, 2.Can fix but may not be able to fix due to time or design limitations.
Definition
Issue
Clue
Root Cause
Speculation
Experitment
Result
Conclusion
Solution
Verification
Next Step
Risk Factor
Function
Performance
Cost
Schedule
Supply
Design Complexity
PCB Placement
BB Team
BB Solution
|  | Open,Ready,Reviewed,Verified,Closed,NA |  |  |  | BB Design

## Database
Date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change? | Project
20170401 | C.RAMP | 6.Display/Touch | 5.6 User Feedback | S2 | Closed | Issue：India market When put the “Fail headset” JBL PUREBASS T150A into Moto G5 plus ，there will be some action similar to Ghost Touch. Jira link:https://idart.mot.com/browse/IKSWN-27437 | link | SW/chenwt |  |  |  | 0.Copperfield
20161118 | 7.DVT2 | 2.Power | 5.3 EE DVT | S3 | Closed | Issue:ALT DVT2B发现正面朝下自动关机 Root Cause: Analysis: Solution: Verification: Plan: | link | 肖志浩/Chenwt |  |  |  | 0.Copperfield
20170113 | B.PVT | 1.Platform | 4.Build | S2 | Closed | 下载工位出现概率性不下载（faboot 识别不到USB） | link | xiaozh/chenwt/chenhy |  |  |  | 0.Copperfield
20161101 | 7.DVT2 | 4.Audio | 4.Build | S2 | Closed | GSM buzz in DVT2B units found | link | 肖志浩/李燚 |  |  |  | 0.Copperfield
20161118 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | Closed | DVT Mdu30 ：thermal test ,Video recording reach 44.2 degree | link | 陈文亭/吴学敏 |  |  |  | 0.Copperfield
20161118 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | DVT EDu14- Surge test (L)，charge 按印度规fail，90V无法开机。需要过120V | link | 肖志浩 |  |  |  | 0.Copperfield
20161208 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S2 | Closed | Description :Turbo charger always not charging after charging a little time | link | 陈文亭/肖志浩 |  |  |  | 0.Copperfield
20161118 | 7.DVT2 | 2.Power | 5.3 EE DVT | S2 | Closed | ALT Battery current drain out of spec. |  | 陈文亭 |  |  |  | 0.Copperfield
20160901 | 5.DVT1 | 3.Charging | 5.2 BB Test | S2 | Closed | Weak 5W charger can not charge | Link | 陈文亭 |  |  |  | 0.Copperfield
20161101 | 7.DVT2 | 1.Platform | 5.3 EE DVT | S1 | Closed | ALT & DVT滚筒实验出现 LTE no camp | link | 范立锋/chenwt |  |  |  | 0.Copperfield
20161208 | B.PVT | 7.Sensor | 4.Build | S2 | Closed | 3rd P-sensor CT too low and can not pass APK test | link | 陈文亭/陈怀玉 |  |  |  | 0.Copperfield
2026-05-09 | 4.EVT | 12.EMC | 5.4 ALT | S2 | Open | Issue: EVT 一供 WH208009，AD: -15kV Zone1 Proximity & Front Light Sensor No Function, 实验室反馈重启未恢复。 Analyze: 1. 机器收到校验CQA中：Proximity 闪退, Front Light 不刷新，现象一致，从现象来看像是器件不识别到I2C设备。但是重启后可以恢复。 2. 抓机器Log，给软件分析：IKSWW-203359，分析结果是I2C通讯异常，判断IC被干扰异常导致无法进行I2C通讯，需要下电才能复位（I2C总线没问题） 3. XM实验室尝试复现：Zone1/通话/-15kV 200次暂未复现，但是发现实验室回来这台机器，打Zone1容易触发屏幕Recovery机制。 4. 测量VIO18_PMU，发现reboot过程确实不会下电，只有PowerOff会下电；—— 提交CR给软件，看能否实现reboot过程VIO1.8下电。 5. Vendor 分析，出现这个问题有两种可能：a) 芯片I2C被干扰到其他ADDR；b) 芯片假死无响应; RootCause：高压空气放电，干扰PUD，reboot过程中VIO1.8也没有下电，导致重启也没有恢复，下电重启才恢复。（高压重启可恢复，属于可接受） Solution：1. 实现reboot过程VIO1.8下电。-- MTK确认不能实现； 2. 增加PUD LDO下电方案，增加控制的IO口，需要软件提前确认导入； -- 直接DVT1导入； | link | 廖哲霖 |  |  | 1.SCH | #N/A
2026-05-11 | 4.EVT | 1.Platform | 4.Build | NA | Closed | Issue: EVT有个板子无法下载，板号NAAA020317 Analyze: 1.Blankflash 的log 发给MTK，待回复。（下载完DA后，无法进入DAmode，拔掉数据线后，板子处于关机状态，没电流） 2.FAE换了 U2001（MT6363））/U2601（MT6375）/U1001（CPU）/U1009(DDR)/U1392(UFS)，发现还没恢复正常。U1392测量底部pad阻抗ok，通断正常 3.按开机键再松开，电流停在200mA左右。说明主时钟已经有了。 4. 硬件测量上电时序，确认时序已经都满足了，也就是板子关键的电都已经上来了。 5.log MTK 分析结果：U1301 初始化失败，返回错误。 RootCause：产线SMT 用错器件，U1301 用错成U1701的器件。U1301 用正确的器件后，ok了。 Solution： SMTowner |  | 文亭 | 敏敏 |  | 6.No Change | #N/A
2026-05-11 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | Issue: EVT 可靠性有两台机器SIM无作用，重启概率性恢复。 Analyze: RootCause： VCC 电容和中框短路 （绝缘实验临时验证ok，不复现） Solution： 中框DVT1 做避让 |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-04-29 | 4.EVT | 9.Memory | 4.Build | S3 | Closed | Issue: EVT 二供BR157907 128 UFS 尺寸太大，造成连焊。（贴了4pcs 板子） RootCause： 二供 SM38F05190 BWU3AKG16D128G U1392 BIWIN，尺寸11.5*13 VS 一供三星的11*13 Solution： EVT二供试产 及 DVT1 备料临时更换回一供三星memory 长期：1.跟进厂家更改尺寸为11*13情况（可行，但是要2027年才能改好，咱们项目用不上了） 2.项目上将三供pull in ，预计DVT2二供来得及导入验证 |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-04-03 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | Issue: 4/3 front camera 22 pin connect error RootCause： NEW SPEC is NC，Old SPEC is power 。 没有用新SPEC进行设计 Solution：EVB rework 割断连接器上22pin-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来， -- changmf1 done |  | 芳梅 |  |  | 1.SCH | #N/A
2026-04-03 | 3.PEL | 2.Power | 5.1 Bring up | S3 | Closed | Issue: 4/3 已知DVDD LDO U3161有点问题，EVB2 ，已经rework板子 bringup。EVT 更改进入主线 RootCause：VIN和VBIAS 连接反了，没有识别出来。 Solution：EVB rework 让LDO能正常输出-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来，已提交修改，待导入 --wuxm5 |  | 敏敏 | 芳梅 |  | 1.SCH | #N/A
2026-04-03 | 3.PEL | 2.Power | 3.Review/Simulation | S3 | Closed | RISK: Display power 和SPK power 的输入端VSYS 过孔只有一个，有风险 Impact：EVB板子不适合 Display 和SPK 最大功率使用，可能会烧毁板子。 RootCause： review没有识别出来。 Solution：EVB rework 让LDO能正常输出-- camera bringup的板子done EVT 更改SCH，VIN和VBIAS 纠正过来，已提交修改，待导入 --wuxm5 |  | 芳梅 |  |  | 1.SCH | #N/A
2026-04-03 | 3.PEL | 10.USB-C | 3.Review/Simulation | S3 | Closed | Issue：CPU和redriver 之间没有串接电容 in EVB1 Impact：EVB1板子USB3.0 没法工作 RootCause：设计错误 Solution：EVB1 rework for DFC 方案（去掉redriver）--ongoing chenwt EVB2 主板上串联电容 --已更改进板子，待EVB2板子到达后bringup。预计4/8 SW收到板子 |  | 文亭 | 芳梅 |  | 1.SCH | #N/A
2026-05-18 | B.PVT | 3.Charging | 5.6 User Feedback | NA | Monitor | RISK：ROW ，无线充的DET信号 发现没有下拉电阻，无线充 检测状态可能会不稳定。 发现来源：PRC（没有接无线充电板子的）PVT后期有出现一台机器开机就显示充电图标。分析是因为DET 中断检测到导致判断 无线充电 被检测到。 前置问题的解决方法：PRC样机没有无线充，禁断所有无线充的GPIO及相关功能响应。已经导入主线，从 36.65-11 导入了更改。 前置问题的扩展评估：那么有带无线充的板子，是否也可能存在这个风险？ review 后发现该RISK Impact： 可能1 ：没有无线充 的时候 有极小概率被检测到无线充在位，显示充电图标，实际没有在充电 可能2： 无线充电器拿下来后，可能还会显示充电图标？ Anaysis: 1. DET信号没有外部下拉，内部也不能做下拉（CPU下拉会影响DET拉高，电平不够。 无线充IC默认状态没有上电，所以也不能配置下拉）。所以DET信号就比较接近悬空了，仅有 CPU和无线充IC 默认的连接，下拉能力非常有限。 2. 请无线充IC厂家确认， 有很微弱下拉，小于1uA RootCase： DET信号没有外部下拉，内部也不能做下拉导致 DET中断可能会误触发。（DET是高电平有效。） Solution: proposal 1. SW workaround ：当DET检测到的时候， 通过其他组合条件进行确认再判定是有效的无线充电。临时版本0519 验证ok，会提交进入主线。 待有正式版本后，再确认下。 For 后续长期： HW方案 ，在stack板子上增加一个47K下拉电阻靠近无线充IC端。后面Pike ，Artura 都这样进行更改（Pike EVT修改要改进去，Artura DVT1 要改进去。） ---chenwt tracking | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-05-08 | B.PVT | 3.Charging | 4.Build | NA | Closed | Issue:PRC 样机试产时候，反馈有1台机器，重启后就一直显示充电图标。插拔充电器后恢复。 Impact： 异常出来充电图标 Anaysis: DET信号没有外部下拉，内部也不能做下拉（CPU下拉会影响DET拉高，电平不够。 无线充IC默认状态没有上电，所以也不能配置下拉）。所以DET信号就比较接近悬空了，仅有 CPU和无线充IC 默认的连接，下拉能力非常有限。 RootCase： PRC机器没有无线充IC，所有接口都是悬空。需要将相关部分的功能关闭。 solution: PRC机器 SW上去掉所有无线充的相关信号响应。 36.65-11 导入了更改，验证ok |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-05-08 | 7.DVT2 | 3.Charging | 5.5 Certification | S2 | Open | Issue：CB认证反馈低温0~-20度之间，充电电流达到1.92A,大于电池SPEC的691mA Impact：认证，电池安全 Anaysis: 1. RD复测，常态状态下是654mA，小于691mA 2. 测试过程发现，插入充电器后几秒钟内，会先电流爬坡到4A左右再降低下来到654mA. 推测是这个爬坡过程被拆机到电流，然后判断为fail 3. 发现2 ：开机后的这个4A是SW可以配置的，所以查到哪里的逻辑申请4A电流 尝试优化逻辑来让 安全机制优先级别更高，就有机会优化开机状态下的结果。 4. SW log 分析 4A是SW初始过程中将FCC设配置为5A拉载出来 。 RootCase： 问题1 开机状态 先到4A左右 3-5秒后降到安全范围内。 原因 ： SW为保证可以正常拉载到大电流，先将FCC设为默认5A，然后配置目标ICL，最后将FCC配置为目标电流，低温场景测试，对充电电流要求较低，会触发一个高于电池SPEC要求阈值脉冲电流 问题2 关机状态插入充电器，会先有default 的5V1.5A的配置（非SW上层配置，是 底层配置） 两秒左右就会过去，然后SW起来开始后续配置。 这个点如果认证不放过，就要 看底层是否有机会优化。 solution: proposal 1. 优化初始FCC配置值，将默认最大值与目标值取小作为最终配置值，保证全程拉载电流不超过电池SPEC要求-验证有效，去掉了 4A左右的脉冲。 proposal 2. 关机 充电5V1.5A脉冲QC答复无解，只能优化速度。 修改XBL加载顺序，将脉冲宽度从1.9s改为1.2s同时压低691mA设置到500mA ，来降低其他抖动带来的可能出现的超过一点儿门限的概率。 --待验证有效性后提交修改进入主线，然后安排复测 | link | 文亭 |  |  |  | #N/A
2026-05-07 | B.PVT | 3.Charging | 4.Build | NA | NA | Issue：PVT CQA测试发现，2台机器出现过OTG问题 N4AC420027 4/17/2026 5:10:29 PM UCT pass 。没有抓log ，直接ABA 交叉验证随芯片PMIH0104 （U3700）） QC初步分析IC异常了，更进一步消息，预计要到5月底出完整报告 N4AC4H0005 CR https://idart.mot.com/browse/IKSWW-198501 ，4/28/2026 6:15:57 PM UCT pass 。软件分析是已经检测到时OTG设备，然后电输出，之后枚举数据没有枚举上。 |  | 文亭 |  |  |  | #N/A
2026-05-07 | B.PVT | 3.Charging | 4.Build | NA | NA | Issue：PVT UCT测试发现，主充测试fail，电流非常小 N4AC4C0057 （4/28 下午2点38发现 ，BT是pass的）这台已经更换芯片之后测试Pass了，交叉验证随芯片PMIH0104 （U3700）） N4AC4C0060（4/28 下午2点45发现 ，BT是pass的）这台已经更换芯片之后测试Pass了，交叉验证随芯片PMIH0104 （U3700）） N4AC4E0002 （4/28 下午3点20发现 ，BT是pass的）保留板子 （这个机器OTG复测是pass的） clue： 1 UCT拦截的不能主充的问题，是4/28 下午2点38发现到4/28 下午3点20发现 突然出来3台。 评审会上请产线查这三台的IC批次，以及产线这个时间段有啥特殊性。（整机测试集中性这么明显，可能产线那时候有出现什么我们未知的情况。板级测试查过是pass的，并且没有集中时间），故障IC刚寄出去给 QC 。 需要较长时间才有分析结果回来。 ） 2.log分析第一台，发现是AICL 一直被限制到0，导致没有电流。（一开始插入瞬间有电流，然后被限制下来），推测是PC的AICL相关模块不正常了。 Rootcause： 主充电IC 故障，待产线寄送故障品给QC分析。这是其他项目MP物料。 CT62275/RMA-113099 : #1 failed in C/Tracer as pin QPH1D (177,190) short to QPH1S (176,189). The detail C/T result attached. CT62276/RMA-113100 : #2 failed in C/Tracer as pin QPH1D (177,190) short to QPH1S (176,189). The detail C/T result attached. The failures are indicate of EOS/ESD damage issue. Please review the application and test conditions. If necessary, open CE case for review. |  | 文亭 |  |  |  | #N/A
2026-05-07 | B.PVT | 3.Charging | 4.Build | S3 | Monitor | Issue：PVT 增加UCT站点的FW版本检测，确认是否升级版本成功。 产线反馈有约30%NTF。重启机器测试pass Impact： FW升级是工厂动作，不会影响用户。影响产线的直通率。 Anaysis: 1. 通过log分析，在启动FW检测和升级后100+ms 范围内，就返回读写状态失败，并没有启动真正的FW写入。 2. RD机器测量供电，这段时间内供电电压是稳定的。但是没有抓到复现问题的波形 3.下一步：先飞线，继续压测，尝试抓到故障时候的更多波形做进一步根因分析。 RootCase： 推测：是否供电后，需要等待较长时间IC才能稳定工作？ solution: 1 ： 同时读写状态加上retry 5次的动作（如果失败，下电，再重新上电再读取），来提高成功率。 临时版本提供了， 产线压测30次，ok 。BB 压测27次，ok （确认log 确认触发了retry 的机制，每次触发1次retry 后pass了），所以看起来solution 有效果。 | link | 文亭 |  |  |  | #N/A
2026-04-23 | 7.DVT2 | 20.NFC | 6.Issue | S2 | Monitor | Issue: During Qingdao Wallet field testing, a failure was observed where card payment does not work when the device is powered off (IKSWW-191864 ). Impact： Wallet card emulation tests fail in the powered-off state, affecting offline NFC payment verification. Analysis / Root Cause： When the device is powered off, the NFC power supply BOB experiences a voltage drop, causing the NFC supply voltage to fall below the minimum requirement of 2.5 V specified by the spec. The FMD feature was not enabled. As a result, during the power-off sequence, a vote triggers a BOB reset (RST) action, which further contributes to the BOB voltage drop. Action / Solution： Apply the QC patch to correct the configuration at register address 0x719A,Waiting for QC release patch. | Link | 李果 | 敏敏 |  |  | #N/A
| 7.DVT2 | 1.Platform | 5.3 EE DVT | S2 | Open | Issue：DVT2有一条机器出现CapSensor ESD后 无功能-所有通道 ，AD:8kV | [5 empty] | #N/A
| 7.DVT2 | 1.Platform | 4.Build | S2 | Open | Issue：SMT反馈stack 板有锡珠，几乎每台都有，位号Q2603,Q2604,Q2801 solution: DVT2 钢网从1：1更改为焊盘中间加0.2mm间距，不良率 12/172 PVT继续减薄锡膏 | link | SMT yanlin |  |  |  | #N/A
2026-03-13 | 5.DVT1 | 1.Platform | 5.4 ALT | S2 | Open |  | Link | 敏敏 |  |  |  | #N/A
2026-03-13 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Open | Issue：DVT1二供 EDU14出现一台机器Fail，一台200V Fail，一台250V Fail（实验室标准250V） Anaysis: 1. 两台机器，拆机分析VBUS浪涌管都未烧毁。 2. 测量机器发现USB充电快充/慢充均没有电流，且OVP MOS后端都没有电，判定OVP MOS没有开启。 3. CP-IC U6400是二供南芯，分析发现VUSB SNS的R6401电阻击穿（22Ω），且VUSB管脚对地电阻异常15Ω，判定是浪涌实验中，CP-IC的VUSB引脚先被浪涌击穿对地，然后再烧毁电阻，进而导致芯片内的OVP模块损坏或无法工作，导致充电故障。 4. EVT1 一供400V，二供300V； DVT1一供400V，二供200V&250V, 判定二供CP-IC在Aviator现有架构下可能抵抗能力不如一供； 5. DVT1二供 浪涌测试 采用的机器是复用跌落的； RootCase：二供南芯CP-IC 的VUSB管脚抵抗浪涌能力不如一供。 solution: 1. DVT2 R6401 更换成33R电阻（0613952X37），加大电阻，已和供应商确认50欧以内都OK； 2. 损坏的两颗CP-IC已经给到Southchip分析中； 3. TODO: Rework机器33R，回归测试： 3/23日复测结果，两台Rework二供机器 到33R的均Pass(250V)，但是余量不够； 3/26日复测结果，两台Rework二供机器 到47R的均Pass(400V)，且未出现漏电，判定方法有效。 |  | 廖哲霖 | 文亭 |  |  | #N/A
2026-03-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Monitor | Issue：SME tuning 磁吸充电时候发现，死电池的机器，用磁吸充电器无法激活，屏幕没有任何反应。 Impact：Apple Q2.2 磁吸充电器无法激活aviator 死电池的机器。（其他WLC 目前测试都可以激活 ，更新3/17 的FW版本0073之后的结果） rootcause: suspect :1 WLC RX IC 输出电压不稳定，导致主充电PMIC无法稳定走死电池激活流程。 为什么输出不稳定？ suspect :1-1 推测是 WLC 输出驱动力太低 以及 手机瞬态 吃电较大导致的 WLC输出电压不稳定。 （系统耗电，这时候电还没进电池） solution: proposal1: 带SME tuning Apple Q2.2 磁吸充电器 default 模式下的驱动力。 3/30 临时版本FW确认ok了。待SW导入主线后继续跟踪。 | link | 文亭 |  |  |  | #N/A
2026-03-03 | 5.DVT1 | 1.Platform | 5.4 ALT | S2 | Closed | Issue： DVT1 ，实验室一些机器返回分析后，放置一段时间，再开机无法开机，插充电器，没法正常充电。有时候屏幕先亮一下，然后就只有5V80mA左右。 clue：1.之前有一台，插着充电器无法开机，长按开机键几十秒后开起来了，不确认是否同一个问题。 目前针对第二台进行拆解分析 2.第二台机器 N4AC130165 ，屏幕先亮一下，然后就只有5V80mA左右。拆机测量Vbat~=0V ，所以电池死电池了。拆下电池连接器，电池电压0V，死电池了电池本体变形严重，确认电芯异常了，转KP分析。（这台机器经过多轮可靠性，包括2.5米跌落）。 后面又回来两台，都和第二台一样的结果，转KP RootCause：闲军 owner （大概是电池内部防护不够，造成漏液了） solution：闲军 owner（大概概括是更改电池内部保护，DVT2整批导入，DVT2 厂家和 咱们同步验证，看是否ok了） |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-02-11 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S2 | Open | Issue： DVT1产线出现4pcs烧毁VBAT-TVS(FR：4/86)，请软件导入降低电流软件后，3pcs烧毁(FR:3/553) RootCause：从TVS烧毁现象怀疑是Peak电压导致TVS异常开启后短路，电源常电进而烧毁TVS管。 Analyze: 差异对比： - Aviator: SF68D39333(Will)+8845; 烧TVS - Horizon: SF68D39333(Will)+8845; - Urus: PTVSHC2EN4V8UF + 8845; 未出现烧TVS 36.12版本：（进入Homescreen大电流） - 4pcs板子，D3500,D3501均烧毁(FR：4/86)，实测电流在进入Homescreen瞬间有一个7A的值，经实验确认是CPU限频解除导致。 36.16版本：(限制CPU频率，确保没有大电流) - 请软件导入不解除全程限频的措施，截至到2/11出现3pcs烧毁，其中2pcs烧D3500,1Ppcs烧D3501。(FR:3/553) 产线测试波形： - 36.12版本下，产线夹具上测试，3pcs 产线主板 3个板子36次压测，均未烧毁，最高Peak电压抓到4.8V （VBR:4.9V），继续在武汉基带用为准电源压测，也未发现明显异常。 - 36.16版本下，烧毁的1pcs板子产线夹具上测试，未发现故障波形。 | link | 廖哲霖 |  |  |  | #N/A
2026-02-05 | 4.EVT | 3.Charging | 5.2 BB Test | NA | NA | RISK：Vendor 调试时候发现 无线充Vout 飞线出来测试，发现有一个NFC 工作频率的电源纹波。NFC关闭后就没有。 impact：如果真实存在，可能会影响到无线充 通讯解码稳定性。具体待确认 Rootcause： 1. 飞线压到NFC天线上导致，误测问题 |  | 文亭 |  |  |  | #N/A
2026-01-30 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | RISK：Qi 2.2 认证预调试时候SME 发现：前置线圈切换电路的Mos 控制端GS 电压 在低频阶段有大于1V的纹波，有可能会误触发 mos 打开（打开门限是1.0~2.5V） impact： 反复打开关断mos会让功率存在波动，影响的是bpp模式Qi 2.2 认证的 Rootcause： 当前的 S 信号是通过AC（线圈信号）耦合过来，其VGATE是IC内部自举电路基于AC基础上升压的，目前看起来内部有 谐振频率附近的干扰 （频率在低频段128KHZ）。 solution： 在GS之间加一个10nF电容 来进行滤波。 临时验证：实际rework 验证有效果，将原来超过1V的纹波，降低到只有0.3V左右，处于安全区间。 项目上：需要在DVT2 发板上改进去。已提交，待发板时候更改 --chenwt 加滤波电容是否会有负面影响？： SME comment 没有负面影响 |  | 文亭 |  |  | 1.SCH | #N/A
2026-01-28 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | RISK：Qi MPP 15W CE : SME 反馈 ICL步进 在1A左右突然功率跳变太大，不符合需求。 Rootcause：QC 答复是 QC IC PMIH0104 SPEC范围内的行为，无法确认不跳变。无法从根上面解决（其他竞品厂家也要面临这个问题） solution：寻找其他解决方案 by SME |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2026-01-28 | 4.EVT | 3.Charging | 5.2 BB Test | NA | Closed | Issue：DVT MDu94.A - Extreme Drop Test WH202994 D5 N4AE060004 Post check:No front camera viewfinder:D2/D5 Post check:Unable to find NFC device Rootcause：前置摄像头脱落，结构泡棉问题。 | [5 empty] | #N/A
2026-01-16 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Open | Issue: - ANT7 N77&N78 interface Front camera leads camera MIPI error on EVT 3/3PCS Analysis/Root Cause: - The logger shows mipi error. - 翻起前置camera模组头部，干扰消失，模组头部的铜箔从主PMIC屏蔽盖下地，ANT7天线回流产生的磁场干扰从camera模组头部进入到sensor本体。 - Camera deco 接地不良，主板上螺丝孔挖露铜后+ 去掉ANT7 LDS天线，只有ANT N78 MCH 有mipi error, 概率降低50%以下 - camera 模组头部贴铜箔到Receiver后，2台测试ok，改变了天线ANT7的回流路径产生的磁场干扰 Action/Solution： 主板上Deco弹片接地区域露铜并增加过孔，确保Deco接地良好。EVT后期Deco下地弹片检查已镀金； —— DVT1已改入； 去掉ANT7备用 LDS天线 更改camera背面石墨片和receiver连起来，改变ANT7的回流路径，测试2台pass---导入DVT1 二供 Verfication： DVT1 自测三台 pass | LINK | 芳梅 |  |  |  | #N/A
2026-01-15 | 4.EVT | 3.Charging | 5.1 Bring up | S3 | Closed | Issue：SW细节bringup 发现 没有放到TX上的时候DET 信号有时候高电平有时候低电平。（这原本是用来作为放到TX上枚举成功的判断中断） impact:没放到无线充时候，有小概率会意外识别为有无线充？ rootcause：1.外部没有加下拉电阻，导致GPIO浮空 （平台内部下拉电阻阻抗范围太大 10K~50K，不稳定） 2.厂家的GPIO输出电平配置没有按照我们需求配置为1.8V（当前测量是1.2V） solution： 1. DVT1 是SW配置 GPIO no pull +HW 外加47K下拉电阻+FW配置1.8V GPIO输出。 （HW 发版 1/16 已经改入stack 板子） 2. EVT ： 是SW配置 GPIO no pull +HW 没有外加下拉电阻+FW配置1.8V GPIO输出 。这样的情况是，EVT机器当刚关闭无线充时候，有可能会有残留电压，导致GPIO 还继续判断到高电平。 大部分情况是ok的。 长期：后续项目默认Det 信号都增加47K 下拉电阻。 |  | 文亭 |  |  | 1.SCH | #N/A
2026-01-15 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Monitor | Issue： EVT ALT WH202971 PRC 1:Accelerometer failed functional parametric test,Recovered after reboot:A1/B2(1)-TH/TC 抓log分析 EVT ALT WH203016 APEM testing 1/17 Accelerometer failed functional parametric test,recovered after reboot:A1/A2/B1/B3(1)-TH/TC,B2(1)-post drop,A3(1)-post shake 分析 ：1. 温冲异常在升级A+G三轴正确方向后不复现。 loop3振动完做全部检查时发现1pcs A2 (XY正常，Z保持-79左右)，loop4跌落新增2pcs B1 B2(XYZ值不变化) SW说TCC使用的测试版本太旧，交给vendor去分析。继续跟踪。 2. 和邓玲确认EVT是否还有实验可以复测？需要确认能使用的版本。 |  | 小熊 |  |  |  | #N/A
2026-01-15 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Open | EVT Tumble WH202942 PRC Flicker sensor no function,recovered after 100 tumbles:D1(80) EVT Tumble WH202981 APEM 2:Flicker sensor no function,recovered after reboot:D1(200)D3(60)D4(100)-CR129483 分析 ：问题分析需要抓有效log，TCC 加滚2pcs各100次，不复现，所以未抓到有用的log。先monitor。 | [5 empty] | #N/A
2026-01-10 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Monitor | ISSUE：EVT ：TCC ESD 中发现机器自动关机 ，厦门自测发现自动重启1次。 Rootcause：是场干扰模型而非直接击中信号线或者器件。 场干扰故障模型的原因推测：1.这个场大概率是 由于大金属块接地不好导致的场太强 。 2.周围的地贯通速度不足以吸收 当前很强的场干扰。 优化方向：临时加强deco 接地，压测pass solution：1.改变场 ，加强大金属块的Grounding。2.增加 PMIC 本体区域及周围的Grounding，板子多打地孔，特别是贯穿孔（ 要有大孔，大孔附近也要有好的小孔，才能形成贯穿导通） | link | 廖哲霖 | 文亭 |  |  | #N/A
2026-01-10 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Monitor | Issue：ESD在CD:8KV下，在Deco区域和侧边出现Flicker Sensor软失效、auto-recycle。 Analyze：1. 厦门摸底机器，已导出Ramdump —— 软件分析是触发了PMIC（PMIC_B_E0） OCP保护，导致PMIC触发RST复位。 2. Deco弹片主板EVT无露铜 —— DOE实验：原始状态 CD:6kV下就复现Flicker无功能；刮开露铜, CD:8kV，AD15kV各打100次均无出现问题。 3. ANT0 Cable 测试CD 8kV下ESD波形，Peak电压有491V，对比Equator ANT0为250V —— Aviator天线小板是新的设计，馈点弹片和下地弹片很近且取消侧弹，相较于Equator天线小板上路径会短一些。 RootCause：1. Camera Deco 两个接地弹片主板对应区域没有露铜, 增大了Flicker板上Deco下地弹片的泄电压力，进而导致I2C干扰。 —— Flicker软失效； Solution： Flicker 软失效： 1. 主板请结构输出Deco对应弹片接地区域(已增加到CheckList) —— DVT1已改入； 2. 增加Flicker弹片过孔下地过孔 —— DVT1已改入； 3. 确认Flicker Sensor Recovery机制 —— 目前已确认有这个功能，现在软件是否打开正在确认。 Auto PowerOff/Cycle： 1. 增加ANT0天线小板过孔下地过孔 —— DVT1 已导入； 3. ANT0主板RF端预留TVS位置，加强下地。 | link | 廖哲霖 |  |  |  | #N/A
2026-01-08 | 4.EVT | 12.EMC | 4.Build | S2 | Open | Issue: 产线报有4pcs机器主板，在4GBT站点出现浪涌管D3500,D3501烧毁； Analyze：1. 和产线TE确认，用的是为准K6206-V20 20V 5A的电源，和之前北京Team遇到的浪涌管烧毁问题一样。 2. 高通SM8845平台开机过程电流大，会超过为准电源的5A输出能力，导致突然有大电流抽电时，电源会顺势加大功率补偿，进而导致电压异常抬升，触发EOS浪涌管导通烧毁。 3. Urus 02版本VBAT浪涌管选用ESD56201D04-2_TR（性能较差，我们已启用），最终选用Prisemi-PTVSHC2EN4V8UF（看Spec参数，和我们ESD56301D04基本一致）； RootCause：产线为准K6206程控电源输出能力和控制速率不够，导致电源异常抬升，触发EOS浪涌管导通烧毁。 Solution：1. 产线增加浪涌防护板；—— 目前产线有1pcs样品，批量至少需要4周，估计要到年后才能上产线。 2. 优化开机电流到5A以下： 目前软件确认是有导入Urus的降电流Patch，但是实测开机电流还是有6A， 已反馈请软件评估进一步优化机会。（工厂build kernel 配置文件没有走perf配置, 走的是debug配置）—— Owner：Jichao Zou； 3. 调整程控电源控制程序，取消VBAT电压调整； —— 修改中； | link | 廖哲霖 |  |  |  | #N/A
2026-01-08 | 4.EVT | 3.Charging | 5.4 ALT | S2 | Monitor | Issue: Alt 3台滚筒 不开机，1台MIL不开机. 故障现象：开机了反应速度也比较慢，关机后，插充电器充电5V/0.3A RootCause：电池连接器松了， 甚至主FPC也松了 Solution：ME |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-12-19 | 4.EVB | 5.Camera | 5.1 Bring up | S1 | Closed | Issue：后置camera SOIS I2C 读写不成功 rootcause：SW i2C 端口设置不成功 Solution：软件setting |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-12-12 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | Issue：前置bringup camera不出图 rootcause：MIPI timming THS-settle(ns) 不满足协议要求 Solution：修改MIPI timming | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-11-12 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | Issue：bringup 发现快充IC插入USB时候能识别到，拔掉USB就识别不到。 rootcause：快充IC的Vbat 和 主系统的Vbat_Plus 没有连接上。（还有B_plus 等网络名接一起，但是VBAT 没有和VBAT_PLUS接一起，由于都有电容，所以不会自动报单端网络。 Solution：EVB ， C6425电容的左侧 飞线到 C3808 电容上端. ongoing EVT 及之后，原理图更改，Vbat 和Vbat_Plus 连接上。 done 长期：checklist 里面专门特别加一条，Vbat 和Vbus 需要确认和主网络连接。（因为这两个网络板子上会多个地方使用，原理图上有很多的网络名，而且基本都有电容导致不会报单端，相对容易漏过。） |  | 文亭 |  |  | 1.SCH | #N/A
2026-03-09 | C.RAMP | 13.Discrete | 4.Build |  | Monitor | Issue：OK2P发现2pcs 电容C2620与屏蔽盖SH1002短路造成大电流，F/R 2/3000=0.0066% Analyze: 1.C2620使用器件21014016001，包含村田，太诱，三星三家物料，村田&太诱 高度为0.8±0.2mm/0.8+0.2mm，三星高度为0.8±0.25mm，且三家物料均走上公差。 2.21014016001 实际高度应为1.05mm，而结构建模该料号器件高度为0.88mm 3.C2620处于屏蔽盖边缘，屏蔽盖在C2620附近有个斜坡，器件与屏蔽盖斜坡之间gap=0.14，器件走上限容易干涉 4.OK2P 使用的物料为高度最高的三星物料 Soltion：1.屏蔽盖改模，取消斜坡，增大与电容之间的Gap 2.处于屏蔽盖边缘的C2620等6pcs器件更改为不含三星物料的新料号:SC48E75627 3.屏蔽盖改模前，21014016001,SC48E75627只发murata物料给Terrain，以满足生产需求 | Link | 院长 | 敏敏 |  |  | #N/A
2026-02-28 | 7.DVT2 | 3.Charging | 5.5 Certification | NA | Monitor | Issue： CB 认证反馈 2. Q.1测试，电流超了8A （具体代表什么意义待 和battery KP确认） Impact：推测：不能宣称满足Q.1 LPS ，只能宣称PS2 Rootcause：因为电池的对外输出能力越来越大，所以自身不能限制到能pass 8A的这个放电限制 。 （测试方法是 短路充电IC的输入和输出，就是将Vbus 和Vbat 短路 ，多少个充电IC就分别短路多少次，分别测试，用来判断整个系统在异常情况下 外部能抽到的电是安全范围的。标准8A 或者100W 是个认证固定标准） Solution： 两个选择 2.1 尝试正向解决：在OTG场景，监控Ibat ，当Ibat 大于某个值（比如6A ），就关闭OTG （包括OTG 对外输出的OVP mos 管 ） 。 原理上推断有机会可以解决这个case 。需要SW进行逻辑更改 ，请SW评估下是否进行更改以及更改plan @Wei Wei9 Xu 2.2 选择放弃这个项 的符合，宣称不支持 。 负面影响是什么，RD无法判断 ，需要请 认证同事 帮忙多确认下 @Xingxing XX18 Wang@Weiting Wt1 Sun | IKSWW-163405 | 文亭 |  |  |  | #N/A
2026-02-09 | 7.DVT2 | 3.Charging | 5.2 BB Test | NA | NA | RISK : 加州能效测试，临界fail 了TMO要求的70% 的加严标准 Impact：对Terrain项目本体无影响，因为没有NA SKU，作为内部测试参考项，不强制pass。 扩展：Artura 同平台，推测会有面临这个问题，所以需要提前触发给SW 研究解决方案，但是非紧急事件 rootcause：第一阶：关机充满电后，还有5V100mA。这个满电维持电流太高了，一版要稳定过加州能效，在60mA以内比较有机会。 为什么满电后维持功耗这么大？ 第二阶：memory 是否配置低功耗模式？ |  | 文亭 |  |  |  | #N/A
2026-02-03 | 7.DVT2 | 1.Platform | 5.2 BB Test | NA | NA | RISK : MTK 要求这个项目增加SPMI在不同地方进行尝试（CPU，PMIC ，以及PMK 都测试）， 并且增加 glitch 指标。 当前刚完成该测试，发现SPMI 靠近CPU端的Glitch 指标严重超标。 | link | 文亭 | 范南 |  |  | #N/A
2026-01-14 | 5.DVT1 | 3.Charging | 5.2 BB Test | S2 | Closed | Issue：BB和SW 测试发现最近的SW版本，手机低电量 1%~2% 开始充电，充几分钟后无线充电大概率异常 ， 故障现象有三种 1. 充电图标一直在，但是充电电量不上涨反而降低最后没电关机了，变成关机充电 2. 充电提醒反复出现 3. 提示位置放偏了 Impact：低电量的手机+moto 15W 无线充电器充电 无法正常工作（充电到2%~5%会停充 或者 出现一些异常提醒 ）。以及推测一些第三方有类似保护功能的TX 也会出现无法工作的问题。 Rootcause： 根因1 ：主充电IC MT6375 检测到 IC端的Vbat=3.6V的时候短时间关闭batfet再打开 -》电池端能吃下的负载瞬断1.5ms左右-》无线充IC输出功率瞬间出现一个大约14W的功率骤然下降 根因2：无线充IC 功率骤然下降-》 MOTO 15W TX 触发 OVP-》TX 主动降 VPA--》TX降频 + 拉满 duty 补功率-》TX IPA 超限触发 OCP 》TX 切断输出》RX 侧 vout/iout 骤降甚至关闭。 solution： Action1：MT6375 batfet转换节点电压 从3.6V改为3.4V （降低可能出现问题的电量比例 ） Action2：无线充开始枚举的时候，如果判断到电量低于10%的时候 就限制无线充功率到10W ,如果判断到电量大于 10%的时候按照15W工作 。 两个Action 在1月28号进入SW主线。 长期：MTK平台建议选择 使用类似的方式，低于10%的时候降低功率到10W 来规避风险。 高通平台目前看PMIC没有类似MTK的这个特性（ 高通PM8350B看到的点是Vbat~=3.05V就已经将batfet 完全打开了） 对应项目最好也再确认下 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-12-22 | 5.DVT1 | 5.Camera | 5.6 User Feedback | S2 | Open | Issue：IKSWW-111442 Vertical streaks appear on cameras 1X-2X (摄像头1X-2X出现竖纹) B2GID:328394128 Analyze: 1. DVT1 样机插联通SIM卡，户外，开NFC，开WIFI（未连接有效网络），预览或者录像时发现有偶发竖条纹。 2. 隔天不复现; 3.拿到样机后，复测主camera天线干扰测试4次，均pass 4.联通注册网络为LTE B1，B3, NR N1和N78 ， 只在这四个频段切换。从天线结构看，N78在camera周围的ANT5和ANT7，按照最大功率26dbm发射测试多次，ANT8 B1 24.5dbm 发射多次也未出现，并未出现异常。B3, N1 在ANT8在，远离camera deco, 远离camera，从理论上不存在干扰主camera的问题。 5.NFC待验证 | LINK | 芳梅 |  |  |  | #N/A
2025-12-22 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Monitor | Issue1：DVT1B ESD 报两台D1,D3机器ANT6 Fail(RX3 B3 B41 B66) ，D4一台 ANT0 Fail(RX0 B28); Analyze: 1. ANT6 ：Tuner NG； 路径：SideKey处进入； Diff：Sikekey音量上按键天线包塑处露金属； 2. ANT0：Tuner NG； 路径：SPK开孔处进入； Diff：SPK口密封胶圈装配偏位； 共同差异是天线TVS换成二供Walsin-TLE1020。 Action: 1. 设计DOE实验判断更换Panasonic ATVS是否有效； 2. 验证新ATVS: TUE10201V06B0性能，是否能完全做一二替代； 3. 请结构判断是否有机会拉齐二供的质量 1）天线塑胶完全包住； 2）确保SPK密封胶圈装配正确； Solution：1. op1：更换性能更好的二供ATVS - TUE10201V06B0 ； op2： ANT0/AN6点位用松下ATVS，其他点位用二供ATVS； 2. MB/SUB板 TVS以及下地电容走线优化，Sidekey FPC增加露铜吸引静电；——DVT2B发板已改入 | Link | 廖哲霖 |  |  |  | #N/A
| 5.DVT1 | 20.NFC | 4.Build | S1 | Monitor | Issue1：产线反馈DVT1 试产中部分中途整机升级的机器中出现不识别NFC,更个stack 板子后可以识别，再装回去也都可以正常识别，直接板测阶段升级软件的机器没有出现过。 Analyze: 1.验证硬件通路是否正常。---从Stack 板测量，开始时候有I2C 信号和NFC_CLK。说明NFC 硬件通路是正常。 2.若SW FWDL流程后，NFC 芯片可以恢复，可以正常工作。 Rootcase： 发送以下的reset指令后，因为一直收不到IRQ, read就会失败，然后就读不到信息， 驱动层面nfcc_hw_check 就不能成功的获取chip type，然后nxpnfcinfo 尝试从驱动获取 nfcc info 的时候 获得的就是0， 然后就不会去 设置 vendor.qti.nfc.chipid. 当前因为涉及到PN560 和SN2260的混用，只有 vendor.qti.nfc.chipid 被设置之后 NFC hal才会真正开始工作。第一次发送 nci_reset_cmd 之后， IRQ 一直没有被拉高，然后即使用polling mode也 read失败 目前从我们抓到的波形以及log看，还是芯片不响应。 Solution ： 在NXP的I2C 驱动这边加一个逻辑，如果probe的时候 nfcc_hw_check 没有成功获取信息， nxpnfcinfo 尝试通过IOCTL获取 nfc info的时候，驱动再次去和芯片交互。 | Link | 李果 | 院长 |  |  | #N/A
2025-12-09 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | Issue: 产线出现2pcs Slave 快充测试fail主板，X-RAY无问题， ABA 交叉确认故障跟随 快充IC U2651 。 total 600pcs Analyze: 1. 一供快充IC SC8586A寄给vendor 分析， Vendor 分析结果是IC没有问题 12/18 返回IC，产线安排复测故障不复现，如果按照以往的逻辑判定，这个可能就是焊接性问题。 2. 通知产线如果再发现同样问题，需要抓取log 分析下线索。 Solution： DVT2 没有复现问题，close |  | 文亭 |  |  | 6.No Change | #N/A
2025-11-25 | 4.EVT | 5.Camera | 5.2 BB Test | S1 | Open | [s1]Issue ：Terrrain EVT 自测天线干扰camera拍照时，EVT1 2台/6台 主camera 被ANT7 N77&N78干扰 Clue: 1. camera模组和FPC远离主板 ok 2. 和天线无关，将主板拆出，camera FPC贴在主板器件上，EVT1和EVT2整机搭配一二供模组都会出现条纹干扰 Root cause: Camera FPC装配后，FPC贴在主板上ANT7的通道上，当ANT7 N77和N78发射时camera 被干扰 Solution：Add copper foil on FL3304 ，Shield the source of interference Verification： DVT1 一供 base 2/ 66pcs DVT1 二供 copper 100 pass | link | 芳梅 | 院长 |  |  | #N/A
2025-11-25 | 4.EVT | 5.Camera | 5.2 BB Test | NA | NA | [s1]Issue ：Terrain EVT 自测手电筒亮着时，强制关机，这时候闪光灯会一直亮着，直到开机后，软件初始化再关闭手电筒 Clue:强制关机时未走完整的下电流程，导致没有ENpin 控制的闪光灯驱动IC AW36518 ，长亮着 Solution： Terrain没有实际的用户场景，不做修改。 针对日本SKU有强制要求的，需要使用有ENpin的闪光灯驱动IC 后续项目： 1. 选用带ENpin的闪光灯驱动，继续寻找一颗用于替代AW36518 2. 目前AW36518如果要使用，新的硬件接线方式需要给TX增加一个GPIO控制，并和软件确认闪光灯寄存器设置 | link | 芳梅 | 院长 |  |  | #N/A
2025-11-07 | 4.EVT | 5.Camera | 5.2 BB Test | S1 | Monitor | [s1]Issue ：Terrrain wide camera 预览可以看到有竖条纹。 Clue: 1. wide Camera 远离主板竖条纹消失，越靠近主板现象越明显 2. wide Camera 下方有PMIC器件，去掉隔磁片，图像上有非常明显的干扰条纹 Root cause: Wide camera放在PMIC屏蔽盖下，电源干扰到camera sensor，EVT整机camera下方有贴隔磁片在PMIC屏蔽盖上， 但是装配后，未完全覆盖camera头部，导致有磁泄露 Solution： EVT2更改隔磁片贴到wide camera模组上，隔磁片尺寸和wide camera一致，待EVT2整机导入 Verification EVT1 导入次方案后，效果ok EVT2 2供模组依然还有问题。因为一二供模组有差异，隔磁片有包边后，实际有效面积内缩单边0.5mm+ DVT1方案： 结构优化隔磁片，不算包边，需要隔磁片能覆盖住模组底部。手工检查7台ok，2台实测RCN pass | link | 芳梅 | 院长 |  |  | #N/A
2025-11-06 | 4.EVT | 6.Display/Touch | 4.Build | S2 | Monitor | Issue: 产线出现2pcs无触屏主板，X-RAY无问题，测量Touch_VCI_3P3无电压，Touch_VIO_1P8开机过程中会有1.8V，5s左右掉电，测量TP所有线路二极体阻值正常; Analyze: 1. 请产线重新刷27软件，没有解决问题； 2. 1#主板更换LDO和PMIC，故障依旧，通过ADB命令回读GPIO状态，没有grep到对应PIN， 3. 1#主板产线自行更换了CPU，不重刷软件，TP电压和功能均恢复正常。 4. 1#主板 怀疑是CPU问题，但是没办法交叉验证（CPU是POP的，EVT没有钢网，产线没办法将故障CPU重新焊接到OK的主板上）。2# 故障主板直接抓Log，软件判断是AP读不到TouchIC的ID，导致初始化流程没有跑下去。且Log中没有看到OCP或者其他的保护类报错。 5. 请产线X-RAY照了下2# 故障机器SPI部分的焊点，未发现明显问题。 6. 2#主板对比测量NG-CPU SPI阻抗，发现CLK MOSI 这两组稍微偏大了点。 RootCase：怀疑可能和CPU有关？ Solution：1. 确认无法交叉验证方法后，2#主板也更换CPU确认下故障是否消除。 2. CPU寄给MTK确认—— 已经请wenting帮忙和MTK沟通，邮件已经反馈了我们这里的分析信息，2pcs主板； 3. MTK反馈管脚IV曲线测试没有发现异常，返回武汉处上板验证，依然不良，已重新寄回MTK处返回台湾ATE进行分析；—— 12/1 更新： 12/19 MTK返回分析报告，判断2pcs CPU分析结果为EOS损坏 link | Link | 廖哲霖 |  |  |  | #N/A
2025-11-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | issue：After 150V surge pulse test,fast charging no function,OTG no function,headset no fuction:D1/D2(Vbus)- 推测：可能1.快充IC的OVP控制模块坏了。如果是这样，有预留串联电阻可以加上电阻进行复测。 Analyze：1. D1机器测量VBUS对地，D2:正向45.5K，反向5.1K，D2：正向 分析：插入充电器，有电压，没电流。插入OTG，看到输出电压只有3V。 拆机测量 OVP 前后的Vbus 电压波形，发现两端电压不等，插入充电器，OVP后端只有1V电压，所以不能正常充电，虽然OVP前端检测到有充电器插入了。 OTG时候，发现后端电压5V，但是接口端3V。 根据以上信息，可以判定，快充IC的OVP控制模块坏了。 根据历史经验评估，OVP模块 坏了，就是浪涌从vbus sens pin 进入，超过了IC的耐受度而损坏了相关OVP控制模块。 解决方向：快充IC的OVP串联电阻，提高这个pin的抵抗力。根据经验以及vendor的信息看，希望加10R~22R之间的电阻。 目前项目上建议直接上最大值22R。 然后尽量小板浪涌管加强接地和走线尽量优化（具体看板子的情况） Rootcase： 浪涌太大，超过快充IC的OVP sens pin 的耐压36V，导致这部分电路烧毁。OVP 模块无法工作导致充电相关都异常，包括OTG。 Solution ：1. 小板浪涌管下地加强——DVT1已导入 2. 快充IC Vbus 侦测pin 预留的串联电阻R2600，从0R改为22R，料号：0613952X33 .---EVT rework 验证，11/24出结果，一台250V Fail，一台500V Pass，结果均Pass（高于200V） DVT 1 原理图已提交对应的更改。 3. 二供两台机器EOS Fail，分析发现一样是OVP控制模块的问题，测量发现OTG可以工作，但是死电池没办法充电，判断还是VBUS SENS PIN损坏导致。（OTG输出时，VCHG有电，OVP模块可以正常工作。死电池时，OVP模块没办法从VBUS SENS PIN取电，所以打不开OVP） 4. 一供250V Fail的机器，分析问题同二供机器。 DVT1 pass | RPA FA link | 廖哲霖 | 文亭 |  | 3.BOM | #N/A
2025-11-12 | 4.EVT | 3.Charging | 5.2 BB Test | S2 | Closed | Issue：产线反馈，CQA1 有些机器无线充测试fail ，情况2 Analyze: 1. FW 升级成功后，有些机器测试依然fail 。数量不明。（因为被FW升级失败的前置case 给掩盖了） 杨楠的机器证明是这种情况，拆开机器后，弹点上基本上没有压痕。飞线焊接后ok 更多故障机还在筛选返回，预计11/24 会有2台类似故障机器到厦门 ME ， ME分析定位为后壳被顶起，导致接触不好（按压后壳后，可以无线充了）（同批机器切片发现，后壳有顶起 大约0.27 ,更具体数据见ME的报告） Rootcase： 弹片和coil 接触性问题。 推测 是小A壳变形导致的接触不上（可能是边上泡棉顶起来了） Solution ：ME 主导 DVT1 ok | link | 文亭 |  | IKSWW-75804 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-11-12 | 4.EVT | 3.Charging | 4.Build | S3 | Closed | Issue：产线反馈，CQA1 32.3% 机器无线充测试fail Analyze: 1.情况1FW 升级失败，这个对应CR 。拿到两台机器功能都恢复了。 针对这个情况下一步：出临时FW版本来回刷，看下是否可以复现故障。然后分析具体原因和电压波形情况 2.情况2 有1pcs机器可能真有问题， N0TI050112 这台的故障是stack 小板弹片由于首板焊接过导致的问题。 这个已经手写首件，没想到还是拿来装配了。 （这明显外观不良。忽略 ） 。 Rootcase：FW 升级失败：1.1 由于无线充再stack 板子上，所以BT站点测试无法给无线充IC升级FW 1.2目前开机升级FW，是一开电，IC供电电压不稳，就立刻进行FW操作，导致概率性失败，电池电量低的时候fail概率越大 。 （而EVT产线就是不插充电器直接开机的，没有一次插充电器再开机的操作，电量又比较低，因为前面的站点也没测试来卡控电量，恶化了这个情况） Solution ：1.1 FW操作在给电源后，delay 25ms ，然后再进行FW操作。（这样更保险，避免供电不稳就开始操作引起失败）--待SW更改后测量波形确认 。plan 11/25 1.2 站点测试看是否可以双保险，自动化测试，直接执行强制升级命令 并回读FW版本来确认升级成功 ---SW 和 factory 沟通完成，DVT1 正式导入 DVT1 ok | link | 文亭 |  | IKSWW-75804 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-11-06 | 4.EVT | 6.Display/Touch | 4.Build | S2 | Monitor | Issue：产线反馈，出现1pcs闪屏，交叉验证故障跟随主板。（周六反馈CQA1检出来2PCS，产线检出来3PCS，待确认） Analyze: 1. 请产线在白屏状态下调节屏幕亮暗，发现闪屏频率没有改变，调整分辨率也没有改善。感觉和ELV关联性不大 2. 抓Log给软件分析中； 3. 已经请产线寄一台故障机N0TR050117回来分析。 11/10：log软件分析，闪频是触发了ESD Recovery机制，等待周一新版本复测看看 —— 测试30min，无出现闪屏； 4. 通知工厂故障机刷96的版本验证 Rootcase：VTDR的DDIC的ESD Revovery机制需要在HS mode下读取，之前的版本是在LS mode下读取导致。 Solution：1. 产线工厂模式验证了4台故障机刷了新版本，CQA跑了一遍循环，未再复现闪屏； 2. ESD检测模式修改成HS mode改入主线。—— Done | Link | 廖哲霖 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-11-03 | 4.EVT | 12.EMC | 5.1 Bring up | S2 | Closed | ISSUE: VBAT D2751反馈异常，EVT Bringup文亭手头板子大电流，以及芳梅手头一台机器都有出现。 Analyze：1.测量电阻，没看出异常，反向19.85K，正向∞，和正常的比对差不多？ 2.产线去掉CPU 屏蔽盖后故障消失 3.发热点位置在快充IC附近，而且是靠近左下角slave 快充IC附近 Rootcause： 推测：CPU 屏蔽盖有些金属造成短路 和 快充IC大电容 短路造成大电流透过快充IC。非常临界，加热等操作都有可能破坏现象 Solution： 1.ME 主导确认屏蔽盖本体问题和解决。 2. Impact：EVT的机器随时可能会自动关机。 |  | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-10-20 | 3.PEL | 11.Thermal | 5.1 Bring up | S3 | Closed | ISSUE： MCHG NTC 温度读值不对？（AUXADC_MT6375_NTC） rootcause: 双贴了NTC solution：EVT change SCH & CPB& BOM ，remove 1 pcs NTC |  | 德太加 |  |  | 1.SCH | #N/A
2026-01-05 | B.PVT | 9.Memory | 5.6 User Feedback | S2 | Monitor | Issue ： "Micron UFS doorbell time out(IKSWW-100968)：问题出现在2台DVT机器，1台PVT机器 Log分析，出问题时，UFS无反应，只有等watch dog time out reset才能恢复，所以QC的增加timeout方法不能解决问题，重点还是需要推动Micron分析原因。 Micron 分析：初步给的结果是 log 看到VCCQ 低于器件SPEC门限的log信息。电压最低到达1.12V ，低于器件SPEC 低门限 1.14V 。 Rootcause：Suspect1：VCCQ 电压低于器件SPEC 低门限 1.14V。 2.但是是推测，不能确认是否是rootcause ，需要micron 继续分析。 Solution： Action1：SW 更改VCCQ电压输出设置，从1.08V~3.04V 改为 1.14V~1.26V ，initial 电压1.2V 要更改才有效 Action2 ：相关的电源 更改LPM mode 为NPM mode | Link | 嘉琨 | 敏敏 | issue 汇总页面 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-11-24 | B.PVT | 3.Charging | 4.Build | S3 | Closed | Issue ：Dallas 故障现象，runin 过后，有的机器插入快充充电器 就出现 反复出现充电图标的故障现象。 插入 USB 和10W充电器，没有故障，可以正常使用。 重启机器后恢复 。 DVT1 RUIN 后的机器出现2pcs （1.27%），PVT RUIN 出现15pcs （2.11%）（截止11/27 统计数据） Rootcause： dallas 电量计从NFG1000A升级到MPC8011B ，主要优势是 MPC8011B的运行内存加大。但是 ，FW设计的时候I2C控制逻辑部分的代码运行空间 从 原来空间 转移到 新扩散的空间中，而新空间的运行速度慢一些， 和 I2C timeout的逻辑 存在逻辑冲突， 存在逻辑漏洞，有低概率导致芯片进入deepsleep模式。一旦进入这个模式会拉住I2C总线，进而导致开机的时候快充IC初始化失败，就出现了接快充充电器插入的时候 反复出现充电图标。 其他线索：目前从fail log 中发现，这种情况下，反复读取电量计后，I2C总线会恢复过来。所以就有了workaround的思路。 Solution： 1 Workaround ：开机的时候对电量计先进行持续读取让I2C总线能活过来，然后再进行快充IC初始化。---plan SW 11/28 进入主线。 2.根除方法：Vendor 将I2C控制代码改回到和NFG1000A 一样的空间，来保证电量计本身不存在这个bug。 2.1 PVT末段的剩余电池，协调厂家过来对电池本体升级后再装机， 并安排压测确认没问题 了---- close 2.2 量产来的电池需要更改过来----ongoing，KP 闲军跟踪中 其他信息：Avenger 也同时出现一样的问题。解决逻辑和dallas 目前安排的一样。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-10-21 | 5.DVT1 | 20.NFC | 4.Build | S2 | Closed | Issue：近期生产线与测试环节出现大量的eSIM概率性掉卡问题。经初步分析，软件层面发现有接收中断（Rx Break） 的异常记录。 CR：IKSWW-60856/ IKSWW-61451 / IKSWW-57936，其现象与本问题一致，但缺乏关键的Modem日志。需要安排重启后进行压力测试，复现问题并抓取Modem日志。 Analysis: 1.工厂环境下的“假性”掉卡：现象：在工厂版本的软件上，执行 -w 命令（恢复出厂设置）后均会出现掉卡现象。本质：底层Modem实际仍能识别到eSIM，但系统UI界面未能及时刷新状态，从而显示为无卡。 2.真实待机下的“真性”掉卡：现象：设备在待机状态下，eSIM会彻底掉卡，无法识别EID。此问题在原有机型上概率约为1-2天出现一次。触发条件：当SIM卡槽1（SIM 1）插有实体卡时，eSIM掉卡的概率显著提升。其触发率遵循：实网卡 > 测试白卡 > 无卡。 根本迹象：通过逻辑分析仪抓取波形发现，在eSIM掉卡前，其通信波形（CLK, I/O, RST）均正常，但eSIM芯片本身无响应，疑似进入“死锁”状态。 临时恢复手段：只有重启设备才能正常识别。此外，实验发现通过NFC向eSIM发送一个复位（RST）信号，可触发Modem重新为eSIM上电并识卡，也能实现恢复。 Root Cause: 经深入排查，问题的根本原因锁定在Modem与eSIM芯片的初始化流程上：Modem复位时，未向eSIM芯片发送必要的 Terminal Profile 指令。由于该eSIM芯片（Thales供应商）默认开启了 UAP（USAT Application Pairing） 功能，此功能若未收到Terminal Profile，会在255个周期后自动关闭eSIM，导致其进入 Mute（静默/无响应）状态。 Solution: 1.SW : 向高通（Qualcomm）提交案例，申请修改Modem底层代码，确保在卡复位流程中必须发送Terminal Profile指令。 2.eSIM : Thales获取默认关闭UAP功能的eSIM芯片或配置文件。 3.HW: 在PVT 2nd 阶段，修改PCB板设计，在eSIM的VSIM供电线路上串联电阻，以隔离来自SIM2的潜在电源干扰。 | link | 李果 |  |  | 1.SCH | #N/A
2025-10-11 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | ISSUE：case3 DVT1 BT 站点测试 有7pcs（截止10/13）二供主板slave Chargepump 固定fail 在 ACCESSORY_CURRENT_CAPSWITCH_Slave，至少包含：N1DA1D0187，N1DT170182，N1DT170181 N1DA1D0103，N1DN1V0101。N1DA1D0170 和N1DT170148 （10/11 增加） Rootcause： 1. double 确认结果：板子装机，用68W充电器功率到不了68W，只到30+W就重新从0W开始了，这个是slave CP fail 的一种表现。 2.抓log 正向分析--slave CP I2C不成功，初始化时候就开始不成功 3.故障板子N1DA1D0170产线 测量R2837=6.24KR左右，和中值6.19K差不多，地址选择电阻看起来没问题。 【10/27】：1.故障厂家确认可以拦截。现在加入拦截机制，并且要留出一定的margin。11/1 前提供1000pcs ok 物料给到moto 做验证。（目前我们外部设置的地址选择电阻在6.19KR，新加拦截机制检测门限在6.4KR 以上pass。） 2. 根因分析：目前推测是制程问题导致 的 地址选择pin 的电流检测门限偏差（最后等效为 电阻检测范围偏差） 10/28 会和厂家第二沟通会议，待更进一步确认厂家 更深层次的根因。（包括 不同批次的偏差情况，以及后续长期拦截的门限值是否要调整 等相关问题讨论。） Solution：【10/30】：Action 1.厂家确认增加拦截，拦截到6.5KR for这批物料，第一批1000pcs for Dallas，计划 10/30 发出，预计11/1 到达武汉。 2.设计上我们选用4.99KR 1%进度电阻来加大margin （根据供应商的整体数据仿真，最低容许电阻门限在6KR左右，咱们选择小于这个范围的值就没问题），确认不会再出现类似故障。（寄过去的故障品用这个阻值试过也都ok了的） PVT 8+256 的BOM 试产这个物料， PVT试产结果- 301 pcs ，all pass close | link | 文亭 |  | IKSWW-59901 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-09-25 | 5.DVT1 | 2.Power | 4.Build | S3 | Closed | ISSUE：4G BT 站点 shipping mode 电流测试项fail ，retry pass 。IKSWW-51092 ，复现概率极低（2%左右） Clue：0. dallas Vbat 就连着两个快充IC和PM8350B。也就是板级测试执行shipping mode后，只有这些能漏电 1.从故障板子看，测试到的电流有时候小，有时候变动 2. 故障板子拿到后，测试漏电流，底电流正常 3. 故障板子拿到后，测试shipping mode ，电流正常 4. 故障板子拿到后，先操作快充的ADC后，直接测试shipping mode ，Ibat 电流再900~1200uA之间跳变，和产线反馈的故障机的400+uA 和 70uA之间跳变的结果不匹配。 Rootcause：suspect ，4G BT 站点测试后，某个器件没有正常关闭，导致漏电流过大。（而且是波动的电流）---怀疑方向就三个： 两个快充IC 和PM8350B 下一步：1.临时测试包，去掉4G BT站点所有充电相关测试项，压测，看是否会复现问题。 方向2：同步评估去掉shipping mode，看下存储时间。 如果满足不了12个月，考虑参考Houston将出货电量改为60%。 solution：去掉shipping mode，看下存储时间。 如果满足不了12个月，考虑参考Houston将出货电量改为60% IKTM-13379 Dallas remove shipping mode & change storage battery capacity from 50%to 60% | link | 敏敏 | 文亭 | IKSWW-51092 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-10-11 | 5.DVT1 | 5.Camera | 4.Build | S2 | Closed | 5.Camera 4.Build S3 Closed "Issue: IKSWW-54362台报主摄拍照dump。 （3台1100台一供） Clue： 1.均是主摄测试fail，且log均提示的MIPI error Root cause： MIPI cphy参数和目前硬件搭配不是最优 Solution： 优化MIPI cphy参数( 修改后EQ=0x0B， CDR PGM=0x40，CDR Coarse=0x0B)，待软件提供版本给产线。" ---10/13 retest fail ，reopen ，软件参数未提交。 10/15 新参数有效导入产线故障机后验证pass 长期：houston 上的参数到dallas 参数为什么就不生效？ SW主导确认 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-10-11 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | 7. sensor -M-sensor 受到干扰影响 clue：隔磁片规格更改for hac 优化。可能影响到M-sensor 了。 solution： DVT1 1供机器通过优化参数解决了，测试5台都pass了。 |  | 小熊 |  |  | 4.Parameter | #N/A
2025-10-10 | 4.EVT | 3.Charging | 4.Build | NA | Closed | ISSUE：DVT1 整机AR站点测试 个别机器slave Chargepump 固定fail 在Cap_Switch_Turbo_Acc_Curr_Cap_30W_01_slave Clue： 1.用真充电器68W，可以看到功率是出来了的，没有fail 。共5台 2.Case1 ：其中4台（分析机器是N1DV110139），在使能快充前 控制电源电压后 增加delay 1秒钟 ，4台复测pass 了 3. case2 ：但是还有1台N1DA120231 fail ，现象一模一样（没有cp的电流） 更改测试程序为每次生压后都再次EN，case2 也pass 了。 转入monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-09-25 | 4.EVT | 2.Power | 4.Build | NA | NA | ISSUE：IF 有些板子不良后，需要强制下载才能恢复。 Clue：SW 先主导看，这边只做一条记录。 |  | 文亭 |  |  | 6.No Change | #N/A
2025-09-01 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | ISSUE："EVT ATT tumble WH195778 1st 6:Cap/SAR sensor Ch2 no function:D8(450)- 0901已返回厦门，分析中 7:Cap/SAR sensor Ch2 no function(Recovered after reboot :D10(500)" 。已恢复 坐压试验 也出了一台SAR sensor Ch2 no function 分析结果一样。 合并处理 Clue：0. 二供机器实验也出现一台450滚出现无作用，重启后恢复了的。 1.机器回来的时候，故障复现。重新开关机依然复现。 2.插入USB后，故障消失 3.装成整机，跌落压测，复现1次。这时候用WIFI adb 查看，发现CH2 没有读值。（所以看起来非门限fail问题） 4. 跌落后又复现了。加热焊接也还能复现。 而且这时候插入USB 无法再恢复了，判断为IC彻底坏了。 5. Houston 是没问题的。 capsesnor没改，可能是其他变化导致的应力发生变化 Rootcause：推测是 IC 被应力破坏，处于半坏不坏的状态。 将这个IC寄给厂家分析内部情况，预计9/10 返回分析报告。 ME 确认dallas 和 houston的结构应力情况。 Solution：建议移动capsensor ，来优化作用到capsensor应力。 Option1 可实现的是往左上角移动，最后移动到屏蔽盖外， DVT1 一供跟踪 DVT1 一供都测试完了 pass，先close |  | 小熊 |  | 分析PA | 2.PCB | #N/A
2025-09-16 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | ISSUE：EVT二供机器自测，发现1台机器，关机充电后，出现PD充电器会出现fail 。最后不充电。1#机器一直fail 。 另外借了2台机器 ，补充复测了8次左右，2#机器概率性出现2次，重新开机会恢复，不好复现。3#机器一直无法复现。 clue：1. 1#2#机器的log 分析 都是BAT OVP 被触发了，关闭了CP。但是实际上电池电量都基本没电了（小于10%，电量计读到的电压才3.7V左右），快充IC就触发高电压保护，门限是4.8V左右，这不正常。 2. 拆机测量波形，确实有 Vbat 高压出来，Vbus 也抬高了电压，但是Ibus是先下降的。 推测是因为充电电流停下来导致的Vbus电压提升，然后导致Vbat 电压过高。 Rootcause：根因是在二供电池端的OCP值偏低，和SPEC不符合 ，导致的 SGM41606S 触发OCP过充行为而后会连带触发OVP行为，停止充电了。 Solution ：DVT1 二供电池修复 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-08-04 | 4.EVT | 3.Charging | 4.Build | NA | Closed | RISK：PEN current test ，EVT 截止8/26早上 数据看，有一些读值0的情况出现。 出现一次65高数据，复测pass。 概率性出现0值的机器，推测可能是FPC 或者触点接触问题。 需要ME特别关注。 线索：有发现个别机器明确接触问题。 其他机器需要找到机器跟踪，看下是否会复现。 rootcause：TBD solution： 组装部分：DVT1 增加MMI测试，避免机壳没有测试就留到装配。（EVT处于调试阶段，一些机壳没有严格管控就流下去了） UCT 测试部分：DVT1 增加 hall IC的检测，来判断工装笔B是否在位，来进一步确认是否漏装笔就进行测试了。 | link | 文亭 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-08-04 | 4.EVB | 12.EMC | 3.Review/Simulation | S2 | Closed | RISK：ANT 上面 ATVS 的方案 BOM 评审结论：提出验证通过后加二供 咱们只有一次DVT，要如何验证？ 8/4 结论： EVT 先用华新科 主要验证一供（样机 EVT BB申请了6台一供for TCC ESD）。 松下放到二供中的试产，并和邓玲沟通做两台ESD作为备用。（样机要和邓玲沟通好） DVT1 根据EVT的情况来定。 结果是都pass。 |  | 廖哲霖 | 文亭 |  | 6.No Change | #N/A
2025-08-04 | 4.EVB | 12.EMC | 3.Review/Simulation | S3 | Closed | RISK：主动笔充电相关电路（包括ADC 检测）被打坏的风险 1. ESD期望设计方案：1最优 在机壳外挡住，2.优 挡不住尽量能接地 或者 3.次优放个间接接地（就是笔身周围给出一小块GND，不接触，但是有露出来。） 4.最差就是悬空金属块（当前状态）。 基于ESD 防护， 尽量不要让ESD进入到电路。请ME 帮忙再想想方法，看是否有机会。 2.EVT试产前，用EVB 飞线进行摸底，看加了TVS后，能抗住多少KV ESD冲击。（充电部分和 电流ADC检测部分） action： 1.实体笔 样品，ESD摸底，ESD轻松的就从笔身传递到触点。 所以目前推测的ESD进入risk 是真实存在的，而且较高。8/4 done 2. 采取了很多措施，已经处理的。 主板端EVT 就会导入TVS 来防护两个弹点对应的电路。（电源正极 和 ADC 采集口，分别各加一个TVS 器件在主板）。done in EVT MB PCB 。具体型号优化选择，EVT 发BOM 前完成 --BB 8/8 3.一些否决了的优化方向：笔身金属 在任何一个位置坐间接空气放电的可能性 ： ME 评估 完全没有办法，IP68防水要求，需要用塑胶完全堵死。不能露出任何一点点 导电金属体。 直接接地就更不用说了----目前为止没有可行方案。 ---ME chenjianxi comment ，没有方案。 4. 备用方案1：将主动笔FPC 上增加加强版，然后加两个TVS，再防护一道。 ---ME yuming 评估是这个导致弹片压力增加，有风险，不建议直接进主线。建议作为备用方案。 增加一版V02 FPC。增加加强板和TVS 以及点胶。具体待发板，plan ： --ME/BB 8/8 " 9/1 BB ESD摸底两台数据都打完了，充电和非充电状态下都有打，15kV/18kV压测下，未发现有Fail的状态，目前摸底结果感觉还行，会继续Monitor下TCC的数据 TCC数据：6 台机器，15KV实验完，笔都是ok的。 补测18KV的笔位置ESD实验。 测试手机ok，1支笔fail。厂家分析。手机ok ，close risk | link | 廖哲霖 | 文亭 |  | 6.No Change | #N/A
2025-11-11 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | NA | Issue ：PRC 售后故障机 356070750758578，不开机不充电 |  | 文亭 |  |  |  | #N/A
2025-11-11 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Open | Issue ：IKSWW-69570 Equator 充电只显示"充电已连接但是不充电“// 新品X70Air DOA申请 clue：第一台IMEI 356070750759253，寄存器看PMIV0102 有些寄存器不对。 该机器重启不会恢复。最后是刷机后恢复了。机器返回武汉，11/11 ETA 武汉工厂 ，shatong2 手上。初步看是可以充电的。 第二台 IMEI：356070750876016 ，11/4 签收，当天反馈充电中但是持续掉电，更换充电器无效，退机。 next ：第一台故障机寄往SW。第二台确认在哪里，以及故障情况。 | link | 文亭 |  |  |  | #N/A
2025-09-28 | B.PVT | 3.Charging | 5.5 Certification | NA | NA | [s1]Issue ： Equator 1725 认证fail，低温下提前停止充电 （一供-2度，二供-10度 。期望值是在-20度+/-3 度） clue：1.log 分析看到，是充电带载电池电压达到4.2V了，走停充流程了。 2.低温下电池内阻看起来很大，-2度之后ATL的内阻258MR，-10度时候CSMOX的内阻458MR。导致的压降很大，一下子就到4.2V了。这内阻正常吗？低温下的电芯内阻曲线如何？---待KP 确认 Analysis/Root Cause: HW根因：低温下电池的内阻会很大，到几百mR，温度越低，就内阻越大，当固定电流下，压降会越大，就会导致提前触发4.2V的低温停充电压。 当前问题1：在-1度左右触发fail的，推测原因是0度以上电流是很大的，电压也很高（带载电压可以到4.5V），转到-1度时候，转换策略会立刻触发判定已经充满（实际电芯电压在3.7V左右） 当前问题2：在-1度这个位置没出问题，继续往下降温，由于限流后还持续充电，温度也越来越低，内阻越来越大，所以电压持续上升，最后再-10度左右（这个值和电池电量有关系）达到了4.2V，然后没有办法继续走完CV 很快就停充了（从log 看到的信息是几秒钟就停了，原因不明）。 当前问题3：当触发充满的状态后，即使温度恢复了，也不会再重新启动充电。就是低温停充恢复机制这种情况下失效了。 当前问题4：插入充电器一瞬间电流很大，然后再变成目标电流。这个会大大加大触发停充的概率 Action/Solution: push_new_image3.zip 主要修改：低于0度的充电电流限制为350mA（ 降低问题2机会 ）。更改FCC来达到一上来的电流不会过大。（解决了问题4）. 前提条件:低温验证不要从0度开始插入充电器测试，要低一些，建议-10度插入充电器，然后继续降温验证。（用操作手法规避问题1） 机器初始电量要低于5%比较保险过。 最多也不能超过10%（越高越可能fail。）这些值是基于厦门温箱环境得出来的结果哈。 摸底by chenwt：这个版本初步验证ok了，低温可以到-21度才停充，-19度恢复充电。 （不触发停充就不会触发问题3） 10/9 认证发出 ：push_new_image3.zip 这个版本给UL 进行复测，根据自测要求 。 反馈测试pass了。 SW 10/9 改进主线 wave1 | link | 文亭 | 李果 |  |  | #N/A
2025-09-26 | B.PVT | 3.Charging | 5.6 User Feedback | NA | NA | [s3]Issue ： Equator 关机不充电 问题IKSWW-51939 线索：1.一次QC3+33W充电器故障后，不充电的时候，看到Vbus5V Ibus80mA左右。D+D- 电压3.05V 从这些信息推测：1.CP的OVP是打开了的。这样才有80mA这么多的电流。 2. 补充模拟实验：1 ：正常关机的时候，DP DM 外部强拉3V，再插入QC3+充电器，看一下波形和机器的表现。 | link | 文亭 |  |  |  | #N/A
2025-09-12 | B.PVT | 10.USB-C | 4.Build | S2 | Monitor | [s1]Issue ：PVT 批量发现USB/充电不识别的整机（之前各轮试产未发现） （TCC 4台，工厂2台，预备送媒体机7台，据不完全统计， 不良发生概率在7%左右） 故障现象：无法识别USB/无法快充（可以5V慢充），关机重启故障依旧存在（软重启） Root Cause:1. 误识别成uUSB接口，导致Type-C 识别异常。关键点是这个寄存器及相关初始化流程只在系统VBAT硬上电时候更新一次，后续不会再进行更新。 2.shipping mode的方式有问题导致的概率性PMIV0102 异常掉电，导致下一次上电瞬间检测错误。 Solution: 1. Workaround Patch机制：在开机时候立即读下2b70寄存器，如识别是uUSB，会重新做一次硬开机后再检测一次option接口，确认是否是Type-C 导入用户版本和工厂版本主线--done 2.Equator 项目取消shippingmode，按照60%电量出货来保证一年以上存储时间。（来不及验证更改稳定性，为避免奉献，不导入新的变更） 3. QC 提供NEW shipping mode entry flow ，待正确的导入MOTO 项目（需要开发 及 压测来验证有效性）---SW plan 9/23 ，压测 Plan TBD QC 新的PMIC 需要新的进入shipping mode的流程来保障不会出现该问题，包括PMIV010X, PM7550B, PMIH010X 这三个系列的PMI器件，原因是这三个系列的PMI在进入shipping mode前需要正确的下电配置后才能保证下次上电硬检测是稳健的。而旧的shipping mode流程是adsp直接写寄存器断了电池的电，无法保障PMIC正确完成下电。 NEW shipping mode entry flow 是将配置标志位给到PMK器件，然后由PMK来负责执行所有PMIC的下电流程完成然后再发起断开Qbat 的操作来断电池的电。（特别说明:SM7635/SM6650/QCM6690, SM7550, SM8635 这些平台的SW架构不支持新的shipping mode方案，只能走Workaround方案） | link | 文亭 |  |  |  | #N/A
2025-09-08 | B.PVT | 1.Platform | 5.4 ALT | S1 | Open | [s1]Issue ： M21 Shock Method 516.8 Procedure IV WH196390 D1 NEQR480147 Unable to read SIM Card:D1(26,Bottom right Back Corner)- TA-LotX Tumbler Test WH196385 D2 NEQR480203 Unable to read SIM Card：D2(300) | link | 李果 |  |  |  | #N/A
2025-08-11 | 7.DVT2 | 5.Camera | 4.Build | S3 | Monitor | [s1]Issue ：Equator Rear main camera OTP Validation Test，EEPROM error FR 0.96% 8/900 Clue: 1. DVT2 2供首次出现EEPROM I2C读取error log, 实测不良波形，确认是EEPROM无响应地址。 2. 测量读EEPROM之前的波形，开机时camera i2C平台内部上拉，硬件上在I2C上做了外部上拉，会往VIO上漏电 Root casue: I2C平台内部上拉2.2K, 和外部上拉1.5K（1M clk）互相漏电，这个漏电压会影响兼容性差的eeprom 内部逻辑异常 Solution： 软件去掉内部上拉2.2K，外部上拉改为1K (来保证I2C 在1MHz clk 情况下的信号质量） LL: 改进EEPROM测试方法，开机测量，并关注EEPROM读取之前的供电电压 开机阶段测量camera时序 | link | 芳梅 |  |  |  | #N/A
2025-08-07 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Monitor | issue: equator 地磁精度受接地影响很大，需要调整螺丝的锁付力矩 Equator项目目前地磁在高功率充电下，地磁的角度偏转会比较不稳定。 分析下来，和主板的接地情况关系比较大。 下图标记的③的位置位于充电IC边上，充电时，它会从接地良好的最短路径回流，也就是②和①通过中框回流。 因为螺丝锁的情况及主板的接地差异，导致从②和①处回流的电流值有差异，从而影响到地磁的性能。 我们建议加强如下③的接地，减弱①和②的接地，从而减小地磁在高压充电下收到影响。 也就是在可接受范围内，尽量增加③的锁付力矩，减小①和②锁付力矩。 明天如果有组装，帮忙直接调整一下力矩。 |  | 小熊 |  |  |  | #N/A
2025-08-07 | 7.DVT2 | 7.Sensor | 4.Build | S2 | Monitor | 目前大致情况为： 1. 昨天又找了一台CT超10000的切片分析，看各部分高度是否符合设计 2.周二ME分析了3台13000的机器，都只拆掉了主板，重新按压PUD板的中部，数据就能到5000（这个怀疑是中框上的泡棉是否贴合有问题） 3.再之前，上周ME拆除过10000+机器的屏幕，然后重新装贴中框泡棉，也没有保压，屏幕掩在中框上，CT就正常了。从这点ME认为泡棉问题也不大。最初的100多PCS机器，泡棉是手工装贴，没有治具。可能影响精度。当初有泡棉贴歪（非治具贴）的，外边缘破损（ME认为是某道工序造成，但是排查没有找到具体工序）的。 4. FAE今天会到现场协助分析，看下有没有进展。晚点或者明天更新。 目前，P SENSOR的CT还是高（设定limit 8000，超门限的有约6.5%），并且ME没有找到清晰的调整方向。 今天Vendor那边的FAE会过去武汉现场看一下情况，明天我再和你更新一下情况。 | [5 empty] | #N/A
2025-08-07 | 7.DVT2 | 2.Power | 5.4 ALT | S2 | Monitor | Issue：ISSUE: Back pressure automatic shutdown/Unexpected auto power off:D3(NEQE220145)(250N/300N)21:00pm 8/5/2025 D4(NEQE220240)(300)，https://idart.mot.com/browse/IKSWW-30027 Clue：1. 机器带回无法复现问题， 等待软件log分析 2. 单板实验结果待测？ 屏蔽盖内绝缘纸被顶破 | link | 敏敏 |  |  |  | #N/A
2025-08-04 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Monitor | Issue：UCT站点的 OTG测试10%左右不良 （包括后续 模仿数字耳机测试同步也大概率会fail，都是走Host USB 通道） Clue：1.“故障机器”用手工U盘测试，没有问题。测试眼图也没有问题。说明手机本身没有用户使用端的问题。 2. 只有UCT站点有问题，包括USB也有问题。其他站点USB没有问题，推测UCT这个站点环境USB需要比较苛刻的参数。 3. 调整了 Option 8 参数 （host mode 的USB 电平降到最低），故障机可以pass 了。 但是最终DVT2正产末期，还是拦截到2台fail 4.最后这两台fail的机器，手工测试OTG 还是pass。盲调9,10,11 三组参数，还是不能pass 5.SM8750 （Orion 项目）需要类似问题，没有解决。取消UCT站点的OTG测试项，用数字耳机测试项来cover 硬件通道正确性。 rootcause： UCT站点（包括夹具，cable ，U盘）---整机（主板 -主FPC-小板 – USB软参数 ） 合起来的匹配兼容性问题 solution ： 1. IKTM-13189 Equator PAT 增加 OTG 测试 和 数字耳机测试 ，PVT导入， monitor PVT情况（同时先保留UCT测试，确认fail的机器继续往下go ， 看PAT是否可以pass。） 2. 协调一套UCT设备，提供给QC 寻求帮助，尝试寻找可能的优化方案。 毕竟UCT OTG 测试失败是从 SM8750 （Orion 项目）和7750（equator项目） 两个平台的项目第一次遇到。 其他信息：Orion 项目 处理方式是 去除UCT的OTG测试项。 用PAT 和UCT的数字耳机测试项来测试相关通道。（USB host 功能）。 | link | 文亭 |  | IKTM-13189 |  | #N/A
2025-08-04 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Closed | Issue：UCT站点，USB 不识别率很高 Clue： DVT2 新增加UCT站点的USB连接需求。 拦截的机器再其他原有的站点，目前测试判断没有识别不到的问题。 PC to 夹具的线换成放大线，暂时不能解决 其他idea：是否可以再调整下USB参数？ --RD comment 不建议，其他站点DVT1到DVT2 调整了参数好不容易稳定下来。 现在新增加UCT 站点的需求进来，没法针对性调整，一旦调整，所有站点要重新确认，不排除变差的可能性。 建议维持现状，如果其他站点能继续维持正常 solution： 更改会DVT1的方案，用无线WIFI 链接方案，做UCT站点测试 |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-07-28 | 5.DVT1 | 10.USB-C | 5.4 ALT | S3 | Open | Issue：NEQE140204 USB接口异常， 现象： 正反面插入经常不识别充电，偶尔识别出来有5V充电，但是马上断开。请结构和熊雄接下来看下一步怎么分析，谢谢！ 分析步骤：1. 拆开后壳，不拆usb小板，外面接到另一个ok的usb小板，充电功能，识别口都正常。判断问题在usb小板上 2．拆除usb小板，测量typec口舌片上信号到小板pin不通 3．显微镜下观察到typec口左侧小耳朵和信号pin脱焊 4．按压typec 铁壳时，焊接pin能看到脱焊 Rootcause： typec口左侧小耳朵和信号pin脱焊，导致信号不通。 下一步：交于结构和KP分析. | [5 empty] | #N/A
2025-07-28 | 5.DVT1 | 3.Charging | 5.3 EE DVT | S2 | Open | Issue: 泡水测试后到下一步复用机器实验前，发现显示充电图标 但是充不进去电。Mxc04 WH193926 2nd source lily pad， D1 initial Clue：1.关机充电到开界面前可以充电，而且当系统起来进行判断后就不让充电。 无线充电也类似结果。电池电压，温度，PD协议功率识别，都是正确的。 以上信息推测不是CC1 或者CC2 的问题 2. CID pin 上有0.3V电压，所以看起来也不是CID pin电路问题。fastboot boot mode 可以充电一小段时间（可以用来做临时补电然后抓log用）。 3.Log 给SW分析：给的判断是PMIV0102 的充电状态不变，aicl是0 （意思是否指向说就是PMIV 出现异常了？），充电状态一直是not charging--继续跟踪 4. EXP：长按开机键1分钟来确认是否可以复原。结果是依然fail。（ 9秒和15秒的时候都各自重启一次，之后就开机了） 下一步：信息share给QC，看下是否有什么分析建议。等待回应 这台机器 ：确认 主FPC连接器上有一些导电材料导致 USB NTC 信号对地短路，进而导致USB NTC 温度过高导致保护了不让充电。 进一步分析： 外观看：主FPC连接器端有个 导电材料 ？ 不像是盐水导致，更像是一种生产材料，非外物进入机器。颜色和焊锡很像，银灰色，但又不是实的而是像棉花絮的，碰触就会变形的导电体（有点像导电泡棉的细碎？ ） 其他的：SUB端的一个pin腐蚀了（但是这是个GND pin，不是导致故障的直接原因）。 板子上我没见过这种材料，建议大家及产线进行下一步确认这是什么，以及怎么进入主FPC连接器的。 Rootcause： 确认 主FPC连接器上有一些导电材料导致 USB NTC 信号对地短路，进而导致USB NTC 温度过高导致保护了不让充电。 板子上我没见过这种材料，建议大家及产线进行下一步确认这是什么，以及怎么进入主FPC连接器的。 Solution：TBD |  | 文亭 |  | RPA分析 |  | #N/A
2025-07-23 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Monitor | Issue; 滚筒180后，上SMART PA无声 分析：从寄存器看，CLK信号未送到SMART PA,重新加热SMART PA 恢复正常 RootCase: SMART PA右下角虚焊 Solution： 结构反馈非大应力区，继续监控 | link | 院长 |  |  |  | #N/A
2025-07-23 | 5.DVT1 | 6.Display/Touch | 5.3 EE DVT | S1 | Open | Issue; no main display:D4(26)-按压连接器可显示，松开不显示。共三台， 分析：屏幕连接器大电流PIN Solder脱焊，测量导通性异常，按压可连通，显微镜下观察到缝隙，分析结果一样 RootCase: 焊盘受外力导致的断开，断开位置结合力不足，焊盘开窗0.45, 实际溢胶后，有效焊接面积0.3mm Solution： 2供Kingwong内部修改焊盘加大覆盖膜开窗，焊盘原设计0.45mm加大到0.6mm,去除完溢胶，有效焊接面积0.45mm, 同一供DVT1数据。 2供封样时间需要等到二供FPC DVT2实验全部合格后，才能启动封样工作，需要项目同采购提前沟通。 | link |  |  | RPA分析 |  | #N/A
2025-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S1 | Open | Issue: 打完ESD TIS/TRP，D1/D2/D3/D5机器，B20/28有问题,B42一台变差问题，ANT0/ANT1-Fail Clue：返回D1机器，分析 1：ANT7: D1异常Band42机器复测TIS，确认ANT7无异常； 2：ANT0: D1机器ANT复测，发现ANT0异常，无源下观察波形和之前摸底出现Tuner损坏的故障现象一致，cmd切Tuner波形也没有变化，判定是ANT0的Tuner器件损坏； 3：ANT1: D1机器ANT1, 更换损坏的电容后，天线测试TIS依然异常，RF测试传导OK。判定是ANT1的Tuner损坏, 今天天线测试发现SW5通路损坏，判断是从主通路进入； | link | 廖哲霖 |  |  |  | #N/A
2025-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S1 | Open | Issue: DVT1B ESD 报一台机器15kV后capsensor全部无功能，ANT很多通道Fail； Clue: 1. CapSensor I2C地址变了，12->13； 2. 一供机器没有此问题，SAR芯片/TVS是二供； 3. 拆机分析发现电容被击穿，CS0通道直接通过电感下地，影响I2C地址，SAR芯片和通路都没有损坏 RootCase: 天线馈点串联隔离电容被击穿 Solution: 1. 25V耐压电容->更换为50V -> 周一天线确认 2. TVS确认，是否是二供影响(一供没有此问题，且走线先经过TVS) | link | 廖哲霖 | 小熊 |  |  | #N/A
2025-07-17 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S2 | Closed | issue:Initial check:Headset no function/OTG no function/USB charging is normal, but fail to connect computer:D4-D4知勇带回厦门分析 Clue: 快充测试ok, 连接电脑不识别口。判断D+,D-有异常。 Rootcause：D4 这台是共模滤波器 FL500 掉件 查看FAEDVT1不良板分析，至少发现7PCS FL500掉件 ME 主导和产线装配沟通，修改装配手法和增加治具。 DVT2 导入 | Link | 文亭 |  | RPA 分析链接 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-07-17 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S3 | Closed | issue：MXC06 WH193914 D1 NEQE1B0126 USB one side no function:D1(225)- clue ：1.CC1 线路 open ，断路点在PMIC 屏蔽盖下边沿底下 layer11，具体看链接截图。 （CC线已经走0.2mm宽度了，但还是断了） 2.WIFI_THERM 这个在CC1 边上的线也断了。 再更边的CID_DET没断（断了就直接没法充电了），另外一边的CC2 也没断，所以可以单面充电。 3. 一供机器没有问题，二供还有另外3台类似故障机器，等待返回后确认。 第二台是：WH193919 D1 NEQE1B0131 USB function intermittent:D1(26,Bottom right Back ) ，现象类似 Rootcause：结构应力太大，导致PMIC 屏蔽盖脱开，并拉动L11 的CC线。（ 推测：二供PCB的抗拉拔力可能比较弱导致出现多台断线。 ） solution： PMIC右下角L11走线都改到L10 & L9 ，DVT2 二供PCB导入修改 |  | 文亭 | 芳梅 | RPA 分析链接 |  | #N/A
2025-07-14 | 4.EVT | 4.Audio | 4.Build | S3 | Monitor | Issue：MIC2气密性问题 Rootcause: MIC 焊盘镀金，需要更换为OSP Solution: 更改主板和小板MIC焊盘为OSP，DVT2更新器件库 LL:MIC器件库修改为OSP，库里已经把项目中不用的MIC器件库删了，目前器件库里存在的MIC器件库全部为新的OSP器件库。 | link | 院长 | 川叔 |  |  | #N/A
2025-07-13 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Monitor | Issue：TCC报一台机器VBAT端EOS-150V Fail，另一台，机器复测后Pass； Clue：EOS走线Review，未发现问题； RootCase: 机器正在寄回，收到后分析 —— D4样机收到后，测试正反OTG都OK，故障无法复现，继续Monitor Solution: 1.DVT2主板，VBAT端浪涌管增加下地打孔；2.继续Monitor 3. 寻找更好的浪涌管，型号: ESD56301D04-2_TR（晓云推荐）—— Prado上有验证过 | link | 廖哲霖 | 文亭 |  |  | #N/A
2025-07-11 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：死电池激活场景 ，在电池保护电路还没完全激活开之前，就开始转到5V1.5A快充，电流超过电池的期望3V以下上限电流0.1C 。 可能有安全风险。 rootcause：3.1V 是5V600mA 切换到5V1.5A设置点。 而死电池内部保护后，mos的前向二极管有0.5~0.6V。 补充说明：以前项目没有关注这个转换瞬间是否会有超过的电流，因为这个测试难准确监控到电流，log 也无法记录。 需要再排查下，以及风险如何。 solution：Option1 ：调高转换的电压点（负面作用是：低电量电池 充到能开机的时间会拉长，具体值需要 KP 主导 take CR） option2：电池内部是否可以优化？（ 充电时候默认就直接激活电池？ 需要KP 主导评估，项目上基本没机会，只能长期看） | link | 文亭 |  | IKSWW-19238 |  | #N/A
2025-07-10 | 5.DVT1 | 7.Sensor | 4.Build | S2 | Open | Issue： CT偏高，和Prado相同的参数，当前CT的max接近12000 Clue： 1.交换前壳组件，不良跟随前壳组件。 2. ME对前壳组件灌胶切片，发现泡棉高度稍微高出SPEC。 RootCase: 前壳组件隔离不良 solution：ME增加泡面厚度，新泡棉机器预计07/16组装，跟踪试产数据 next: 跟踪DF数据 | link | 小熊 |  |  |  | #N/A
2025-07-10 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Open | Issue： 60W充电情况下，地磁输出的方位角度会被干扰，最大可能偏转60度。PRC版本表现很明显，EMEA相对正常 Clue： 1.地磁附近的螺丝孔，锁紧后地磁角度偏转明显，拧松后角度偏转很小。 2.DVT1(V05)版本相比EVT(V04)，ANT增加了BOT面地磁附近螺丝孔的露铜。 RootCase:充电场景下，地磁附近的地通过中框回流到GND。回流电流产生的磁场影响到地磁感应到的磁场，造成精度偏差。 solution：和ANT确认，螺丝孔露铜去掉，回到EVT状态 | link | 小熊 |  |  |  | #N/A
2025-07-08 | 5.DVT1 | 12.EMC | 5.4 ALT | S1 | Open | Issue: DVT1 ESD三台机器CapSensor后CH0无功能，重启后不恢复(硬性故障)；另外也在损坏前出现ESD时无功能，重启后恢复(软性故障); Clue: 1. 分析发现是CapSensor硬损坏ESD机器，熊姐分析发现是在主板SAR芯片附近的100R电阻被打穿，测量阻值为开路，更换后ANT0处功能恢复正常。但是USB处感应失灵，进一步测量发现小板上R806击穿，更换新小板恢复OK； 2. 和EVT对比，发现M802的下地电容被天线DNI了，导致M802处静电直接进入SAR通路，击穿100R和1K电阻； 3. 测量隔直电容，发现没有短路【EVT复测二供Recovery机制时，有一台机器在高压下也出现了隔直电容击穿短路的问题，经核查电容耐压为25V，由于只寄回一台样机，无法确认其他样机是否存在类似问题，因此也在DVT1B导入50V耐压电容】； RootCase: M802下地电容C806被DNI导致静电损失下地通路； Solution: 1. DVT1B 小板C002处手工Rework TVS, C806是否可以Rework待天线确认影响; 2. DVT1B 小板C001/C006已确认更换为50V耐压的电容； 3. 针对软性故障，一二供供应商会确认下Recovery机制，并合入(实测若C001/C806处都加上TVS，打ESD时软失效问题基本不会再出现) | link | 廖哲霖 | 小熊 |  |  | #N/A
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Monitor |  QBOOT_BLANK_FLASH_01（9008 SW下载），NTF，FR 3.07% -----SW：志龙 BB 文亭 Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 solution：DVT2 对PCB 上介于repeater 和CPU之间的USB 线路进行差分 90ohm 阻抗管控。 monitor DVT2 结果。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  |  | 2.PCB | #N/A
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Monitor | Issue FASTBOOT_FLASH_01（ SW 大包下载），NTF，FR 2.42% -----SW：志龙 Open Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 solution：1.DVT2 会特别提出对这段线进行阻抗 90ohm 中值管控。 2.调整FASTBOOT 模式底下的USB参数：Squelch Detector Threshold Adjustment. 静噪检测电压门限调到一个中间值 （112.5mv） option4 monitor DVT2 结果。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  | IKSWW-16177 | 2.PCB | #N/A
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | S2 | Monitor | Issue: EQUATOR DVT1 eBT （板级测试）概率性无法识别 端口,交换站点有时候pass ，不固定。 约7.7% NTF clue：1. APEM 一开始数据还好 0.39%，但是后面的其他3个SKU测试数据看就又不理想了 （15+9+2）/(228+95+13) = 26/336 = 7.7% 2.目前信息：这些fail的站点都是夹具上加了各种延长线和开关，非用户场景，用USB直连电脑 是没有问题。 Rootcause: 1. PCB 上介于repeater 和CPU之间的USB 线路阻抗没有设置阻抗控制线，导致阻抗控制偏差及离散。 2.测试夹具整体环境和板子USB 兼容性不好叠加让问题更加突出 Solution: 1.DVT2 会特别提出对这段线进行阻抗 90ohm 中值管控。 2.调整所有devices 模式底下的USB参数：Squelch Detector Threshold Adjustment. 静噪检测电压门限调到一个中间值 （112.5mv） option4 monitor DVT2 结果。 其他一些做过的验证：1.建议产线再尝试下加信号放大器的线，并调整下放大器的参数。（产线反馈没有明显改善，看最后的情况看哪个站点需要导入 ） 2. 尝试Option1 将眼图改为最大 ，以及option2 将眼图改为最小。实际结果都不理想，没有明显改善。不适合 3.Squelch Detector Threshold Adjustment. 静噪检测电压门限，从默认的87.5mV改为137.5mV （可配置的最大值） option3 ---结果：故障板好了，但是正常板fail了。所以 这组参数不能批量使用，再优化下参数。 lesson learn：优化checklist ，对USB阻抗review项 ，描述出各个段都需要考虑到阻抗设置。 | link | 文亭 |  | QC CR ：7969230 | 4.Parameter | #N/A
2025-07-04 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | IKSWW-16494 [Equator][Factory][CQA1][DVT1] OTG intermittent failure solution：调整OTG 断连门限到最大值，初步压测ok。IKSWW-18561 导入主线后monitor DVT2 |  | 文亭 |  |  | 4.Parameter | #N/A
2025-06-25 | 4.EVT | 10.USB-C | 4.Build | NA | Closed | Issue: EQUATOR EVT eBT 概率性无法识别 端口,交换站点有时候pass ，不固定。 约10% NTF clue：1.交叉测试夹具和USB测试板，有些变化，但是没法完全解决。EVT2 留下两个板子，一个大概率fail，一个较容易pass的做验证。--TE 2. DVT1 USB 眼图测试pass的参数 V01导入后，对保留的两个板子验证，结果没有改善 --BB&SW done。 3.顶针从细针改为粗针，没有明显改善。 （但是也作为后续主要方案，避免因为细针的干扰因素不好排查）--TE 4. 用USB线直接连接最后夹具和电脑试一下（跳过中间的一些开关测试板）是ok的。 用个人笔记本电脑直连也是ok的。--TE 检查电脑前后端口：有变化，但是无法解决问题。 5. DOE 尝试各种眼图参数，先看下是否对该结果是否有改善。--BB&SW 6. 继续尝试换各种线看下结果 --TE Rootcause: 测试夹具整体环境和板子USB 兼容性不好。（电脑端口，USB线，开关板，板夹具 等加起来的综合影响） Solution:以上确认可以导入的先导入，monitor DVT1的实际数据。 DVT1 还是fail ，重新创建一次问题 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-07-04 | 4.EVT | 12.EMC | 3.Review/Simulation | NA | Closed | Issue: 【自测Risk】使用EVT机器，摸底ANT0-Tuner ESD过程中，发现有概率损坏Tuner； Clue: 1. 之前测试EVT实验室回来的一供D1/D5，二供D4，三台机器，天线没有发现问题； 2. 本周天线那里软件tunner-code ready，找邓林协调了一台没打过ESD的机器进行验证，前测ANT0无源，采用天线常用的B28 B5 B8三个频段的code组合，在ANT0区域打了 ±8kV，±15kV，±17kV三组ESD结果，天线复测无源结果Fail(Tuner切换通路失效)； 3. 走线上由于空间限制，ANT0部分TVS是预留在与弹片同面，而Tuner的天线路径线是在TVS路径上穿孔到背面，经过下地电感后进入Tunner。因为Tunner到弹片的位置很近，下地电感和背面的TVS可能保护效果比较有限，存在Risk； Rootcase：空间限制导致走线不佳，前期布局没有预留第二颗TVS位置； Solution: 1. 关注TCC-DVT实验结果，看是否也会出现Tunner损坏的情况； 2. 尝试直接在Tuner面手工Rework再加一颗TVS，然后加上接地导电泡棉，看能否保护住Tunner； 3. DVT2改板，和天线沟通，天线尝试取消Tunner前端的下地电感，让位给TVS，周末Ruiming会调试，下周一左右会有结果；否则就是走外加TVS改版方案；—— Ruiming已确认无法删除下地电感，走外加TVS路线； 4. 让结构DVT1B先导入接地泡棉，增加小板的接地； | link | 廖哲霖 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-07-02 | 4.EVT | 9.Memory | 5.2 BB Test | NA | Closed | Issue：12GB DDR can not run up to 4.2Ghz，only3.2G Clue：8GB OK. Rootcause: 高通在代码中限制12G频率跑到3.2G Solution: 高通提供patch，8-14号软件包含patch，确认已经跑到4.2G。SI启动测试。 | link | 嘉琨 |  |  |  | #N/A
2025-06-18 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Issue：EVT USB eye test fail Solution：import 0xfd57-0x5-0xfd51-0xa ,test ok . import CR :IKSWW-12700 。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-16 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Issue：（定义为无线充电问题4） EVT2 板级测试 TURBO_CHARGE_OVERALL_STATUS 不良 5/58 Clue: 1.无线充电IC读到的电压电流值异常大（10+A ，70V ），这明显是异常ADC值。（然后导入其他后续的逻辑错误） 2. 5PCS 不良。 有1pcs retry 后pass。 有3pcs 更换无线充IC SC9624后OK，还有1pcs 重复写入FW后pass Rootcase： FW 升级过程异常打断（AP申请dump 寄存器）导致升级fail，并且没有再次触发升级的机制。 Solution： SW 更改FW 升级过程，确保升级稳定性。DVT1 验证 | CR ：IKSWW-10183 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-11 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Monitor | Issue: TCC实验室二供EVT1报CAP-Sensor ±8kV下无功能，重启后恢复；D2 Cap sensor no function(CH0,CH4), recovery after reboot. Clue: 1. 观察到D2机器Intital测试中，CapSenor也有无功能的问题Cap sensor no function(CH1,CH2,CH3)； 2. EVT1二供贴二供厂家的SAR IC，邮件厂家沟通提示公司的驱动可能没有合入软复位模块，已经通知厂家联系对应负责软件同事; 3. 周一收到样机，检测CH1/CH2/CH3无功能，确认是校准参数问题；6/17日刷入校准参数后，ESD测试后，SAR-Sensor参数丢失，软件确认软复位机制还没有合入。此外出现了软失效后第一次开机SAR芯片识别不到的问题，第二次开机OK，已经提交CR给软件分析； Rootcause: 目前推测软件驱动未合入软复位机制可能性较大，另外前测capsensor也有部分问题，推测软件驱动还不完善，进一步monitor； Solution: 1. 检查二供sensor的recover机制；—— 确认6/23日可以完成，DVT前可以导入，已验证； 2. 加强CH0-capsensor部分tvs接地; —— DVT已导入； |  | 廖哲霖 | 小熊 |  |  | #N/A
2025-06-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue: TCC实验室二供EVT1报PUD低压下出现无功能，重启后恢复；D4 后测发现 After +8KV air discharge at post check, Proximity sensor no function, recovery after reboot.(2025/6/9,14:00) Clue: 1. 实验室软件版本：user 272版本； 2. 导出LOG结构分析，对应时间点bug report显示功能是正常的，有接近远离状态变化，但是这个时间点没看到打开cqa测试的操作； 3. 使用D2机器，在厦门实验室打ESD ±18kV，200次，无复现PUD无功能故障； Rootcause: 软件定位以及实验，推测是TCC误判； Solution：1. 请邓林安排复测，判断问题； —— 机器复用其他测试，实验室暂无资源安排复测，同时观察到该问题不仅在ESD出现，在微跌等其他场景也有出现，存在共性，目前没有稳定软件版本；使用155稳定软件版本，厦门复测结果OK； |  | 廖哲霖 | 小熊 |  |  | #N/A
2025-06-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue: TCC实验室二供EVT1再次报报两台机器低电压下ESD重启/关机：After -8KV air discharge at zone9 (Aging 10 ), Unexpected auto power off,recovered after reboot (2025/6/8 23:09). After -8KV air discharge at zone4(Aging 10), Unexpected auto power cycle , recovery after power on.(2025/6/9,14:54)； Clue: 详细分析过程见后面文档连接 - 更新： 1. 6/17日，软件确认D4机器两次黑屏都是进入dump，并且和modem crash有关，拉modem同事确认，modem crash在TCC所用软件版本中中是已知问题，根源是ipa和modem通信出问题报错，这个问题在新版本中已经fix； 2. 6/18日，再次在D4上出现一次黑屏故障，但是状态是在 非ESD&充电，导出对应时间log给软件同事分析，确认还是modem crash 导致； 3. 6/18日，收到的D1/D3机器，使用modem同事给的软件版本测试ESD ESD +15kV 200次，未出现黑屏； 4. 6/19日，RF/ANT确认，打完ESD后一供D5机器TIS/TRP和正常机器比较无下降；二供D2/D4机器，因为ANT软件还未调通，暗室容易出现掉线，RF非信令测试传导无异常，ANT无源测试驻波效率均无异常。 5. 手动通过adb指令触发ram dump，观察到现象和poweroff类似，黑屏40-50秒后才会进入重启状态； RootCause：根据实验结果以及软件分析，目前判断结论是软件modem不稳定导致系统进入dump状态，进而导致黑屏(实际上没有poweroff)； Solution: 优先考虑改版，预留防护方案： 1. 基带：影响系统重启信号：SM_RESET有预留电阻/电容(10nF DNI),若后期出问题可以贴上；PS_Hold信号CPU端已增加一个0R电阻；PWR_KEY有预留TVS位置; FAULT_N并联器件过多，走线多集中在板中央，暂无方案预留； —— 已经导入 2. 结构：3D VC，结构增加镭雕，加强整片VC在受到ESD冲击时放电通路；—— 已经导入； 3. 后续等待软件版本稳定后，若TCC有资源，提供无panic的软件版本供结构复测 ——— 目前都暂无稳定的版本，最新的稳定版本要月底才能出来，所以等机器收到后先尝试自己复测； 4. D1/D3机器，刷软件给的modem fix后的新版本，提交TCC复测； [7/10] DVT1 一供6台ESD实验未发现问题。 | link | 廖哲霖 |  |  |  | #N/A
2025-06-09 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | Issue：CQA 报一台黑屏，U1000 Disp_rst pin损坏，更换cpu后正常 Clue：总共发现了2台，1台是产线在烧录后发现的，他们再次做离线烧录现象就消失了，还有一台就是机器到了CQA才发现的，ME准备做离线烧录看能不能好，但是离线烧录失败，拆机验证不良随主板，，才把板子送到FAE分析的 rootcause： 黑屏烧芯片的问题，确认到因为屏FPC难扣合，EVT应结构研发需求，都是使用压棒按压FPC，导致FPC有露铜死折风险，露铜区域容易与前壳接触导致短路，有短路烧伤主板芯片风险 Solution： 跟结构的研发核对的是，DVT前壳会挖槽0.8MM避让 DVT也会验证增加FPC预弯折 [7/10] DVT1 400台 CQA 未发现问题。 |  | 廖哲霖 |  |  |  | #N/A
2025-06-06 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | Issue： WH192420 C1 NEQE080018 Rear flash light no function-间歇性无作用 Clue：实测无作用 RootCase：FPC接触pinw位置接触不良，原因是背胶太小，拆装后无粘性 Solution: 结构增加背胶 |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-06 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | Issue：TCC NEQE080036 SIM 无作用，无线充无作用，cap sensor ch3无读 clue：可以复现 RootCase：无QCN，不是SIM卡，Capsensor CH3参数问题， 无线无作用跟踪到无线充的问题1 Solution: 机器给TCC需要校准，不能调测。cap 参数软件去调试。无线充问题1，刷了修复版本后ok |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue: MIL drop 1.5 WH192393 D1 NEQE080016 Volume(up) button no function:D1(final) Solution:复测结果不明，升级软件后，功能测试ok |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue:MIL drop 1.5 WH192393D5 NEQE080025 Self defined sidekey no function:D5(final) RootCase：早期版本 AIkey 的配置有些问题（两个模块一起配置，导致配置错误） Solution:刷最新版本后OK |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-06 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | issue：WH192390 D1 故障机， NEQE080016 AI key 无作用（ Self defined sidekey no function:D5(final)） Clue：拆机测量发现 AI key 弹片只有1.3V。这个和之前发现的问题类似。 机器版本可能比较旧了 。 RootCase：早期版本 AIkey 的配置有些问题（两个模块一起配置，导致配置错误） Solution:SW修改配置。 刷解决AIKEY的临时版本后，这个机器AI Key 功能ok了，电平也正常了=1.8V |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-06 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | Issue：TCC实验室EVT1一供ESD报D1机器，在CQA前摄开启状态&Charging下，8kV下出现自动关机问题； After +8KV air discharge at zone1(Aging 10),Unexpected auto power off(2025/6/2 10:49). Clue： - 尝试复现：D1/D5两台机器在 zone1 区域厦门打ESD ±10kV/±18kV各100次，未复现；加压对D1问题机zone1区域ESD打±18kV各500次，未复现； - 复查ME设计：前摄被屏幕模组覆盖，模组背面有完整接地铜箔，Rec开缝紧靠金属边框(与中框一体)，整机实验发现zone1静电会优先被边框吸引释放，未发现明显问题； - 复查BB设计：检查AP开关机关键信号(SM_PS_HOLD/FAULT_N/KPD_PWE_N), 均有屏蔽或远离前摄位置，未发现明显问题； - 拆机实验：使用替代机器拆开后壳对Camera模组和REC风险点放电(±8kV)100次，未复现关机； - 故障机Log数据和故障时刻已提CR给软件分析，软件分析结果如下： 软件Log初步分析，判断自动关机时机器应该是在factory mode下打ESD，机器触发了VBUS OVP关机，实验数据不具备参考价值； 1. 标准ESD测试是需要在normal mode下打，该模式下OVP不会直接切断VBUS；在factory mode下电池功能失能，VBUS切断后就会关机； 2. 本批测试错误在factory mode下打ESD的原因分析：第一批机器软件版本不稳定，normal mode下无法打开拨号盘进入CQA，所以TCC采用的替代方案是实验员在打ESD前，首先切换到factory mode初测功能，再切换回normal mode打ESD，最后再切换回factory mode检测功能，手工反复切换，存在误操作风险； 3. 复现：手动切换到factory mode模式，在厦门插充电器在zone1打ESD +18kV ESD，成功复现自动关机故障； 分析log可以看到自动关机前，机器触发了VBUS OVP保护后导致VBUS切断，触发factory kill功能导致自动关机； Rootcase：判断自动关机时机器是在factory mode下打ESD，机器触发了VBUS OVP关机，实验数据不具备参考价值； Solution: - Monitor第二批ESD结果(最快周二晚上打完，跟踪结果) 周二上午和TCC实验员确认，第二批ESD用的软件版本可以正常进入拨号盘，截至周二上午，暂时没反馈自动关机的问题； - 后续Align TCC ESD测试时机器不能处于factory mode下； [7/10] DVT1 一供6台ESD实验未发现问题。 | link | 廖哲霖 |  |  |  | #N/A
2025-06-04 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Monitor | Issue：Rear main camera 64X RCN超标，且有竖条纹 Clue: 1.EVB2 PCBA 测试时 RCN pass,EVT整机fail， EVB2 板子+0603版本 2次测试1次fail 2. 更改sensor setting ， 更换为orion 模组，均无效 3. 使用外供替换更换AVDD，有效且稳定 4. 更改AVDD 上OR电阻为磁珠，输出电容4.7uf 改为10uf， 不稳定，单次有效，多次失效 5. 更改AVDD上 AGND到DGND，无效 6. 更改AVDD LDO输入端为外供电压2.33V，稳定且有效 7. 更改AVDD LDO 输入buck电压2.33 V 1uf 为10uf, 不稳定 8. 翻起电感L4131, 稳定且有效 Root casue: Buck 电源FB 走线在L2层 电感下方，收到干扰，具体可见buck输出频谱波形 Buck电源输出电容值不足（参考设计20uf, 因空间问题只保留了10uf） Solution： 修改buck FB 走线线宽并且避开电感 buck输出端增加10uf电容，因屏蔽盖无位置放置，所以更换AVDD LDO输入电容1uf 为2*4.7uf AVDD LDO输入预留0R电阻，可更换为磁珠，做RC滤波 DVT1复测结果：RCN 30， fail，图像确认有条纹 Clue: 1. DVT1主板干扰频率 2. 更换R4124 为2R， p Root casue: ongoing | link | 芳梅 | 敏敏 |  |  | #N/A
2025-06-05 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Issue：（定义为无线充电问题3）有些机器无线充电有图标也有1.5A左右电流进电池，但是CQA测试，无法返回电压和电流值。 Clue: SW主导分析 Rootcase： Solution： |  | 文亭 |  | IKSWW-8971 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-05 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：（定义为无线充电问题2）有些机器无线充电有图标，但是没有电流进入电池。BB 提交CR ：IKSWW-8419 Clue： 0.SW log 的分析是：PMIV0102 的charge state一直没有变，这个是直接读的寄存器。导致走不了充电的流程。 by Xuyf4 1.目前反馈问题的都是整机，而且几乎所有有充电图标的机器都报这个问题，（无充电图标的是问题1） ，不良率接近100% 2. 板子飞线线圈+假电池+EVB屏幕+EVB 主FPC。 3个板子都是ok的。 3. 实验1： 故障机1# ：拆后壳后，故障依旧；拆开小后盖再扣合上，故障依旧；拆开小后盖并修改线圈将线圈引导到手机外部，测试故障依旧。---推测不是TX干扰主板导致的，至少去掉干扰不能恢复。 实验2 ：最后，主板拆出来，线圈直接飞线焊接到弹片上，用EVB的Display +假电池，测试发现问题2 恢复ok了；拆掉飞线，将主板装回机壳中（弹片上有些焊锡），还是ok的。故障机1# 的故障不复现了 推测恢复机制：弹片相关 或者 供电相关 变化会恢复。 实验3：故障机2# ，拆开后盖，扣掉电池连接器，等待5分钟后，再扣合链接器，发现故障恢复了。 结论：故障时候，是PMIV 0102内部哪里异常了，导致只有Vbus有电的时候charge state一直没有变， 要彻底断电后就会恢复正常。 4. 分析Action：1.故障机的PMIV0102 寄存器dump出来给高通分析，看下 寄存器有哪里异常发现。 2.恢复的机器，尝试各种操作尝试复现故障来找到复现路径，尝试找到触发PMIV0102 异常的更进一步的路径。 Root cause : 1.wireless charging process can no go due to PMIV0102 charge state can not change in wireless charging. why 2.PMIV0102 charge state can not change due to PMIV0102 trig OVP （checked by QC by 6/9 ），why 3.插入快充后拔出快充，OVP停留在快充的设定值 10.8V 。 无线充输出是12V ，触发OVP solution：拔出快充的时候，重新设定OVP 为13.2V。临时版本验证ok。修改已导入主线 6/12 。 | link | 文亭 |  | IKSWW-8419 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-04 | 4.EVT | 3.Charging | 4.Build | S2 | Closed | Issue：（定义为无线充电问题1）有些机器无线充电没反应。BB首批5台有2台无反应。 TCC 10台有3台 （A3,A5,A6）， SME 都有发现故障机。不完全统计大概30%左右不良 Clue: 板级测试，无线充IC 读ID都是pass的。 1台故障机：确认ID是对的，FW是对的。故障出现时，TX上面没有指示灯亮（也就是无线枚举都没有成功） 1台TCC故障机D2： 是否装配问题？实验：线圈焊线到主板弹片上测试，故障依旧，推测非装配问题。（实验室的D2机器） SW 拿到一台故障机，实验：更新FW将inhibit 禁用，看下是否inhibit 异常高了导致。 结果：NG 。所以和inhibit 应该没有关系。 是其他问题 SME 拿到2台机器有1台故障机，交给 Vendor 同步分析。 Rootcase： 分析结果1.目前南芯手上的问题1机器确认trim 被修改了（存储着校准参数等信息），导致ADC等数据错乱。导致的无线充fail没有图标。 （这个可以通过SW修复方式修复回来） 2. BB手上的机器升级一次FW后无法再升级。推测I2C地址变动了。这也是trim被改动的一种结果。（不可修复） 问题严重度 ：高 。 solution：1.出临时包，加上修复trim 被异常改写的情况，这个临时小包和大包都准备一下，但是不进入主线（避免将ok的机器也变成NG的风险），仅用来修复故障机。 ---实际验证，发现有些 2.同步准备去掉所有trim相关操作的代码，提交到主线。避免更多的机器出现这种情况（特别是担心出现不可逆的修改，比如SC9624的I2C地址被修改了，就再也修复不回来了）。 6/6 提交修改 https://gerrit.mot.com/#/c/3418718/ 。monitor EVT2 生产情况 （已发邮件和CQA 强调判定方法，待生产反馈，预估13号出结果） EVT2 只测试6台，都是pass 。目前没有更多机器可以测试。先close 了。 |  | 文亭 |  | IKSWW-9596 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-06-03 | 4.EVT | 6.Display/Touch | 5.4 ALT | S1 | Closed | Issue：ALT滚筒测试，两台机器出现无显示的问题 概率2/6。 Clue: 替换SIM-FPC后，两台机器显示OK；测试走线发现ELVSS等Bottom面走线不通，用手轻微掰动Display连接器部分FPC会恢复导通； Rootcase：万用表显微镜下点阻抗，定位最终断裂区在 屏幕B2B连接器左侧焊盘 - FPC出线 这一段，推测折弯区距离焊盘过近，以及屏幕连接器与上支架间隙过小，导致滚筒实验时屏幕连接器不断被掰动，导致连接器左侧焊盘与走线断裂； Solution： 1. 结构分析后，改动钢片外形，B2B位置钢片外伸，SIM卡槽部分钢片内缩； 2. 第二条故障FPC周末寄出给PBH，等待工厂double check下问题和建议； [7/10] DVT1 一供10台滚筒实验未发现问题。 | link | 廖哲霖 | 芳梅 |  |  | #N/A
2025-05-31 | 4.EVT | 1.Platform | 4.Build | S3 | Closed | Issue：首版验证，AI key无测试界面，测量AI key的电平1.3V Clue :bringup 时ok得。 rootcause：SW 其他模块配置改到这个GPIO得配置了，导致配置出问题 solution ：SW 清理并修改配置部分，临时版本确认ok，CQA有AI key得测试界面 也确认测试ok 。 SW IKSWW-8434 导入改进措施 |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-05-31 | 4.EVT | 11.Thermal | 4.Build | S3 | Closed | Issue： 工厂BT反馈CHARGER_THERM_READING读值错误和BATT_CHARGER_THERMISTOR_VERIFY_STAT数值异常 （读值接近于0度，超出SPEC） Clue : 1.这个NTC 接到PMIV0102 得SMB_TEMP 端口上 （不知道QC SW是否有限制，QC 原理图review没提有问题） 2.反查EVB bringup时候就是这样的读值，只是当时没有识别出来是一个异常 rootcause： TBD 1. SW CR 07888869继续跟踪下是否有机会通过配置来解决。 2. HW CR 07893610 solution ：SW proposal 0 继续debug 看是否能解决 如果SW上明确无法解决得话。---06/03 SW CR 07888869 答复说 不支持这样更改。请换口来实现。 HW Proposal 1 再找一个 ADC 口给这个NTC用。 -----06/03 QC HW 建议 ：PMIV0102 GPIO_06 / GPIO_02 ,(02 目前预留JP 关闭Vbus 用）， 06/04先用GPIO_02 飞线 tuning，结果目前温度不准，测量电平看起来像是内部上拉电阻不对导致分压不对，还在请QC 协助分析 HW Proposal 2 如果proposal 1搞不定，就将不常用得一个NTC 挪过来用给这个用 6/9 update ：detj:DVT1 阶段计划用【SCHG NTC】来取代【MCHG NTC】，同步用【WIFI NTC】来监控【SCHG】和【WIFI】 |  | 德太加 | 文亭 | CR 07893610 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-05-30 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | RISK：特殊版本，关闭SC8541 ，只留PMIV0102 工作。用假电池测试，概率性发现Ibus 不工作 （大概30% ，不稳定） Clue:1.假电池内阻大可能有影响 。 实验1：用电池再试一下是否有概率复现。结果依旧能复现。 Rootcause：启动电压太高导致的概率性fail solution：修改启动电压低一些后，验证ok 6/16 的临时版本。 SW 跟踪导入主线 |  | 文亭 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | RISK： 当前log 看快充68W，两个CP的电流 差异值比较大。 充电性能RISK Clue： 1.目前使用的是临时电池+转接FPC/焊线来提前bringup ，仅能作为参考（内阻不对，影响左右通道的电流分配） 2.目前值是通过log 读取，准确度有问题 3. EVB PCB 仿真看 ，Rbat1 比 Rbat2 小了0.47mR 。和实际测试结果影响看起来是反向的。 （推测偏差结果可能是电池 或者 CP 的特性引起的） 4. 目前的SW版本+houston电池+转接FPC+串联电流检测电阻 测试出来， Ibat 最多差~1A （Ibat1 =5.4A VS Ibat2 =6.4A） 5.这个属性要以实际电池作为最终判定，EVB数据仅供参考（因为和电池的内阻属性相关性也很大） KP给的时间是5/28 equator 电池出来，第一时间寄送给南京和厦门进行确认。 Rootcause : EVB仿真点位有些偏差，按照QC新仿真模型重新仿真数据看左右通道阻抗有偏差 solution： 修改PCB走线。 尽量减少slave CP相关的阻抗，并适当增加master CP的阻抗来尽量平衡。 DVT1 导入。（目前PCB已经修改好并且仿真ok。） 最后优化方向： target ：左右通道Ibat 差值小于1A thermal 结果趋势来进一步判定。 DVT1 机器测试：左右通道Ibus 差值再200mA 也就是对应的Ibat 差值400mA （MAX）。 已符合预期 ，close | link | 文亭 | xuwei | QC CR：7848684 | 2.PCB | #N/A
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue：快充时候，log 打印数据和预期是不匹配 Rootcause：可能1 ：PMIV新架构，log打印还需要澄清。 可能2 ：ICL 等充电配置目前有问题，没有如预期配置，所以看起来log 对应不上。 ---需要dump 寄存器给QC确认具体配置值，然后修正配置后dump确认配置对了，才能往下继续测试事宜。 Next action： 1和2 都要同步排查。然后再进入下一个均衡问题确认。 方向1：5/16 QC给的配置，配置后判断还是觉得不对，继续沟通中 （CP 和 Buck 的电流混在一起）） 5/22 QC提供一些配置建议，导入后，看起来比较接近了。（CP 和 Buck 的电流已经可以分别读取了）-分开后的读值是否正确，正在tuning 方向2. 5/16 中午 dump 成功第一份寄存器，发给QC ，待回应。 5/22 QC提供一些配置建议，通过解决方向1后的log 显示 和设置值还是对不上 5/28 快充时候 BUCK charging ICL设置100 （实测电流是100mA）但是log 打印出来BUCK charging 电流是300+ 。PMIV0102的快充DIV模块 实测在2900mA左右，但是 log打印出来是2450mA ,偏差了450mA，问题及log提交给QC ，暂时没有找到根源及提供有效改善方法。 建议SW 从6/3 开始拉QC 例会核对这个问题的分析和解决来加速case解决。 6/13 highlight 给各位领导 ，并重新触发QC CR针对 PMIV CP 电流读值偏差问题。启动邮件追踪push 该case 1. PMIV 快充的Ibus电流已经比较准了，最大电流情况下，误差值预计在100mA左右，可以满足项目需求。 6/20 2 .QC bug ：100mA 的ICL设置时候，内部电流检测倍率不对，是真实值的5倍左右，其他电流档位没问题。 最后临时patch是将读值/5的值再log输出就比较接近了。可以接受，先这样go。具体正式修改，QC会加到高通代码主线中 6/25 | link | xuwei | 文亭 | QC CR：7847941 |  | #N/A
2025-05-12 | 4.EVB | 9.Memory | 3.Review/Simulation | NA | Monitor | RISK：仿真fail（64%UI， target=65%UI） |  | 嘉琨 |  |  |  | #N/A
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue： 两个PM8550VS PMIC的GPIO ，无线充SW再ADSP 里面初始化配置后直接就开不了机。 Rootcause ：SW主导和QC继续确认原因。--xuwei9 solution： WLC_inhibit 改到CPU 的GPIO口上GPIO125。将WLC_MODE_SEL 改到 PMIV0102 的GPIO08 上，EVT导入 （项目上无法承接风险往下go，保险方案是改GPIO口后继续往下go） Action：0511 已通过飞线将更改后的口rework 出来 初步看符合需求，可以控制了，后续再EVT试产前完成细节bringup 。 负面作用：EVB 板子无线充电默认不能正常工作。 如由需要调试的板子，找Xiamen BB rework。 额外发现：CPU GPIO63 GPIO list 描述是PD 口，实际测量是PU口，需要和QC确认。--HW chenwt EVT 确认OK |  | 文亭 |  |  | 1.SCH | #N/A
2025-05-09 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue： 无线充SW在ADSP 里面初始化配置后 PMIV0102 的GPIO08作为中端口，实际测试无法收到中断 Rootcause ： PMIV0102的GPIO 应该是不能作为中断使用。 solution： 将WLC_DET改到CPU的GPIO63 。EVT导入 Action：0511 已通过飞线将更改后的口rework 出来 初步看符合需求，可以控制并收到中断了 EVT 确认OK |  | 文亭 |  |  | 1.SCH | #N/A
2025-05-07 | 4.EVB | 3.Charging | 3.Review/Simulation | NA | Closed | RISK：SW 无线IC SC9624 ，在houston 印度工厂量产中，工厂测试发现大概0.15%无线充电无作用，换无线充电IC后OK。（试产约0.07%，所以产线认为可以接受，没有反馈问题） Rootcause : 无线充IC 内部校准参数被改写了，厂家怀疑是咱们FW升级时候有小概率动到校准参数。（但是厂家自己测试无法复现问题） solution： 1.for houson 已经出了版本导入量产（同时加入对校准参数的log 跟踪，以便万一再出现可以抓到细节log确认在什么情况下出的问题），需要较大数量的数据来看是否解决。（预计5/25 出10K左右的结果。） 2.for equator ：备份 PCB 可以兼容的方案CPS4038（老方案，但是会cost up 0.035$），以防万一SC9624的生产良率 无法达到PE能接受的程度。 但是需要在EVT试产前决定用哪个。 PE 主导收集houston 数据。 action : rework CPS4038 的PCBA出来（5/12 到达南京），待SC9624 bringup 完成后开始开发CPS4038 的bringup 。期望在5/20 前完成。 具体待跟进SW进度 Houston验证10K ok， 维持目前SC9624设计 |  | 文亭 |  |  |  | #N/A
2025-05-07 | 4.EVB | 3.Charging | 5.1 Bring up | NA | Closed | RISK：SW 无线充 bringup ，南京有两个无线充调试的板子开不了机。 Clue：1. 说是焊接线圈后出现的故障，但是实际上线圈和板子其他开机相关模块没有任何相关性。（推测是否当时哪里操作不小心短路到哪个电源导致PMIC烧毁） 2.厦门BB 1个板子ok，南京后面用最新版本+第三个板子也ok， 没发现问题。 Rootcause : 1.寄送一个板子到厦门，分析没有漏电，重新刷版本后可以开机，不复现问题。 （不排除是当时SW代码有问题导致的不开机。） solution： keep monitor 没有再报问题 |  | 文亭 |  |  | 6.No Change | #N/A
2025-03-27 | 3.PEL | 5.Camera | 3.Review/Simulation | NA | Closed | Issue： wide camera 背面有WIFI芯片，S3b 2P2 会干扰camera Clue：1. 在houston 上验证2.2V 会干扰wide camera Rootcause : 13M sensor受到干扰 solution： 预留隔磁片空间 6/20：去掉隔磁片在WIFI最大发射功率，以及正常下载和上传时，测试RCN pass, 去掉隔磁片。 DVT1 monitor | LINK | 芳梅 |  |  | 2.PCB | #N/A
2025-04-29 | 4.EVB | 1.Platform | 3.Review/Simulation | S2 | Monitor | Issue： SIM卡座有一供HRD和二供Lecton，一二供的物料不可以混搭。供应链需求一二供都需要在FPC厂PBH和kongwing试产，这将会产生4款SIM FPC Clue：1. 厂家物料管控方案 2. ESD的风险管控 Plan： 1. EVT和DVT1 SIM FPC BOM按照一供配一供卡座，二供FPC配二供卡座。哲林确认TVS的贴片方案 2.DVT2试产一供FPC+2供卡座， 二供FPC+1供卡座，若出现ESD或者其他实验fail, 舍弃会fail的搭配 | LINK | 李果 | 廖哲霖 |  |  | #N/A
2025-04-30 | 4.EVB | 6.Display/Touch | 5.1 Bring up | S1 | Closed | Issue： 开机fastboot下，插入USB线时，有50%概率会有display先黑亮起后绿屏，如果插着USB数据线，fastboot reboot bootloader 100%会绿屏 Clue：1. 插座USB数据线会出现 2. 按开关机键重启不会出现 Rootcause : 发版的Gerber数据输出错误，原因：工具软件bug问题， cadence未解释详细原因。 Solution： 增加数据输出Datebase 检查。 CAD 增加shorts文件的检查。 BB&RF 调试临时对策： EVB 屏幕和USB数据线或者充电器不可以同步使用 需要使用屏幕的板子AVDD飞线，如bringup notice | LINK | 川叔 | Chenyc4 |  | 6.No Change | #N/A
20250430 | C.RAMP | 3.Charging | 4.Build | NA | Open | Ramp Build ,CQA2 ,12pcs can not wireless charge when phone power off. Total/13K ? clue : 1 .Wired charge can work when phone power off and power on .Wireless charge can work when phone power on . 2. Wireless charge can not work at power off but can charge after short press power key . 3. EXP : replace relate components . Q2800 (can not recover) ,U2801 (can not recover ) & U1001 (CPU and need replace memory at same time for power on ,it recover),suspect it is related U1001 issue. 4. EXP : NG U1001 replace to ok PCBA ，result ：TBD 5. EXP : check waveform for fail unit （WLC_DET before and after R2811 & CHRDETB ）to check why it can not work，result ：TBD Rootcause： Solution ： RISK assessment ： | link | 文亭 |  |  |  | L.Prado
20250409 | B.PVT | 3.Charging | 5.6 User Feedback | S3 | Closed | DF :BATTMAN-24617 Power Charging issue :wired charger can not charge ,wireless charge ok .PVT NP8N4E0289 clue : 0.Factory test all pass 1 .with factory SW ,and CQA show battery health unknown 2.log check :Slave CP I2C 0x63 can not work . 3. EXP :catch available address on I2C bus 9 （adb：i2cdetect 9） ，result：0x55(fuel gauge),0x60(wireless charge ),0x61 (master CP).only lost 0x63 （Slave CP and not other I2C added） 4. EXP :flash a latest userdebug SW(limit to 30W charging when slave CP I2C can not work) ,it can charge . but with around 27W . test 10 times ok . and check charging curve ok .(30W power) 5. EXP : temp SW that open the power limit of 30W ,change to 68W when slave CP I2C can not work . result:charge to 5.2A Ibus. it means slave CP should work at 0x61 address ,and master REG right take effort into slave CP too . Rootcause： Slave CP SC8541D I2C address jump from 0x63 to 0x61 (HW IC bug) . Factory SW early version block charging in this case to check this kind of item （import from prado DVT2 , SW V2VD35.62/39720a-92145e used in this CR ） Solution ：1. Flash to a User SW and it charging ok ，can charging to full . (about 9 mins slow than MAX power in this case) 2. Factory SW will not block charging in latest version.（import from V2VD35.63-F.2 ）. Just block charging when I2C address jump in factory mode . RISK assessment ：Low risk . more action for other new project : suggest to add an external pull up R (30kohm-300kohm) between addr pin and Vregn of SC8541D to avoid I2C jump when use 0x63 address.(to make the voltage of ADDR stabler) | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
20250113 | 7.DVT2 | 3.Charging | 3.Review/Simulation | NA | NA | RISK：MOTO NUDD 磁吸背夹 PCMCR 进入，处于approve 状态中，相关方案的各种事宜分解需要细化清楚 BB相关：1.HALL IC 磁仿真OK， 其他sensor 评估ok ，mag sensor不受影响，不需要两套参数，cap sensor 要启动重新校准。 2. WLC 需要两套参数来匹配（磁吸背夹 吸附 和 没有磁吸背夹，要各自一套参数） 单独增加 GPIO 设计 让AP通知 WLC IC，DVT1B 开始导入到机器中。 被动影响问题：DVT1A和EVT机器 导入这样的FW后WLC 充电会乱掉，怎么处理。 评估ongoing --chenwt ，wanggc6 3.thermal WLC charging 部分，需要两套参数 （磁吸背夹 吸附 和 没有磁吸背夹，要各自一套参数），具体参数需要最终的WLC FW 基本lock 后才能tuning，需要多久时间？目前预估3周是否ok？ | link | 文亭 |  |  | 6.No Change | L.Prado
20250107 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | DF :chagring slow ,total 3pcs NA CDC found . clue : 1 .unit log show Slave CP I2c can not work ，user SW will not charging in this status. 2.this unit factory test all pass Action ： 1.Need fail unit back to xiamen for analysis ，---Jinrong （1 unit will back by Ronli hand carry ) 2. other 2 units Log update and analysis 3.factory test process check : can Factory cover similar fail unit ?---海建，文亭 Rootcause：TBD Solution ：TBD | link | 文亭 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
20241220 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S2 | Closed | Issue ：A+G may can not work after reboot phone . 1unit in NA report this case. Clue :1.Milos can reproduce in some units .at lease 2 units in XM . 2units in shanghai 2.logic wave form check : after reboot ,A+G I3C SDA is low at most time .MTK suspect it is A+G device issue .master can not pull down SDA at so much time. 3. if disable P-sensor ,it can not reproduce (SW debug information ,need confirm) Rootcause :I3C bus error due to IBI function of TDK A+G sensor I3C have some bug that it may pull down SDA line always. Solution :Disable IBI function of TDK A+G sensor I3C | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
20241210 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S1 | Closed | Issue: 电话中，离开头部，屏幕无法恢复 Clue: P-sensor CT值没触发门限 Rootcause:此PUD共性问题（MILOS也有）， CT值随时间漂移比较大， Action: 优化算法 |  | 小熊 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
20241210 | 5.DVT1 | 5.Camera | 2.Design | S1 | Closed | Issue:前置 Camera马达铁壳不接地，去除铜箔评估 | link | 廖哲霖 | 芳梅 |  | 6.No Change | L.Prado
20241210 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S1 | Monitor | Issue: PUD EVT1---DVT2 CT值偏大 Clue: 泡棉位置和大小对值影响非常大 Rootcause: 1.1硅胶套作用的认知 1.2隔离效果差，材料不合适 1.3 参数 2.材料隔离度的认知：实验设计 Solution: DVT2B 研发验证，PVT 工厂验证 Action: 1. 1.8V增加RC电容，增强电源稳定性 2. PUD板和中框之间改导电胶，解决原来泡棉值大的问题 3. 中框和屏幕之间泡棉减窄，手工验证OK |  | 小熊 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
20241205 | 5.DVT1 | 12.EMC | 6.Issue | S1 | Closed | Issue: EDU03 DVT1 ESD d1 SIM卡坏 Clue： 测量SIM卡DATA引脚，二极管挡对地压降为0.9V，正常为0.5V，判断DATA信号被打坏； Root Clue：zone9（ActionKey）前一个区域zone8是SIM卡槽处，且6号引脚是在外侧，推测ESD从SIM缝隙处放电，打到SIM-DATA引脚处损坏SIM卡； Action： 1. 加强SIM屏蔽壳接地(PCB)； 2. SIM卡DATA,SWP引脚，增贴TVS，在DVT1B版本导入验证； 3. SIM_UIM1的DATA/SWP串33R 电阻（0613952X37） CLK/RST/DET串0R电阻（0613952Y66） DVT2 ok | link | 廖哲霖 | 李果 |  | 1.SCH | L.Prado
20241205 | 5.DVT1 | 12.EMC | 6.Issue | S1 | Closed | Issue : DVT1 ESD WH185467 1ST d3 Right louder speraker no function(15kv, zone7, 通话状态）; Clue: 拆机，测量Smart-PA输出LDSP-DM网络阻抗对地0.1欧，判断Smart-PA输出端损坏； Root Cause: 整机Costdown, 删减SPERKER接地泡棉; 先前设计的镭雕放电区，没能成功防住ESD； Action: 1. LDSP-DM & LDSP-DN网络，DVT1B USB板紧急rework 6 台机器，增加TVS进行验证（Presemi PESDMC2XD18VB 18V），月底出结果。；提前Prisemi索样，在DVT2版本全部导入； 2. 天线确认，可以增加泡棉接地；结构确认中框预留导电泡棉预留位置；（DVT1B如果没问题，先不加泡棉0.2元） 3. DVT2版本USB PCB进一步优化TVS放电路径； DVT2 OK | link | 廖哲霖 | 院长 |  | 2.PCB | L.Prado
2024-12-03 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | Issue ： 部分机器快充时候指南针APK 20241105-3Dcompass 1.apk 测试结果会偏转很大（有时候一直转角度不停） clue：1.部分机器会部分机器不会。 和机器EVT或者DVT1 没有直接关系。 2.出现问题时候M-sensor会一直偏移，不会停 3.复现问题偏移过程中，灭屏再亮屏，有较大概率就不再偏移。再碰一下手机，就会继续偏移。---推测这款 APK 和A+G 有关系，而不只是M-sensor，而问题可能出在 A+G的数据而不是M-sensor 4.更换另外一款 指南针APK，确认不复现故障。更加推断是A+G有问题导致的。 rootcause：suspect A+G sensor impact by thermal what is cause by fastcharging. Action：寄送故障机给A+G 的vendor 进行进一步分析 。 solution：proposal ，A+G 更换到手机靠上端比较不热的地方（手机 Y轴靠近上端） DVT2 ok |  | 小熊 | 文亭 | link | 2.PCB | L.Prado
2024-12-03 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue:Barometer 放快充背面，温漂风险 Action：快充同时用气压计场景少，漂移范围可以接受，无更合适位置 |  | 小熊 |  |  | 6.No Change | L.Prado
2024-12-03 | 4.EVT | 7.Sensor | 2.Design | S3 | Closed | ssue 1: Taptap has a low recognition rate Root Cause: A+G sensor is on the low half of the mainboard, making it not responsive enough Action: Move to top part of the mainboard Impact：Camera effect needs to be re-tuned. | link | 小熊 |  |  | 2.PCB | L.Prado
2024-11-04 | 4.EVT | 5.Camera | 6.Issue | S3 | Closed | [s1]Issue ： Prado main camera 客观RCN 测试fail，主观测试fail clue: 1. Camera AVDD2.8V AGND单点接地回路远 Root cause : IMX896 AGND要就近接地 AVDD2.8V LDO输入电源滤波,LDO GND 和 AVDD 输出电源地有压差 Solution: 1 . 修改AVDD2.8V，AVDD1.8V AGND表层接地 2. AVDD 2.8V LDO从2.2uf 改为10uf 3. AVDD2.8V LDO 输入, 输出电源和LDO GND 共地后下主地 LL : IMX896 AGND 接地回路要短。 参考houston布局或者是等prado DVT1的效果 | link | 芳梅 | 院长 |  | 2.PCB | L.Prado
2024-11-04 | 4.EVT | 7.Sensor | 6.Issue | S3 | Closed | [s1]Issue ：和Milos同组参数的情况下，Milos CT=6000，Prado P Sensor CT=39000。配houston硅胶套后，CT=9000 clue: 1. HW设计影响排除，ME差异待拉齐 2. ME设计确认，TP-PSA和Psensor泡棉 Follow Milos Rootcause： 中框和屏之间的泡棉无法防止CT，改用houston DVT2的物料后OK | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | L.Prado
2024-11-07 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Task ：USB 2.0 眼图测试。长线1m测试结果按照短线标准过不去 solution：调整预加重 从10改为11 ，有些优化，基本上擦边pass | link | 文亭 |  |  | 4.Parameter | L.Prado
2024-10-16 | 4.EVB | 5.Camera | 6.Issue | S3 | Closed | [s1]Issue ： wide camera工作时有条纹干扰 clue: 1. Wide camera 抬离主板8mm，条纹消失 2. 用手遮盖镜头，光线变暗时，条纹会变很明显。 Root cause : Wide camera 50M sensor抗干扰能力弱，受到主板上camera下方的电源干扰（VSYS，Vs3_pmic， VBB） Wide camera参数错误，ISP设置4~5X，干扰被放大，和软件沟通的是大概率设置在2X。 Solution: 1. Sw 效果部分集成参数， 增益调整2X（和SW zhangbo54确认ISP增益为2X），贴隔磁片效果可以接受。 2. DVT1主板VS3 ，VBB 避开camera 修改layout。Vsys无法修改。 3. EVT2 装配增加60um隔磁片，RF ok，ANT需要测试，ME已经备料。 LL： 电磁干扰的是camera模组上的哪一部分？模拟转数字电路部分？投影到camera上在哪个区域？ 待做实验验证，不同的区域加变化的电磁场，看效果。是否只和camera模组的AVDD pad 走线区域重合？ | LINK | 芳梅 |  |  | 2.PCB | L.Prado
2024-10-15 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | Issue S3: 死电池激活，WLC 不能自动转入关机充电界面。 Clue：1. WLC 死电池依然能持续激活，充到超过开机电压了3.6V以上，只是系统没有自行转入关机充电界面。 2.有线充电是ok的。 3.测量电压发现 WLC_DET电压不够，只有0.4V VS 期望的1.2V以上高电平。 Rootcause： R2811 电阻和系统漏电产生分压，导致控制电压不够 solution： R2811 从10K 改为1K。（1K 在glory 上面有量产，所以基本上可以确认没问题） ，EVT mems 导入修改 具体rework 实验TBD。 |  | 文亭 |  |  | 1.SCH | L.Prado
2024-10-12 | 4.EVB | 10.USB-C | 5.1 Bring up | NA | Closed | Issue S3: CID no function Clue： 插入设备后，CID GPIO 电平只有1V VS 0.63V以下，所以获取不到中断 Rootcause： GPIO的上拉内阻 和串联的10K电阻 分压比例不好 solution： EVT 串联电阻临时改为1K电阻。（改为1.5K的临时更改验证ok） 负面作用：串联电阻太小，担心MP防护不够高，担心有问题。 DVT1 GPIO 更改到上拉内阻比较大的，预计改到GPIO30 。rework 待验证 |  | 文亭 | 院长 |  | 1.SCH | L.Prado
2024-08-29 | 3.PEL | 1.Platform | 4.Build | NA | NA | Issue S3: EVB 首版验证 不识别USB口 Clue： 1.AP_good 没有信号-》推测可能是没有时钟 2.确认26M 晶振没有震荡-》查找相关。 3.确认 CLOCK IC 使用MT6685LP 没有贴错。-》怀疑 晶振是否贴错及电源是否有。 Rootcause： CLOCK IC 使用的晶振贴的52MHz导致Clock模块无法工作（24M 平台需要使用26MHz晶振）。进而导致不识别USB口 solution： 更改晶振为26MHz，具体型号RF负责 lesson learn ： RF 主导 |  | 文亭 |  |  |  | L.Prado
2024-08-29 | 3.PEL | 4.Audio | 3.Review/Simulation | NA | Closed | Issue S2: Smart PA should can not work at EVB Clue： Milos bringup fail & we re-review check same issue in prado （ Smart PA I2S DO & DI connect error ） Rootcause： Smart PA I2S DO & DI connect error solution： 1. get smart PA demo board and wired to EVB for bringup 2. change Smart PA I2S DO & DI to correct connect -from EVB2 lesson learn ：双向改为MISO,MOSI规范命名 | LINK | 院长 |  |  | 1.SCH | L.Prado
2025-03-24 | C.RAMP | 3.Charging | 4.Build | NA | Closed | Issue： Wireless Charge Test Get Results (Houston IN) ,FR ~0.26% in Dixon . Clue：1. No such case in WHP 2. L2vision test no any data but not just test limit fail （TELL_WirelessChargeTest_GET_RESULTS） 3. BT test ID is 38436 （Asc ii） ，it is 0X9624 ，same as ok unit （WIRELESS_CHIP_ID_TOP_VALUE） 4. Log check Wireless charge IC U2801 FW is right 5.but there is no interrupt from the wireless charge IC to CPU . 6.EXP ：wire out the coil and retest ：fail 7.EXP ：replace of U2801 with a new one : ok 8.EXP： force U2801 FW update ：fail Root cause : wireless charging IC U2801 issue .need vendor get the fail unit & fail board for further analysis. TRIM(IC calibration data ) error after FW update. solution：Vendor change FW update code to avoid edit TRIM data. | link | 文亭 |  |  | 6.No Change | K.Houston
2024-12-25 | 7.DVT2 | 3.Charging | 6.Issue | S3 | Closed | Issue：IKSWV-66067 SM6475 // Houston India // V //The battery cannot be charged to full. Stop @97% Clue：1. india charger +india phone test issue. NA SKU no issue found in same test so far. 2.replug charger and it recover and charge to full. 3.from log: it is due to main charging IC PM8350B abnormal at this time . it show charging ,but no charging current. 4.from log :SW noticed PM8350B abnormal , it happened at about 77% ,and user notice it @97 % when phone closecharge pump. Action : SW add dump REG of main PMIC in temp SW version trying to reproduce and get more information first for rootcause research ,waiting for reproduce Rootcause : TBD solution： workaround :when notice it by disable USB port and enable usb port again or similar action . | link | 文亭 |  | IKSWV-66067 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-12-02 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Camera power up fail sometimes -Houston 1.issue 定级 Issue ： camera 概率性不能打开，自动恢复，下次可以打开。runin 数据是这台机器 1/3500 。Total 20台？出现1次？ 测试也有单次出现，自动恢复。正常压测不能复现 等级：软性可自动恢复。 影响：不会影响退机，但有一定的影响用户体验 。 2. 深入挖掘，尝试找到根源清理 。 2.1 runin这台复现1次的机器压测1万次左右，复现问题后的状态抓到了，当前故障也理清，I2C 总线活着，设备也都活着。 2.2 压测复现的log 使能PMIC时候看I2C错误过，但是I2C错误到恢复是几乎一瞬间。 所以现场自动恢复了，复现问题瞬间 不知道具体如何。尝试寻找抓取瞬间I2C错误现场的方法？ ---压测4天没有复现，暂时没有抓到故障 12/9 2.3 如何加大复现概率？：尝试修改脚本，可以离线运行（不连接电脑），次数60万。--- Mingfeng MF3 Yang ¦ 杨明枫 。 然后 HPM协调10台机器进行压测，来看是否能复现？（也用来作为后面workaround 后是否解决问题的验证手段） 3. 是否有解决或者临时解决方法来解决或者降低对用户的影响 可能方案：proposal 继续研究打开camera 时候的PMIC 输出电压的I2C控制接口，争取这边加第二次使能，并且中间加1ms delay。（by Mingfeng Yang 12/9） 方案:加1ms延迟，方案验证通过 | link | 敏敏 | 文亭 | 外部open 的link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-12-02 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Issue：CCT RD复测精度 ，HZ和A 光源 超标准 50% ,其他光源 ok ，共测试8种光源（camera给的标准是 +/-15%） rootcause：推测 1 金机可能不是中间值机器，推测2 算法cover 范围不够导致的。 solution： 1. 通过产线大数据，找到接近中值的机器，重新整理后制作成金机for 后续使用。-------经讨论，金机可以沿用，不更新 2. rework 极限属性的IC到机器上，收集极限数据，然后算法优化来覆盖极限机器。目的是保障极限机器也ok 。这个是优化的新开发流程，paros 没有这一步。 plan 预计12/15 完成相关工作-------抓完6台机器的rawdata，更新了校准系数，验证了PVT NA,DVT2 INDIA,DVT2 NA都可以pass | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-11-18 | 7.DVT2 | 11.Thermal | 5.5 Certification | S3 | Closed | Issue：认证反馈 ，NA SKU 电池NTC 附近温度到达60度后，充电还没有停止。（在电池NTC附近加热电偶进行温度监控） Clue：返回的机器自测pass ，无法复现故障。 rootcause： suspect SW版本比较老怀疑是认证当时有bug solution: 1.更新到最新版本，再次送认证复测 2.同步Action：同步请认证机构打开Battery tracer APP，记录手机温度和电流状态。 万一复现，拍照手机和认证设备上温度和电流的照片，分析数据来判定为什么会fail。 11/28 更新：复测发现 问题1 ：TMO的已经到达58度，Battery tracer APP显示 charging current loading （表示上层通知停充了），但是认证测试的电流表上还是显示有260mA进入电池。 问题2：非TMO的机器，到达62度，电流还是显示-1611 （一直不动，整个过程都是这样，APK似乎出问题了。），这时候夹具上确认到只有120mA电流进入电池，也是判fail。 认证表示 没法提供log ，SW 无法进一步分析。 线索：认证是将电池电芯断开，再电芯和电池保护板之间串联电流计来进行监控判断电流。 12/2 更新：1. 返回的机器 log 捞出来给SW确认判定为pass 。2.对应两台机器，在我们实验室用我们的电流计 和 加热台加热 手机，不会出现11/28 出现的问题1和问题2 。 都是pass 的。 暂时无法理解为什么认证那边测试会fail 下一步: 1. 参考Orion 这周测试 12/6 2. onsite 跟踪测试进一步确认是什么问题导致的？ | link | 德太加 | 文亭 |  | 6.No Change | K.Houston
2024-11-18 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | Issue：Build P-sensor cover APK test NTF ,NA DVT2 一供报5.15 NTF。 rootcause：1.分析抖动比较大导致的，solution1 ：加大测试margin 看下改善情况 2.P-sensor 冷启动时候一开始抖动比较大 。 3.测试夹具环境 Display 对CT有一些影响 solution：1.（降低灰卡挡板从22mm改为18mm ，然后将*倍率从0.95改为0.9 ，DVT2 二供全面导入） 2.DVT2最后200+台机器，导入action： 将P-sensor常开并在测试P-sensor前关屏，目前结果 NA SKU 159台都pass。 将这些action都导入PVT ---ongoing （修改12M） 。 然后monitor PVT data PVT当前200台出现1台，继续monitor 数据。 0.6% （3/500） | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-11-18 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | DVT2 ESD WH184180 2nd 11/20 unable to power on;D5(15KV,zone8手写笔孔位置) Rootcause : 绝缘膜没有贴好，ESD从空隙穿过打到FPC上，打坏了hall IC 和 主板 solution：加强厂家对贴膜的管控质量 -ME monitor PVT | link | 廖哲霖 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-10-18 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s2]Issue: WH182655 2nd source EDU14 fail @170V D1 /190V D2 Clue: 1.EVT和DVT1 一供机器 都是pass的（pass 最高电压600V），主要差异器件是快充IC 和 OVP mos 。但是OVP mos 原理上没有直接相关性，所以主要嫌疑对象是 二供快充IC 2.D1 不能充电，但是OTG可以使用，机器漏电21mA / D2 漏电流4mA，功能没有异常。 从以上信息推测，主充电IC模块还能工作，接口识别还ok， 推测故障点在 快充IC的VAC口。拆除IC后主板漏电流正常。证明IC坏了 3. 二供快充故障IC 1# Vendor 第一步确认到 VAC 对GND有漏电，REGN 有些异常。 推测电大概率是从VAC进入。 具体待进一步分析后确认。南芯Demo 上面暂时没有复现到故障。 Rootcause： 二供快充IC SC8541D VAC 端口浪涌抵抗力比较弱导致本体损坏。 下一步： 故障1# IC详细分析，查找浪涌进入损坏的路径。以及 2# IC的初步确认，看是否和1#IC 一样的失效点。10/25 早上提供 。 mona 机器上实测情况含波形抓取（测试条件：插着充电器，浪涌每个电压连续打5次浪涌，浪涌间隔5~10秒 ） ，10/25 早上提供 优化方案 （包括板子修改 或者 器件调整 ） ，10/25 早上提供 demo 上测试条件和 联想测试状态的逼近再复测一下。（CP工作，不工作，开启过程各种状态 浪涌 ） TBD？ solution： serie R on VAC R2743 change from 22R to 100R .Import into DVT2 2nd source .（mems 已经备注） Verify : Temp rework 2 units， test pass . DVT2 2nd source EDU14 ， test pass . | link | 文亭 | 廖哲霖 |  | 3.BOM | K.Houston
2024-11-18 | 7.DVT2 | 1.Platform | 5.4 ALT | S2 | Closed | DVT2 ATT drop WH184222 2nd Unable to power on:D4(1.5m,front) Clue：1. display poewr short to GND 2. change to a NEW display module and it can power on Rootcause : Display module damaged cause power short to GND and cause phone can not power on. solution: ME &KP stracking |  | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-10-18 | 5.DVT1 | 10.USB-C | 5.3 EE DVT | S3 | Closed | Issue:DVT1 EDU15 WH182510 1st ,OTG no function,and translater no function,cannot recover after reboot Clue:1.D2- TVS损伤，D+对地68K，D-63K， 问题现象同之前wrangler类似。 2.RD实验：短路5V 到TVS上，不会造成TVS损伤但是短路的同时有浪涌可能会有此现象 3.据实验人员描述这台是测试到Vbus ，D+，D- ，GND 四个短路后的实验后fail。 4. 二供TCC实验无法复现，RD实验参考实验室操作也无法复现。 5.实验室测试方法是先插OTG，再来一根根短路信号出现问题。 实际用户 场景如果有段路，基本上也是配件本来就短路，再插入手机，而这种情况手机会直接软性保护，原则上不会出现故障。所以实际影响很有限 Rootcause：推测是测试中触发浪涌或者ESD并且一直维持5V短路造成的烧毁 solution ：monitor 长期：如果要根除这种实验触发的故障，要更改TVS 型号，选择高电压的TVS，并尽量选择 恢复电压比较高的。（但是对CPU的ESD和浪涌防护会变弱一些）。 所以不太建议更改，具体建议ESD 专家 和vendor 及各地专家沟通下 再说 | link | 文亭 | 廖哲霖 |  | 6.No Change | K.Houston
2024-10-15 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | Issue ：DVT1 ALT WH182695 2nd source： unable to power on:C2(15kv，Zone9 ，耳机孔附近) clue：C2这台故障机（ After +15KV air discharge at zone9 , Headset mic no function, and unable to recover），收到CQA测试耳机MIC功能确实异常 拆出测试SUB板，单独测试HS_MIC_N和HS_MIC_P网络阻抗，均为OL 接入主板，测试HS_MIC_P阻抗为284Ω，HS_MIC_N阻抗为0.9Ω ，VS ok板子 的230kΩ左右 ，确定是codec芯片被ESD打坏 rootcause：中芯国际的WCD9370 比较弱，ESD 直击到耳机通道比较容易损坏。自能尽量增加防护来降低15KV出问题的概率，但是没法确保一定不出现。 solution：1.耳机MIC 串联电阻 从10R增加到100R。DVT2 一供开始导入 2. DVT2 二供优化PCB ，TVS 401 DVT2 都使用中芯国际 的IC 来加大验证数量 DVT2 一供测试pass ，先Closed | link | 廖哲霖 | 院长 |  | 1.SCH | K.Houston
2024-10-14 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | Issue ：DVT1 ALT WH182596 1st source 第二配色 unable to power on:C2(15kv，手写笔孔) clue：样机返回厦门，预计10/17到达 rootcause：1. 主板HALL_INT_S端口阻抗异常，FPC部分VREG_L8E_1p8，HALL_INT_S，HALL_INT_P阻抗异常，确认主板CPU和HALL IC损坏； solution：1. DVT2及以后机器增加绝缘麦拉片 ，确保堵住Hall IC开孔； proposal 2. Hall FPC信号线修改为内层走线，过孔打在焊盘上，并尽可能增大黑胶覆盖厚度面积，在工艺允许情况下增加正面露铜接地区域；---FPC厂家评估无法实现。 proposal 3. 主板TVS根据修改后实验情况决定是否贴；----Hall IC损坏，TVS 不能解决该问题，不走这个方向。 其他项目：应提前审查到导电笔悬空的ESD风险； DVT2 一供测试pass ，先Closed | link | 廖哲霖 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-10-18 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | issue： 产线反馈DVT1 出现2次SIM卡不识别，重新插拔恢复了 action： 产线压测，出现问题不要插拔，直接做飞行模式及开关机看是否恢复，用来判断是否连接器接触不上导致不识别，还是其他原因。 rootcause：插拔过程中 SD 卡座弹片刮到 SIM卡的金属片，导致SIM卡严重磨损。进而导致SIM卡接触不好。 solution：SIM 向下移动0.4mm 来尽量避开 SD卡的刮线。 |  | 李果 |  |  | 2.PCB | K.Houston
2024-08-29 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue S2: P-sensor CT test result:20000~40000 ，Fail（target <3000，deadline：5000) IN EVT DVT1 方案： V2：黑色泡棉+0.03黑色背胶+RX硅胶套+机壳不喷黑（应急生产92pcs） V4：黑色泡棉++0.03黑色背胶+接收区域开孔减小（替代硅胶套作用）+no RX硅胶套+机壳不喷黑（主要生产） V4: 黑色泡棉+0.03黑色背胶+接收区域开孔减小（替代硅胶套作用 ）+no RX硅胶套+机壳喷黑" （期望的比较好的状态，DVT1 一供末期主要方案，包括L-sensor 金机也用这个状态） DVT1 结果：CT 数据在6000~10000 之间，没有达到预期理想状态 DVT1 末期：只能导入临时硅胶套+侧面喷黑方案来降低CT，根据之前的rework 确认 预计CT在3000附近,批量数据 ：200台数据集中在2000~3000，最多不到4000 长期：DVT2 导入修改的防呆的硅胶套，以提高产线装配可操作性（同步PCB修改让位给防呆及检查用） 其他项目：目前的结构设计情况下，需要硅胶套+黑色泡棉+中框侧壁喷黑的方案。 DVT2 目前导入硅胶套后，P-sensor CT已经控制住。 该问题先收敛close ，关注其他问题 | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-27 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | Issue: DVT1 一供50pcs天线干扰camera测试已完成，其中2pcs测试fail, 问题1：一台主摄N77干扰导致预览fail, 问题2：一台Wide wifi 2.4G阈值超标 analysis：1，问题1：主摄N77干扰，因为前置camera石墨片贴着主摄camera连接器 2. 问题2：Wide wifi干扰，log无报错，怀疑测到最后一项从盒子拿出导致，压测150次pass。 Solution：问题1： 结构负责，工厂执行，调整贴装石墨片夹具，保证石墨片到主摄连接器间距1mm 问题2：Monotor 已经执行，暂时没有问题，先close 如有问题再reopen | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-27 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | Issue: ATT drop No power on issue 跌落后概率性不开机 1台 analysis：1.当故障复现时候，测量发现 BB clk 不能输出，但是32K始终有。推断 CLOCK IC PMK6450 或者对应的晶振 有问题。 2.按压晶体后不复现，装成整机加测跌落后复现故障。测量 还是BB clk 不能输出，32K有。 3. 加焊晶体后恢复了。（但是由于 PMK6450 和晶体紧靠着，也会同时受热，所以会一起背加焊到） 4.应力确认这边最大0.2% ，低应力区域。 Root cause： PMK6450 或者 晶体虚焊导致。 Solution：1. PMK6450 和晶体 加大钢网 -DVT2导入 ---BB文亭 -done 2. 预留点胶孔 -DVT2导入---ME jianxi DVT2 一供测试 没有问题，先close | Link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-27 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue: DVT1 一供ESD，6台出现2台前置camera无作用。CQA 和 Moto APP都无法打开，稳定存在，重启也不恢复 Clue：1.重启后直接开CQA 或者用第三方APP 是ok的。但是使用moto APP 切换到前置camera 会自动退出，再进CQA就是无作用，并ramdump。 2.D2机器重新刷其他版本后ok，刷回原来的版本确认也还是ok ，推测 代码哪个关键参数出现错误了（存储在ROM里面的）。 3.当前log没有有效信息，SW 需要添加更多log 抓取的patch，然后重新抓取有效错误。 analysis：D2 软件升级后，恢复。加camera抓去log的patch后，待压测复现问题，抓log D3 TCC 实验室，待下线，加camera抓去log的patch后 抓log rootcause: SW MOTO camera APP 没有定义空指针，导致死循环。 solution: 更改空指针兼容策略，预计 10/11 后开始导入。 DVT2 一供测试 没有复现问题，close | link | 廖哲霖 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-10 | 4.EVT | 11.Thermal | 5.2 BB Test | NA | Closed | Issue： 前摄视频通话温度过高：F: ↑0.11°C/B：↑1.97°C clue： 软件功耗过高： Houston：48.11℃/49.97℃ @ 3.35W Wrangler 48.07℃/ 49.86℃@ 3.35W Boston：无whatsapp 数据，wechat 2.7W 硬件散热不足： 前摄石墨面积↓30%（从215mm²减小到150mm²） Solution： 1、摸底DN 方案收益，收益1C就达到预期 2、DVT1 二供增加DN方案 | link | 德太加 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-10-18 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | Issue：OTG有时候无作用，出现问题后就一直存在，需要重启后才能恢复。工厂和ESD实验都有报，但ESD报的问题无法完全确认和ESD本身是否没有关系。 clue： Chai Lu added a comment - 17/Oct/24 5:29 AMFrom aplogd_0947 logs： CID is ok after connect OTG devices --PASS type c could detect OTG device connected – PASS OTG vbus 5v outpud --PASS 4. The reason is ucsi could not get OTG info Line 26064: 10-15 09:47:52.429 83 83 E UCSI : ucsi_qti_glink_write: timed out for sync_write_ack Need USB module further check UCSI SW issue ，QC 给了个patch ，初测OK |  | 文亭 | 院长 | IKSWV-28598 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-27 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | Issue: IKSWV-23174 3台报主摄拍照dump。 Clue： 1.均是主摄OIS拍照或者AF对焦拍照时出现问题,且log均提示的MIPI error 2.这3台可以录像preview 100% dump 3.跟WIFI无关（工厂测试用WIFI指令控制） Root cause： MIPI cphy参数和目前硬件搭配不是最优 Solution： 优化MIPI cphy参数( 修改后EQ=0x07， CDR PGM=0x47，CDR Coarse=0x09 )，待软件提供版本给产线。 | LINK | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-09-20 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | issue：cap sensor no function 4pcs in EVT 改善rework 机器复测 ，D1，D3，D4，D6 故障机待分析汇总：D1 ，D4 ，D6 确认都是I2C不同，D4 D6已交叉确认IC不良。D1原加焊后ok，但是过后隔天又fail。 D3有其他故障，待分析 其他线索：1.PCB 焊盘没有看到损坏货焊盘掉落 2.IC上的焊盘也没看到异常。3.IC本体没看到明显撞击痕迹，更细节的待vendor 进一步确认。 4.有个确认项”故障IC 和正常IC的阻抗对比确认。（如果有厂家的报告，这个其实就不需要，只是在这前，如果想要初步看下哪个pin 异常，一般也就这个方式） 。昨天 shihai给的信息是D6没有差异 Rootcause：Pin1 bounding crack . due to stress on the component solution： move the cap sensor up 1.5mm . | link | 小熊 | shihai |  | 2.PCB | K.Houston
2024-09-18 | 5.DVT1 | 4.Audio | 4.Build | S2 | NA | Issue S3: L406 PCB package not match Rootcause： 1，DVT1 一供发板前没有进行FL的自检，直接发出去了，PCB一供返回问题L406焊盘没有开窗，临时：处理方式是，让一供 厂家自行将开窗开起来。 2. 然后 范南更新一版PCB和gerber 到服务器上，用的旧的名字覆盖。备后续使用。 实际 DVT1 二供已经用新的制作中。 Solution： 1. HD的板子上是否有FL的库的检查项：还是要检查的，这个比较危险。容易出现没有焊盘开窗而无法SMT的情况 会批量板子报废的！！！ 2. 出现临时处理方案的时候（CAD处理后结果和正式的设计不完全一致的）建议同步CC给主设，这样可以提前和后续工序（比如SMT 等）进行提前沟通，避免后续以为是异常停产导致延误项目。 （中秋假期器件报问题，比较难找到对应的人一一沟通清楚，所以尽量提前sync 好信息） |  | 范南 | 艳红 |  | 2.PCB | K.Houston
2024-08-29 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | RISK : Flicker FOV not good because ID change request Change request： 1. DVT1 ID要求改为类似camera 本体镜头的外观，1.凹面透镜+材料改为 vegas材质 （外观墨绿色）。 X轴 FOV 38，Y轴FOV 49 2. 要改图面透镜+材料改为 vegas材质 （外观墨绿色） 预估 角度还会更小，待有样品摸底，时间TBD Rootcause： solution： 1. 为了区分两种透镜，希望能区分两种机器，增加HWID来做区分，以便后续可以出两个参数来匹配。---chenwt -done 2.9/29 确认按照新打样的墨绿色的，凸面，2.4mm直径方案（材料要用vegas的），已按此准备DVT1 二供及 金机事宜 --xingshengnan-done |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-22 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | Issue S2: WH180780 ，tumble test， D5 cap sensor nofunction （CQA 所有通道一直显示绿色） ，recover after reboot "EVT TMO tumble WH180780 1 out of 5 cap sensor no function,recover after reboot:D5(150) EVT ATT tumble WH180784 Cap/SAR sensor no function:D5(450) EVT MIL drop WH180788 1.5m Cap/SAR sensor no function:D3(post)" clue： 其他两台硬性故障机器，8/28 到厦门 Rootcause：1.第一台软件故障 。2. 结构CH3 板子断裂问题导致，同MIC2 3.capsensor 单体故障。 solution： 1.软件优化2.同MIC2 无作用的修改板子增加一个钢片进行加强 3.单体寄给厂家分析，同时ME 应力仿真值确认及想办法降低形变。monitor DVT 1 一供没反馈问题 |  | 小熊 | 文亭 | WH180780 TCC FA link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D4 -8KV air discharge at zone8(Aging10),OTG no function， clue： D4 OTG is ok ,can not reproduce .安排压测 50枪，不复现 EVT2复现3次，重启恢复， 软件 log 分析，没有ADSP log 暂时没有进一步的结果。 SW有已知的问题：IKSWV-19512 故障发生后，和ESD 测试时的故障结果一样。 OTG和USB都无法连接，Vbus有电，但是USB就是枚举不上。 Rootcause： suspect SW issue 。 Action ： DVT1 ESD 打开ADSP log 后再进行测试，有故障后抓取对应log 进一步确认是否同一个问题。 solution：monitor DVT 1 一供没反馈问题 |  | 廖哲霖 | 文亭 | WH180794 TCC FA link | 6.No Change | K.Houston
2024-08-22 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | Issue S2: EVT ATT tumble WH180784 Headset no function:D4(300)- clue：样机已带回厦门 8/26 Rootcause： 耳机FPC断裂 solution：优化耳机FPC外形和走线 ，import from DVT1 DVT 1 一供没反馈问题 | LINK | 院长 |  | TCC FA link | 2.PCB | K.Houston
2024-09-19 | 4.EVT | 7.Sensor | 5.4 ALT | NA | NA | Issue：1pcs P-sensor no function in ATT drop ，D3 Rootcause：initial fail 。临时rework 装配问题，泡棉装偏了。 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-22 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | Issue S3: ATT drop 1.5M MIC2 no function 5 in 10 unit Rootcause：corner PCB crack （near MAIN camera ） Solution： 1.PCB外形加大0.2往camera，2.top增加一个小钢片用来加强板子。 import from DVT1 DVT1 第一轮ATT drop 没有发现相关问题。 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-29 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | Issue S3: Flicker FOV not very good in EVT ，~65 degree ，target 70 Rootcause： 材料和仿真的不是一个材质，PMMA-CM211-5‰ 均光粉 VS 仿真 NW432D ， solution：1. 打样NW432D ，角度到~80度，性能OK 负面影响：材料的外观颜色会更加浑浊，会影响外观 |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-27 | 4.EVT | 20.NFC | 4.Build | NA | NA | Issue S3: NFC FW 下载校验失败。NTF ~10% Rootcause： TBD solution： SW 改QC 默认驱动，DVT1导入 |  | 李果 |  |  | 6.No Change | K.Houston
2024-08-22 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | Issue S2: EVT ATT tumble WH180784 ，unable to power on:D8(500) （ID：N0QT060208） clue： 1.可以进入9008模式，认到口，但是Blankflash 失败。CPU认到，但是没有跑到memory部分 2.Uart log 确认，DDR 认到，但是没有认到UFS。 三星 8+128 memory 3.拆IC确认 点胶异常 Rootcause： UFS damaged 。 故障样品韩国分析，预计9/14前给报告。 solution：optimize underfill design ，import from DVT1 |  | 嘉琨 | 文亭 | TCC FA link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-23 | 4.EVT | 5.Camera | 3.Review/Simulation | S3 | Closed | Issue S3: houston Flash LED 出光孔位置和结构需要不匹配 clue：1. EVB基带自测闪光灯功能正常，EVT试产产线自测功能正常 2.EVT整机camera测试灯效，发现出光孔和Lens中心点不一致，偏心。 Rootcause： 1.结构需求未出给 2.硬件设计未确认到位。 solution： 1.临时方案： EVT rework 闪光灯板给camera测试Lens效果。 2. DVT1 修改PCB板设计 2.项目长期： 长期： 1）结构EVB根据Lens出光孔输出闪光灯摆放方向图纸给CAD，包含焊盘形状和出光孔标识，并且检查和验收主板设计闪光灯出光孔是否符合Lens出光孔的要求。若有闪光灯不同阶段的更换物料，也同样适用此条。 2）基带负责闪光灯按照结构的要求放置闪光灯，协助结构判断出光孔是否一致。严格遵守BB review 发版检查。 | Link | 芳梅 |  |  | 2.PCB | K.Houston
2024-09-02 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | Issue: EVT USB 默认参数眼图 电平过高 solution：调整SW 眼图参数，参考geneva 的参数修改，临时调试复测pass . 相关更改DVT1之前集成 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-29 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | Issue: 自测5台，4台出现 ANT7和ANT8的 N77&N78干扰后主摄像头 1）ANT7 N78 有preview failed和camera error found 2）ANT8 N77 preview failed Clue：log提示后摄MIPI error 实验: 1. 石墨片不动，去掉Inlay, pass 2. 去掉camera石墨片，裹紧Inlay, pass 3. 去掉camera石墨片，去掉Inlay上camera ring，裹紧inlay，pass Root cause: ANT7和ANT8 N77和N78 最大功率26dbm干扰到inlay camera ring和石墨片，两个同时存在就会有fail Solution： 修改石墨片形状，避开后置camera连接器区域， 负面影响：thermal 前置camera 发热较大，有风险。 但是DVT1 还是用这个作为主线 DVT1 二供 导入氮化硼对比测试 。 预计DVT2 thermal MCN 前决定用哪个方案。 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | K.Houston
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D2 -8KV air discharge at zone16(Aging10),Earpiece and Loudspeaker no function,recovered after reboot.D3 +8KV air discharge at zone1(Aging10),earpiece and loudspeaker no function,recovered after reboot， clue： 安排压测 50枪，不复现 Rootcause： TBD solution：EVT2 不复现 |  | 廖哲霖 | 院长 | WH180794 TCC FA link | 6.No Change | K.Houston
2024-08-21 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue S3: WH180794 ESD D1 mic1 and mic2 noisy After -8KV air discharge at zone16（rear camera） clue：can not reproduce ，安排压测 50枪，不复现 Rootcause： TBD solution： EVT2 ok |  | 廖哲霖 | 院长 | WH180794 TCC FA link | 6.No Change | K.Houston
2024-08-29 | 4.EVT | 5.Camera | 5.2 BB Test | NA | Closed | Issue S？: KP camera power noise 测试，主camera测试数据超标4.5（标准4） Rootcause：IMX896 sensor 问题，参考wrangler也是超过4， KP判断pass |  | 芳梅 |  |  | 6.No Change | K.Houston
2024-07-03 | 2.PCL | 7.Sensor | 3.Review/Simulation | NA | Closed | Issue S3: Flicker sensor & A+G sensor reuse I2C bus impact performance clue：1.houston First SOIS+Flicker on SM6450/SM6475 Rootcause：SOIS 占用了SM6475平台ADSP的所有接口 （一组I2C for OIS控制，一组SPI for OIS A+G 数据上传，以及 I2C 的A+G UI通道数据 for EIS）。其他所有ADSP端的sensor只能和A+G UI通道复用I2C. 一些极限场景会同时调用A+G UI 数据和flicker 数据，就会出现总线性能不足的风险（按照SME 的数据计算模式，可以确认同时调用A+G UI 数据和flicker 数据 无法满足 CTS 认证的 EIS 和 AR core 相关认证） 其他同期项目情况：paros 项目 OIS+flicker ，所以ADSP 接口资源够用，不需要A+G和flicker 复用I2C 抢总线。 需要解决问题：1.认证问题：EIS 和 AR core 相关认证 solution：proposal 1. AR core 测试camera 场景默认不开flicker sensor 。 EIS场景（录像？） 使用A+G SPI数据通道获取UI数据，SOIS （拍照物理防抖）场景再配置成 OIS需求数据模式。 ---Need SW camera team evaluate ，ongoing proposal 2. flicker sensor change to AP side。---need SW sensor & camera team evaluate ，ongoing （mey need HW rework base on boston ，waiting SW feedback） proposal 3. houston change main camera to OIS module （similar to paros）--没提上议程，毕竟我们目前的设计有很大的cost down ，如果回到OIS 方案，我们的costdown 就没了，以及会产生一些设计变更。在其他方案不可行的情况下，最坏情况下考虑这个方案。 | link | 小熊 | 文亭 |  | 6.No Change | K.Houston
2024-07-24 | 4.EVB | 1.Platform | 5.1 Bring up | S2 | Closed | Issue S2: SIM detection failed during the SIM bringup clue：1.SIM 波形分析发现 SIM IO/CLK 异常，VCC/INT 正常，RST没有串电阻无法测试 2.卡座飞线出来测试波IO/CLK /RST/INT/VCC 都正常，同时此时验证可以识别到SIM卡 Rootcause：卡座和卡托不匹配，新SIM卡座和老款SIM卡座的卡托不一样（旋转了180度） Solution： 1.临时方案： 将卡托rework 满足EVB调试（Done） 2.EVT PCB SIM卡座旋转更新（Done) EVT check ok | Link | 李果 | 文亭 |  | 2.PCB | K.Houston
2024-07-24 | 4.EVB | 3.Charging | 5.1 Bring up | NA | Closed | 二供快充bringup issue： Issue 1： 大概率 master CP I2c 访问失败。（表现是电流只有20+W） Rootcause： SC8541D的I2C地址选择pin 是E6 ，和BATN_SRP功能复用，链接到电池的C-上，在Vbat链接后200+ms内，就决定了I2C的地址。在扣合电池过程中，Vbat 和GND 大概率会比C-先上电（电池连接器的设计，防止C-先接触上造成其他问题），这样导致I2C是个错误的值（期望值是接地，实际是悬空了） Solution: 将master CP的 E6 和D6 都直接接到GND。 Issue 2： Master 和Slave CP的电流 差异值很大。超过2A以上（68W的期望值是500mA以内） Clue: slave CP的电流非常低，有时候只有1A以下，不正常。 Rootcause： SC8541D Slave 的C2756 多贴了 Solution: SC8541D Slave 的C2756 不贴。 跳贴表格进行更新 Houston 更改EVT导入 | link | 文亭 |  |  | 1.SCH | K.Houston
2024-10-29 | D.SHIP | 2.Power | 6.Issue | NA | NA | [s2]Issue:SOC not change ，always 60%-Wrangler aftersale Clue: 1. SW setting SOC to 60% and voltage to 4.2V when fuel gauge not work. 2. reassembly 2 units battery connector and issue gone. Root Cause: suspect battery connect issue.Why ？waiting for fail unit back Solution: | link | 文亭 | 李果 |  |  | J.Wrangler
2024-06-04 | B.PVT | 2.Power | 5.4 ALT | NA | NA | Issue: PVT MXC06 Unable to power on 4台 Clue:PMK_VREG_BB is only 0.5V at msm side and 1.2V at PMK7450 2pcs; VREG_SYS_1P8在PMK6450端电压为0V,在PM6450端电压正常，2pcs. Root Cause:PMK_VREG_BB 在Layer11平行屏蔽盖轨迹的地方断开 ； VREG_SYS_1P8在L11层往PMK6450方向屏蔽盖轨迹下断开 Solution: 加宽PMK_VREG_BB 在Layer11平行屏蔽盖轨迹这一段的走线； 加宽L11层VREG_SYS_1P8横向走线(未导入PCB) |  | 敏敏 | 文亭 | Link |  | J.Wrangler
2024-05-22 | B.PVT | 3.Charging | 5.3 EE DVT | S1 | Closed | Issue: WH178095 EDu15 Soft Shorts test After OTG 2 ohm resistance Soft Short,OTG no function and data transmission no function(10:37 5/20/2024),unable to recovery after restart.D2 Clue: in OTG mode Vbus is ok but USB not (ADB and fastboot can not work too in USB mode ) Root Cause: sub board TVS on USB D+ damaged （TVS502）. USBD+ is not related to EDU15 test purpose. (short Vbus to GND ,but not D+) suspect the tester mistake short Vbus to D+ . Solution: N/A ,monitor | link | 文亭 | 韩凯 |  |  | J.Wrangler
2024-05-09 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S1 | Closed | Issue: user feedback,录像状态下有主摄有异响 Clue:OISVDD电压3.3V高于模组要求的2.8V Root Cause: OISVDD电压3.3V高于模组要求的2.8V，为何回响camera KP分析中 Solution: change LDO to 2.8V output LDO（PN：SC98D62703） |  | 韩凯 | 敏敏 | link |  | J.Wrangler
2024-05-08 | 7.DVT2 | 2.Power | 5.4 ALT | S2 | Closed | Issue:MXC06 WH177228 Unable to power on:D1/D2(270） Clue:PMK_VREG_BB is only 0.5V at msm side and 1.2V at PMK7450 Root Cause:PMK_VREG_BB 在Layer11平行屏蔽盖轨迹的地方断开 Solution: 加宽PMK_VREG_BB 在Layer11平行屏蔽盖轨迹这一段的走线 |  | 敏敏 | 文亭 | Link |  | J.Wrangler
2024-05-07 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | NA | issue:Charging slow in DF |  | 文亭 | 德太加 | link |  | J.Wrangler
2024-04-03 | 7.DVT2 | 7.Sensor | 5.4 ALT | S1 | Closed | issue：Wh176592：DVT2一供ALT India 15kV AD capsensor Ch1 no function Clue1：ch1通路阻值异常，只有100ohm Clue2：参考通道下地电容耐压只有25V Clue3：上支架ANT1 LDS pattern距后盖缝隙很近（天线功率不足需要足够LDS pattern需要足够靠近边框天线） Clue4：R3708 短路 Root Cause：Ch1线路扛静电能力不足，能量从LDS进入冲击CH1 R3708，导致器 件单体短路，检测通路异常 solution： 2、L113 变更为21014050209（27pF，50V耐压） 3、改版主板，线路上增加一个TVS预留位 PVT验证 |  | 韩凯 |  | link |  | J.Wrangler
2024-04-03 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | issue: DVT1 2供 ESD Air -8K capsensor no function,recovery after reboot Clue1：上支架ANT1 LDS pattern距后盖缝隙很近（天线功率不足需要足够LDS pattern需要足够靠近边框天线） 厦门和武汉无法复现 |  | 韩凯 |  | link |  | J.Wrangler
2024-04-03 | 5.DVT1 | 9.Memory | 5.4 ALT | S1 | Closed | issue: Unable to enter system:D5(270) 3/26/2023, Clue: 1.按power键上电不保持 2. 按压memory 可以正常开机 rootcause: memory 虚焊，点胶不均匀，memory表面有胶水和屏蔽盖粘连，侧面无明显点胶量，转ME优化点胶 |  | 敏敏 | 嘉琨 | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
2024-04-02 | 5.DVT1 | 2.Power | 5.3 EE DVT | S2 | Closed | Issue:DVT LotX tumble Unexpected auto power off:D1（225滚） clue: 1. 不开机 2. 接上假电池(没有开机)，量测B_PLUS(VPH_PWR)电压及VBAT端的电流,VBAT上面每隔1s会有1.45A(MAX)的电流，把B_PLUS(VPH_PWR)从4V 拉到3.574V 3. 加焊后按压还是会自动关机，大概率还是PM8350B本体故障，寄回武汉做PM8350BH 芯片交叉验，问题依旧 4. PM7325有裂纹和破损，PM7325 VREG_SYS_1P8 ，BAB后，PM7325 VREG_SYS_1P8 电压正常，问题依然是不开机，但是由于板子变形严重，分析截止 |  | 敏敏 |  | LINK |  | J.Wrangler
2024-03-18 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | issue：DVT1 1st stack WLC 红墨水fail, 第二方案WLC 红墨水fail [s3]Issue ：DVT1 WLC 红墨水实验fail Clue：1. 脱落pin不影响WLC功能，功能检查正常，判断会影响充电性能，用户无法感知。 2. 两次实验，脱落位置不固定，第二页和第三页图示 3. stack板装配后虚空，怀疑在跌落或者震动的时候，stack板晃动导致wlc芯片部分管脚脱落 Solution： ME owner 基带看是否可以优化WLC的开窗，增加焊接面积 |  | 文亭 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
2024-04-01 | 5.DVT1 | 4.Audio | 5.4 ALT | S1 | Closed | Issue: DVT1 ALT 2供ALT跌落碰撞，USB板Speaker信号线串联的L303，L304 脱落 rootcause： 器件在板边，怀疑应力问题？ 另此类器件铜丝绕线到焊盘底部且二供焊盘0.8*0.3，一供0.8*0.4 solution: 1. L303.L304位置向板内移动，支线发版验证。 分析： 1) 结构壳体尺寸正常，未出现撞击的痕迹 2) 二供的焊接面会比一供小，如下图二和图三， 3) SMT工程师分析，二供的焊接正常，不存在焊接问题 4）一供器件焊盘0.8*0.4， 二供的器件设计焊盘0.8*0.3。二供器件焊盘小，会出现图二的问题。 器件实体焊盘如下图四，图五 5）此类器件铜丝绕线到焊盘底部，并且器件侧面不爬锡，SMT工程师反馈之前项目这种设计，线把底部顶起来发生过器件偏移和脱落。 |  | 院长 | 芳梅 | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
2024-03-29 | 5.DVT1 | 6.Display/Touch | 4.Build | S3 | Closed | Issue: DVT1二供组装，3台华星屏幕显示偏绿，KP反馈现象跟随主板 analysis: 1. 现象固定，此主板搭配天马屏幕ok, 搭配所有华星屏幕发绿 2. fastboot下显示ok， kernel 异常，怀疑有参数更改，监控从正常到变绿时，电压，帧率，MIPI clk均正常 3. AP mipi data 测试，相同主板，点白色图片。天马模组MIPI data 波形正常，华星模组MIPI data异常，说明使用华星模组时，AP有对白色图片进行处理。 样机寄送供应商分析： 1.IC bist画面测试，白色色坐标正常。---说明模组及相关设定正常。 2. 删除效果参数，偏绿没有变化。 3. 删除效果参数及校准文件，偏绿恢复正常。 4. 将校准文件重新写入，效果正常。 rootcause: 华星效果参数用错成别的项目，需要重新调试效果参数。DVT2已经导入新参数，目前未报问题 |  | 芳梅 |  | link | 4.Parameter | J.Wrangler
2024-03-07 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | Issue：front camera RCN value exceed standard analysis: rootcause: crosstalk from display solution: remove to KP yaocf1 |  | 邦邦 |  |  |  | J.Wrangler
2024-03-05 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | Issue：DVT1 CQA test camera0 N78 干扰测试failed , failure 1pcs (测2台)，批量数据待测 rootcause: MainCamera CPHY interfered from thermal graphite film coupled radiation of n78 on ANT9 solution: change the shape of graphite to avoid overlap the main camera connector fromDVT2 |  | 邦邦 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
2024-03-02 | 5.DVT1 | 10.USB-C | 4.Build |  | Closed | Issue: Sub usb Type-C连接器屏蔽壳对地短接的电阻被ANT删除，这6颗电容位按照最初讨论为DCM 贴电容，ROW 贴0R，ANT为兼容DCM和ROW公用天线，直接将ROW 这6颗本来贴0R 电阻 DNS掉 Rootcause ： 此6颗接地位需要和BB/RF一起商定贴片方案及铁壳接地方案，ANT在warroom上提出问题，但未收集到BB和RF反馈，直接修改方案 solution：DVT1 贴0R下地，ANT 优化天线设计， DVT2 因为DCM SKU删除，不需要兼容DCM，DVT2小板删除预留电容位，直接铁壳打孔接地-done lesson learn ；职责划分清楚，兼容部分涉及到更改，需要同步到ANT ,BB ,RF ,若需更改BOM，需要提交给基带进行修改 |  | 芳梅 | 文亭 | wrangler usb typec屏蔽壳接地方式评估 | 2.PCB | J.Wrangler
2024-02-21 | 4.EVT | 1.Platform | 5.4 ALT |  | Closed | Issue：EVT EMEA P+ESIM， Unable to read PSIM Card ， failure 4pcs （2 Alt, 2 xiamen ant ） Rootcause ：校准数据丢失 |  | liguoa |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
2024-01-31 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue：EVT EDU14 surge test fail on VBAT test point test ，200V fail. clue：B_PLUS short to GND Rootcause ：U1571 PM7350C damaged in surge test surge TVS layout is not best solution：Optimize Vbat TVS layout . monitor DVT1 test lesson learn: add Vbat surge TVS layout in checklist 。DVT1 pass |  | 韩凯 | 敏敏 |  | 2.PCB | J.Wrangler
2024-01-29 | 4.EVT | 3.Charging | 4.Build | NA | Closed | RISK：add WLC TX function，PCMCR：https://idart.mot.com/browse/PCMWRANGLE-7 Solution：Go with Option1 （1.PM8350B change to PM8350BH bacause PM8350B only support 5V haptic boost but PM8350BH support 10V haptic boost 2.add a loadswitch to get power from haptic boost，3.add TX Modulation and Demodulation component 4.DNI FW update power MOSs because can reuse haptic boost power from Loadswitch）. Change import from DVT1 。DVT1 ongoing ，TX function ok。detail tuning ongoing | link | 文亭 |  |  | 1.SCH | J.Wrangler
2024-01-29 | 4.EVT | 1.Platform | 4.Build | NA | Closed | Issue ：India P+P SKU SIM2 can't not recognized Rootcause： The VSIM2 power supply design is different in the S21 and S54K Solution：VSIM2 resistor is disconnected inS21 desgin |  | liguoa | 芳梅 |  | 1.SCH | J.Wrangler
2024-01-22 | 4.EVT | 3.Charging | 4.Build | NA | Closed | Risk ：SC8549D may not able to work ，About 30% on Glory&Aura Clue：1.incoming date Later than 20231222 lot should have problem 2.Wrangler EVT ：E03 35pcs， E05 8pcs firstboard ， E04 30+pcs use Old component ，should not have problem Others ~400pcs ，use new component should have problem. Issue ：india SKU firstboard 1pcs fail/total 3 pcs. sent fail IC to Vendor for analysis Rootcause：waiting for Vendor analysis solution ：change SC8549D to SC8541 from DVT1. PCMCR:https://idart.mot.com/browse/PCMWRANGLE-8 |  | 文亭 |  | glory 无法快充分析 | 1.SCH | J.Wrangler
| 4.EVT | 2.Power | 5.2 BB Test | NA | Closed | Issue ： power off current leakage 5.4mA clue: 1. fastcharger IC(VBAT2) can reduce 0.5mA maybe charging setting issue 2. charging Patch1 (CP related)： reduce 1mA . so there is other part issue too. Solution:update 310 continuous build,UI power off leakage=274uA |  | wuxm5 | 文亭 | 可能漏电器件汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | J.Wrangler
| 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | Issue ： camera PMIC bringup fail & Smart PA2 bringup fail Rootcause： I2C address conflict on Smart PA2 & camera PMIC 2 . both are 0x35 Solution：EVB rework ，solution ongoing EVT change smart PA2 I2C （have 4 I2C address option ） lesson：Need to add all the I2C component into Qwiki -I2C map page. and check if I2C address conflict happen when setup ,change ,add 2nd source. --- All Experts remind 1 time at the day before EVB gerber out---platform design owner |  | chenbang |  |  | 1.SCH | J.Wrangler
2024-04-23 | C.RAMP | 3.Charging | 4.Build | NA | Closed | issue: L2vision wireless charge CHIP ID fail. 1pcs Clue： PAT pass Rootcause：： Q2801 虚焊 |  | 文亭 |  |  | 6.No Change | G.Manaus NA
2024-04-23 | C.RAMP | 3.Charging | 4.Build | NA | Closed | issue: PAT wireless charging fail Rootcause：：1.一部分机器Stack 板子没装。这部分制程问题工厂处理--统计这几天有15pcs Stack 板子没装。 2.有两台机器是stack 有装，但是FW升级一直失败。 Q2803 虚焊 ，具体还有多少台 由产线统计及SMT参数修改解决。 | link | 文亭 |  |  | 6.No Change | G.Manaus NA
2024-04-15 | C.RAMP | 1.Platform | 5.3 EE DVT | S3 | Closed | Issue ：[Factory][TCC][OK2P]TCC AutoCycle Test，The Device can not power on .3 in 12 IKSWU-124341 Rootcause： 1.开机过程中GPIO79判断到高电平后，手机进入9008 导致不开机 2. ANT tuner U100（QAT5655）在超低温下（低于 -30 °c）逻辑异常 导致上电瞬间 DATA 输出高电平 。而该器件QC的温度 SPEC 范围是-30度~85度，我们的实验环境超过器件SPEC。 BB意见：这个是test issue，非用户实际issue，因为 issue 低于-30 °c温度下才会发生的， 而我们手机的工作温度SPEC is -20~60 °c . 其次保险一些就是SW加入 fuse 为固定开机点，不要受GPIO79的影响。（ 不能解决TCC issue，能解决用户万一超SPEC使用遇到的问题。） solution: proposal1.Workaround :Moto SW efuse Boot config to fixed 0100 .（1 unit RD test ok） | link | 文亭 |  | IKSWU-124341 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2024-04-11 | C.RAMP | 10.USB-C | 4.Build | S3 | Closed | Issue ：type-C port can not work after test (FOD、UCT、L2VISION). ~1% Clue1:power cycle can not recovery,reasembly battery connector recovery. Some component on VPH_PWR error. clue2: plug in Type-C analog headset can recover too. Suspect ：Audio switch control logic issue. clue3 : Rootcause： The Hi-z state of CC_out is not instability. solution: Pull down CC_out by gpio configuration | Link | 院长 | 文亭 | https://idart.mot.com/browse/IKSWU-126081 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2024-02-23 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | Issue ：[PVT]TCC ALT Test,shake test ,Unexpected auto power off,Power on only after charging.2 pcs loop5 1 time Clue1: log show PMIC PM6150C abnormal UVLO & BOB OCP found. clue2:Power on only after charging clue3 : same unit B1 show PM6150C abnormal LDOs &BOB both OCP (auto power cycle 1 time in loop2 Drop test IKSWU-80251). Rootcause： solution: monitor | Link | 敏敏 | 文亭 | IKSWU-81779 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2023-12-18 | 5.DVT1 | 5.Camera | 6.Issue | S3 | Closed | [S2]Issue: 产线装配后拍录像/播放竖线 ( ~ 2/300) clue: 拆机重扣之后，故障概率下降很多，十几次出现一次， 交叉模组实验，故障跟随主板 Exp1：Video record, 开WiFi，MIPI log 报错 rootcause: CPHY was interfered by wifi and n78 solution: Tuning CTLE EQ and CDR register |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2024-01-10 | 5.DVT1 | 8.PCB | 6.Issue |  | Closed | Issue ：Manaus NA DVT2 所有机器无线充电都不能正常工作。 Rootcause：E2001 位置焊盘没有开窗，虽然有钢网，但是E2001 器件贴不住。 导致Vout 不导通。 短期方案：rework 板子，恢复EVT的通路方案（刚好还预留，没有删除） | link | 德太加 |  |  | 3.BOM | G.Manaus NA
2023-12-20 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1 ALT A3(loop5)背跌 不开机 clue: 1.关机漏电流100mA+，无串口； Clue： 1.发热点：从背面看是PM8350B靠左边的位置，这部分是用电端，不是充电部分。（推测是马达，或者显示相关部分电源驱动器坏了），结合第7点情况，推测有可能是显示相关的电源部分有问题，外围器件等可能哪个出问题了。（推测：有可能是外围器件等坏了导致的烧坏IC） 2.确认PM8350B是故障IC，寄厂家QC进一步定位分析（分析具体是哪个模块坏了，以及是否可以看出是否有微小裂纹）；厂家分析结果：电性能烧毁，短路位置150,161,160---指向OLEDB 电源相关 3. 换了新IC屏不亮的问题，排差PM8350B外围的电路是否异常：检查下PM8350B OLED相关供电及器件是否OK（分析来源推测：是否会是外围问题导致IC烧毁？）-- 测量VREG_OLEDB发现对地短路，去掉这个网络上所有连接器件，依然是短路。推测是PCB本身短路，导致大电流烧毁IC。这个网络走线在L12 和L10.以及过孔。 4.板子到板厂时候测试发现短路不见了。寄回板子也是没短路，焊接上正常器件后，开机亮屏 Rootcause： 板子上有某些原因导致VREG_OLEDB对地短路引起大电流，最后将IC PM8350B的对应驱动电路也烧毁。 但是造成短路的具体是什么，目前无法考究，monitor 。万一有类似故障，关注短路原因 Solution：Monitor | link | 文亭 |  | TCC analysis | 6.No Change | G.Manaus NA
2023-12-18 | 5.DVT1 | 5.Camera | 6.Issue | S2 | Closed | [S2]Issue: 主摄Slowmotion出现横条纹 clue: Exp1：新版本U2UAN34.11 OK Exp2： rootcause: SW Issue solution: |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2023-12-13 | 4.EVT | 10.USB-C | 5.6 User Feedback | S3 | Closed | Issue ： USB can not connect sometimes-Manaus NA Clue ：1.when it happen ，it last for a long time and can reproduce when replug USB on phone 2. it can be recovery by replug USB on PC . 3.it can be recovery with CID pin connect to GND on phone . 4.it is hard to reproduce after phone power cycle. 5. after power cycle, 3 units keep not move ,after 1.5hours ,1 unit reproduce the issue. 6.log ：it is in host mode Rootcause： SW logic error Solution： change SW and recheck ok | link | 文亭 |  | IKSWU-34055 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2023-11-17 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S2]Issue: EDU03 WH169432 Rear flash light always on , and could not recover:D2/D6(15KV,zone14）, clue: PM6150C BOB short Exp1：Flash 导电泡棉没有接地（盖在石墨上），ME将下接地该区域避让开。 Exp2： rootcause: Flash 导电泡棉没有接地，导致PMIC被打坏 solution: 石墨接地位置区域避让开 | Link | 韩凯 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | G.Manaus NA
2023-10-19 | 4.EVB | 5.Camera | 5.1 Bring up | S2 | Closed | [S2] EVB3 Main Camera IMX896 Bringup, preview stuck Analysis Exp: 1. IMX896 is OK on boston (SM6450) 2. OV50A with CPHY 1.9Gsps failed on both EVB1 and EVB3 3. IMX896 failed with 0.9/1.9/2.4Gsps on both EVB1 and EVB3 4. smoothly preview under heating board, while stuck preview under cool board 5. IMX896 works well on front and wide camera MIPI path 6. smoothly preview while add extra power supply in parallel with S2B/S3B/S4B 7. IMX896 works well with C1515 removed rootcause: GND return path of PMIC Buck S2B/S3B closes to MIPI CPHY Vias solution: change MIPI traces fanout frome layer 6 to layer 4 | Link | 邦邦 | 院长 |  | 2.PCB | G.Manaus NA
2023-09-20 | 4.EVB | 3.Charging | 3.Review/Simulation | S3 | Closed | Risk：EVB3 simulation ，Master & slave charging patch impedance not match ,delta 3.1mR VS <2mR （desired value） Rootcause： slave battery connector is too far away from charge pump because of RF placement limitation. & No place for double width of Vbat2 layout. Solution： 1. decline width of master Vbus wire to 2mm. & add some coper for Vbat2 . Simulation ongoing ，import from EVT 2. battery have some delta design for Manaus NA （if it is used in Manaus NA only，it shoule be ok . but if reuse other project`s ,may have problem） |  | chenwt |  |  | 2.PCB | G.Manaus NA
2023-09-20 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | Issue ：dead battery Wireless charging fail Clue ：modesel go to 1.2V at about 2ms after wireless Vout on .it cause Vout off. repeat Rootcause： WCHG_DET output high to CPU cause modesel go to 1.2V (current leakage ) . Solution：1. change WCHG_MODE_SEL to PMIC PM8350B GPIO_o4 ,import form EVB3 -EVB3 recheck ok 2. add 10KR on WCHG_DET ,import form EVT | link | chenwt |  |  | 1.SCH | G.Manaus NA
2023-10-24 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | NA | [S3] Issue： EDU14 WH168701 , D1 After 150V surge pulse test,Cannot charge phone by USB. Clue： 1. RD can not reproduce when get D1 exp: D1 do test again Root Cause: 1. Monitor Solution: TBD | link | 韩凯 | 文亭 |  |  | #N/A
2023-10-24 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Monitor | Issue ：Type-C Shell case connect to SUB PCBA GND (JP SKU DCM require Type-C Shell case dont connect to GND） Rootcause： Type-C Shell case fix part connect to middle housing Solution：PCB：sub PCB dont design soldermask under type-C fix part. （螺丝孔） ME proposal 1 ： ME proposal 2： |  | 李果 | 文亭 |  |  | #N/A
2023-08-19 | 1.Concept | 2.Power | 1.4 Solution | S3 | Closed | Issue ：storage time with power can not match Docomo requirement. 来源：Manaus -Eng【24夏スマホ】機能一覧表1.0版(Function list)这份文件，① 24 Summer Main specification 页面的157行 A period of 27 months or more must be secured from factory shipment to overdischarge Rootcause： poweroff current around 300uA PCBA +50uA battery=350uA ,can only support 8month storage with power Solution： go with Shipping mode. which is about 50uA PCBA +50uA battery=100uA MAX ,can support more than 27months. |  | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | #N/A
2023-11-10 | D.SHIP | 10.USB-C | 5.3 EE DVT | NA | NA | [s3]RISK：TCC test 5% Nacl 溶液相对容易造成Type-C 腐蚀 Clue：1.XM test 5% Nacl 溶液填满Type-C连接器 很大概率会触发OTG，刚开始周期性触发，最后就一直触发着。 2.对比 QC平台的bronco 项目，XM test 5% Nacl 溶液填满Type-C连接器，就很难触发OTG？ Next action： 抓出CC和Vbus 波形及对应的log，创建CR ，寻找MTK支持一起分析 及找可能得改善方案 Rootcause ：TBD solution：TBD | link | 浩总 | 文亭 |  |  | F.Manaus Row
2023-08-14 | B.PVT | 7.Sensor | 5.3 EE DVT | NA | Closed | [s2]Issue: chopchop fail when phone deeply sleep Clue1：Latch time locked and not change Root Cause: 1. MTK SCP work abnormal in deep sleep Solution(Work around): 1.Change A+G INT mode to level trigger | link | xiongsn1 | liguoa |  |  | F.Manaus Row
2023-07-20 | B.PVT | 7.Sensor | 5.3 EE DVT | NA | Closed | [s2]Issue: CH0 fasle trigger in DVT2 on AW96308 , when holding TOP ant Clue1：Semtech is ok Root Cause: 1. Noise larger than threshold of CH0 due to amplitude too big to meet long distance detection 2.1 IC performance limitation 2.2 ANT Sporton tests require a very long distance for CH0(24mm back) Solution: 1.Vendor optimising with parameter |  | xiongsn1 | liguoa |  |  | F.Manaus Row
2023-07-20 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [s3]issue:ALT WH166331 C1 After -1 out of 2 Unable to find NFC device/read SIM Card C1（15kv） Clue1：issue happen only once Clue2：not produced in stress test on vsim1_vcc Root Cause：1、SIMIO1 of NFC IC SN220 damaged solution： 1.1st source +2nd source SIM tray fail , Will do SIM tray ABAB DOE by 7/24 2. Running change with SWP Add TVS in MP |  | Hankai | 李果 |  | 3.BOM | F.Manaus Row
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]issue:DVT2 :EDU03 SIM card insert detected fail,NFC no function(1/6) Clue1：issue happen only once Clue2：not produced in stress test on vsim1_vcc Root Cause：1、Vsim1_VCC of NFC IC SN220 damaged 2、proposal poor grouding that related to P2I which was introduced on DVT2 solution：1、update 3 more clean area of SIM subboard 2、change C414 0.1uF cap to TVS |  | Hankai | 李果 |  | 3.BOM | F.Manaus Row
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue： EDU14 WH165529 ,DVT2 surge 200V fail，OTG &fastcharging can not work Clue： 1.fail unit Log show PD can not work .& Ibus=0 when Ibat =~2A. 2.DVT2 all build with P2I. DVT1 without P2I. Root Cause: 1. MT6375 damaged （replace a new MT6375 ，function,ok）. Proposal 2 ：poor grounding related to P2I which import in DVT2 Solution: ME update 3 grounding more clean area of USB Board after P2I | link | Hankai | 文亭 | 实验汇总表 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | F.Manaus Row
2023-06-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue： EDU14 WH165555 ,DVT2 surge 200V fail，OTG &fastcharging can not work Clue： 1.fail unit Log show PD can not work .& Ibus=0 when Ibat =~2A. 2. use 2nd source Surge TVS 3.DVT1 &DVT2 bosth 2nd source Surge TVS test result bad than 1st source TVS Root Cause: 1. MT6375 damaged （replace a new MT6375 ，function,ok）. 2 ：poor Surge TVS cause higher Voltage go to MT6375 Solution: remove 2nd source Surge TVS ，from PVT .BOM change done | 实验汇总表 | Hankai | 文亭 |  | 3.BOM | F.Manaus Row
2023-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | NA | [s3]issue:EDU03 WH164325 2nd NFC unnormal clue: root cause: solution: |  | Hankai |  |  | 6.No Change | F.Manaus Row
2023-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]issue:EDU03 WH164325 2nd SIM card insert detected fail Root Cause：SIM1_INT pin short to GND solution：ADD TVS on DVT2 ,TCC Validated Pass | link | Hankai |  |  | 1.SCH | F.Manaus Row
2023-05-22 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]issue：DVT WH164184 D4After -15KV air discharge at zone9,SIM card is broken. Analysis: 检查SIM接地良好 Root Cause: solution： 1、SIM_IO pin 增加tvs（DVT2导入） 2、SIM卡座接中框泡棉改用导电布 | Link | Hankai | 李果 |  | 1.SCH | F.Manaus Row
2023-04-21 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:TDD Noise Found in EVT Root Cause:1.Receiver Affected by Magnetic Field of GSM-PA which is closed to Receiver 2.1 Multimode RF PA cannot meet the TDD design rules-RF Solution: 1.Add audio switch design for optimization validation | Link | 院长 | 院长 |  | 1.SCH | F.Manaus Row
2023-04-17 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]issue：EVT WH163350 D3 After -15KV air discharge at zone8,Unable to detect SIM Card，unable to recovered Analysis: 检查SIM接地良好 Root Cause: solution：SIM1 IO 串联33R电阻 | Link | 邹仕海 | 李果 |  | 1.SCH | F.Manaus Row
2023-04-18 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S1]issue：EVT WH163344 1 pcs 背压第9点界面异常，第11点时不开机 Analysis: 1.样机未复现故障现象 2.之前出现故障前出现安卓小人界面，怀疑死机导致，SW 抓下log 进一步分析 Root Cause: solution： | Link | 邹仕海 | 敏敏 |  | 6.No Change | F.Manaus Row
2023-05-22 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3]Issue: Cap sensor no function on D2 post Root Cause: Poor SMT soldering Solution:Re-weld to restore normal,SMT optimization | Link | Xiongsn1 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | F.Manaus Row
2023-05-15 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3]Issue: CH1 fasle trigger in DVT1 on AW96308, Semtech EVT ok Root Cause:1. CH1 diff value affected by hand holding bottom of the phone Solution: 1.Vendor optimising with parameter |  | Xiongsn1 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | F.Manaus Row
2023-05-11 | 5.DVT1 | 6.Display/Touch | 6.Issue | S2 | Closed | [s3]SGM Release FCN that mention SGM3837 OLED Driver Frozed,Change to Novatek. Root Cause: SGM3837 出货有0.3%芯片本体损坏，导致整机会在VBAT上有漏电流，供应商数据10mA+ 影响度：量产项目： london na 无影响，London Row 13K , Juno 5K 试产项目：munaus 5G DVT1 1K 主板 , ODM XXX 项目 solution：1. 冻结所有在库SGM3837物料，退货处理。 2. 量产项目主板和机头进行sorting方案，挑选异常 主板方案： MMI夹具上分别测试主板漏电流 和主板+屏漏电流。 Juno 漏电流大于0.5ma的有16pcs/2882pcs=0.555%（16pcs中有12pcs漏电流大于10ma，12/2882=0.416%） 整机待定： 3.manaus 5G 主板sorting方案： 挑出>=0.5mA 漏电流主板 4. 圣邦之后供货初定3K，联想SMT后做sorting。 | Link | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | F.Manaus Row
2023-04-01 | 4.EVB | 2.Power | 5.4 ALT | S3 | Closed | [S1]issue：结构摸底测试中出现电感脱落（没有屏蔽盖） Analysis: 1. 厂家同批次验证，未发现焊盘脱落现象。 2.EVT 麦捷验证，未出现脱落现象。 3.EVT 太诱TMO 跌落中未发现脱落现象。 Root Cause:EVB没有贴屏蔽盖，可能是导致整机应力异常 solution：后续跌落实验室继续跟踪，有问题再重新提出 | Link | 敏敏 | 李果 |  | 6.No Change | F.Manaus Row
2023-04-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S2 | Closed | [S1]issue：EVT WH163330 C2 After +8KV air discharge at zone3/9/15,Drop call-GSM（连接仪器下） Analysis: 实网下测试正常 Root Cause: 可能匹配未调试导致 solution：跟踪DVT1后续实验，有问题再重新提出 |  | 韩凯 | 李果 |  | 6.No Change | F.Manaus Row
2024-01-25 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | issue : London NA WLC can not work after rework stack board | link | 文亭 |  |  | 6.No Change | E.London NA
2023-06-27 | B.PVT | 3.Charging | 5.6 User Feedback | NA | NA | issue :DF charging slow |  | 文亭 |  |  | 6.No Change | E.London NA
2023-04-06 | B.PVT | 1.Platform | 5.6 User Feedback | S3 | Closed | [s3]Issue:abnormal power off during charging, 3 units till now,1 time/month . Clue:MT6363 POFFSTS[0xD]=0x8800 Clue:check vbb quality, Result:.vbb with big margin ,hw low risk Clue:Shut VBB through I2C Intentionally, Result:Not matching Clue:Heavy switch working mode(PFM/PWM) of VBB , Result:No issue Clue:Simulate Vsys and VBB Shut down, Result:Not Matching Clue:Run in 2400 units and check，Result:No Relative issue found Root Cause: 1.VBB Dip and trigger UVLO under extreme High Peak Current. Exp1.1 Force VBB Dip to 2.15~2.5 V@~4.5A，Result: Reproducing 0x8800 Exp1.2 Set UVLO to 2.0V and Draw 4.5A , Result:No Issue Exp1.3 Set UVLO to 2.4V and Force VBB Dip to 2.45V , Result: Phone Working Fine. Exp1.3 Set UVLO to 2.3 and Force VBB Dip to 2.35V , Result:Phone Working Fine. Exp1.4 Set UVL to 2.9V , Result: Dfer Reproducing rate increase 30 times/Month 2.SGM BOB PowerGood Trigger Solution: 1.Set MT6363 UVLO Value to 2.4V from 2.6V, Suggest to import asap and monitor DFer Data. 2.Restart when MT6363 POFFSTS[0xD]=0x8800/0x8000 confirmed in bootloader @charging boot up. | link | 敏敏 | 文亭 | 故障list汇总 | 4.Parameter | E.London NA
2023-04-06 | B.PVT | 1.Platform | 5.6 User Feedback | S2 | Closed | [s2]Issue:London NA unexpected reboot clue: Power off reason[PMIC][0xD] reg=0x40 which mean power cycle due to Long press powerkey 1.Suspect Power key stuck solution: change Key to panasonic 。monitor | link | 文亭 | 敏敏 | 故障list汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-05-08 | C.RAMP | 1.Platform | 4.Build | S3 | NA | Issue ：Pilot ORT 1pcs auto power off@Mxc06 40 tumbles ，D1，https://idart.mot.com/browse/IKSWT-137715 Clue：Log show[PMIC]POFFSTS[0xD]=0x2 ,means some power OCP or OVP. Clue.X- ray 查看之前CPU屏蔽盖风险点，看起来OK,没问题 Clue.故障机 看到气压计本体的盖子脱开了，掉在旁边的受话器磁钢上。（有磁性） Solution: 鉴于这台机器fail一次 ，项目整体的滚筒实验中也没有，风险度较低，monitor。 单体寄给厂家分析， Tracking 厂家单体分析，看是否有更进一步线索。 | link | 小熊 | 文亭 |  | 6.No Change | E.London NA
2023-04-17 | B.PVT | 10.USB-C | 4.Build | S2 | Closed | [s2]Issue: London NA PVT 耳机插拔压力测试，概率性无法识别，重新插拔ok，总不良率：0.4% （5/ 1240 ） SW CR:IKSWT-115443 ，log 判断有插入拔出事件 4/17 chenwt：目前log 分析 及 RD 实验室模拟，这属于连接性问题。 实验过程：先插入耳机，识别好耳机，然后断开一根CCpin 链接，之后就设备就不认了。 （如果再接上这根CC，就会再认到。 ） 这样模拟的log 和 issue 的log 一模一样。 转KP xiongxiong跟踪。 还有DVT2 时候IKSWT-92056 看着有些类似。 DVT2 一例接近100%复现的，log一样。 xiongxiong分析结果是 Type-C 连接器上有一层赃物，但具体是什么，不清楚。 action：PVT 继续确认下故障机，看下是否也有类似的问题。" Pilot 测试都ok，close |  | 文亭 |  | IKSWT-126520 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-03-21 | B.PVT | 12.EMC | 4.Build | S2 | Closed | [s2]Issue:PVT WH162948 D2&D4 TRP fail clue:stress test on ANT spring with tuner code control ，reproduce clue:Ant -> Funer :1.3nH->0R rootcause: 1.Tuner U100 damaged by ESD ，from ANT spring exp: C102 add ATVS ，RD test 4 unit ok with tuner coder 2.P2i destroy the grounding between sim board and usb board in PVT. solution:1.use non p2i usb board | link | 韩凯 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-03-01 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [S1]issue：WH161516- Main band48 No camp - LTE:D3/D4 Root Cause: 1.D3 band48 RX1 of FX6880(Switch PA) damaged、D4 band48 RX0 of FX6880 damaged 2、DVT2 LDS pattern changed in order to pass certification，may increase ESD risk exp：1、change FX6880，result：RF confirmed chip damaged （2023/03/03） 2、add TVS to ANT4、ANT2 result：研发自测ok action :rework 5 unit for retest in TCC ,from 3/9 . solution：add TVS to ANT4、ANT2 ，PVT import PVT reproduce ANT5 1unit fail solution：add TVS to ANT5、ANT7 & more RF component protect . PVT 二供 pass | link | 韩凯 |  | 故障汇总 | 3.BOM | E.London NA
2023-04-03 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S2 | Closed | [s2]Issue: Back camera cannot take pictures clue: rootcause: Not correctly connected after mic seal verification by ME exp: solution: | Link | 邦邦 |  | https://idart.mot.com/browse/IKSWT-116698 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-03-25 | 5.DVT1 | 5.Camera | 5.6 User Feedback | S2 | Closed | [s2]Issue: Rear main camera fail to open clue: rootcause: repaired, DVDD LDO bias short to GND leads to trace open exp: solution: | Link | 邦邦 |  | IKSWT-113215 | 6.No Change | E.London NA
2023-03-21 | B.PVT | 12.EMC | 4.Build | NA | Closed | [S3]Issue:1:PVT NFC test fail rootcause:1.Extra NFC Ant Discreat Component SMT on Stacking Board duo to not in DNS List. 2.Those DNS Part was removed and not adding back. Solution:1.removing DNS Part | link | 芳梅 |  | link | 3.BOM | E.London NA
2023-03-21 | B.PVT | 12.EMC | 4.Build | S3 | Closed | [S3]Issue:1:PVT USB can not used rootcause：TVS507&TVS508 orientation error due change from dual orientation TVS to signal orientation TVS but without orientation mark on build file Solution:1. rework TVS507&TVS508 2、update build filewith orientation mark of TVS507&TVS508 ，done by 3/22 | link | 韩凯 | 文亭 | Link | 2.PCB | E.London NA
2023-03-06 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S2 | Closed | [S2]Issue:1:DVT2 TRP error rootcause： ANT0 tuner damaged Solution:1.add mylar under LDS ，PVT import 2、add TVS on SIM board，PVT import PVT issue reproduce ，reissue it | link | 韩凯 |  |  | 3.BOM | E.London NA
2023-02-24 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:D1 All capsensor no function 2023/2/22 Root Cause： 1.Mylar was sticked uncorrectly，SX9375 exposed to the BTB connector 2.Mylar sticked artificially Solution：Import fixture to locate mylar , ME Planed DVT2 2nd source test pass PVT move capsensor far awar from camera connector | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-02-03 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | Issue: Temp / Humidity and Temp Cycle ， ALT drop 3units( 3/12) flash led no function. Root Cause: 1.2rd sourcing vendor flash led FPC ，LED SMT poor welding, need fpc vendor PBH improve DVT2 fail too Root Cause: 1. The heightening of the sea ring leads the flash FPC poor contaction, After opitimizing the structure， not find the issue in PVT. | link | 芳梅 | 川叔 | FPC vendor PBH analysis report | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-02-22 | 7.DVT2 | 4.Audio | 4.Build | NA | Closed | [S3]Issue:[LondonNA][Factory][CQA1][DVT2] When inserted the headset to phone, the phone hasn't recognize the earphone micphone NTF | IKSWT-92072 | 院长 |  |  | 6.No Change | E.London NA
2023-02-22 | 7.DVT2 | 10.USB-C | 4.Build | NA | Closed | [S3]Issue:[London NA][Factory][UCT][DVT2]USB_HOST GET_USB_HOST_MODE_STARTS Fail NTF solution：update test recipe for polling mode and issue not found | IKSWT-91107 | 文亭 |  | MTK CR | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-02-27 | 7.DVT2 | 3.Charging | 4.Build | NA | Closed | [S3]Issue:[London NA][Factory][BT][DVT2]BATT_CURRENT_CAPSWITCH_CHARGER_ Fail NTF solution: 1.加retry ，每次retry 增加0.1V，并在每次retry 都是Ibus 测试完直接测试Ibat 。 2.低门限放宽一些，从2.5A改为2A | IKSWT-95557 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD WH160481 D6 NKCT130135 ANT :EIS degradation exceeds 3dB, and TIS value out of spec(LTE Main_Band5):D6 final test rootcause：ESD -》ANT0—》ANT0 spring—》ANT0 TVS—》ANT0 Tuner damaged 。ANT0 TVS layout not good enough . Solution: 1. change SIM board layout，import from DVT2 2nd source build，monitor DVT2 2nd source test pass | link | 韩凯 |  | 故障汇总 | 2.PCB | E.London NA
2023-01-09 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | [monitor]Issue:TMO drop WH160497 D6 NKCT130126 Unable to enter camera mode:D6(5) Rootcause ： 1.Unable to enter camera mode/no audio function : U4153 damaged ，should be SMT issue or component issue .(MP component ) 2.Send Unit to Vendor ,monior DVT2 no reproduce | link | 院长 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-30 | 5.DVT1 | 4.Audio | 5.4 ALT | NA | Closed | [S3]Issue:WH160519 NKCT1E0116 Earpiece no function/ Loudspeaker no function/ Cap/SAR sensor no function/No vibration:C1 in initial(before Drop test) Clue:I2C reading audio parts are ok . From log check :capsensor initial fail block audio SW initial Root Cause:1.Capsensor Damaged Solution:1.NA |  | 小熊 | 院长 |  | 6.No Change | E.London NA
2023-02-03 | 5.DVT1 | 1.Platform | 6.Issue | S3 | Closed | Issue: London NA can not rampdump IKSWT-66439 Next A2+ (MT6879V/TZA) / /London NA // T //echo c > /proc/sysrq-trigger,Failed Clue： EVB ，EVT，DVT1 all can reproduce 100% Tesla MP & some PVT units fail too. EXP：Swap CPU with Tesla DVT2 chip ，and issue gone. Issue Follow CPU solution： MTK provide a patch and Solve the issue | link | 文亭 | 敏敏 | IKSWT-66439 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-30 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | Issue:WH160519 B3 NKCT1D0011 Unable to enter system:B3(1)-TH/TC Clue： Rootcause: 4 units all recovered after recharging the battery. Low battery leads the phone can't enter system. monitor | link | 芳梅 | 文亭 |  | 6.No Change | E.London NA
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD WH160481 D3 NKCT130197 NFC NFC no function 1. ESD from MIC3 hole （add from DVT1） -》NFC ANT spring-》NFC IC damaged Solution: 1.ADD TVS on NFC ANT spring DVT2 test ok | link | 韩凯 |  | 故障汇总 | 3.BOM | E.London NA
2023-01-20 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:1:ESD all Cap sensor no function,unable to recover:D2(15KV,zone1)/D4(15KV,zone16)/D5(15KV,zone12) 2:All capsensor no function,CH1&2&3&4 recover after reboot,CH0 unable to recover.D1(15kv,zone4） 3:Capsense(Ch2) no function,recovered after 15min:D6(15KV,zone4） Root Cause: 1.Ch0,Ch1,Ch2 of SX9375 Damaged through Wide Angle Camera and camera ring Exp1: Well Grounding of Wide Camera ,ESD No issue, Same unit, Isolate Wide Camera Grounding ,Reproduced Exp2:Add anti-esd film on cap-sensor area. Result: verifed pass. Solution: 1.Add anti-esd film on cap-sensor area. rd verifed pass. TCC validated Pass DVT2 2nd sourcing test ok | link | 韩凯 | 小熊 | 故障汇总 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-09 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue ESD WH160450 Cap/SAR sensor no function:C1(15KV air） Root Cause: 1.SX9375 damaged Exp: REF_CAP_ANT0_2 shorted to GND Exp: recorverd after changing SX9375 2.ESD Path Analysis ,by 1/16 solution:add TVS on main board (near cap sensor) ，import from DVT2. DVT2 2nd sourcing test ok |  | 韩凯 | 小熊 |  | 3.BOM | E.London NA
2023-01-09 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [Monitor]Issue:build 7pcs can not download clue:remove CPU shielding case SH4309 and ok ,remount shielding case and ok too . R1601，C4411，C4416，C4478 are the High risk point base on the X-ray Root Cause : suspect some cap short to CPU shielding case SH4309 due to shielding case tolerance . Solution：1. ME control CPU shielding case SH4309 tolerance . 2. change PCB to provide more margin space for Risk components ,From DVT2 DVT2 ok | link | 文亭 | 敏敏 |  | 2.PCB | E.London NA
2023-01-12 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue :WH160450 ALS、PS No function A5(5) Root Cause: P-sensor damaged Solution： change PCB outline near P-sensor 。（Y+0.15mm to protect sensor componnet）,DVT2 import ,monitor | link | 小熊 |  |  | 2.PCB | E.London NA
2023-01-09 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue WH160450 No Main display B2(2) B4(3) A5(2) ,recovered after pressing power key repeatedly clue：all recovered, 1 times/4 units from 10 units Analysis:1/20 No available log ,4 units log no match log found in the phone after get the phone 1/31 new log shows，phone sleeps in when fingerprint HBM mode ,that leads no display，it's a SW bug. 2/1 can reproduce the issue at xiamen, phone sleeps in when fingerprint HBM mode ,that leads no display. next action:ALT test ,turn off fingerprint hbm mode Root Cause: NA | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-11 | 5.DVT1 | 5.Camera | 5.4 ALT | NA | Closed | [S3]Issue WH160450 Rear camera viewfinder has noisy points:A1/A2/A6(1)-TH/TC Root Cause: not reproduce in XM。 try to reproduce but can not reproduce |  | 邦邦 |  |  | 6.No Change | E.London NA
2023-01-11 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue WH160450 Cannot charge phone by induction A2(5) ，A1(5) Root Cause: wireless charge coil FPC assembly issue : Spring can not contact to the FPC finger .Assembly issue solution：Assembly issue ，ME tracing assembly quality | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-09 | 5.DVT1 | 1.Platform | 5.4 ALT | NA | Closed | [na]Issue WH160450 Unable to read SIM Card:B5/B6(1)-right Clue：replug SIM card and recovery Root Cause：1.get SW log for recheck 2.tear down phone for short risk check by ME No issue found。 reproduce：drop and SIM tray drop out a little and No SIM，can reproduce ，ME issue . Solution :ME Own |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2023-01-09 | 5.DVT1 | 4.Audio | 5.4 ALT | NA | Closed | [na]Issue: TMO drop WH160497 D6 NKCT130126 no audio function/no vibration(25)/unable to detect SIM card(29)/2nd L-sensor no function:D6(56) Root Cause:1.Stack connector damaged lead to failure ,ME tracking | link | 院长 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2022-12-08 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]Issue TDD : receiver mode . Root Cause: Up SPK PA Capacitor noise Solution ： change to Low noise Capacitor ,import in DVT1 . DVT1 retest and similar to tundra ，acceptable |  | 院长 |  |  | 6.No Change | E.London NA
2022-12-05 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [s3]Issue: WH159074 TMO Drop 10:Unable to power on:D5(47) rootcause: ：1、high PCB Strain 2、low inductor anti-strain capability, Taiyo Engineering Sample Solution:change PL2301,PL2318,PL2319 to microgate MP inductor,import in DVT1 [s3]Issue 2.1.2 : WH159076 ，ATT DROP， Unable to power on:D1/D14(1.25m),D5/D6/D9/D11/D13(1.5m）,D12/D15(1m) rootcause & Solution: same as WH159074 D5 DVT1 no reproduce so far 1/12 | Link | 敏敏 | 文亭 |  | 3.BOM | E.London NA
2022-12-05 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S3]Issue 2.1.1: build ，NKCN040279 NKCN050156 NKCN040229 not power on Clue：connect J2702 and big current。remove RF DCDC shielding case and ok . rootcause: RF DCDC shielding case short to C2745 & C2744 Solution ：change RF DCDC shielding case from DVT1 -ME 。DVT 1 no issue found | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2022-12-05 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: WH159074 TMO Drop 1:Proximity sensor no function,recovered after reboot:D1/D3/D4(14),D2/D5(28 rootcause: suspect no P-sensor parameter optimize , optimize it in DVT1 SW . monitor DVT1 and no issue so far 1/11 |  | 小熊 |  |  | 4.Parameter | E.London NA
2022-11-29 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue: Wide camera power noise rootcause: Low frequency radiation interference from BOB power in light loading PFM mode solution：1.set BOB in forced-PWM mode when camera open, PFM mode when exit camera app. RD Verified Pass 2.optimize BOB VSYS layout， far away from Wide camera module as far as proposable. DVT1 PCB import （PCB change improvement is similar to SW change） | Link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2022-12-08 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | [S3]Issue ：EDU03 WH159065 D3 After -8KV air discharge at zone9(Aging10),Mic1 and Mic2 no function,recovered after reboot.(only once not count 2022/12/6 15:09) rootcause: N/A Solution ： Monitor |  | 韩凯 |  |  | 6.No Change | E.London NA
2022-12-08 | 4.EVT | 4.Audio | 5.1 Bring up | NA | Closed | [na]Issue 12/13 SW版本开机后马上自动关机。 rootcause: 报电池温度70度所以高温自动关机。从EVB 到EVT SW 上面 电池NTC 都从 Fuelgauge IC 内部的集成NTC读取而未从我们要使用的 FPC上的NTC读取， 12/13 SW Yuechai 提交的更改 将Fuelgauge NTC读取 切换到产品要用的 FPC NTC读取 。 结构设计上有短路，短路点在小板上 的一个金属压板支架 和备用的NTC电阻焊盘 Solution ：SW 当读取的FPC NTC 大于等于70度，自动切换到Fuelgauge NTC HW 删除SIM小板上备用battery NTC位置，避免结构压板金属件短路 ，From DVT1 |  | 林峰 | 文亭 |  | 1.SCH | E.London NA
2022-12-05 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: WH159076 ，ATT DROP， Unexpected auto power off.D1/D5/D7/D11/D12/D13(1m) rootcause: waiting for unit back to XM [S2]Issue: WH159074 TMO Drop 8:Unexpected auto power off:D4(4) rootcause: SW issue Sometimes press the power button a few times and it will automatically shut down | IKSWT-51733 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2022-11-21 | 4.EVT | 8.PCB | 4.Build | S3 | Closed | [S3]Issue: Factory SMT build found SMT Stencil not match PCB for SUB USB Board rootcause: 1、In PCB design, the ORGB position was not updated, which led to component position drift during panel assembly. 2、The PCB factory adjusted the data according to its own experience to what it thought was reasonable, but did not give us feedback. The factory directly produces according to our actual output information. The steel mesh and plate do not correspond 3、Data conflict in EVT USB board assembly design solution： 1. Do not paste the offset part. Used for assembly verification of the first version 2. Urgent fabrication of SMT 3. Change Panel design lesson learn : 1. Update in《 PCB 拼板 Step by Step》， to improve the inspection process. 1. During the assembly inspection, check whether each layer is complete; Check that the position is correct. 2. the TGZ file completed by valor assembly will be sent to CAD colleagues for inspection. | link | 太加 | 艳红 |  | 2.PCB | E.London NA
2022-10-21 | 4.EVB | 5.Camera | 5.1 Bring up | S3 | Closed | [S3]Issue: Sois can not work rootcause: Sois I2C Pin Swap （KP output wrong SPEC when design & review） solution： correct EVT PCB SOIS I2C . rework some PCBA for camera team SOIS bringup lesson learn : 1. Vendor change SPEC and do not notice KP，KP didnot distinguish the change from Vendor. maybe KP can optimize vendor design change process 2.Bringup sheet need more detail check point for detail function . |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | E.London NA
2022-10-21 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Issue:wireless can not work on EVB rootcause: suspect Nmos can not open due to no 5V at Vbus of Charge Pump solution：EVB not impact other bringup.rework 1 pcs for wireless related bringup . EVT change Charge Pump Vbus to CHG_VBUS(net after Nmos) | Link | 文亭 |  |  | 1.SCH | E.London NA
2022-10-21 | 4.EVB | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Issue:OTG can not work on EVB rootcause: Nmos can not open due to no 5V at Vbus of Charge Pump solution：EVB not impact other bringup.rework 1 pcs for OTG related bringup . EVT change Charge Pump Vbus to CHG_VBUS(net after Nmos) | Link | 文亭 |  |  | 1.SCH | E.London NA
2022-10-21 | 4.EVB | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3]Issue:can not find USB port rootcause: Audio switch power =1.8V Voltage is too low due to use VIO 1.8V ,but not Vsys or BOB . solution：EVB rework , remove R4573 ,short bottom pin of C4585 to bottom pin of C305 .(short Audio switch power to Vsys)--ongoing EVT change Audio switch power to VYSY (change MB SCH &PCB )--done lesson learn： 1.EXCEL表的PIN定义，写信号全名，不简写，以免改原理图时误解 2.EXCEL的PIN定义更改后，由更改人通过更改文档提交更改，以免REVIEW环节缺失 | Link | 院长 | 文亭 |  | 1.SCH | E.London NA
E.London NA
2024-06-24 | D.SHIP | 1.Platform | 4.Build | NA | NA | [s3] MP产线发现概率性无法下载的主板（IF站点），比例~0.3% 初步判断： SCC8C83981 （EXS00A-CS12311）76.8MHz晶振，使用在几十个项目中，近三年的QC项目几乎都用这颗，没有报相关问题。晶振相关导致不下载故障从2024年5月份开始集中爆出。共性的情况就是都是用SCC8C83981 晶体，推测是SCC8C83981 最近批次有什么参数变化，（有可能还在器件SPEC范围内，因为厂家拿到故障IC给出的单体分析报告是pass的）导致和PMK IC无法很好的兼容工作。 RD分析：PMK IC供电都很正常，没有问题。实际测试XO 晶体本身的波形，发现故障板XO 是完全没法工作起来而不是频率偏移。而XO SPEC提供关键参数目前都看不出异常。 高通也给不了进一步的分析建议，让咱们找XO厂家确认除了 频率指标外还有什么会影响XO起振的情况。 临时方案建议：更换SCC8C83981 晶体批次，跟踪后续情况。更换后暂时没有问题，持续关注。 长期：找XO厂家继续确认还有什么情况会影响XO起振。 | link |  | 文亭 | QC CR：07311754 | 6.No Change | H.Boston
2024-03-25 | C.RAMP | 10.USB-C | 4.Build | NA | Closed | [s3]Issue:IKSWU-111557Boston CQA1不充电、不识别端口 NG，重启后才能pass（包括低电后充电起来的重启） ，比例 4/15000 Clue: 1. Factory 版本测试出现的 。 2. 默认没有ADSPlog ，SW从现有log 无法得到有效信息。 3.恢复的过程包括没电关机了，所以基于此的推测是：机器没电后 内部异常的状态就消失了，可以正常充电继续使用，不会变成砖头机。 exp: 打开ADSPlog ，针对出现问题的机器 以及其他机器共10台，进行压测。截止3/29 验证1300次，未复现。 NEXT：CQA2上追踪 其他建议：产线加入ADSPlog 的批量生产跟踪（这样一旦出现问题，可以获取到有效log，只加在整机端），产线评估中 -TE solution: TBD |  | 文亭 | 院长 |  | 6.No Change | H.Boston
2024-03-25 | C.RAMP | 3.Charging | 6.Issue | NA | NA | [s3]Issue:先放到无线充电盘上，等待5秒左右，插入PD充电器，出现充电图标但是实际没有充电电流的问题 Clue: 1. 时间短或者长都没法复现。 2.插入其他充电器ok （10W充电器，或者QC 充电器）。 exp: solution: | lin'k | 文亭 |  |  | 6.No Change | H.Boston
2024-02-23 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S2]Issue:EDU14 50V surge on Vbus，can not fastcharging (2 in 2) clue1: EDU14 WH172566 2nd source FVCT4J . PVT 1st source is pass. 1. Charging IC Nuvolta NU2115 was damaged Exp: measured surge waveform when broken. Result: surge voltage maximum only 13V, less than IC spec 22V 2.NU2115 analysis by vendor - report ETD 3/6 Exp: Adjust internal OVP Setting of NU2115 , 5 Pcs Exp: 6 More Units to Validate with new setting . Result: pass 3/8（ each unit test twice ） rootcause: surge voltage maximum only 13V, less than IC spec 22V solution:Adjust internal OVP Setting of NU2115（VAC OVP From 14V to 13V； Vbus OVP From 12V to 10.5V ；PMID2Vout_OVP from 12.5% to 7.5% ） （purpose： faster protection triged for surge test）—-verify 6 unit test pass | link | 韩凯 | 文亭 | TCC sheet | 4.Parameter | H.Boston
2023-11-08 | B.PVT | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: +15kV ESD, Flash always on, PM6150C BOB short clue1: flash板接地导电泡棉厚度压实后有1.0mm左右，接触正常 clue2:13M CAM背面贴了隔磁材料， exp：整改未贴隔磁材料机器进行摸底验证 exp：加贴一个tvs，初步验证ok rootcause: solution: PVT test pass | link | 韩凯 |  |  | 3.BOM | H.Boston
2024-01-05 | 7.DVT2 | 3.Charging | 4.Build | NA | NA | [s3]Issue ：4 unit wireless charge can not work after flash SW. （FR：4/200=2%）CR IKSWU-53713 Clue： 1.SW update to FW1.1 and then update to FW1.3 ，so it will update FW twice . 2. Log ：battery capacity are low （only 20+% for these 4 units when issue happen ） 。and then FW=0x 00 3. SW FW update logic：dont allow update FW if FW=0x 00 （to Solve other project issue ：power on with DP insert ，it disconnect DP） Rootcause ： 1.suspect FW update unstable with low voltage battery . 2.When FW updated fail ，it will show 0x00，and can not be updated again base on SW logic now. Solution： 1.change FW update battery capacity limit from 20% to 50% 2.change SW FW update logic ：allow FW=0x00 update again . SW change would be submit from ⅛ ，monitor | link | 文亭 |  | IKSWU-53713 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2024-01-03 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [s2]Issue:Display missing pixel Clue: exp: solution:中框加麦拉盖住底部中框跑道型通孔 | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-12-12 | 5.DVT1 | 10.USB-C | 5.6 User Feedback | NA | Closed | [S3]Issue: USB connection strange B2GID:324037417: unexcepted USB interrupt (Xiangdong`s EUT phone) Clue:1. stress test can not reproduce in test team. 200time USB plug &unplug. 2.Log analysis :some OTG interrupt found frequently. rootcause: LP，Foreign objects entered the Type-C (presumably saline or beverage), causing corrosion solution:NO |  | 文亭 |  | IKSWU-41681 | 6.No Change | H.Boston
2023-11-08 | 7.DVT2 | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: ALT, ESD, headset MIC no function clue: dvt1 二供有开始验证中芯的codec，可能与芯片厂变更有关 待确认故障位置 Exp1： Exp2： rootcause: solution: C2718 33pf电容为改TVS，降低概率 |  | 韩凯 |  |  | 3.BOM | H.Boston
2023-12-06 | 7.DVT2 | 5.Camera | 5.2 BB Test | S2 | Closed | [S2]UW Camera with new sensor GC13A2 got line noise Clue: 1. When the module was upright, there iwas no noise, indicating radiation interference. 2. Sticked magnetic shieding film, noise was gone. The radiation source comes from the module projector surface of mainboard. 3. Replaced S5B or set S5B into pwm mode, noise was disappeared. The S5B working mode is affected. Rootcause: Interference comes from S5B. Solution: 1. Stick magnetic shielding film under camera module. (need to verify BB ESD, RF desense, ANT perf, CamKP Mag Simulation) 2. Set S5B into pwm mode when opening camera. (still working with BSP) [Verification] No noise in PVT |  |  |  |  | 2.PCB | H.Boston
2023-12-05 | 7.DVT2 | 8.PCB | 4.Build | S3 | Closed | [S3]PCB from redboard silkscreen layer was broken after cleaning underfill gel clue: 1. problem was not with Compeq PCB 2. Redboard slice the offending PCB and Compeq PCB Solution: Redboard will thicken film of silkscreen layer as thick as compeq's | Link | 川叔 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-11-23 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ： wireless charge ，Irect >Ibus （Impact Qi Certification tuning. Some weak Tx maybe can not work） Clue：1.Ibat *Vbat >Ibus *Vbus （2.77*4.28 >0.78*11.9 ），output poewr >input power .suspect Ibus is error 2.short E1679 ，OK Rootcause ：E1679 impact PM7250B Ibus detection in wireless charging status. Solution：change E1679 to 0R. Import from DVT2 （DVT2 board check Ibus ok 4pcs .DVT2 phone RF check desense ok ） | link | 文亭 |  |  | 3.BOM | H.Boston
2023-11-08 | 5.DVT1 | 12.EMC | 5.4 ALT | S2 | Closed | [S2]Issue: ALT, ESD, Flash always on, PM6150C BOB short clue: flash板接地导电泡棉厚度才0.2mm，而实际flash板到主板屏蔽盖间距有0.58mm Exp1：flash板接地导电泡棉厚度改为0.6mm（result：TBD） Exp2：c1524电容改为0.1uF（result：TBD） rootcause: 屏蔽盖泡棉未接地 solution: 加厚泡棉 | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-11-13 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: EDU03的报告，从OTA的数据看D4 ANT0通路有损伤 clue: Band 71 TRP degradation exceeds 3dB, and TRP value also out of spec. exp: rootcause: solution: improve sub PCB layout，调整TVS位置 |  | 韩凯 |  |  | 2.PCB | H.Boston
2023-11-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S1]Issue: Main Camera preview flicking after ATT trumble 400 cycles clue: 1. camera ois get gyro data fail 2. a+g function fail in CQAtest rootcause: PCB conner broken solution: ME FA |  | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-11-08 | 5.DVT1 | 5.Camera | 4.Build | S3 | Closed | [S2]Issue: Main camera video record got obvious line noise clue: DVT1A, FR 3/406 exp: rootcause: solution: Increase MIPI VOD parameter |  | 邦邦 |  |  | 4.Parameter | H.Boston
2023-11-08 | 5.DVT1 | 1.Platform | 5.4 ALT | NA | Closed | [S2]Issue: WH169799 MD ALT 2019 DVT1 (Loop1)//ALT kernel panic clue: exp: rootcause: solution: |  | 敏敏 | 文亭 | IKSWU-28732 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-08 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: ATT tumble WH168486, Unable to enter system:D2(400) clue1: ramdump at moto logo processing，log show DDR abort clue2：remove back housing and it can power on（memory test ok in this status）--suspect some component solder crack clue3: slice test , no solder crack found rootcause: unknown solution: Monitor DVT1 / ME confirmed low risk | Link | 文亭 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-20 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S1]Issue: Main Camera preview flicking after ATT trumble 400 cycles clue: 1. camera ois get gyro data fail 2. a+g function fail in CQAtest rootcause: Pads of A+G sensor chipset were cracked solution: ME analyze |  | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-27 | 4.EVT | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue: Insertion mistrigger when stylus closes to the tp area above hall. clue: exp: rootcause: solution: |  | 小熊 |  |  | 6.No Change | H.Boston
2023-10-26 | 4.EVT | 2.Power | 5.2 BB Test | S2 | Closed | [S2]Issue: autopower off on some unit (2 in 7) when charging clue: 1. some unit can reproduce in charging mode （reproduce when SOC =94% ,SOC=100% ,and others） 2. Log analysis: PM: OCP Occured: PMIC: 4; SMPS: 8 . it is PM6150C S8E .suspect S8E in LPM mode when charging EXP2.1 :add loading on S8E found 100mA trig OCP, so it is in LPM mode. 2.2 :SW change it to NPM mode , result TBD （1unit 3days ok ，the other one seems not in NPM mode） rootcause: solution: change S8E from auto/retention mode to auto/NPM under sleep |  | 敏敏 | 文亭 | Link | 4.Parameter | H.Boston
2023-10-16 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Closed | [S1]Issue: UW Camera power noise, RCN value > 20 clue: Short AGND to GND close to UW connector, RCN got pass. rootcause:AGND of LDO is separated, leads to power noise solution: GND optimize & AVDD add 0R |  | 邦邦 |  |  | 2.PCB | H.Boston
2023-09-28 | 4.EVT | 5.Camera | 5.1 Bring up | S3 | Closed | [s3]Risk: The SOIS signal is out of step clue: The SOIS signal is out of step when two sensors on the SE0 simultaneously collect signals. clue: rootcause:SW Own solution:Camera Feedback Acceptable | Link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-08 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: EDu03 WH168449, D2, Flash LED was always on after ESD test on UW Camera ring clue: 1. PMIC damaged leading to VREG_BOB shorted to FLASH_LED rootcause:shot on CAM ring,energy strick the CAM shell to coupled discharge the spring of flash solution: Add TVS On Flash_LED |  | 韩凯 | 邹仕海 | Link | 1.SCH | H.Boston
2023-10-07 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: EDu03 WH168449, capsensor CH2 8KV NG clue: 1. L901 was short damage rootcause: capsensor CH2 sparated from ANT9，remained a suspended metal leading to weak ground solution:1、ADD TVS on the path of CH2 2、change higher voltage capacitor （25V to 50V） | Link | 韩凯 | 邹仕海 | Link | 2.PCB | H.Boston
2023-10-07 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH168459,Cap sensor ch1 no function:D1(25) clue: rootcause: Main board was broken by stress solution: ME Own |  | 小熊 | 邹仕海 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-07 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [s3]Issue ：ATT tumble WH168463, Unexpected auto power off:D1(350/450) Clue：1.it can reproduce in drop .2.Battery connector seems loose （other normal unit seems ok） exp1：wireout Vbat& GND and connect to power supply(without back cover)，RD drop 35 times and can not reproduce. exp2：wireout Vbat& GND from Battery and reassembly phone , RD drop 50 times and can not reproduce 2. This batterty connector is a new part that not MP in lenovo. Rootcause：1.phone power off in drop due to Battery connector contact issue.（connector damaged） 2.Why？ KP and ME analysis -weaker connector Solution： change BAT connector to molex BTB （MP parts） from DVT1 | link | 敏敏 | 邦邦 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-16 | 4.EVT | 1.Platform | 5.4 ALT | S2 | Closed | [S2]Issue: MDU72 ,WH168468, D1 , NB9A040201, 不识SIM卡 clue: no issue in EDu03 ESD test before MDu72 Clue: SIM recognition failure is due to modem crash Clue:Modem crash is caused by the factory's lack of complete calibration. Rootcause:The unit lacks complete RF calibration, resulting in modem crashing. Solution:Recalibrate RF parameters | Link | 李果 | 韩凯 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-10-07 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: TMO tumble WH168459, Unexpected auto power off:D3(125/150/200) clue: same as WH168463, Unexpected auto power off:D1(350/450) rootcause: battery connector deform solution: change BAT connector to molex BTB from DVT1 |  | 敏敏 | 邦邦 |  | 2.PCB | H.Boston
2023-09-08 | 4.EVT | 8.PCB | 3.Review/Simulation | NA | Closed | RISK：Some line layout under shielding case Corner ， may be broken in Drop test Monitor EVT ME Drop test 。 EVT drop test no related issue found ，close | link | 邦邦 | 文亭 |  | 6.No Change | H.Boston
2023-09-28 | 4.EVT | 8.PCB | 4.Build | S3 | Closed | [s3]Issue ： always in Fastboot mode total 13 units in EVT1 build Rootcause： There is some solder added between the bullet of V - and the positioning gold wire, which leads to a short to GND and keeps entering fastboot mode.The SMT process suspects that the opening of the steel mesh is too large, causing too much solder to float onto the positioning wire and causing the short. Solution：EVT2 SMT reduces the steel mesh at the corresponding position. Monitor | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-09-08 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ：3.0V~3.5V battery Wireless charging fail Rootcause： wireless charge stop output due to WLC_Mode_sel setted to 1 when SW detect 3.0V Solution： proposal 1.set WLC_Mode_sel in ADSP when phone power up （over 3.6V）--- -test pass，go with this Option proposal2. WLC_Mode_sel change control logic :default 0 =EPP , 1=BPP ,default not need to set it when SW detect 3.0V -test fail， proposal2 Drop | link | chenwt | 德太加 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-09-08 | 4.EVB | 7.Sensor | 5.1 Bring up | S1 | Closed | [s3]Issue ：FOD bringup fail Rootcause：the FOD connector was 180 degree turned exp： Solution：modify PCB |  | xiongsn | 邦邦 |  | 2.PCB | H.Boston
2023-08-28 | 4.EVB | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue ：dead battery Wireless charging fail Rootcause： PM7250B do not charge with Vbus available only. Need CC logic work fine too. and dc_in_pon can not replace it.(Design in EVB ) exp：use reserved solution （a logic cirruit to pull CC to Vbus with 51KR when dead battery Wireless charging） pass Solution：1. add a logic cirruit to pull CC to Vbus with 51KR when dead battery Wireless charging. inport from EVT | LINK | chenwt | 德太加 |  | 3.BOM | H.Boston
2023-08-28 | 4.EVB | 1.Platform | 5.1 Bring up | S2 | Closed | [s2]Issue ：EVB Boston cannot force 9008 with V+ Rootcause： U1016 orientation error-clockwise 90 degree due to error not clear orientation mark on component Solution：1.turn U1016 anticlockwise 90 degree -EVB rework 2.sync correct orientation identification with SMT Engineer | link | chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | H.Boston
2023-08-29 | D.SHIP | 1.Platform | 6.Issue | NA | NA | Geneva NA Cannot charge & NTO EWG ID :180574&180463 180574 Analysis ：NTO and can not charge 1.Log found a clue: PM: OCP Occured: PMIC: 1; LDO: 25 it is PM6450的VREG_L25B_3P072 ，output to PDphy of PM7250B and USB power of CPU 2 VREG_L25B_3P072 impedance test： 11KR VS normal 200+KR，suspect some IC EOS。 3. Main PCBA USB DM&DP impedance test： DM is Infinity （abnormal），DP=1MR 。 4. PCBA USB DM&DP impedance test： DM is 11KR（abnormal），DP= Infinity 。 Next action：similar to 180463 ， wating for 180463 check if it is CPU damaged Rootcause: suspect EOS or High DC go into the phone through USB DM pin. and cause component damaged (TVS damaged ,CPU damaged) sent IC to QC for futher analysis. Clue：TCC 3T EOS surge test data ：USB DM DP can pass 45V . it is good next action ：1. monitor QC analysis 2. find ORT unit to do USB DM DP surge test again 3. try to do ESD test on USB DM DP. 180463 is similar | link | 文亭 |  | link |  | D.Geneva NA
2023-02-27 | C.RAMP | 7.Sensor | 5.4 ALT | S2 | NA | [S2] Geneva5G Polit, ALT loop5, Light sensor功能异常，2台 现象：light sensor参数异常 root casue: 遮光膜开裂 Analysis: 1. 测试暗环境正常。--->电通路正常。 2. 结构拆机分析。----> 遮光膜开裂 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-02-27 | C.RAMP | 3.Charging | 5.4 ALT | S2 | Closed | [S2] Geneva5G Polit首批ALT测试后, 不充电 现象：不充电 root casue: connector pin crack Analysis: 1. 不充电，不能抓log 2. CQAtest, type-C test, CC pin test PASS 3. 拆机分析主FPC小板端，bat_thm pin翘曲 4. log分析：batt temp检测正常, 无法检测到usb插入 5. CQAtest U盘测试，usb host fail，log上看到可以识别VID, PID, 以及vbus 5V |  | 文亭 |  |  |  | D.Geneva NA
2023-02-27 | C.RAMP | 4.Audio | 5.4 ALT | S2 | Closed | [S2] Geneva5G Polit首批ALT测试后Audio问题 现象：Left Loudspeaker no function. root cause: recv装配歪斜 Analysis: 1. log: i2c probe成功，不是之前见到的i2c断线。 2. spk, headset mic正常 3. ME分析 -- recv装配歪斜 |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-02-24 | C.RAMP | 1.Platform | 5.4 ALT | S2 | Closed | [S2] Geneva5G 量产首批ESD测试后不开机 现象：测完ESD，放置一个小时，换成normal模式开机，2台有1台出现卡死在moto log界面。 Analysis: 1. log分析：安卓没起来，data/misc_de/0/apexdata/com.android.permission/runtime-permissions.xml文件被破坏 SW action: 40次清除log，重启没有复现。 （目前判断不是硬件问题） |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-02-15 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT EDu03 - ESD Certification Test, headset mic no function, SMIC codec, WH160401 ,1 units from 4 Root Cause: 1.Codec damaged through naked Mic Pin in Audio Jack Exp1: 2 TVS apply on ESD Path . Result: RD test pass (1/1), PVT TCC test failure (1/4). 2. SMIC codec anti-ESD too weak under IC spec Exp2: ESD 2kv directly on IC. Result: FAIL. 3. Geneva ESD protection is not strong enough to protect 15kv Exp3.1: Milan5G 15kV PASS, Geneva 12KV PASS. (Isolation of audio signal and ANT, TSMC & UMC codec pass ESD test before DVT2B.) Exp3.2: HW workaround, add extra TVS on audio path of MB, MDu30 test PASS. Solution: 1. Add extra TVS on headset mic path of MB. | link | 韩凯 | 李果 | link2 | 3.BOM | D.Geneva NA
2023-02-14 | B.PVT | 5.Camera | 5.3 EE DVT | S3 | Closed | 【S3】Issue:DVTMXc03, drops front 100 times, Cannot enter rear 2 camera mode:D1(front), NGVADB0139 rootcause: connector pins solder crack on MB, SMT for further analysis |  | 邦邦 | 锦康 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-02-14 | B.PVT | 2.Power | 5.3 EE DVT | S3 | Closed | Geneva NA T4P 1台机器开不了机，充电发热 (机器准备做ALT，检查时发现故障） Analysis: PM6150C IC crach, BOB pin short to GND |  | 敏敏 | 锦康 |  | 6.No Change | D.Geneva NA
2023-02-03 | B.PVT | 2.Power | 6.Issue | S2 | NA | [s2]bt crash B2GID:322334682 //Unexpected restart clue: no BT issue leads to unexpected restart. OCP on PMIC LDO19 (UMCP VCCQ2) rootcause: solution: |  | 敏敏 | 嘉琨 | https://idart.mot.com/browse/IKSWT-82029 | 6.No Change | D.Geneva NA
2023-02-07 | B.PVT | 3.Charging | 5.5 Certification | S3 | Closed | Issue: TMO CEC PM fail ,0.31 W VS target 0.3W，CR ：IKSWT-83174 Clue：Pm is the charger input power of power off charging mode （when charging full） rootcause：charger input power of power off charging mode is too high than TMO SPEC. solution：change UFS to low power mode in power off charging mode， Lower down charger input power of power off charging mode（when charging full） TCC retest pass WH161567 ，pm=0.11W |  | 文亭 |  | IKSWT-83174 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-02-03 | B.PVT | 2.Power | 6.Issue | S3 | Closed | [S3]Phone Crash during second restart after skipping SlotB for OTA test , and then Restart failed. Clue:1.Press power key will help to continue the power on process. Clue2:Log shows GP Fault 7 and uvlo Clue3:HardReset or Battery Removed will recover. Clue4:Factory SW Also Reproduce , ~2% Root Cause:1.System Suspend duo to Fault Issue on of PMK6450 which caused by Secondary Power VREG_XO/RF/BB not shut. Exp:Measure Pon_rst_n/Fault_n/PS_Hold when crash reproduced, Result:PMK6450 Trigger Fault_N duo to Vreg_xo keep alive and drop after L17B. 2.BootLoader PSI File issue. Exp:Upgrade newest Bootloader Result: No issue Solution:1.Latest SW resolved Un-reproduced by QC mainline update | link | 敏敏 | 院长 | IKSWT-74127 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2023-01-31 | B.PVT | 2.Power | 6.Issue | S3 | Closed | [S3]FPS of First Vendor Get Hot and Short ，System crash， Clue:Second Source No Issue Rootcause: 1.system crash duo to Vreg_L28B Drop Exp1:log shows TZBSP_KRNL_FATAL_ERR_TYPE Fatal Error type:TZBSP_ERR_FATAL_RPM_ERR )，RPM Trigger Crash 2.Vreg_L28B Drop duo to FPS Module Broken and Short. Exp1.3.0V(VREG_L28B) 400+mA，OCP max=220mA~550mA，voltage drop to 2.4V Exp2.Father Power VREG_BOB Normal Voltage Solution:1. Fix PMIC OCP setting by SW and QC |  | 敏敏 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-01-30 | B.PVT | 3.Charging | 5.4 ALT | S3 | Closed | [s3]Issue: Cannot charge phone by USB: D7 (350) after ATT tumble , WH160949 Clue: PMIC sheilding case solder crack more than 40% .press sheilding case it recover. Root Cause: Batt_thermal Layer9 wire crack duo to ME stress (PMIC sheilding case solder crack ) | link | 文亭 | 邦邦 |  | 2.PCB | D.Geneva NA
2022-12-29 | 7.DVT2 | 2.Power | 5.4 ALT | NA | Closed | Issue: DVT2 ALT WH159234 FVC T2H Unexpected auto power off.A2(1) TrackID: NGVT2H0110 HW: DVT2 SW: genevn_factory-userdebug 13 T1TGN33.7 d5a45-e78dce release-keys AP Log: https://drive.google.com/file/d/1-I8MHqvwROxQwy7XEVP2LI1Nv30weR7U/view?usp=share_link 问题及线索描述： 1. 插SIM卡，灭屏待机，静置2min，自动关机。按power键或者插USB直接开机。 2. 界面信号图标空白，Mobile Data图标反复On/Off，像是不断地尝试注网 3. 不插SIM卡，未出现故障 4. 飞行模式关机，开机再待机，未出现故障 5. 开机一段时间，尝试注网之后，再开飞行模式，待机可出现故障 Root Cause: 1.Unexpected auto power off duo to GP Fault7 triggered which means XO issue from log. 2.Next Step: Check XO -RF Cannot reproduced | link | 邦邦 | 敏敏 |  | 6.No Change | D.Geneva NA
2022-12-23 | 7.DVT2 | 6.Display/Touch | 5.4 ALT | S3 | NA | [s3]LTE B12 Low RX1(DRX) Leve;D20, Initial check:Display Flickering, WH159301 analysis: 观察了是60Hz在严重闪屏，切换到90和120Hz闪屏消失。 怀疑为液晶电荷残留导致。80度加热半小时后，闪屏消失。（和博文沟通，还是ＤＶＴ２之前暴露闪屏问题，已有方案和对策） |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-12-22 | 7.DVT2 | 1.Platform | 6.Issue | S3 | Closed | [s3]Issue:SM6450 Device unable to boot after anti-rollback version is incremented Root Cause:1.VDD_QFPROM (connect to VREG_L23B_1P8) Power lost when TME checking anti-rollback efuse. 2 :It is difficult for SW to control VREG_L23B_1P8 in TME. Solution:1.workaround:change VDD_QFPROM power supply to an always on 1.8V power(VREG_L21B_1P8 on SM6450 platform), Import in PVT3 SW test ok in Factory | link | 文亭 | 敏敏 |  | 1.SCH | D.Geneva NA
2022-12-22 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | S3 | NA | [s3]ALPS两套屏共用一套参数 |  | 小熊 |  |  | 6.No Change | D.Geneva NA
2022-12-22 | 7.DVT2 | 9.Memory | 4.Build | S3 | Closed | [s3]CQA测试过程中主机dump-IKSWT-54990 Info: DVT2, Samsung 4+128 memory exp1: 交换memory --- issue follow memory ---> 寄memory给三星分析 |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-12-15 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | NA | [s3] Mdu30,TMO safety 55℃ |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-12-15 | 7.DVT2 | 7.Sensor | 5.4 ALT | S2 | Closed | [s2]Cap/SAR sensor no function:C2(CH2)(15KV), DVT2B ALT WH159234 2nd RootCause: cap short demaged by ESD Exp1: add tvs on path, to be verify by Hank Exp2: monitor in PVT ALT test Solution: Add TVS on cap sensor ch2 | link | 韩凯 | 院长 |  | 3.BOM | D.Geneva NA
2022-12-15 | 7.DVT2 | 4.Audio | 5.4 ALT | S2 | Closed | [S3]Phone Crash during second restart after skipping SlotB for OTA test , and then Restart failed. Clue:1.Press power key will help to continue the power on process. Clue2:Log shows GP Fault 7 and uvlo Clue3:HardReset or Battery Removed will recover. Clue4:Factory SW Also Reproduce , ~2% Root Cause:1.System Suspend duo to Fault Issue on of PMK6450 which caused by Secondary Power VREG_XO/RF/BB not shut. Exp:Measure Pon_rst_n/Fault_n/PS_Hold when crash reproduced, Result:PMK6450 Trigger Fault_N duo to Vreg_xo keep alive and drop after L17B. 2.BootLoader PSI File issue. Exp:Upgrade newest Bootloader Result: No issue Solution:1.Latest SW resolved QC最后一次大版本33.46不复现。 | link | 韩凯 | 院长 |  | 3.BOM | D.Geneva NA
2022-12-07 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Final LTE band 5&band13 TRP/EIS degradation exceeds 3dB After ESD testing Root Cause:1.Ant Holder Changed which easy to affected by ESD. Exp1：DVT2 Units change with PVT ANT Holder, Result: ESD Pass Exp2: Exp1 Change back to DVT2 Ant Holder, Result: ESD Fail Solution:1、Import PVT ant holder 2、naked ant feedback point shrink 0.2mm inner.(0.7mm->0.5mm) 3、Enhance GND of TVS | link | 韩凯 | 李果 |  | 2.PCB | D.Geneva NA
2022-11-28 | 5.DVT1 | 2.Power | 5.6 User Feedback | S3 | Closed | [s3]Issue: Micron 6+256 found VCCQ2 Power Dip in Memory Log. Clue:Micron Memory log shows low voltage happened. 4 units till now Root Cause: 1.VCCQ2 Power Dip due to its Front Switching Power Supply S8E Power Dip when wake-up 2.After Set to PWM , S8E PWM can’t hold the Voltage even when Current stable 3.Switching Freq = 2.0MHz when Dip ,while No Dip when Switching Freq = 3.0MHz Exp Result:Failed Unit work normally in 3.2MHz when Start up and Home Idle. Solution:1. Change Retention Mode to Auto-Mode in Sleep -QC 2.Change 6 pulses in PWM back to 1 pulse during sleep. -QC 3.Modify 2 other Registor - QC No side effect observed. | Link | 嘉琨 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-11-16 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | [s3]Issue:DVT1 some not charging found in Factory PAT,FR 6%. Clue:Recovered after re-assembly Battery or Trigger HW Reset from Power Key. Root Cause: 1. Charging Failure caused by PM7250B initial failed due to unstable power supply when the first Battery connector Plug in. 2. Battery Pack Sensor Signal C+(with 100R in Series) contact first before P+ due to P-,C-,C+，P+ assignment and C+& P+short on Main Board Solution: 1.Remove C- &C+ of battery（change PCB） , Return to P+ and P- Design. PVT import 。PVT ok | link | 文亭 |  |  | 1.SCH | D.Geneva NA
2022-09-22 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:EVT ATT tumble WH156483 1st,No voice. clue:Earpiece no function:D4(450),D11(300),D15-follow mainboard rootcause ：1. I2C line of smart pa damaged in innerlay on corner solution ：1.line expand to 0.2mm 2. optimize Solder Paste to reduce strain， DVT1 monitor DVT1 tested improved ，but still fail 2units ，optimize layout again ，DVT2 monitor No issue | link | 院长 |  | TCCFA | 2.PCB | D.Geneva NA
2022-11-03 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]DVT1 Camera Power Noise Test ,RCN Value: Avg 9.2 ，Min 5 ，Max 13. Root Cause: Camera sensor analog gain 255 was not be correctly write into register Solution: SW corrects setting Lesson learn: check power noise as soon as possible in EVT phase, especially, close loop to check analog gain ect. in register value. | link |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-10-12 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]EVT1 Main Camera Previous Freeze when Air ESD +8KV. recover after Quit camera Root Cause: 1.1 Camera Module Hung after ESD Strike through Camera Deco. 1.2 Camera SW not stable in Darkness mode. Exp1.2.1:upgrade new sw , Result: Issue not reproduce. Exp1.2.2: Shadow Camera, Issue reproduced. Exp1.2.3:base on Exp1.2.1/Exp1.2.2 ,upgrade to old sw , Result: Issue reproduce. 1.3 Factory CQA SW version is a naked version, No robustness strength for ESD. Exp:Update to User version SW and ESD strike on wide Camera. Result:Not Reproduced. Solution:1.new sw fixed. | link | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-10-10 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [s3]Issue: EVT 滚筒实验反馈有4台机器开机键无作用。 CLUE：1.锁紧或者松开螺丝，故障可能恢复（暂时没找到锁紧还是松开更容易恢复和复现问题） 2.出现问题的时候，测试开机键测试点，电压1.8V，按下开机键变成0V，松开又回到1.8V。所以推测：弹片接触没问题，上拉电源也没问题。 Rootcause：应力过大，多次撞击导致屏蔽盖频繁拉动内层线路，导致PHONE_ON_N 网络在第8层 有部分断线 补充疑问：以往一般在L9就断了，L8基本没见过。 原因推测：L9 这部分铺地，比较强，力往L8 传递较多。 solution：1.PHONE_ON_N 网络改板走线改到0.2mm宽度-DVT1二供的板子导入更改。 2.同区域的I2S信号4根线一起加粗到0.2mm ，降低其他功能fail风险。 | link | 文亭 |  |  | 2.PCB | D.Geneva NA
2022-10-20 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | [S3]EVT dead battery charging test ，can not charge on with battery cell Voltage 1.9V~2.6V Clue：1. can charge ok with discharged battery package voltage to 0V 2. Cell voltage lower than 1.9V can charge to around 1.9V. higher than 2.6V can charge to power up Root Cause: 1.VPH_PWR drop when PM7250B detect Vbat=3V 2. Cell voltage <2.5V whenVbat=3V ,so package =0V when charger buck stops switching. 3.Due to a design bug in PM7250B, charger buck stops switching for ~150 μs when it transitions from pre-charge to fast-charge state. The battery voltage at which charger buck does this transition is determined by VSYS_MIN threshold which is 3V by default and 3V Geneva NA battery can not support Vbat when charger buck stops switching Solution:change VSYS_MIN voltage configuration to 3.1V | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-09-22 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]EVT TMO tumble WH156479 1st,P-Sensor no function Clue:issue follow mainboard rootcause ：1.P-Senser line on corner damaged in inner layer. solution：1.change line to next inner layer. 2.other rest line expand to 0.2mm DVT1 ok | link | 小熊 |  | TCC FA | 2.PCB | D.Geneva NA
2022-10-14 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | [na]EVT2 wide Camera Previous Freeze when Air ESD +8KV. recover after Quit camera Root Cause: 1.1 Camera Module Hung after ESD Strike through Camera Deco which lead to Previous Freeze. 2.1 8M Camera Module Housing isolated GND duo to Cost Down before(0.x Cents) which lead to Module Hung. Exp:Grounding 8M wide camera by copper and conductive foam($0.05). Result:Not reproduced. 2.2 Camera Deco is conductive and floating from GND which lead to ESD Discharge to Camera Iron Housing. Exp:Remove conductive Deco ,Result:Not reproduced. 3.0 Factory CQA SW version is a naked version, No robustness strength for ESD. Exp:Update to User version SW and ESD strike on wide Camera. Result:Not Reproduced. Solution:1.EVT ESD is an engineering evaluating method. in Real user SW scenario ,issue not happend. Accept it . |  |  |  |  | 6.No Change | D.Geneva NA
2022-09-22 | 4.EVT | 4.Audio | 5.2 BB Test | S2 | Closed | [s2]Risk: EVT TDD Noise Risk Root Cause:Calling sw not ready. Solution:SW fixed and test performed |  | 院长 |  |  | 6.No Change | D.Geneva NA
2022-09-26 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | EVT 眼图调试完成 device mode | link | 文亭 |  |  | 4.Parameter | D.Geneva NA
2022-09-12 | 4.EVT | 11.Thermal | 5.6 User Feedback | S3 | Closed | [s3] Issue:Geneva NA EVB/EVT待机过热问题 Clue： 1. 系统可以正常休眠，休眠电流正常 ，平均9mA，未发现硬件漏电问题 2. 亮屏待机电流高，平均电流超过1.1A，导致发热厉害 （70%的屏幕亮度）,从log看是CPU 频繁重载导致 3. 打开飞行模式后，CPU负载减轻，平均电流降到500mA，发热明显减少 4. 需功耗进一步分解并优化，重点看下modem端 Root Cause： 1. 未导入校准参数，导致功耗异常高，主板发热厉害； Solution： 1. 导入校准参数，亮屏待机电流降到500mA 2. 500mA平均电流，依旧过高，需进一步分解； |  | 林峰 | 李果 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | D.Geneva NA
2022-08-29 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue:Geneva NA EVB HWID incorrect Clue: 0. Geneva ROW have same issue too 1.GPIO38 B band detected as A . (when set pull up with exter pull down 10K , it read high ,VS normal is LOW .) 2.Waveform check : it stop at 1.25V ， so it is high . suspect :Pull up R is about 4.3K VS SM6375 SPEC 20K min （No SPEC in SM6450 yet） 3. change to GPIO 37(HWID 1) ,same issue. 4. change to GPIO48 ,it is ok. change to GPIO113 ，it is ok too. Root Cause: 1. HWID detect error due to Low logic detect error when setting GPIO 37 & GPIO 38 pull high with exter pull down 10K 2. GPIO 37 & GPIO 38 Low logic detect error due to GPIO 37 & GPIO 38 Pull up capability is too high 3. GPIO 37 & GPIO 38 Pull up capability is too high ,Pull up range is 3kohm to 10kohm & Pull down range is 5kohm to 10kohm (QC reply 09/06) Solution: HWID GPIO change from GPIO 37& GPIO 38 to GPIO 48 & GPIO 113 ,From EVT (change done ). further check: need QC comment if there is other GPIOs similar to GPIO37&38 | link | 文亭 |  |  | 1.SCH | D.Geneva NA
2022-08-25 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue:After download adsp.img phone power off Clue: 1.after download adsp.img machine power off,off current is 48uA VS normal is 200+uA 2.after 1 ,then first short press powerkey,no current VS normal current is 170mA 3.Waveform check VPH_PWR Drop and never go back to Vbat when issue happen（suspect shipmode or AFP triged） exp3：short VPH_PWR and Vbat ， then it can power on . 4.Log check :no shipmode mode trigged (after rework VPH_PWR and Vbat to short) ,so suspect AFP triged 5.check BATT_THERM NTC (RT500) & batt_ID R found BATT_THERM NTC no mount on sub pcba exp 5.1： rework RT500 with 100KR and it can power on . （confirm it is AFP triged） exp 5.2 disable AFP function and it can power on too.（no rework HW） Root Cause: 1. phone power off due to batfet close cause ,and cause VPH_PWR Drop （after adsp.img loaded ） 2. AFP mode triged by Low temp caused by RT500 not mount Solution: 1.workaround :disable AFP function in EVB 2. add RT500 into BOM in EVT | link | 文亭 |  |  | 3.BOM | D.Geneva NA
2023-01-05 | D.SHIP | 9.Memory | 5.6 User Feedback | NA | NA | Issue ： Dubai+ NA (TMO): NTO After MR0 OTA(IKSWS-176032) ，total 3pcs by 20230105 |  | 嘉琨 | 文亭 |  | 6.No Change | B.Dubai+ NA
2022-06-17 | C.RAMP | 11.Thermal | 5.5 Certification | S3 | Closed | [s3]Issue:TMO Safety Test, CPU Heavy Loading+Max Volume + Max BrightNess+Charging+White Nosie，Result=53°C >48°C. Root Cause: 1. Top Speaker Over Heating on White Noise. Exp1:Using new Audio EQ ,when SKP Temp < 80°C （Original 90°C）and using 1X1 mm2 Avg Temp in stead of dot temp， Result: TMO Reset. Exp2:Using new Audio EQ ,when SKP Temp < 70°C for back up. Solution:1.Using new Audio EQ ,when SKP Temp < 80°C ，And RCA | Link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-06-17 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue: Tesla some times can not charge in DF (DVT2 &PVT),Recovered after power cycle, 5 users reported. Root Cause: 1.not charge due to cc logic error,and can't detetect cable. Exp1:CC /Vbus Waveform Plot. Result: 1.CC Open 2.CC 5.1K Conclusion:CC Logic in error stats 2.CC Logic error duo to interrupt source masking Exp2: embedded reg plot in User Debug 1 , Result: ISR Mask （mean not support INT now） 3.Int mask duo to int Arbitration issue of system Exp3: Import Patch2 and try , Result:Pass Solution: 1. import patch 2 to main line（I2C INT flow optimize），Validated Pass | link | 文亭 |  | IKSWS-127586 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-07-25 | C.RAMP | 11.Thermal | 5.5 Certification | NA | Closed | Issue:Downloads drops from ~ 2Gbps to 50Mbps Clue1:LV1 52°C Trigger NR CA Off Clue2:LV2 55°C Not Triggered in this case Root Cause:1.NR CA off not correct in Modem Policy Lev1 Exp1:Remove NR CA , Result:Downlink > 5 Min . Conclusion:Pass Solution:Remove NR CA off, DownLink Validated Pass. Issue:Uplink drops observed during test. Clue1:LV1 52°C Trigger NR CA Off Clue2:LV2 55°C Not Triggered in this case Root Cause:1.Uplink trigger in Modem Policy Lev1 Exp1:Remove Uplink Throttle in Lev1, Solution:Proposal:Remove Uplink Throttle |  |  |  |  | 4.Parameter | B.Dubai+ NA
2022-06-17 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | NA | Issue:IKSWS-129202 Phone battery will not charge B2GID:320148798 my phone will not charge from either the 30 watt usb-c AC charger or the Verizon turbo DC charger in the car Clue：1.HW： NDPA2G0018 2. From the log ，No Vbus detect from the 2 charging IC（MT6375&BQ25960） Root Cause: suspect Type-C connector damaged such Type-C connector liquided or other connection issue Action ：1. check Type-C connector if there is some abnormal 2.Check if there is PRC user feedback same issue ？ Solution: ? |  | 文亭 |  | IKSWS-129202 | 6.No Change | B.Dubai+ NA
2022-06-17 | C.RAMP | 9.Memory | 4.Build | S3 | Closed | [s3] Issue:Download Failure, FR 0.3%(12/4000) Root Cause: 1. Downloading block by rank1 size check failure duo to write leveling calibration failure. Exp:Force Dual Rank Downloading , Result:Pass . 2. ddr write leveling calibration failed duo to no expected return value from Dram after calibrating command sending. 3.ddr not response duo to WCK（Write Data Capture & Read Data Output CLK，Diffential Pair） not align(Sync/Unsync). Exp3.1: Change Command mode with Byte Mode. Result:Failed Exp3.2: Change Command mode with Normal Mode . Result: Pass Exp3.3: Sync Dram WCK Status before rank detected .Result:Pass Exp3.4: Rank Detection Retry 5 times. Result:Pass 4.Where wck misalignment? Conclusion: WCK Sync Status Abnormal When WCK On Exp:4.1 retry rank detection only DRAM init flow,Dump WCK Status(Sync/unsync) ,result:6/21 Exp:4.2 Setting as WCK to low power mode from high performance mode , Result:No affection Exp:4.3 move WCK On/Off Position, Narrow Down the misalignment code. Result: WCK Sync Status Abnormal When WCK On. Exp:4.4 Ask Micron if any special request/constraint, Result:Not affected Exp:4.5 Any Margin Concern- Discussing ,Result:Not relative 5.Why WCK Sync Status Abnormal? Conclusion: Exp:5.1 Check Dram Controller Reg Difference and change procedure , Result: Dram Controller Reg Changed during ddr boot acceleration in Boot Rom（new feature from other platform but with compatibility issue） Solution: 1.re-compiling DA and Preloader， where reg status fixed in the later init process. rd validated pass. factory validated. |  | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-06-07 | C.RAMP | 9.Memory | 4.Build | S3 | Closed | [s3] Issue:After power off, phone take long time to boot up, FR 3%(55/1759) Clue:ETT Mem Test Pass, Rd & Wr Eye-Diagram Pass. Root Cause: 1. boot up latency due to mr5/8 and ddr rank_size check failure and preloader reset repeatedly. Exp:log Result: show mr5 0x1, rank0_size 0x0000000040000000, abnormal 2. read failure happen on the first check during the Fast ddr lane calibration (Parameters read from UFS after the first full ddr lane calibration) Exp 2.1: Disable Fast K and test. Result: Pass ( 30 units 30 times,1 time failure and not reproduce) Exp 2.2: Retry RX RDDQC, Check if always pass after the first failure. Result: All Pass. Exp 2.3:Check Rx Config Register on the first Fast ddr lane calibration compare to the other times. Result: Quit Different ,Conclusion: bad/wrong Rx Config Exp 2.3.2 Recheck RX Config Register. Result:Rx Config Resister is same ， Revert Exp2.3 Conlusion by Rx Config Normal Exp2.4 Check HT/LT , Result: LT boot up OK. Conclusion:bad rx performance on failed unit Exp2.5 Check 26M CLK, Add 500ms in Mem init and RDDQC(Read Data Q Calibration), Result: No improved, Conclusion: CLK OK. Exp2.6 Check HV/LV ,Result: No Improved , Conclusion:Voltage OK. Exp2.7 Check Power Timing, Result:Power Timing OK. Exp2.8 Lower ddr Frequency to 1600Mbps during preloader， Result:Failed. Conclusion:CLK OK. 3.read failure happend duo to missing of DramCPhy Initial Exp3.1.1:Compare the diffirence between first cali and others. Result: Dram Phy Reset Not executed. Exp3.1.2:Execute Dram Phy Initial Before Fast calibration , Result: No Issue. Conclusion: Issue happend duo to missing of DramCPhy Initial Solution: 1.sw work around:RDDQC retry. no side effect. rd validated pass, Factory Validated pass(60PCS*50times pass) 2.SW Patch:Execute DramCPhy Initial before Fast Calibration. RD Validated Pass. |  | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-05-17 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [na] Issue：Edu 03 ESD test，4/6 OTA Performance Degrade. Root Cause： 1.Tuner Damaged by ESD Through ANT seam in Bottom 2.1 Wasin CES TVS can't stablly protect Tuner Exp:2.1.1 Change Wasin CESTVS to Panasonic ATVS , Result: RD validated, 1 failure of 3. Exp:2.1.2 Add 2 ATVS,Result:failed Exp:2.1.3 Change Wasin CESTVS to Panasonic ATVS,12KV ,Result:Pass Exp:2.1.3 Change Wasin CESTVS to Panasonic ATVS,15KV ,Result:PASS 3. 13% Avg shorter interval(0.1mm) between Conductive Ant and boarder compare with PVT and DVT Exp:3.1 anti-ESD foam cover on the exposured and pad and test. Result: Rd validated , Pass Exp:3.2 enlarge interval by 0.35mm in middle frame, Result: 6/? Solution： 1.Change Panasonic ATVS from Wasin CES TVS.PVT import 2.enlarge interval by 0.35mm in middle frame. ,6/? me running change | LINK | 韩凯 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-05-17 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [na]issue:Edu03 ESD test ,NFC no function after 8k air AD ,D1 units Recover after standing for hours；D2 recovered after battery removed and restart. clue: issue reproduced after esd retest. Root Cause: 1.NFC Ant 330pf 25V resonance capacitor C1352/C1353 broken . 2.Low Capacitor anti-esd performance Exp2.1: Change 330pf 50V cap ,Result:RD Validated Pass Solution:1. Change 330pf 50V cap , 12KV validated pass. 15kV validated pass |  | 韩凯 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-05-17 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | Issue：Edu 03 ESD test，D6 After - 15KV air discharge at zone12 (Aging 10),Cap/SAR sensor ch0 no function, unable to recover route cause：R4509 open solution：add tvs |  | 韩凯 |  |  | 3.BOM | B.Dubai+ NA
2022-04-29 | 7.DVT2 | 7.Sensor | 5.3 EE DVT | S3 | Closed | [NA] Issue： WH150730 DVT2 EDU03 ESD Test ,D6After - 15KV air discharge at zone12 (Aging 10),Cap/SAR sensor ch0 no function Root Cause: 1.R4509 is open，never seen before Exp1;Send Damaged Resistor to vendor for FA. Result:TBD Solution: 1.Monitor following Test to see if reproduced. |  | 小熊 | 韩凯 |  | 6.No Change | B.Dubai+ NA
2022-04-29 | 7.DVT2 | 4.Audio | 5.3 EE DVT | S3 | Closed | [NA] Issue： WH150730 DVT2 EDU03 ESD Test ,D1After -15KV air discharage Zone19 aging(10),mic3 no function Clue:Second Source Verification units Root Cause: 1.mic3(AAC) damage through mic FPC stiffener steel and Mic Hole on back housing Info: 1.noisy risky if Mic FPC stiffener steel grounding Solution: 1.Monitor following test to see if reproduced another one . |  | 院长 | 韩凯 |  | 6.No Change | B.Dubai+ NA
2022-04-26 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3] Issue： WH150801 DVT2 EDU14 Surge Test ，1mA Leakage current is out of spec.D1(180V),D2(160V) Clue1：2nd source charge pump SC8541 verification FVC A2R Root Cause: 1. VBAT Pin of SC8541 which leak 1mA. Info:1.first source TI BQ25960 300V Pass. Exp1.1:Check leakage Current stable？ Result: 5/12 2.Surge Path from VBUS to VAC1 Exp2.1: Surge Signal Measurement ,Result:Surge Peak Voltage 46V>36, 80ns duration. Exp2.2:Add 100nf Cap to suppress peak voltage. Result: No affection Exp2.3:Add 100R Resistor in VAC1 and verify . Result: Pass Exp2.4:Send Failed IC to Vendor for Further FA. Result:Application suggestion provided Solution: 1.Add 100R Resistor in VAC1，RD validated Pass ，TI BQ25960 also Validated Pass ，Running Change | link | 文亭 |  |  | 1.SCH | B.Dubai+ NA
2022-04-28 | 7.DVT2 | 3.Charging | 5.5 Certification | NA | Closed | [NA] Issue： Safity certification in Shenzhen Sporton , FOD test fail , Root Cause: FOD limit debug for certification Solution: SW FW update for FOD (change to 800) |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | NA | Issue: DVT2 2 PCS Cap Sensor No function Clue：1.Main FPC BTB connector Pin burned in sub board side 2. Cap_ANT1 short to GND after burned Root Cause: ？ Solution: ? | Link | 林峰 | 林峰 |  | 6.No Change | B.Dubai+ NA
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | Closed | Issue: DVT2 Factory IF fail mostly when battery NTC pin connected in IF fixture , IKSWS-83340 Clue：1.EVT have problem in Wuhan factory but can not reproduce in XM WWTE LAB . So monitor DVT1 Root Cause: Solution: 1. remove battery NTC Pin of IF fixture on DVT2,not impact test |  | 文亭 |  | CR IKSWS-83340 | 6.No Change | B.Dubai+ NA
2022-04-13 | 7.DVT2 | 1.Platform | 4.Build | NA | Closed | [S3] Issue：Issue:Factory IF fail in DVT2 2nd source build ? IKSWS-89240 Clue：0.Phone can't power up after download sw 1.DVT2 1st source build ok 2.DVT2 BB 2nd source component including 8+128 Hynix memory ,SC8541 30W charging IC ,Barometer sesnor ,? 3.6+128 Hynix memory with other 2nd source board fail too (suspect not Memory related) 4. other 2nd source +1st source 30W charging IC BQ 25960 ,result TBD? 5. can download and power on in BB LAB with same PCBA (when first board verify), So it should related factory IF envirenment，Power drop is too large.（Vbus & Vbat） Root Cause:why 实验室复现单台故障的，发现Vbus 有时候会下降比较多，最大的时候Vbat也下降很多。 并且有时候看到电流往Vbat流入（这样会加重Vbus的负载） 分析发现产线IF上电顺序有问题，Vbus 比Vbat早上电。 Solution: 尝试将ICL改为1A，并且disable 电池充电路径提前一些。 2. Vbus 从原来的5.8V 改到6.5V 3.修改测试序列，将Vbat上电提前到Vbus 之前。---实际验证后 三条solution 都加入后，良率上升到95%以上。该问题不block 生产了。 4.产线加上retry ，良率会再次提升。 依此跟踪PVT生产情况再看是否ok | link | 文亭 | 林峰 | CRIKSWS-89240 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Closed | [S3]Issue:DVT1 APM current 13.3mA no meet TMO request(<5mA) Root Cause: 1. p-sensor polling interval time 50ms after awake. proper value=250ms. 1.5mA -SW On-Going 2.Modem cannot be powered off due to RF different designs (0.43mA) 3.Display RST 0.3mA Optimized. 4.TP Power 1.5mA ,Optimized. 5.Display 16M CLK -0.77mA Optimized. 6.Esim Removed 2.2mA Optimized 7.Hall IC GPIO Configuration 3 mA Optimized. Solution: Proposal:1.PSensor Polling interval time optimization. 2-7 according to the root cause 3.32.32 SW meet MTK target(average current=6.93mA,Min=5.77mA) | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Monitor | [S3]Issue:DVT1 MP3 playback current fail,70mA higher。 Root Cause: 1. DVDD_Core Cosume extra 34mA when Mp3 Play. CPU ocupied. 1.1 Why CPU not sleep? - SW 2. Current Not Stable 2.1 Dolby Enabled 2.2 GMS Enable 2.3 Battery Tracer Enable 2.4 TBC Solution: 1.TBD | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-03-30 | 5.DVT1 | 2.Power | 6.Issue | S3 | Monitor | [S3]Issue:DVT1 Video Playback (local storage) BSP current fail,CD=340mA。 Root Cause: 1.Display Current Cosume 1.1 Fresh Rate Difference. 2.SW configuration or backgournd Service. Exp:Test with Facotry Version 148mA = MTK Demo Phone 148mA. The platform power consumption data is the same as MTK Demo Phone data （W/Display+Factory SW version) 2.1 Dolby Enable -3mA 2.2 DDR Config - SW Solution:1.TBD | Link | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-03-30 | 5.DVT1 | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue:DVT1 Sensor not work after ALT？ 1 in 15+2 in 9 total 3 in 24(only in 2nd mainboard) clue: Root Cause: 1 I2C wire crack at BB shielding case Top left corner 2. PCB over Strain - ME Analysis. Solution: Proposal: 1. Modify Shielding Case Solder Mask to reduce, under validated. 2.Optimize I2C width | link | 小熊 | 李果 |  | 2.PCB | B.Dubai+ NA
2022-03-30 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1 Vibration not work after ALT 3 in 10 Root Cause:1 VIB_RST wire crack at BB shielding case Bottom left corner （layrer 2） Solution: 1. Change VIB_RST to Layer 3 ，PVT import. |  | 院长 | 李果 |  | 2.PCB | B.Dubai+ NA
2022-03-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:DVT1 Cap Sensor not work after ESD. clue:Sending Unit to Xiamen. 3/8 Root Cause:1.No tvs Protect for this channel Solution:1.Add TVS on failed channel. | link | 韩凯 | 小熊 |  |  | B.Dubai+ NA
2022-04-06 | 5.DVT1 | 10.USB-C | 4.Build | NA | Closed | [S3] Issue： 2% unit can not work on USB connect （No USB port ），CR IKSWS-84946 Clue 1：power cycle cannot recover but Blankflash and Long time press powerkey can recovery 2.waveform ok onUSB D+D- test point but no signal on Type-C ---Analog switch control problem 3. Analog headset can work ，and after this ，USB connect recover. Root Cause: Analog switch control issue Why ---SW : analysis ongoing---liaohj Solution: SW Analog switch initial change | link | 文亭 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-04-13 | B.PVT | 1.Platform | 4.Build | NA | Closed | [S3] Issue：[Tesla][Factory][IF][PVT]WAIT_FOR_NETWORK_INTERFACE_ARRIVAL_POST_FLASH Clue：实验室复现类似问题，发现这时候，Ibus 一直是0A ，也就是没有抽任何电流， 需要SW 分析下log ，为什么 rootcause：产线设置Vbus 6.5V触发chargepump 默认的OVP最低值6.3V. solution：产线设定Vbus电压到6.2V. | link | 文亭 |  | CRIKSWS-102720 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | B.Dubai+ NA
2022-02-18 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue: Camera Power Noise Abserved in Darkness in DVT1 units. Clue:EVT not found duo to SW not ready. Root Cause:1.AVDD Power Noise 2.Camera AVDD Capacitor need to fine tune Solution:1.update Camera AVDD Capacitor C4159 to 4.7uF+2.2uF. DVT2 import | Link | 邦邦 |  |  | 3.BOM | B.Dubai+ NA
2022-02-11 | 4.EVT | 11.Thermal | 5.2 BB Test | S3 | Closed | [S3] Issue： BB test ，CQA battery temp=36 degree ，plug in charge ， battery temp jump to 43 degree 。when 26degree ，jump to 31 degree. clue ：1. Vbus charging current =3A 。plug out charge ，jump back to 36 degree （Vbus current impact battery NTC reading？） 2. When charging with QC charger ，jump is 3 degree （27 to 30） Proposal 1：小板和主FPC 共GND造成的偏移？ Exp1: 小板和主FPC上面NTC拉单独GND，依然有4度的偏高存在。 Proposal 2：ADC 的GND 有干扰，和MTK确认BATON 的参考地是CS_N 而不是GND。 EXP2：飞线NTC- 到CS_N上面，验证有2度左右改善 Proposal 3：SW上面COM_FG_METER_RESISTANCE 默认的75 ，表示补偿了7.5mR。实际上不需要 EXP3：去掉补偿。改为0 。实际验证下来 结合EXP2，基本没有偏移了，温度准确。 Root Cause: 1. HW：BATON 的参考地是CS_N 而不是GND ，有个5mR对地的采样电阻。 2. SW：MTK默认代码加了个补偿值7.5mR ，给电池内部的NTC用的。不符合项目设计。 Solution: 1.SW：去掉补偿。改为0 。DVT1 导入 ---柴璐 ，20220215 提交更改 2.HW：NTC- 改到CS_N，需要更改主板，主FPC，小板。DVT1来不及改，计划 DVT2 导入---林峰 -done | link | 林峰 |  |  | 1.SCH | B.Dubai+ NA
2022-01-10 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3] Issue：EVT power off current =424uA，too large ,VS normal project 100+uA Root Cause: 1.100uA current leakage on MT6685 Solution:1. MTK will upgrade new version MT6685 , import in DVT1. 2.测试DVT1主板(机器) 5pcs，4pcs power off current= 259uA~275uA,1pcs =325uA,关机漏电流有明显改善 | Link | 敏敏 |  |  | 3.BOM | B.Dubai+ NA
2022-01-20 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S2] Issue： EDU14 Surge Test WH147427 ,D1 Vbus test 150V,D2 test Vbus 100V ，power off current is more than 1mA. Root Cause: MT6375 damaged （replace a new MT6375 ,power off current go to 0.4mA ，ok） Exp 1: change OVP point from 18V to 14V ,Result:Failed. Exp2:change surge TVS D501 to a better part ,Result: DVT1 Verify. Exp3:change R2701 to 33R from 0R ( R on PD_Vbus of MT6375) .Result:DVT1 Verify. Exp4：add one more TVS near MT6375 .Result:DVT1 Verify. Solution: Proposal 2 :change surge TVS D501 to a better part. Proposal 3: change R2701 to 33R from 0R ( R on PD_Vbus of MT6375) Proposal4 :add one more TVS near MT6375 retest :DVT 1 with proposal 1+2+3+4 pass 2/25 . rework with Proposal 1+2+3 result ，pass 3/1 WH149393 Fix solution ：change surge TVS D501 to a better part ESD56161D24 +change R2701 to 33R from 0R +change OVP point from 18V to 14V . Import in DVT1 already | link | 文亭 |  |  | 1.SCH | B.Dubai+ NA
2022-01-14 | 4.EVT | 9.Memory | 4.Build | S3 | Closed | [s3]Issue:EVT Units auto boot up after power down on workaround version. Clue:1.No this issue with older sw . Clue:2.Not affect current usage. Closed. Root Cause:1.4 Power for DDR keep alive after power down which lead to reset and auto power on. Solution:1.NA |  | 院长 |  |  | 6.No Change | B.Dubai+ NA
2022-01-08 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S3] Issue：EVT unit Can't Download on First Board Validation. Root Cause: 1.DDR5 Power Supply VDD2H not enable duo to MT6368 boot config to LP4. 2.Audio I2s Circuit Optimization which lead to affecting the config duo to Shared GPIO Usage，this change Point confirmed with MTK. Solution:1.Enable VDD2H in Downloading Agency Phase, Validated Pass. 2.Recover LPDDR5 HW Config in EVT V03 Version. | link | 林峰 | 文亭 |  | 1.SCH | B.Dubai+ NA
2021-12-17 | 3.PEL | 6.Display/Touch | 4.Build | S3 | Closed | [S3]VMC_PMU ，power for 16MHz clk can not config to 1.8V yet (default 3V) SW bringup ok |  | 芳梅 | 文亭 |  |  | B.Dubai+ NA
2021-12-13 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [S3]Risk: Deadbattery wireless charge with QC charger can not work Root Cause:1. QC charger will output 12V，and wireless charge output 10V ，which trig BQ25960 OVP 6.5V Solution:1. FW change ，WCHG_MODE_SEL pull down will output 5V。 FW 1.7 ，import from EVT 2. WCHG_MODE_SEL pull down R 2834 change to mount from EVT . SCH done. 12/13 | link |  |  | change link | 1.SCH | B.Dubai+ NA
2021-09-23 | 3.PEL | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3]Risk:Battery Connector/GSM PA/Spearker Placement of Dual Speaker Feature can't meet TDD Noise Design Rule. Root Cause:1.Speaker Interferrenced by magnetic field of Ground Current Flow in Receiver Mode. Solution:1.Move Battery Connector to the edge and 90 rotated. Xianjun Feedback that FPC too short to be achieved. 2.Proposal:Adding High Voltage Analog Switch YHM1106(2022/1 MP) ,Cost up 0.15$ EVT TDD test pass | Link | 院长 | 邦邦 |  |  | B.Dubai+ NA
2021-09-23 | 3.PEL | 7.Sensor | 1.4 Solution | NA | Closed | [NA] requirement: 气压计 sensor， tdk的20100，目前反馈是spi 可以解掉OTP的问题，希望能把气压计挂到SPI上 ，系统资源是否可以？ Solution:1. 厂家无SPI驱动，不往这个方向评估，close |  | 文亭 | 小熊 |  | 6.No Change | B.Dubai+ NA
2022-07-14 | D.SHIP | 1.Platform | 6.Issue | NA | Closed | 2 in 23 pcs CPU damaged. 178512 ：Charging too slow。 CPU USB_HS_DM impedance abnomal.CPU damaged by ESD/EOS. 178318：No Turn On. QC analysis result CPU damaged，suspect is EOS/ESD from USB_HS_DM/DP cause it. USB_HS_DM&DP TVS are both short to GND too. |  | 文亭 |  | EWG sheet | 6.No Change | A.Milan 5G
2022-04-06 | B.PVT | 2.Power | 5.5 Certification | NA | Closed | [s3] Issue 1: TMO test ，discharge capacity is too small . 2465mAh . root cause 1 : The discharge capacity test have problem . discharge test form 71% but not 100% ，Log data in : old-power_supply_info（Total capacity is just 71%*5000mAh=3550mAh）,log link root cause 2: external R that caused by the test is too high . 262mΩ(from the test log file by TMO with rework parts log link)-106mΩ(From internal test log file with close phone)=152mΩ （ this cause power off at SOC 16% too earlier than normal one . When it power off, battery OCV is about 3.7V . Which is the real battery voltage . ） | link | 李果 |  |  |  | A.Milan 5G
2022-03-09 | 7.DVT2 | 4.Audio | 5.6 User Feedback | S3 | Closed | [s3]Voice Echo found in DF with Car kit audio. Root Cause:1.Audio Car Kit input resistance below 5KΩ，which lead to apply earphone mode echo surpression. Solution:1.Shift Input Resistance Judge Point to 2KΩ ，Validated Pass. 2.Carkit Audio mode params optimized. Validated Pass |  | 院长 |  |  |  | A.Milan 5G
2021-12-30 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Issue:ESD 3/8 units 8KV/15KV auto power off on Second Vendor FPS. Recover after boot up. Root Cause:1.Clk of FPS affected by ESD. Exp:1.add TVS on FPS_Clk , Result:No Issue on 1 units. Exp2.Repeat Exp1 on more units. on-Going Solution:Proposal:1.Add TVS on FPS_CLK. |  | 韩凯 | 小熊 |  |  | A.Milan 5G
2021-12-10 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue:FVCV29 capsensor ESD ，15KV air，100 times/zone1：Ch1 no function,unable to recovered 15KV zone1:D2 Clue :1 . CAP C502 shorted to the GND Root Cause: electricity discharge through the signal between camera deco and the inlay fleeing into the antenna and damaging the capacitor, causing the capacitive sensor to function Solution: 1、Proposal: ME add black film to cut the discharge path ，12/15 2、ANT 5 and ANT 10 add DNS TVS |  | 韩凯 | 小熊 |  |  | A.Milan 5G
2021-12-20 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue:MILAN5G USB can not connect sometimes IKSWS-25957 , Get 1 unit N5MV120284 that can reproduce. Clue: 0. NEW cable can not reproduce . some old cable easy to reproduce. 1. when it reproduce ，move Type-C at phone side , it turn ok 2. when it reproduce ，replug cable at PC side ，it still NG 3. when it reproduce ，Power cycle Phone ，it still NG 4. when it reproduce ，replug Battery connector and Cable At PC side ，it still NG 5. swap TMO Main PCBA ，old cable can reproduce，NG 6. swap a NEW sub PCBA ,old cable can not reproduce, ok. 7. Type-C Connector Vendor of this unit is Lecton Root Cause: Type-C connect issue Solution: KP do the further analysis -xiongxiong | IKSWS-25957 | 李果 | 文亭 |  |  | A.Milan 5G
2021-12-17 | 5.DVT1 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3] Issue:MILAN5G 2nd source Ti BQ25890H OTG easily to triged when connect some hub ，report by SW test team Clue: 1.change Boost limit from 1.2A to 2.4A ,it is better (some hub can work ) 2.SGM41542 is ok with 1.2A boost limit . 3.test the current waveform ,SGN41542 is same to BQ25890H 4.there are to many Current burst when a hub is working . 5.different hub have different current burst 6.TI reply they can not change OCP deglitch time (250uS）.it is BQ25890H HW limitation . And OCP setting is = boost I limit. Root Cause: there are big Current burst when a hub is working , and some hub have more big current hurst that trig BQ25890H OCP . Solution: change Boost limit(OCP) to max and add Ibat monitor to make sure Ibat will not Over the battery SPEC 3.5A (monitor Ibat ,if Ibat is bigger than 3.5A ,disable OTG . Import form 20211217 . It can cover more hub . | link | 文亭 |  |  |  | A.Milan 5G
2021-12-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue:FVCV19 capsensor ESD ，15KV air，100 times/zone1：Cap sensor no function,unable to recovered 15KV zone1:D2(40),D3(20),D4(70) Clue :1 . CAP C502 shorted to the GND Root Cause: electricity discharge through the signal between camera deco and the inlay fleeing into the antenna and damaging the capacitor, causing the capacitive sensor to function Solution: 1、Proposal: ME add black film to cut the discharge path ，12/15 2、ANT 5 and ANT 10 add DNS TVS |  | 韩凯 | 小熊 |  |  | A.Milan 5G
2021-12-06 | 5.DVT1 | 2.Power | 5.3 EE DVT | S3 | Closed | [s3] Issue::DVT1 2nd WH145578 fail (unable to power on：D1/N5MT1C0102(after desence)） Clue : Root Cause:1 .L7A short to GND which lead to power on failed. 2.The short-circuit area was found inside the PCB Exp:L7A is still short-circuited after removal IC 3.Why pcb short ? Exp:send to Tripod for analysis,Result:L7 A Short to GND Via on one Point. Solution: 1.Expand Via distance on this point. and DRC the whole PCB to find if other risk exit. | Link | 敏敏 | 李果 |  |  | A.Milan 5G
2021-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3] Issue::DVT1 edu03 WH145517 fail (Unexpected auto power off:C1(8kv air,Zone6),C2(15KV air,Zone6） Clue :1 .Unexpected auto power off:C1(8kv air,Zone6),C2(15KV air,Zone6 Root Cause:FPS signal interference leads to system shutdown Solution: 1.FPS SPI MISO/MOSI resistance from 100R change to 470R 2.FPS CS/RST/INT resistance from 100R change to 1K Test Verification PASS | link | 韩凯 | 小熊 |  |  | A.Milan 5G
2021-11-04 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3] Issue:DVT1 ATT Drop(WH145506) Cap-sensor CH2 no function Root Cause:1. Solution: 1.ME will change screw holes to optimize structural stress 2.Optimize cap sensor signal line width(0.05->0.2) | LINK | 小熊 | 李果 |  |  | A.Milan 5G
2021-11-04 | 5.DVT1 | 9.Memory | 6.Issue | S2 | Closed | [s2] Issue:DVT1 ATT Drop(WH145506) Unable to enter system:D6(1m,top),D11(1.25m,right)/Unable to power on:D10(1.25m,back) Clue: 1.The units enters the 9008 mode 2.If memory pressed by external force, it can be turned on. 3.one unit Press Memory Display error and system hanging with blank display. 4.One unit sometime can't boot up ,no uart log,Qdutt sometime abnormal connection. Root Cause:1.Memory signal path broken Exp: Memory Solder Crack from red dye test and cross section Result: PCB inner Via Crack and Solder Crack Observed. 11/10 Solution:1.ME Optimize Strain Design 2.Reserve Memory Underfill Capability on Shielding Case. | Link | 嘉琨 | 李果 |  |  | A.Milan 5G
2021-10-14 | 4.EVT | 2.Power | 6.Issue | S3 | Closed | [s3]Issue:Unable to power on after Pulse Transient Surge Test on 150V. （1）WH144512 DVT EDu14 - Pulse Transient Surge Test fail 2.After 150V surge test, unable to power on,D3(486uA)D4(14.58mA)(Vbat） 3.Initial Leakage Current:D1(240uA)D2(225uA)D3(220uA)D4(227uA) （2）WH144526 DVT EDu14 - Pulse Transient Surge Test fail 1:Initial leakage current out off spec:D1(230uA).D2(229uA) 2:unable to power on:D1(250V,12.7mA)D2(150V,115mA) Vbat Clue: Monitor DVT build if any failure rate. Result: DVT build Root cause: 1.Surge cause damage of Charger IC and Fuel Gauge which connect to Vbat 2.Charger IC and Fuel gauge have lower anti Surge Capability(6V) then QC PMIC. Exp1. Change a better surge protector(10.5V->8V Clamping Voltage) and layout improved for fuel gauge , Result:10/26-- two machines pass EDU14 test Solution:1.Change a lower Zenar Diode. 10.5V->8V 2.layout improvement for fuel gauge with Solution 1&2,DVT1 (1st RT/FG+1st SGM/Charger) Vbat EDu14 test pass | Link | 敏敏 | 李果 |  |  | A.Milan 5G
2021-11-16 | 5.DVT1 | 3.Charging | 5.3 EE DVT | S3 | Closed | [s3] Issue:DVT1 EDU14 Second Vendor Verification Unit Vbus 1 unit 190V <200V failed Clue :1 .EVT 2unit ，DVT1 2unit pass 500V 2. The Variant is OVP Second Vendor Root Cause:1.OVP IC damaged Solution:remove SGM Second Vendor OVP from Milan 5G . Done from DVT2 BOM further study for incoming project： add a 22pf cap on OVP voltage feedback pin Verified pass 2 units .but no place to add the cap in Milan 5G. | link | 文亭 |  |  |  | A.Milan 5G
2021-11-15 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | [s3] Issue:DVT1 2nd charging IC Ti BQ25890H , input current can not reach 3A. （setting to 3A，test result is about 2.7A ） Clue :1 .Log check :IINDPM occurred . (suspect some Ilimit occurred . but why it occurred ?) 2.setting to 3.25A（MAX setting） , test result =2.8A . setting to 2A， test result =2.2A 3.setting higher Vbus ,Ibus no change . 4.setting higher Ibat MAX to 4A from 3A , Ibus no change 5. Ti reply it is average current limit . Root Cause:1.Proposal:Ibus limit accuracy problem Solution: Keep current setting ，and use higher Voltage for enough input power | link | 文亭 |  |  |  | A.Milan 5G
2021-11-09 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [s3] Issue:DVT1 2nd barometer TDK 20100 pressure deviates from 10K Pa relative to 1st BMP580/Bosch Root Cause:1.Configuration Issue Exp:1.mode config check. Result:Issue Solved. Solution:1.SW bug fix |  | 小熊 | 李果 |  |  | A.Milan 5G
2021-11-09 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3] Issue:DVT1 2nd charging IC Ti BQ25890H , QC 3 can not work sometimes Clue :1 .D+&D- can not out put 3.3V (similar to the EVT phone that without Dsel 47nf cap) 2. Ic charging type detection it too slow. (similar to the EVT phone that without Dsel 47nf cap) 3. V D+& D- At Charger IC is 3.3V . and 0.983V at USB connect side. --suspect CPU pull down the USB BUS Root Cause:1.Proposal: Dsel Cap is too faraway from pin and wire width is only 0.05mm. Exp1: EVT1 phone rework 1 unit 47nf cap and clue1 &2,result is ok exp2:DVT1 phone ,reowork 1 more wire from 47nf cap and pin. result :ｆａｉｌ exp3 : DVT1 phone , rework 47nf cap closer to pin . result :ｆａｉｌ 2.SW logic control for CPU High Z have some bug（BC1.2 interrupt do not set CPU High Z） Solution: 1. BC1.2 interrupt change to set CPU High Z ---SW change import from 11/12 .temp sw test ok 2.change Dsel 47nf cap closer to IC pin and add wire width in DVT2 for better cap performance. done---wenting | link | 文亭 |  |  |  | A.Milan 5G
2021-10-22 | 4.EVT | 3.Charging | 6.Issue | S3 | Closed | [s3] Issue:Charging I2C bus error sometimes(Feature firstly ready on 10/22) Clue: 1.Reproduce 1 time when use 2A OTG , recovered after power cycle （press powerkey for 10S）。When Issue happen no charging status change can happen again：such as USB cannot work，charge Icon not change 2.There are some charger IC I2C reading error before I2C bus error in Log --suspect charger IC I2C reading have some problem. 3.this unit use SGM41542 charger IC. I2C error is I2C error -110 when I2C Bus can not work. 4.Rry to reproduce. Pressure Test. Result: 1 units reproduced. 5.There are some interference on I2C when OTG 2A working. 6.Not reproduced on formal Maximum Current Charging Scenario ,Test by BB and Test Team. Root Cause:Proposal: 1.SDA Signal of I2C interfered. Exp:Add 33pf on I2C SCL&SDA (close to AP) .result : 1 unit can not reproduce in OTG mode. (remove 33pf and it reproduce again ) 2.AGND and DGND not separated in Charge IC Design and Noise coupled to SDA. Solution: 1.Add 47pf +47R on SDA(Close to AP),reserved 47pf +47R on SCL(Close to AP) . reserverd 20R on BTST at charging IC . DVT2 Import. | link | 文亭 |  |  |  | A.Milan 5G
2021-09-23 | 4.EVT | 2.Power | 5.2 BB Test | NA | Closed | [NA] Risk： CC SGM7220 current leackage is about 70uA when phone power off . （found by ODM project） Root Cause: VDD is VPH_PWR ，and /EN design to GND . which means the SGM7220 is always on . solution : proposal 1:no change and accept 70uA current leackage proposal 2:change EN to a GPIO 58 (reserved Pull down 0R ) ，from EVT2 EVT V04机器低电流是194mA，比V03降低42mA 。 close |  | 敏敏 | 文亭 |  |  | A.Milan 5G
2021-10-22 | 4.EVT | 3.Charging | 6.Issue | NA | Closed | [s3] RISK:Charging IC EN GPIO control ，can it work when Battery is very low (System not turn on) Solution:test and check can charge dead battery . so no risk |  | 文亭 |  |  | 6.No Change | A.Milan 5G
2021-10-09 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [s3]EVT Handset TDD -60dB clue: Block the MIC hole，noise disappear Rootcause: 1.Spring on Sub board ? Exp:Check Spring. 2.other noise auido come into mic. EXT: Remover C304,improve to -80dB Rootcause:The 100pf CAP vibrate on GSM max power , the special position Intensifying problem. | link | 院长 |  |  | 3.BOM | A.Milan 5G
2021-10-09 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [s3]Issue:WH144494 Rear flash light lens fusion:A1~A6,B1~B6(2)-TH/TC Root Cause:1.Flash on time set to S level,too long. Exp:1.Re-Config to the right parameter. Result: Solution：1.Fix config bug. |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | A.Milan 5G
2021-10-14 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA] Risk： USB disconnect in GSM900 MAX power with long USB cable for Audio tuniing ，report by Xiaozh1 Root Cause: long USB cable easier to be coupled by RF energy. solution : monitor ,EVT build no issue found . and this is not a user case |  | 文亭 |  |  | 6.No Change | A.Milan 5G
2021-10-09 | 4.EVT | 3.Charging | 3.Review/Simulation | NA | Closed | [NA] Risk：Charging IC NTC design risk ，Vendor review Root Cause: Need to check with Vendor again and get a design for DVT1 build (pull up and pull down R ,and NTC selection ) solution : 1. Change to fix temp design for charging IC。 2. and SW config the thermal protection base on Fuelgauge NTC data |  | 文亭 |  |  | 1.SCH | A.Milan 5G
2021-10-11 | 4.EVT | 1.Platform | 4.Build | S3 | Closed | [S3] Issue ：SOL LED light guide performance not good Root Cause: need to check the phone with ME solution : ME own |  | 文亭 |  |  |  | A.Milan 5G
2021-09-14 | 3.PEL | 2.Power | 5.1 Bring up | NA | Closed | [NA] Issue: 1 EVB2 board RT9246 fuelgauge Device ID read error |  | 李果 |  |  |  | A.Milan 5G
2021-09-14 | 3.PEL | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3] Issue: RT1715 PD fail sometimes . found by SW Chailu Clue1: 1.I2C go keep low most of the time . 2. power on with charge plug in and it can work 3.Resester reseted found by vendor. Root Cause: I2C SCL keep low cause RT1715 reset . (reset function is open with vendor SW code ）. SW find the rootcause and solve the issue Solution: Proposal 1. disable RT1715 reset buy I2C timeout function . （temp SW checked ok with 2pcs PCBA） Solution2. make I2C keep high when no I2C communication . change import | link | 韩凯 | 文亭 |  |  | A.Milan 5G
2021-09-13 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [S3] Issue: 2nd charging IC RT9467 bringup found ,the phone power up when no USB plug in sometimes . Clue1: 1.log show power on reason is charger power on 2. RT9467 REGN = Vbat some time (without USB plug in) 3.checked ，REGN will on 500mS when plug in Battery or each I2C reading. Root Cause:1 REGN = Vbat some time (without USB plug in) ，which will cause main PMIC power on then cause phone on Solution: Proposal 1. For EVT temp solution ，Delay 550mS before kernel shutdown ？----SW：Weiwei，huosheng Proposal 2. For DVT1 ，change to Vbus for the mos control ？---BB：Xuemin Exp2： use VBUS replace REGN to pull down CBL_PWR_N,VGS=1.5V can drive the MOS to pull low CBL_PWR,R1:R2=7:3 ，When VBUS=13.2V,VGS=3.96V;when VBUS=5V,VGS=1.5V Close: remove Rt9467 From Milan 5G base on GCM feedback (replace it with BQ25890H from EVT) | link | 敏敏 | 文亭 |  | 3.BOM | A.Milan 5G
2021-09-03 | 3.PEL | 1.Platform | 5.2 BB Test | S3 | Closed | [S3] Issue: Keys can not work in Fastboot mode Clue1: 1.it is ok in normal mode. 2. it is first time connect V+ to PMR735A . 3. Corfu 5G DVT1 meet same issue Root Cause:1. suspect pull 1K to 1.8v for PMR735A GPIO is too large . Exp1. change pull up R form 1K to 10K and it works . (only SM4350 use 1K pull up ,other projects use 10K ) Solution:1. change pull up R form 1K to 10K（R1018） ，done from EVT |  | 文亭 |  |  | 3.BOM | A.Milan 5G
2021-10-12 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | IKSWR-143124 SM8350// Yukon // R //Phone is OFF. Connect the usb cable, the phone keeps turning off 关机界面的瞬间，插入USB，关机后不会自动进入关机充电界面 1.not a real issue |  | 文亭 |  |  | 6.No Change | 9.Yukon
2021-09-29 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | [NA] Yukon DF DP issue IKSWR-137479 cable issue change a cable and ok | LINK | 芳梅 |  |  | 6.No Change | 9.Yukon
2021-10-09 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | 电量计：充电到68% ，关机后，一段时间开机变成56%. IKSWR-139932 高通 case：Case Number 05446277 [View Hierarchy] Action：外加检测电阻用电源侦测一下，看实际电量和UI 偏差到底多少。 10/13 前 Root cause：SW config issue。 Solution： change SW |  | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-09-24 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH144198 D3 ESD capsensor ，After -8kv air discharge,capsensor ch4 no function and recovered after reboot, 15kV ok. Root Cause:1. monitor Solution: Pilot ok |  |  |  |  | 6.No Change | 9.Yukon
2021-10-09 | B.PVT | 5.Camera | 5.4 ALT | S3 | Closed | 【故障来源】PVT MXc03跌落试验。 【复现现象】敲击主板的时候图像卡住，重开相机可恢复。测量连接器各个引脚阻抗、连接正常。 【历史线索】产线也有发现几台主摄异常，有发现U1000 和J3150-15印刷少锡。 【推测原因】U1000 MIPI引脚缺锡断裂，震动时断路，MIPI信号终止，CQA图像卡住。 【Next Plan】 1. X-ray查看锡量。=====> 无异常 2. 安排切片查看U1000和J3150引脚是否锡球断裂。===> 发现J3150连接器底部出现开路情况（报告待更新） | Link | 邦邦 | 范南 |  | 6.No Change | 9.Yukon
2021-10-09 | B.PVT | 1.Platform | 4.Build | S3 | Closed | Issue Description: PVT ROW 8+256 bom wrong Root Cause analysis: PCM CR @ DVT2 after DVT2 BOM released,Manual Changed variant BOM at DVT2，but Lost update ROW 8+256 BOM when PVT BOM released. Solution: Add 8+256 memory configuration variant to schematic files Update the BOM Corrective / Preventive Actions Check released BOM list base on SKU information table （including Memory config ，HWID config ，SKU config） | link | 韩凯 | 文亭 |  | 3.BOM | 9.Yukon
2021-09-06 | 7.DVT2 | 4.Audio | 5.3 EE DVT | NA | Closed | [S2] uplink has noise when handset calling clue: 1. When charging ,noise dispappear 2. When close calling arithmetic, noise disappear 3. On idle calling mode,no noise 4. On record mode,no noise 5. Volte MODE no noise 6. GSM mode (low power transmit) has noise 7. No noise on handfree mode and no noise when change mic1 to handfree mode 8. No noise before moden node. Next step: 1..Ask qualcomm for help 2.Moden team analyze | LINK | 院长 |  |  | 6.No Change | 9.Yukon
2021-09-29 | B.PVT | 2.Power | 5.6 User Feedback | NA | Closed | [NA] Yukon DF Device Rebooted - Stuck in Boot Screen IKSWR-139460 Clue ：1.L5E LDO error in Ramdump log. QC CR：https://qualcomm-cdmatech-support.my.salesforce.com/5004V0000181Vef 2. L5E is RF Power for SDR RF Tracking this case |  | 敏敏 |  |  | 6.No Change | 9.Yukon
2021-08-27 | 7.DVT2 | 12.EMC | 5.3 EE DVT | NA | Closed | [NA] found 1 WH143148 D1（NYKR270825） After-8KV air discharge at zone3,Display Flickering and Display color change ,30 minute recovery.(11:06 2021/8/26) clue: 1. Root Cause:1. suspect display module damage Solution:1.PVT ok |  | 韩凯 | 芳梅 |  | 6.No Change | 9.Yukon
2021-09-26 | B.PVT | 3.Charging | 5.5 Certification | S3 | Closed | [S3] TUV certification ：battery output current =5.8A >4.85A of CB in battery spec. testmode : pull current from type-C Root Cause:1. PM8350BH OTG dont have OCP . Solution: add a detection on Ibat to monitor Battery current . when it output >4.85A ,disable OTG . temp SW test ok by BB . TUV retest 4.69A ,<4.85A pass |  | 文亭 |  |  | 6.No Change | 9.Yukon
2021-08-26 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]Yukon intermittently notice Pluging/out after charger connected. Root Cause: 1.Charger Reset Frequently 2.CC GND Voltage >0.43V 3.Cable GND Mesh Broken ,165mΩ(Spec 83mΩ） 4.2018 Cable Solution:1.Cable Team Own |  | 文亭 |  |  | 6.No Change | 9.Yukon
2021-09-15 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | [S3] Issue: 2nd micron memory stress test ，3/20@55°C ， 7/20@-20°C auto power cycle. Reproducing:Retest No Issue@55°C， ，5/20@-20°C Clue1: 1.RPM_ERR and AOP Log show some LDOor SMPS fail.-Need RPM expert Double Check and confirm it. Root Cause:1.Memory Power Issue? Exp1.Monitor Memory Power @-20°C. Result:9/17 Exp2.Log Analysis. Result:SPMI Communication Time Out. Exp3.Enhence SPMI Driver Strength. Result: 9/17---with SW RRX31.Q3-50,memory stress test run 24hrs,no auto power cycle happen Solution: 1. Enhence SPMI Driver Strength，Validated Pass，SW updated |  | 敏敏 | 嘉琨 |  | 6.No Change | 9.Yukon
2021-09-06 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH143213 C1 ESD capsensor ，After -15kv air discharge,capsensor ch2 no function without recovery. Root Cause:1. C204 on CH2 short to GND， change C204 CH2 recovery 2.found crack on C204 Solution: Factory check build process PVT No issue found in build and TCC test. | Analysis link | 韩凯 | 小熊 |  | 6.No Change | 9.Yukon
2021-09-06 | 7.DVT2 | 3.Charging | 5.6 User Feedback | NA | Closed | [NA] EUT found 1 charger+cable cannot charge clue：1. it is 45W DVT1 charger sample + cable（without any mark on calbe） 2.swap EXP check :issue follow Cable 3. issue happen when Iubs >3A Rootcause：the cable R of GND is too high causing PD process abnormal(160mR VS 83mR MAX in SPEC ）. solution：No real issue | link | 文亭 | 韩凯 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-09-06 | 7.DVT2 | 2.Power | 5.6 User Feedback | NA | Closed | [NA] found 1 DVT2 unit go dead when sleep ， sometimes 1 day,Need press powerkey more than 10s to recovery. clue: 1. reflash some SW version but all reproduced . 2. 128GB Kioxia UFS exp：The fail is very similar to the Kioxia UFS issue . We update the SW to latest one RRX31.Q3-44 which checked solve the Kioxia UFS issue . monitor the result From 9/10 to 9/15 ，no reproduce Root Cause:1. memory ufs issue Solution:1. chenge SW | IKSWR-130146 | 敏敏 | 文亭 |  | 6.No Change | 9.Yukon
2021-09-06 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2] DVT2 WH143213 ALT A1这台有出现跌落后P/L sensor no function，重启后P-sensor 恢复，但是L-sensor问题还是存在，Loop5（NYKC2F0130） Clue：Issue：ALS can not go DARK status （maybe light leakage） Root Cause:1. CG tilted(CG翘起) increased ALS reading Solution:ME follow | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-08-20 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [S3] DVT1 Mdu30 Failed on Charging Scenario(7.1°C@back,4.0°C@Front). Root Cause:1.SW Bug and Thermal config fine tune. Solution:1.SW Bug Fix and import New Charging Thermal Config. RD Validated pass. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-07-19 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] Issue: cap sensor can not work on CH0&CH4 after ESD ， recover after charger Plugin. Clue1: D1、D2、D4 failed without chargers，D3 pass with a charger Clue2：recover after charging Root Cause:1. CapSensor Affected by ESD Through ANT. Exp1. take another phone ，recover after quiting CQA texting Exp2. catch log after cap sensor ch0、ch4 no function Exp3:Confirm the detailed recover duration Solution:1. Accept |  | 韩凯 | 李果 |  | 6.No Change | 9.Yukon
2021-07-19 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3] Issue: DP Eye Diagram 4 lane fail on 8.1Gbps Clue1:Eye Height not enough Clue2:Layout Improved. Root Cause:1.Voltage level not enough or Pre-emphasis Exp1. Fine Tune voltage and Pre-Emphasis Parameter,Result: 8.1G mostly Pass while 1 lane failed a little. 2.Proposal:Parasitic capacitance effect Exp2.Optimized lane and Grounding separation . Result: DVT2 verify. Solution:1.Update Redriver Parameter. Validated Mostly pass 2.Optimize FPC and PCB layout . DVT2 import and verify. | LINK | 芳梅 |  |  | 2.PCB | 9.Yukon
2021-06-22 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [s3] Power off current =350uA Vs normal project 200-uA Clue:1 NFC boost is on when phone power off 2. Lenovo MP project DOOM =320uA ，Qualcomm phone QRD= 340uA Root cause: 1.NFC boost alwayse on . 59uA ,should be off when phone power off 2. SM8350 power off current is higher than other platform solution : 1.NFC boost EN change to pull down from EVT-B （V03） 2. Yukon Power off current target should be 300~350uA ，monitor in DVT1 factory BT test 3. Base on the DVT1 test data，output shipping keep time limit for Yukon project to PQM. DVT1 testdata：300~350 uA. sync result to PQM yet | Link | 敏敏 | 文亭 |  | 1.SCH | 9.Yukon
2021-06-28 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue:Camera Team feedback DVT1 unit, RC adjust Value Avg=13, Over Spec 10 . Issue Check: After Test with more Units , We found Yunkon has Same Performance with Sierra . Furtherly seek if any chance to improve R/C adjust performance. Root Cause: 1.Speculation: AVDD Ripple , Result: Not AVDD Ripple. Exp:AVDD Measurement . Result: <19mV ,Best Class. 2.Speculation:EMI ,Result:No effect Exp:Shielding Whole Camera with System Ground , Result:No effect. Exp:Dismantling PCBA and Change Cam Grounding , Result:Worse 6%. Exp:Replace 100pF Cap with 2.2UF after Dismantling. Result:Better but little optimized than Original. Exp:Supply Cam DVDD externally. Result: No effect. 3.Speculation:Camera Thermal Noise? Result:Suspend duo to no available exp. Exp:Cooling help to reduce background noise , and R/C increasing 4.Speculation:Camera Module? Exp4.1:Switch Camera.Result:Suspend duo to no available exp Exp4.2:Replacing AVDD&DVDD ,Result:No Effect. 5.Camera Sensor Exp:Exp4.2:Replacing AVDD&DVDD ,Result:No Effect. Exp:Optimize Sensor PSRR through Parameter Setting from samsung. Result:Better. Solution:1.Replace 100pF Cap with 2.2UF, DVT2 BOM import. 2.Optimize Sensor PSRR through Parameter Setting from samsung. | LINK | 邦邦 | 范南 |  | 3.BOM | 9.Yukon
2021-07-19 | 5.DVT1 | 5.Camera | 5.2 BB Test | S3 | Closed | [S3] Issue: camera LED torch brightness differ with EVT Root Cause:1. EVT pcb LED CH1 leakage to CH4, CH2 leakage to CH3 2.Async on Capture and light. Exp:1. camera tunning issue,Align Capture and light Timing and adjust light width, Result: 8/3 Solution: 1.SW update | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-08-02 | 5.DVT1 | 1.Platform | 5.5 Certification | NA | Closed | [NA] Issue: ADR test can not read IT3 SIM (一种模拟SIM卡for test ) Root Cause:1. Data line without pull up Solution: 1.ADDpull up 15K，retest pass . Import form DVT2 2. rework 2 more unit for ADR test |  | 李果 | 文亭 |  | 3.BOM | 9.Yukon
2021-07-13 | 4.EVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3] Issue: RS Pretestfail ，uplink Over 13DB clue1: test 4 headsets with same result Root Cause:1.Audio Switch Modulation Exp1.ADD 1nf cap on headset MIC channel ，after Audio switch （C1817 ） Result: 4dB improvement,Still failed 8dB Exp2: Modify Cap 2.2 nf ,Result: pass(over 15DB margin）on 1 unit Exp3: without Back Cover and Graphite Film ,Result: fail 5DB on 1 unit. Exp4: Modify Cap with bigger value and with Cover and Graphite Film,retest 2 units. Pass Solution: 1.Modify Capacitor Value on Aux Channel. Validated Pass. | LINK | 院长 | 李果 |  | 3.BOM | 9.Yukon
2021-06-28 | 4.EVT | 5.Camera | 5.2 BB Test | S2 | Closed | [S2] Issue:Obvious line noise on 108M image preview in darkness. Root Cause:1.AVDD power noise Solution: 1.Optimize AVDD Power feedback routing,DVT1 Improved 2.Optimize AVDD Grounding on DVT2 |  | 邦邦 | 范南 |  | 2.PCB | 9.Yukon
2021-06-28 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [s3]Issue:Flash Led can not work 4/300 in EVT. Root Cause:suspect LED CH 3 control impact LED CH 2 Exp: enable LED CH 2&3 at same time by adb command and it can work . Exp: SW version enable LED CH 2&3 both ,but fail . need more check Solution : 1.Change SCH&PCB to disconnect LED CH3&4 （LED driver 1CH can support 1.5A ,we just need 1A each CH ,it is enough .） monitor DVT1 DVT1 no issue so far | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-06-28 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [s3] Backlight not work sometimes , recover after power cycle .(found by Chenwt) Clue 1 .Log checked : Backlight Driver IC I2C read fail when initial . but Other ICs on the same Bus I2C reading are ok. Can not reproduce solution : close ，reopen it if it reproduce | link | 芳梅 |  |  | 6.No Change | 9.Yukon
2021-06-21 | 4.EVT | 5.Camera | 4.Build | NA | Closed | [s3] rear camera 2 test in CQA will cause rampdump sometimes Camera2 Kernel panic https://idart.mot.com/browse/IKSWR-100409 clue：can preview ，and video capture fail Root Cause：Speculation:SW issue Solution: temp SW continue build 107 checked ok . close issue . |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-06-28 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3] Obvious Audio noise in receiver when calling enable. Clue1:400hz and Harmonic, Not TDD. Clue2:No noise with Wechat and Earphone Root Cause:1. Wrong audio path config and noise import by sidetone Solution: Modify audio path config ,temp SW check ok. plan to merged form 7/2 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 9.Yukon
2021-06-22 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | [s3]Dark display 3 in 24 pcs in EVT build Clue: 1. display connector damaged . 2. Backlight IC burned . Root Cause: 1.Display Connector Damaged which lead to IC Burned. 2.Connector is not in the best place 3.ME need one time to adjustment the accurate position Solution: 1.Move connector upper 0.66mm, PCB modified in DVT1. Tracking in DVT1 ，reopen it if issue reproduce in DVT1 build |  | 芳梅 | 邦邦 |  | 2.PCB | 9.Yukon
2021-06-21 | 4.EVT | 4.Audio | 4.Build | S3 | Closed | [s3] SPK sound weak in EVT CQA test ，100% Root Cause: 1.Smart PA out N & sns N swap Solution: 1.Fix current 32+3 units through Change R4650，R4651 to 0201 0R, done. 2.Fix Smart PA Sch in DVT1 Version,Done Tracking in DVT1 ，reopen it if issue reproduce in DVT1 build | link | 院长 | 文亭 |  | 1.SCH | 9.Yukon
2021-06-21 | 4.EVT | 7.Sensor | 4.Build | S3 | Closed | [s2] Cap sensor CH3 no function in CQA test ，100% Rootcause： parameter not ready . Solution: change parameter,New parameter tested and CH3 can work. by 6/22 | link | 小熊 |  |  | 4.Parameter | 9.Yukon
2021-10-09 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | [na]Issue:some user feedback power drop when Video when battery on 4%. Root Cause:1.Battery Voltage drop to 3.0V. Solution:Proposal:1.3.2V Shut down voltage ->3.4V , 50mA 1% power loss. |  | 李果 |  |  | 6.No Change | 8.Sierra
2021-07-15 | C.RAMP | 3.Charging | 4.Build | S3 | Closed | [s3]Issue: CQA-BATTERY- USB test result unknown,CR :IKSWR-110537 Clue1: log check 4, BATT_ID_2 = 239720 ， Unknown battery detected, unknown_battery_behavior: 1 Root Cause: 1.Batt_ID pull down R=243K +/- 1%， but reading 239.9K from SW log. SW check ： 240K ~450K .Can not cover this case Impact：phone can not charge and con not power on when Vbat is too low (lower than power on voltage limit) Solution: 1. SW Open limitation to 220K ~450K . Import from 7/19 in to mainline. change : https://gerrit.mot.com/#/c/2012268/ coming project : Yukon change Batt_ID to 100K which SW check is 15K ~137K . Milan5G use 100K too . notice Corfu 5G change to 100K too. |  | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-07-12 | B.PVT | 11.Thermal | 5.6 User Feedback | S3 | Closed | [s3]Issue: USB Connector Temperature Detection 125°C mistriggered found. Clue1:No abnormal signal on NTC found. Root Cause: 1.Speculation:ADC Not stable when sampling. Solution: 1.Notice triggered only after Sampling 3 times each second and all over 75°C. SW release new version and verify. on-going |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-06-11 | 7.DVT2 | 10.USB-C | 4.Build | S3 | Closed | [na]Anti -water Icon showed when DP insertion in Factory ,recovered after unPlug for 1 Min，0.4% FR. Root Cause:1.LPD Mode Active when only one CC Ra attached in 200ms(Powered Cable without Sink attached). Solution: 1:SW Workaround to re-verify cc status before Show Anti-Water Icon.-SW ，Validated Pass. |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-07-12 | B.PVT | 10.USB-C | 5.3 EE DVT | S3 | Closed | [s3]Issue: DFer Feedback that LPD Triggered when Charged with 120W VIVO Charger. Clue:VIVO 120W has their own protocol and SBU used. Doc link:https://docs.google.com/presentation/d/1n0tqqY8eS7C6cWWbVOopxZkmtI4Qo3L22XRAebT7d2g/edit#slide=id.g4057557fca_0_46 Root Cause: 1.When Charging,CC Detection Triggered and SBU found 45K resistance,which match LPD condition and trigger Notice. Exp:Log analysis. Result:VBUS Shut Down and CC&SBU triggered. 2. SBU(45K resistance) used in VIVO 120W Charging Cable, When no VBUS input,LPD tirggered. Exp:Test Samsung S20 ,Same Issue happened. Solution: 1.Proposal:Accept it. since this issue also found in industry released products. 2.Proposal:Adding uncompatible attachment found in LPD notice context. |  | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-06-18 | 7.DVT2 | 10.USB-C | 5.6 User Feedback | S3 | Closed | [na]Screen Keep Turn on/off in about 10s when PD Charger Plugged(Display LG 2K Game TV) -Brazil DFer feedback . Clue1. Reproduced in third party Dongle. Clue2: No Issue without PD Charger Plugged. Clue3:No error found in log. Clue4:Verify about 20 different 4K Display/TV in china，Result:Can't Reproduced Root Cause:1.Using LG 2K Gaming Display low speed hdmi port. No Issue with high speed HDMI Port. Solution:1.need user to plug into right hdmi port |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-09 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [s3]Issue:DP not work when Plug Charger with a 9 in 1 hub. -Brazil DFer feedback . Clue1:No issue with inbox dongle. Clue2:Buy Same Dongle to reproduce. Result:Tahoe using Parade PS5169 Redriver also have issue.Onsemi No Issue. Root Cause: 1.PD Charger Insert and raised up to 9V,Hub Reset occured at 8.6V. 2.PS5169 Redriver shut down data Lane after hardware reset received which lead to DP re-training failed. 3.Speculation: If Plug in PD Charger Firstly and then plug sierra，Hub Keep Reseting duo to 9V3Amode comsume more current and more voltage drop on hub and triger the hub defects,this is reset on 8.6V. Solution: 1.Hub Issue,Accept it. 2.SW Pick newly PS5169 Fix from QC,Issue fixed in XiaMen Dongle when PD Charger Plug Later.But If Plug in PD Charger Firstly，Hub Keep Reseting,Issue Remained. 3.Proposal:SW Workaround - Keep PD Charger working in 5V/3A Mode after multiple Hardware reset received and DP on Position. -It Works but needs SW Evaluation. | Link | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-09 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [na]Issue:DP not work when Plug Charger with a 3 in 1 Dongle. -Brazil DFer feedback . Clue1:No issue with inbox Dongle. Clue2:Buy Same Dongle to reproduce. Clue3:No any error found in log Clue4:No Issue with 1080p Root Cause:1.Speculation-Issue in HDMI Part between 3 in 1 Dongle and Display in high speed. Solution: 1.Change Dongle. | Link | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-06-02 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | issue：display stuck after 15kV air/6kV contact discharge，recoverde by Slide screen clue1：remove deco board testing camera module，appear easily clue2：12kV air not appear when removing the copper foil on the back of the main camera Root Cause：camera mipi data of module shocked when ESD testing solution： |  | 韩凯 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-06-02 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue: QC3+ can not work with 33W Saierkang Charger ,but ok with 33W Kangsu Charger Clue 1. Different Charger Vendor . Root Cause:1. Saierkang charger can not output 6V when 2nd QC 3+ process . The time form 1st QC3 process to 2nd QC3+ process is about 845mS Solution:1. change SW，complete QC3+ process at first process，similar to Berlin. solution import from 6/4 | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-27 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3]Issue:Test Thermal @元神 keep 60FPS，46°C observed. info: Mdu30 Pass. Root Cause:1.High Performance Game Mode. Solution:1.Optimize Thermal Config to meet thermal target. on - going. |  | 林峰 |  |  | 4.Parameter | 8.Sierra
2021-06-06 | B.PVT | 3.Charging | 5.2 BB Test | NA | Closed | [s3]Issue: 30W charging PD charging current low at last stage Clue:1. Code change at sm8250 baseline: 296 /* This is for burton ONLY – specific to the battery configuration / 297 / Enable float voltage compensation (0x1071) and set resistance to 30 ohms (0x118B) */ 298 err_flag ¦= pm_comm_write_byte(0x2, 0x1071, 0x60); 299 err_flag ¦= pm_comm_write_byte(0x2, 0x118B, 0x0F); Root Cause: AFVC cause this case Solution:1.SW Config, RD Validated Pass. | https://idart.mot.com/browse/IKSWR-101718 | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-18 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | [s3]Issue: 30W charging UI100% point test result is 2A VS 0.82A in SW setting. CR：IKSWR-94815 Clue:1. USB charing result 100% in UI VS 90% in Coulomb Counting . 2. charging current jump up for a few minutes when BQ 30W charging switch to PMIC charging Root Cause: 1. SW Not Config Correctly Solution:1.SW Config, RD Validated Pass. | link | 李果 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-28 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [na]Risk:33W Charging full power rate Verification Exp:SW build a Open limitation of 33W and verify. Result: 6/2 BB test done. No issue related power found. | Test summary link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-24 | 4.EVT | 10.USB-C | 5.3 EE DVT | NA | Closed | [s3]Issue:DVT2 Mxc04 ,Can't Charging and Can't Recognize PC. Clue:Tester Enable USB Function though USB Port Damaged Informed. Root Cause:1.Observed ForeignMatter over most of USB Socket Pin Pad.- ME Analysis Solution:1. |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-20 | 4.EVT | 10.USB-C | 5.3 EE DVT | S2 | Closed | [s2]Issue:Mxc04 USB Corrosion 1/4 in EVT. Root Cause:Salt Water in USB Port and VBUS/CC/D+/D- Active in Plugin which lead to Electrolysis effect Solution:1.Import Salt Water ingression detection ,DVT import and Validated 12 units Pass. 2.Proposal:Refer Samsung S20/S21 's mechanism,Enable 2 Level LPD Notice:Vibrating and notice on charger plugin when in LPD Mode. |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-05-12 | 5.DVT1 | 10.USB-C | 5.2 BB Test | S3 | Closed | [s3]Issue: Sierra Current abnormal （+100mA）when plugin A to C cable without PC or charger connected Clue1： There is 56K Pull up Resistor from CC to VBUS in A to C Cable Clue2： No issue with C-C cable which used as standard configuration in 30W PD Charger. Root Cause: 1.constant typec-or-rid-detect-change interrupt lead to extra current drain. Exp1:Log observation ,result:too many typec-or-rid-detect-change interrupt cause current abnormal 2.1 speculation:cc pin pull 56k to ground lead to interrupt ? ，Conclusion:Not Relative Exp2:pull 56k down to gnd, result:reproduce interrupt 2.2 speculation:Added Audio Analog Switch trigger? ,Conclusion:No Relative. Exp:Connect CC Pin to Vbus with 56K in mainboard and remove sub board(Include Analog Switch with CC1 parallel). Result:typec-or-rid-detect-change keep triggered ,Issue Reproduced. 2.3 CC Pin interrupt lead to extra current drain Exp:CC Trigger Source Validation. Result:Pull down resistor below 444K will trigger. Info:125K Resistor 3. water ingression detection lead to CC Pin abnormal Interrupt Exp1:water ingression detection keep triggered when insert A-C Cable but failed to confirm water ingression. Exp2:Flash EVT SW, Result:No Issue(No Water Ingression Detection in EVT) Solution:Proposal:1.Disable Temporarily to help Auto Current Test. 5/18 （Kiev project have same problem ，and Disable LPD with adb command before Auto Current Test ） 2.set long time for recheck to lower down current. (2 mins pers detect and avarage current up 1mA VS 100mA in issue）. | Link | 文亭 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-25 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3] Issue:WH137571, unit A1 Cap sensor no function after loop 5 Clue:1. CH1 no function Root Cause:1. M101 Spring collapse Solution:1.ME Improve | Link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-25 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | [S3] Issue:WH137608,unit B2(1) cannot enter front camera mode and unable to read SIM Card Clue:1. issue happened before loop1 drop test. Root Cause: 1.SIM Card connector PIN cold solder joint 2.camera BTB connector damaged by assembly Solution:1.Factory Improve Process. | Link | 李果 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-23 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | Issue:WH137571, DVT1 ALT loop4 one unit auto power off after drop test Clue:1. drop test in 4 areas（bottom,left,right,bottom right corner）,unit was blank screen,can power on normally without ramdump Root Cause: 1.Battery connector assembly issue.Retest pass after fit connector again. Solution: Assembly improve-owner:ME | Link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-14 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:DVT1A Instant 60mA Current Found. Clue:1.EVT found abnormal current in sleep mode, solved through QCN update. 2 units verified. Root Cause: 1.L5A@S6A used for PCIE/UFS/USB/SDC PHY Consume 200mA Current which lead to extra 60mA@3.8V 2.SPU Consume additional 200mA@0.85V 3. L5A affected by magnetic interference of S7A when CPU Big Core and PCIE works in the same time Solution:Optimize L5A Layout,using Star type Routing for VDD_SP_Sensor. RD Validated 3 pcs ,Pass.Import in DVT2B | Link |  |  |  | 2.PCB | 8.Sierra
2021-04-11 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue: RS pretest fail. noise value over 15DB Root Cause:New .Analog Switch FSA4480UCX need new parameter Solution:1. SUB1,SUB2 add 100PF /REF,R,L change to 0R / REF,AUDIO_GND add 1NF, Validated Pass. DVT2 Import. | Link | 院长 |  |  | 3.BOM | 8.Sierra
2021-04-11 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue: -90dB Noise found when in talking/recording mode on Earphone when display off. Root Cause:1.Analog Switch FSA4480UCX 's Power supply Vbob lower down frequency from 40Kto 2K in PFM mode when display off which lead to noise in earphone. Solution:1.Add RC filter(10K+1uF) in Vbob,Noise downgrade to -110dB.RD Validated.DVT2 Import. | Link | 院长 |  |  | 1.SCH | 8.Sierra
2021-04-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue:charging curve not correct ,need check why it jump to 500+mA from 1.8A . Analysis: Log share to SW , SW analysis ongoing Root cause:SW related . Need solve the bug | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-12 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | [s3]Issue:When charging ，Battery NTC data is higher than Battery ，Over 46 degree ，impact charging performance Clue：2-3°C Gap. (Ref RIO-H 30W Charging Design) Root Cause:wired NTC additionally heated by Battery Protection Board and Mainboard Solution：Action ：1 checking the battery test data with full speed charging rate.(including Voltage,current,capacity, NTC reading and surface thermal data .) 2.checking if we can have better thermal solution for battery? Not block PCB gerber out. |  | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-04-12 | 5.DVT1 | 3.Charging | 1.4 Solution | S3 | Closed | Issue:SM8250 can not support QC3+（33W charger running change）with 3rd part chaging IC Root Cause:1.Qualcomm announced no support plan on SM8250 duo to software development complexity and high couple with SMB. Solution: 1.SW Develop 33W QC3+ | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 8.Sierra
2021-03-20 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:Blank Display when ESD strike on Display,1 of 6,Recovered after power cycle. clue:can't reproduce on failed one. Root Cause:1.Display Issue,Inform risk to Display Team. |  | 韩凯 |  |  | 6.No Change | 8.Sierra
2021-02-04 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | CR： SIM 2 can not work Rootcause：connector design issue : UIM2 power and GND not connect solution：1. rework UIM2 power and check SIM2 function ok 2.change EVT Main board and main FPC |  | 李果 | 文亭 |  | 1.SCH | 8.Sierra
2021-01-25 | 3.PEL | 7.Sensor | 5.1 Bring up | S3 | Closed | CR： VIB，SPK，DP，Capsensor...can not work ， Clue：1. share 1 I2C 2.remove Capsensor and ok Rootcause： Cap sensor not power on before I2C Bus work may cause I2C issue. solution：1. change cap sensor power L8C to always on ，need to check SW ok or not 1/27 shengnan 2. EVT change to Singal I2C for capsensor for better |  | 小熊 | 文亭 |  | 1.SCH | 8.Sierra
2021-01-25 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | CR： Camera No power Rootcause：I2C error (SDA &SCL swap) solution：1. rework LDOs IC I2C -Done 2.change EVT PCB --SCH -Done |  | 邦邦 |  |  | 1.SCH | 8.Sierra
2021-01-25 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | CR： USB can not work Clue：Main board ok，sub board issue。 Rootcause：OVP GND not connect solution：1. rework the Vbus（short output and input of OVP） 2.change EVT PCB --SCH change done |  | 文亭 | 韩凯 |  | 1.SCH | 8.Sierra
2021-04-06 | B.PVT | 4.Audio | 6.Issue | S3 | Closed | [na]Issue:Audio Aux Detection Issue Root Cause: When insert the AUX cable, trigger PHP surge protect, and the PHP Impedance test error. The AUX is dectcted as headset. Solution: workaround :When the impedance is dected as 0 ,Change the headset mode to AUX mode. | LINK | 院长 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2021-03-14 | B.PVT | 7.Sensor | 5.5 Certification | S2 | Closed | [na]Issue:DVT2 units Barometer Test Failed in TMO,Avg Data@4 Group @24units Exceed +/-36Pa. Root Cause: 1.Precision of Reference Calibrator BMP388(calibrated by Drunk8100) over Spec. 2.SMT Thermal Strain Not Released when Calibrated which lead to over calibration.TDK 2.6Pa/Day.ST Pass@5D Standing after SMT Solution: 1.Recalibrate PVT Units for TMO in Chicago Mart. 2.Recalibrate BMP388 with Drunk1000 that calibrated with Pace5000.Done. 3.Sending long Standing Time units,re-calibrate for LE. 4.Hold Standing Time for at least 5 Days from SMT to Calibration for TDK and ST. Go OK2Pilot. 5.Proposal:Furtherly low down Standing Time Solution from Vendor. 5D OK ,Try 3D . 6.Proposal:Import dynamic calibration for barometer.TMO Agree Using Google | LINK | 小熊 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2021-01-26 | 7.DVT2 | 5.Camera | 5.3 ME DVT | S3 | Closed | [S3]DVT2 2nd source ATT drop, TP no function/cannot enter camera(FR 2/15) Root Cause: 1.TP Signal and SAR_Int Signal Open near Screw post and and under shielding case corner duo to High PCB Strain Exp:1.1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify Exp:1.2. Add More Foam on Shielding Case to reduce PCB Strain. PVT Verify Solution:1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify | link | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2021-01-26 | 7.DVT2 | 5.Camera | 5.3 ME DVT | S3 | Closed | [S3]Issue1:DVT2 ATT 12 RASS-Tumble WH135516 48M failed (FR 1/15). DVT2 2nd source TMO drop, cannot enter camera(FR7/10) Root Cause: 1.Camera RST Open under Shielding case corner duo to High PCB Strain. Exp:1.1.Reduce SolderPaste on Corner of Shielding Case Solution:1.Reduce SolderPaste on Corner of Shielding Case,PVT Verify | link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2021-01-21 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue1: Denver DVT1B WH135380 ALT ,P/L sensor no function：B5(4) 1 of 11. Clue:reworked units 6pcs 2nd display+5pcs 1st display Clue2:Can not reproduce Root-Cause:Monitor | Link | 小熊 |  |  | 4.Parameter | 7.Denver
2020-12-10 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S2]Issue1: DVT1 ALT ESD ，C2 After +15kv air discharge at zone 9(aging 10), headset MIC no function without recovery.(12/23/2020 18:30) Clue：1.EDU03 6units pass 2. have add TVS and layout is ok. Root Cause: wating for the unit back to XM for analysis，maybe ETA XM by 12/30 Solution:1.No reproduce when get the fail unit。 keep monitor |  | 韩凯 |  |  | 6.No Change | 7.Denver
2020-12-10 | 4.EVT | 8.PCB | 5.4 ALT | S3 | Closed | [s3]Issue: 1.Mic2 Drop during TMO&ATT ,⅕ Loop2 ; ⅕ Loop3 2Mic1 Drop During ALT ,1/12,Loop5 Root Cause: 1.unti-pcb strain lower than pcb strain Exp:increasing space between Mic2 and PCB by more solder Paste workable? 2.lower down pcb strain through more support on pcb near mic2 Solution: 1. to add space between mic & PCB through +15% Solder Paste Mask Area from 0.37*0.65*2 to 0.75*0.65 (mm) on both Mics. DVT1 Verify. 2.Add more support on PCB near mic2. DVT1 No issue so far | Link | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2021-01-22 | 5.DVT1 | 7.Sensor | 5.4 ALT | NA | Closed | [na]Denver WH134702 Tumbling on Second Vendor(including PCB Vendor Found) Issue 1: 1:7 of 9 Capsensor no function :D1/D3/D8(100),D4(450),D5(300),D7(500)D9(300) Issue 2:4/9 P/L sensor no function :D1(500),D3(450),D4(400), Issue 3:1/9 Boot Failure. Clue 1:P/L sensor no function：D4 ，I2C wire open ， 2.No Camera Foam Attached and BTB Connector Deattached Root Cause:1.No Camera Foam Attached in Assembly lead to Mainboard Deformed and extreme high PCB Strain occurred. Solution:1.Invalid test,Assembly Correctly and Retest. | link | 小熊 |  |  | 6.No Change | 7.Denver
2020-12-14 | 4.EVT | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue1: Denver found Auto Power Off/System Hang Issue on EVT/DVT1 on 10% Reproduce Rate each day. Root Cause: 1.PBS_WD_TO/GP_FAULT2 duo to SPMI Hung which lead to Power Off/System Hung 2.SPMI Hung duo to CPU/RPM Hung 3.CPU/RPM Hung duo to Dip found in S5A which in PFM mode in deep sleep and happened when AP need more power when wake up. 4.S5A Couple with other buck through Grounding under PMIC. Exp4.1:Improving S5 Buck Response Time. Result:100mV improved. Exp4.2:Improving Grounding Path Isolation of S5A . Result:50mV improved. Exp4.1+4.2,No Dip found. Solution: 1.Work Around:Increase S5A by 150mV . 1/4 validated pass. 2.S5A Layout Improvement+Improving S5 Buck Response Time. Validated Pass. | slide link | 李果 |  |  | 6.No Change | 7.Denver
2020-12-03 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:Hand-Free Mode Mic -65dB,Spec -71dB Root Cause:1.Mainboard Mic Routing Solution:1.Modifiy Mic Routing,DVT1 Verify. 20201218:updata DVT1: -76dB ok |  | 院长 |  |  | 2.PCB | 7.Denver
2020-12-03 | 4.EVT | 1.Platform | 5.6 User Feedback | NA | Closed | [NA]陈文亭机器：遇到一次按开机键开不了机，插QC快充充电器，没反应，SOLLED 也没反应。 clue:1. 前一天充满电，然后放在抽屉里面 2.SW 版本 denver_retail_userdebug_11_RRE31.1_e3622e_intcfg-test-keys_retail_US 3. 电池 断掉一次后故障现象暂时不复现。开机显示电量96%。 合并到 后续总issue里面 | link |  |  |  | 6.No Change | 7.Denver
2020-11-24 | 4.EVT | 1.Platform | 4.Build | NA | Closed | [s3]Issue:power off current =240uA ,normal should be 100+uA clue:1. VDD_1P8_SYS =80uA 2.QC release reference design with solution of power off current issue. rootcause： PMK8003 current leakage solution：add 10K pull down on pin5 ，base on QC reference design. DVT1 PCBA test ok |  | 文亭 | 敏敏 |  | 1.SCH | 7.Denver
2020-12-01 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA]issue:USB 2.0 eye-diagram test,marginal pass Clue:tune1=default ,marginal pass debug:temp change tune=0x47 ,pass. 0x67 is better. SW change done ，from 12/7 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2020-06-05 | 2.PCL | 9.Memory | 4.Build | NA | Closed | [s3] SM4350 will support UFS2.2 物料上会有2.2和2.1两种，需要关注下FW升级问题。 1.针对hynix料，ufs2.2的4+64和4+128都是新料，不存在FW升级问题。 2. 针对三星，ufs2.2的4+64是新料，不存在fw升级问题。 ufs2.2的4+128是目前nairobi上用的2.1的料，需要FW升级，三星不愿意单独区分料号。 3.针对micron，ufs2.2的4+64和4+128都是目前nairobi在用的2.1的料，需要FW升级，micron不同意区分料号。 我先把信息先放在这儿，我们都从各自site看看solution和risk，产线混料风险谢谢 Denver使用hynix4+128 ufs2.2做一供，三星4+128做二供，产线升级fw到ufs2.2。 |  | 嘉琨 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 7.Denver
2019-08-28 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | [S2]Issue: Stingray Black screen making call issue ，after sale Clue: 1. CT higher than 400？IKSWP-105766 CT=600. 2. Factory build CT up limitation is 350 now. Root cause: 1. Proposal: with a screen protector that cause CT higher？ 2.Proposal: Build without a rubber? Solution: 1 .Proposal: New SW calibration algorithm，CT coverage change from 0~400 to 0~654 ---done in MR 2.Proposal: change the CT up limitation to lower Action: change the CT up limitation to lower to get the units CT higher than 200 and check the rubber status. change CR IKTM-5940 :Update P sensor Test limit in JOT station From 0~350 to 0~150 | link |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-08-20 | D.SHIP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue: 3 units in 13 EWG units, Blank display. Clue: 1. #167400, VINT block damge.#167406,VLOUT3 DCDC damage. #167412,VGL FPC abnormal. 2. No display permanent damage issue in 3T TCC ESD(Edu03) test. 3. ESD and 5 ORTs , No Display Relative ESD Failure. Issue1: #167400 VINT block damge Clue: Get power block from MagnaChip to figure out the relationship among VINT, VLOUT3 and other power source. Root Cause: 1.Speculation:Inrush Current/EOS cause by Hot Plugging Exp1.1:Hot Plugging and Observe . Result: Issue is not reproducible after hot-plugging. Conclusion:NA Exp:1.2:Higher Voltage on Vreg_Oledb Result:Issue is not reproducible after 8V/9V/10V 20us@1Hz pulse charge on VREG_OLEDB(7.6V, the input of DCDC). Conclusion:NA Exp:1.3:Factory Failure Data Collect. Result: similar failure in LDA electronic test. 2.Speculation:User ESD? -> Low Pissibility Exp2.1: ESD after MP . Result:1 Day Return. Conclusion:Low Possibility of ESD Exp2.2:ESD Test Result Summary. Result:13 ESD before MP and 1 ESD & 5 ORT after MP,No Display Relative Issue. Conclusion: Low Possibility on ESD of User. 3.Speculation:Abnormal Loading of Panel Exp3.1: Add load on VINT/VLOUT3 to verify. Result: ?? Issue2:#167406,VLOUT3 DCDC damage. Clue: Root Cause: 1.Speculation:Inrush Current/EOS cause by Hot Plugging Exp1.1:Stress test Hot Plugging and Observe on 1 unit . Result: Issue is not reproducible after hot-plugging. Conclusion:No Conclusion Exp:1.2:Higher Voltage on Vreg_Oledb Result:Issue is not reproducible after 8V/9V/10V 20us@1Hz pulse charge on VREG_OLEDB(7.6V, the input of DCDC). Conclusion:NA Exp:1.3:Factory Failure Data Collect. Result: similar failure in LDA electronic test. 2.Speculation:User ESD? -> Low Pissibility Exp2.1: ESD after MP . Result:1 Day Return. Conclusion:Low Possibility of ESD Exp2.2:ESD Test Result Summary. Result:13 ESD before MP and 1 ESD & 5 ORT after MP,No Display Relative Issue. Conclusion: Low Possibility on ESD of User. 3.Speculation:Abnormal Loading of Panel Exp3.1: Add load on VINT/VLOUT3 to verify. Result: ?? Issue3:#167412,VGL FPC abnormal. Clue: Root Cause: 1.Proposal:FPC Material? SDC Send it to FPC Vendor for FA. Action: 1. Get power block from MagnaChip to figure out the relationship among VINT, VLOUT3 and other power source. 2. Add load on VINT/VLOUT3 to verify. | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-08-09 | D.SHIP | 7.Sensor | 5.6 User Feedback | S2 | Closed | [S2]Issue:Phone goes dark during calls Clue:1.Try to get the units. 8/23 (VZW will get the units on 8/23?- Syncing)-Ross Clue:Try to Reproduce- 8/26 Tony Root Cause: 1.Proposal:Screen Protector? 2.Proposal:CT>400 Solution: 1.Proposal:User Abuse,Remove/Modify Screen Protector in case of no cover on P-Sensor 2.Proposal:Update Calibration Algorithm on High CT. Before MR 8/30 | Link | 文亭 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-08-09 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167653 RTT function on the phone is physically off, make an outgoing call it shows up on my phone call, and the ppl on the other line canot hear me properlyl Clue:There is screen protector . RootCause: 1.Speculation: It will increase the CT of the Prox sensor , and more important is that the increases count is unstable because the screen protector is not fully adhered to the 2.5D glass at the edges which is the Prox area. Solution: 1. Requirement for screen protector is to cut off the prox area. other same root cause return unit :FFRP ID 167693 | link | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-08-09 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | Issue:FFRP 167552 45 - Uninitiated actions Powers off CR ：https://idart.mot.com/browse/IKSWP-101607 RootCause: 1.Speculation: Solution: 1. |  | 敏敏 |  |  | 6.No Change | 2.Stingray
2019-08-09 | D.SHIP | 9.Memory | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167409 SW-Kernel Panics Clue:Continues ddr error when MemTest. Clue:Samsung Involved, Result:?? RootCause: Why Issue? 1.DDR flip Exp:Log Observation Result: ddr flip Conclusion: R1 Confirm. Why R1? 2.1 Speculation:Mememory Solder Crack Exp2.1.1:ReHeat Memory ,Result:No ddr error until 300 Cycles. Conclusion:May R2 Exp2.1.2:Solder Crack point checking using QDUTT ,Result:on-going Due data?? Solution: 1. | Link | 嘉琨 |  |  | 6.No Change | 2.Stingray
2019-08-09 | D.SHIP | 8.Mods | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167457 MOD Detect Failure Clues: UI shows “the Moto Mod isn’t lined up correctly. Make sure the connector is clean and try attaching again” when attach Mod. Analysis： Experiment: 1. Measure SPI & CC pins with multimeter ----> OK 2. Measure the waveform of SPI -----> there is some clutter on MISO when CC is connected. 3. Measure BPLUS ----> No BPLUS output when Mod CC is connected. 4. Measure EN pin ---> OK 5. Measure OC pin of switch ----> 1.37V voltage at idle time. It should be 1.8V.---->same 1.37V on normal unit, why? Root Cause: PowerSwitch U710 (FPF2595) is Damaged（Apply new IC to replace and verify BPLUS control---> Verified OK.） Next Step: Send IC to Onsemi for failure analyze EOS ,monitor | Link | 邦邦 |  |  | 6.No Change | 2.Stingray
2019-08-09 | D.SHIP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167513 01 - Does Not Power On at all Device will not turn on Clue：Blank Display RootCause: 1.Speculation: Solution: 1. PM6150A EOS ，monitor | Link | 芳梅 |  |  | 6.No Change | 2.Stingray
2019-08-09 | D.SHIP | 4.Audio | 5.6 User Feedback | S3 | Closed | Issue:FFRP ID 167519 No Mic Audio RootCause: MIC brocken Solution: 1. Audio team owe | Link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-07-21 | D.SHIP | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:Field unit:PVT:Stingray: Prox keeps on falsing and waking up during calls on earpiece IKSWP-99509 RootCause: 1.Speculation:Prox Keep bad performance due to High Threshold Setting by calibration 2.Speculation:recheck FFRP ID 167516 HW ： meet 0.3mm Blank card detection design Solution: 1.IKSWP-102131 to correct observed calibration issue | Link | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-07-19 | D.SHIP | 4.Audio | 4.Build | S3 | Closed | [S3]Issue:Motor Keep Vibrating or no vibration，60%+ failure Rate on AAH4 Batch after over 100K mass production. Clue:Failed I2C：Address High>0.98V ，I2C Adress due to Address Low<0.82V Clue: IC Work normally if 10M Pull Down Clue: Can read chip ID noramly when start up RootCause: 1.AWINIC 8690 work abnormal due to I2C Address shift. EXP1: I2C Control to read chip ID after power on Result: Address form 0xB4 to ox B6 Conclusion: i2c Address shift 2.1 wrong config EXP3： Reset chip register Result : Chip address recover Conclution: wrong config EXP4: One by one config start up register Result:0x36 config to 0x01 (0x21 defaut-Internal 2M Pull Down) after initiating Conclution:: wrong config(0x36 no showed in spec.) 2.2 I2C shift due to Batch difference, AWINIC under investigating Solution: 1.Don't set 0x36(Hiden Register) to 0x01(Disable Pull Down，Default 0x21-Internally Pull Down) SW CR :https://idart.mot.com/browse/IKSWP-101218 | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-07-08 | D.SHIP | 10.USB-C | 4.Build | S3 | Closed | [S3]Issue:Stingray CFC 发现76%直通率，出现问题时是掉口 Clue:1. 换一根 新的C to C 数据线 就好了。 2. shelby ，shelby+ ，RIO 没有问题。 3. 更换USB 2.0 的下载盒子和数据线，有极大改善，到97%+ RootCause: proposal 1：USB 连接器的铁壳比较短，由结构和较短的外壳限位，稳定性比较低。 proposal 2： Solution: 1. 更换USB 2.0 的下载盒子和数据线 2. Quattro 有同样问题，同样的solution |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-05-21 | D.SHIP | 5.Camera | 4.Build | S2 | NA | [S2]Issue:Stingray 后拍录像播放卡顿异常反馈 ，视频 link Clue:1.video 里面帧在不在？ 2.卡顿出现之后，声音和 视频 是否同步 3. 手机稳定拍摄 背景动态 和 手机 动态 拍摄 静止背景。 4.[‎2019/‎5/‎21 11:48] Shunyong SY6 Xu: 有概率出现录的时候也会卡，大部分是播放的时候卡 5.通过视频观察：停顿时，声音播放，但是画面丢失。（停留在卡顿前画面1S左右，然后跳到另外一个画面，而不是连续画面） RootCause: Solution: 1. |  |  |  | 视频link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-05-07 | C.RAMP | 2.Power |  | S2 | NA | [S2]Issue: CQA found some units auto Black Display ,CR：https://idart.mot.com/browse/IKSWP-84566 analysis：1.when it happen ,current =30+mA . Need long press powerkey to power on the units. 2. power on current some units more than 300uA . and unstable 3.replace U2400 with a new one , it it ok. 4. fail units retry IF and BT ,it it ok. then go PAT & JOT , it fail again . 5. fail units most reproduce after power on 5 second . ( few need longer) RootCause: 1.U2400 PM6150A damaged on VBAT? 2.Power Supply on Vbat set to 4.35V,and Over Voltage 4.95V Observed on Vbat(B_Plus) when Power Supply on. 3.Proposal:Place board with VBAT on during IF Solution: 1.Power Source Set to 3.8V,and using 2 Phase Power Supply(0->2V->3.4V->3.9V) 2.Proposal:Longer GND Pin in IF&BT. 3.Proposal:Adding 100K between VBAT and GND Pin in BT Fixture. and Connect GND Pin with other Position Column 3.Proposal:Close IF VBAT,Try in Quattro first. | link | 敏敏 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-04-26 | C.RAMP | 2.Power | 5.6 User Feedback | S3 | NA | [S3]Issue: 1 unit auto power off when make call in China Mobile SIM . Clue ： 1.USE CMCC SIM ,it is ok 2.open the Display module with 90 degree , It is ok. Close the Display module ,it reproduce 3.Not Reproduce. |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-04-01 | C.RAMP | 2.Power | 4.Build | S3 | Closed | [S3]Issue: Issue 1.Accessory_On_Current_Board_1, True Failure, Clue:April Clue:Several 7.5V 100ms burst on VBAT will reproduce U2400 Failure. Clue:Battery_Off_Current_Board_1 ,1-3Mon 0%, 4/1 - 4/25 0.22%, 4/25-5/7(2 stairs Power Supply 3.9V) 0-0.75%. Clue:1.Accessory_On_Current_Board_1,0-4%,NTF,Small Amounts units. RootCause: 1.U2400 PM6150A damaged on VBAT, QC Feedback:Vddgen on metal layer 4 EOS issue 2.Power Supply on Vbat set to 4.35V,and Over Voltage 4.95V Observed on Vbat(B_Plus) when Power Supply on. 3.Proposal: Place board with VBAT on during IF 3.Proposal:CDM ESD? Need follow up Action - TE liubin Exp1:Longer GND Pin Result: Wait for Pin Arrival . Conclusion: Exp2:Add 100K Between VBAT and GND Pin,And Connect GND to Position Column 4.Proposal:PM1650A Lot? Exp:Analysis Lot Relative, Result:Not Relative, Conclusion:Proposal Drop Solution: 1.Set to 3.8V,and using multiple Phase Power Supply(0->2V->3.4V->3.8V), 1.77%->0.05%, Validated. Need follow up action with more IF site. 2.Longer GND Pin in IF&BT. 0.8%->0.2% 6/10 3.Proposal:Grounding Positioning column |  | 敏敏 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-04-01 | B.PVT | 8.Mods | 5.2 BB Test | S3 | Closed | [S3]Issue: Mods USB SS Drive Strength level change from 925 mV -100% to 253.6 mV-27%, Data ThroughPut = 51Mbps Clue1: While Shelby Plus finalized 261mV duo to failed on DF when use 219mV Clue2: 5G Mods Fixed on 290mV. Root Cause: 1. USB SS Drive Strength 220mV(0x21) Can Not Meet Minimum Signal Integrity Requirement Solution: 1.Using 265mV(0x23 confirm by 4/9) , Match Shelby Plus Driver Strength Level Data ThroughPut=808Mbps (User Debug SW) -Soak Test on USB SS 0x23 under -30°C and 60°C .Pass -Test Data ThroughPut on 0x23 with User Version- 4/12 | link | 邦邦 | 文亭 |  | 4.Parameter | 2.Stingray
2019-03-25 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: Cap sensor impact Active pen Root Cause: Both Cap snesor & Active pen Woring Freq 25Khz Solution: Evalute change Cap snesor Woring Freq to 41Khz , there some bug ,need to be fixed Can not use 41KHz ,No time for the SW update. |  | 小熊 |  |  | 6.No Change | 2.Stingray
2019-03-25 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: Cap sensor Bug when tempreture change too quickly Root Cause: Solution: FW update？, there some bug ,need to be fixed. No time for the SW update. |  | 小熊 |  |  | 6.No Change | 2.Stingray
2019-03-25 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue: Some times can not power on , Track ID NNBA2K0001 ,NNBA2K0008(DVT2B) Root Cause:suspect 9008 mode issue Solution:Rework these 2 units and sent back to user（CXD Matias ） monitor from 3/26 to 4/4 No problem by 4/22 ，close |  | 文亭 |  |  | 6.No Change | 2.Stingray
2019-03-04 | B.PVT | 9.Memory | 5.4 ALT | S2 | Closed | [S2]Issue: Unit Stuck on Andriod Logo Screen after Power On. CR : KSWP-69943 1.DVT2B 1 unit failed /183 ,PVT 18 unit failed /319 2.Issue found on IF,Assembly,CQA,ALT Root Cause:1.Sequence of Register Dump Process for Log Error when Error Correction,Known WD Memory Issue 2.PCN Supposed to release on 3/7 but fail to sync with lenovo before 3/12. Solution: 1.Using New Memory with new Ver.78 FW, -DF update and no issue found. 4/4 -Edu12 eMMC Durability Test Pass. 4/1 2. -Build Validation & Rack Test on 4/15 , SMT on 4/9 DF Validate Pass over 10,000Hrs. Go WD. | link | 嘉琨 | 文亭 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-01-23 | 7.DVT2 | 1.Platform | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT2A thermal test camera related fail Root Cause: RC1: camera power consumption & performance need balance Solution: 1.Proposal:SW29.64 import 1st mitigation Strategy for camera ，waiting for TCC retest PQM ,PQA,SW,BB check accept the result 29.105- |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-03-04 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Unexpected auto power off after ESD CD on MODS area, recovered after reboot. TM display RootCause: Display error 1.Display TE check failed and carry on recover procedure. 2.Display pwr_mode register meet error after power down and on. 3.AP halted after two recover fail. Solution:1. Not reproducible in PVT and Quattro |  | 吉吉 |  |  | 6.No Change | 2.Stingray
2019-03-08 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: Cannot detect MODS after ESD Front camera(and Front flash) is ON,After +8KV air discharge at zone16 (zap16),The 360 mods I used had the constantly sound of devices connected,Then changed the turbo mods and it completely undetectable in CQA test.I restarted the phone and I found all mods connected normal. Root cause: 1. mods cc signal error. 2. mods detection IC error after ESD Solution: 1. hard to design better |  | 吉吉 |  |  | 6.No Change | 2.Stingray
2019-03-04 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone stopped at "Android" sreen after ESD testing Clue: After +8KV air discharge at zone16, then check the CQA function at CQA screen,wait for about 30s later,phone auto entered the "Android" screen.Then wait for about 7 minutes,the unit entered to main screen. Root cause: 1. Audio might crash. 2.Could be reproduced without ESD. 3.CQA TEST APP Crash 4.Solved by SW update 29.96 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-03-07 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone dropped call after ESD testing Clue: After +8KV contact discharge at zone8 (Aging10) , Phone dropped call. When the issue occurred, you can re-call the phone without restarting the phone. Root cause: 1. SW analyse logs. 2.All the call is normal disconnecting, there are no abnormal issues found in the UE side. |  | 吉吉 |  |  | 6.No Change | 2.Stingray
2019-02-25 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | NA | Closed | [S3]Issue: CR :IKSWP-63410 PPF29.78 Rahul calls suba with phone on his earpiece Prox triggered correctly and display was off for 1 minute while in call over earpiece After one minute of in call, the prox suddenly triggered again bringing the display on and the in call audio route moved automatically to speaker Timestamp of event : 3:22 PM approximately, please check around this time in the b2go attached Suba has also encountered the same issue multiple times on her DVT2A retail SKU as well on the same sw rahul b2go : 305418529 Root Cause: black hair issue Solution:Touch IRink change ： from 2 round hole to racetrack，Improve black Card detection performance | link | 文亭 | 小熊 |  | 4.Parameter | 2.Stingray
2019-02-24 | 7.DVT2 | 1.Platform | 5.4 ALT | S3 | Closed | [S3] Stingray_TCC_ALT:1 unit auto power off after drop test ，CR IKSWP-53809 DVT2A 1time in Loop3 （total 3 groups of ALT ） ，DVT2B 1time in Loop4 monitor |  |  |  |  | 6.No Change | 2.Stingray
2019-02-24 | 5.DVT1 | 12.EMC | 5.6 User Feedback | S3 | Closed | [S3]Issue:Kernal Panic - DDR Flip found on NNBV120029,DVT1a on Rack Test RootCause:1.ESD Relative Exp1:Correct ESD Issue Exp2:DVT2A and after Data Exp3:Reproduce 10 times Crash on DVT1A udner ESD ->Result:ESD Relative Solution: 1.DVT2A imported Same Root Cause and Soluton with DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 | here | 吉吉 | 嘉琨 | here | 6.No Change | 2.Stingray
2019-01-23 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue: DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 Root Cause: RC1: Jtag ESD Risk RC2: Short tisk between Jtag & rear housing . Solution: 1. change to DVT2A units and monitor | here | 文亭 | 敏敏 |  | 2.PCB | 2.Stingray
2019-01-30 | 7.DVT2 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue: BSP Target 32.1 Hrs，Current 29.8 Hrs. EBL on DVT1A 20Hrs Current BSP on NA version,32.8Hrs | here | 李果 | 敏敏 |  | 6.No Change | 2.Stingray
2019-01-23 | 5.DVT1 | 1.Platform | 5.3 EE DVT | S3 | Closed | [S3]Issue: MDu44 fail . especial U2400 right bottom corner 1.DVT1B use 2nd PCB 2.DVT1B display easy to separated 3. use 1st PCB ,From DVT2A (remove 2nd source PCB) . MFAL check if there is difference 4.display assembly ok ,From DVT2A Root Cause: 1.PCB Strain 2.ALT Drop Solution:1.PVT function ok . go with no underfill (aligned with PQA &PQM) | link | 文亭 |  |  | 6.No Change | 2.Stingray
2019-01-23 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2]Issue: 产线装配发现硅胶套装偏导致 sensor 被遮挡的 Action：请整理相关信息关注ME action落实情况，ME Informed to HouXiRong& XianQing | LINK | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2019-01-23 | 7.DVT2 | 8.Mods | 5.2 BB Test | S3 | Closed | [S3]Issue: An error message appears when restarting the mod Root Cause: RC1: Mods B_plus dont have a good enough discharge path.when the mods restart ,the B_plus should go down and restart to make mods restart . but it dont restart,and it cause mods go into the Flash mode and can not restart Solution: The change point is : add a discharge path for mods B_plus | link | 邦邦 | 院长 |  | 3.BOM | 2.Stingray
2018-12-26 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: ANT LowB performance degraded after ESD @Calling@Bottom Ant in DVT 2A WH112926 6 Fail/6 units -8dB loss@ B5/B12 Root Cause: RC1:QAT3550 Tuner U200 Broke -Pin CIO，SW3，SW4 -Internal C1 Damage also found RC2:ESD Protection by Varistor not enough Solution: 1.Using ESD128(Infineon) TVS on VR240 , ESD +/-15KV 200 times Evaluate Pass. RSE Evaluate Pass. TRP Evaluate Pass. -Verify one more units for consistency. 2/15 -6 units PCBA reworked and will do ESD Test and TRP Verification in WuHan TCC after assembly. 2/19 -Sample meet PVT requirement. Will Follow Component Qualification Process and Supply. 2/19 | link | 吉吉 | 文亭 |  | 1.SCH | 2.Stingray
2019-01-23 | 7.DVT2 | 3.Charging | 5.2 BB Test | S3 | Closed | [S2]Issue: shelby 售后不开机主板，分析CC1和CC2 pin 损坏比例较多，评估是否能改善 6150 CC1,CC2 耐压22V，Better than 660 which is only 6V. Iteration:Review |  | 院长 | 敏敏 |  | 6.No Change | 2.Stingray
2018-10-22 | 4.EVT | 8.Mods | 5.1 Bring up | S2 | Closed | [S2]Issue:Mods DP no display Clue: 1.Mini DP Qualcomm not ready until 11/15 2.DP over Tpye-C can work with no HDCP DP->HDMI Adpator;Aux and DP HW Verified. 3.HDCP Error found,QC feedback that should be TZ issue. HDCP1.x Key and deploy，$0.01,Using new test key ,resolved 4.DP Adaptor over this Channel ,Verified OK. RootCause: 1. Trust Zone Error/No Key For HDCP,Fixed on 12/14 2.Horizental & Vertical Syncronization Signal extact fail，Analogix RD Involved and Digging- 1/7 Solution:1.Source config |  | 邦邦 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-26 | 5.DVT1 | 12.EMC | 5.6 User Feedback | S2 | Closed | Issue: caizhiyi机器反馈原来ok 机器，胜男拆机返工CTP后（P-sensor油墨孔改成跑道型），之后打开蓝牙灭屏后就像自动关机了 clue： 1. 开启蓝牙或者WIFI ，然后进入休眠，自动关机（没有关机画面），都关闭就不会 2. Action：a.拆除LCD 是否能复现？” b.能复现，测量L10A的电压变化，同时关注电流变化，同步找一路参考电压。c.关机状态测量L10A的阻抗变化 3. L10A 外部加电源后，没有问题。 4. 用不休眠的SW版本验证也没有问题。（比如29.35 ） 5. L10A 用外部电源替代，并用电流计查看，有小脉冲电流 ，故障板能到140mA ，宽度130uS 以内。 6. 不开BT或者WIFI，故障板 L10A 外加负载10mA就会掉电 ，另外一个正常板子，外加30mA都不会掉电，再加上BT，WIFI打开也不掉线。 7. 20180106 试用人员又反馈一台 CR： IKSWP-52032，同样是DVT1A机器，现象类似，但复现概率低一些，短时间内不能必现。 Root Cause:1.PM6150 L10A LPM Mode Damaged Action ：Jtag check PMIC 寄存器 Solution:1. use NPM mode for L10A in all mode 2.JTAG Removed （DVT2B removed ，DVT2A change to test point ，done） 3. 3W Routing with GND on FPC ，done 4. Optimized Placement on Receiver Area.（DVT2B ，done）增加GND 开窗保护 5. L10A PM6150 side reserved 1 TVS , 屏蔽罩内无空间在PMIC端加TVS管。L10A在屏蔽罩内已四通八达。 长期事宜： 1. Test case 增加休眠模式 2. 亮屏下用ADB 读取寄存器判定是否ok | link | 敏敏 | 嘉琨 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-22 | 5.DVT1 | 8.Mods | 5.1 Bring up | S2 | Closed | [S3]Issue: 1.DisplayPort Aux Communication Failure,Over 50% Root Cause: 1.Aux Signal Integrity Issue Exp1.1-Clear Log and Start Mods on passed one and failed one on two unit，Log and send to SW for analysis Result:Passed with no error; Failed with all Aux error Exp1.2-Aux-P /GND Wave Form Measurement Exp1.3-Repeart Reading through Aux on failed unit and Passed Unit.Observed the Waveform on Aux P/N from Phone side. Result:Failed unit entering Repeating Read mode,Can't Insert one Read operation Exp1.4-Remove R755Mod,Remove R743Mod,Remove C748 Result:Fail Exp1.5-Remove R756Mod,Short C747mod Result:Fail Exp1.6-Aux n Pull up to L17A using 100K；Aux P Pull Down 100K after Capacitor Exp1.7-Measure Aux P/N ,Observe Waveform after P-N(Math Minor) Reslut:P-N=0 Solution: 1.Sol1.6:Adding 100R after Capacitor on Aux Verified OK,BOM Change in DVT2B | here | 邦邦 | 李果 |  | 1.SCH | 2.Stingray
2018-12-26 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue:SW 反馈有人报Foles通话不容易灭屏的问题（caizhiyi的机器） clue： 1.SW caoyi 告知，手机左手拿着，P-sensor 位置比较容易跑到耳朵意外的区域，导致读值很低，不能判接近。 2. 右耳朵也会出现，那应该是0距离状态下的 Root Cause:1.左耳朵飘出耳朵范围 Solution Action：1.DVT2B 旋转P-sensor 180度，将发射灯更靠近手机中心。（硅胶套同步更改） |  | 小熊 | 文亭 |  | 2.PCB | 2.Stingray
2018-12-26 | 5.DVT1 | 7.Sensor | 5.6 User Feedback | S3 | Closed | Issue: Black Card Performance Can't Meet requirement Root Cause:1. Double Holes window on CTP Solution：1.Change Double Hole to Singe Oval Type Hole ,Verify on DVT2B ： Samsung Display PVT 100+pcss TianMa Display DVT2B TBD |  | 小熊 | 文亭 |  | 4.Parameter | 2.Stingray
2018-10-22 | 4.EVT | 8.Mods | 5.1 Bring up | S2 | Closed | [S2]Issue:Mods Camera not Bring up,Block on Lanes Overflow Clue: 1.AP CSI2 worked with Front Camera 2.APBA Lane2 Signal detected,25Hz/21Hz 4. RootCause: ... RC6.SM6150 CSID Can't Decode CSI Low Speed Data? Exp6-1.Using Front Camera,Wiring to CSI2,Setting Low Pixel Clock Rate ,to Check if no overflow issue on CSI2. Result: Exp6-2:Try to figure out the relation between APBA Clock and SM6150 CSI2 Reading Clock and DSP Codec Clock 1.Different APBA Clock 2.Different SM6150 CSI2 Reading Clock 3. FIFO Status 4.DSP Decode Clock 5.Frame Received(Judge by SOT/EOT Count), 6.Escaped Time when overflow Result: Solution:1.Proposal:Config Muc APBA CSI Clock to match CSID of SM6150 2.Proposal:Config SM6150 CSID to Match each other. | here | 邦邦 | 院长 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-16 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S2]Issue: Factory Download 50%+ can not connect to 9008 (enumerated 9008 with "！") Clue: 1. No Issue with Computer USB 2.Error code:Windows cannot load driver for this hardware.The Driver may be corrupted or missing.(Code 39) 3.Remove TVS no affect 4.USB Suspend found 5.Proposal:Long USB Cable（0.9m+Expander Board+0.6mType-C Cable） 6.PCIE USB Hub 4 Channel ,Validate Pass Root Cause: 1. Issue only happend during 16S duration windows when restart to re-enumerate after provision when 2 or more unit flashing. 1.PCIE USB 3.0 Hub+Moto Driver，Change to USB2.0+Qualcomm Newest Driver 2.0，No Issue 2.1 We import USB 3.0 Function Check in this process. 2.2 Proposal:Unknown Device relative to the driver updation. Solution: 1. Seperate Provision Site 2.USB USB2.0 & Qualcomm Newest Driver,Need seperate USB 3.0 Flip Test. 3.Proposal:Using Delay 35s, Validate Pass. Factory WWTE Issue | link | 文亭 | 林峰 | SW NEW CR https://qualcomm-cdmatech-support.my.salesforce.com/5003A00000t2cYrQAI | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-16 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [S3]Issue:MDu30 Thermal Test Fail-WH111596 Clue: 1.Camera 4K torch，flashlight area overheating 2.wifi streaming with charging，mods connector area over 3℃ 3. Processor loading overheating 4. Gaming with charging，mods connector &metal frame over 2℃-3℃ RootCause: 1.Driver Current Set over Spec in Torch Mode 2.Flow Media Play current drain too big,Charging Current too big. 3.Processor loading is reference only，CPU mitigation not start. 4.Gaming with charging，High Power Comsumption,Charging Current too big Solution:1. Touch Mode Current Fix in DVT1B SW,Validated take effected. 2. DVT1B optimize Charging Current 3. DVT1B import CPU mitigation，target<45℃ 4. DVT1B Using CS CPU for test to eliminate ES High Power consumption DVT1B: All Pass except Data Link over 2℃，It is a reference item. | Link | 林峰 |  |  | 4.Parameter | 2.Stingray
2018-11-26 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S2]issue:BB test ，P-sensor oil test fail in EVT and Black cardtest fail in DVT1A Clue: Rubber EVT =0.25mm, DVT1A=0.65mm Root Cause:1.Isolite Rubber Thickness need balance between Anti-Oil and Black Card Test Performance. Solution:1.Change Rubber to 0.55,0.65,mm ,Verify on DVT1B |  | 小熊 | 文亭 | test data | 4.Parameter | 2.Stingray
2018-12-26 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | Issue: caizhiyi机器反馈原来ok 机器，胜男拆机返工CTP后（P-sensor油墨孔改成跑道型），之后打开蓝牙灭屏后就像自动关机了 clue： 1. 开启蓝牙或者WIFI ，然后进入休眠，自动关机（没有关机画面），都关闭就不会 2. Action：a.拆除LCD 是否能复现？” b.能复现，测量L10A的电压变化，同时关注电流变化，同步找一路参考电压。c.关机状态测量L10A的阻抗变化 3. L10A 外部加电源后，没有问题。 4. 用不休眠的SW版本验证也没有问题。（比如29.35 ） 5. L10A 用外部电源替代，并用电流计查看，有小脉冲电流 ，故障板能到140mA ，宽度130uS 以内。 6. 不开BT或者WIFI，故障板 L10A 外加负载10mA就会掉电 ，另外一个正常板子，外加30mA都不会掉电，再加上BT，WIFI打开也不掉线。 7. 20180106 试用人员又反馈一台 CR： IKSWP-52032，同样是DVT1A机器，现象类似，但复现概率低一些，短时间内不能必现。 Root Cause:1.PM6150 L10A LPM Mode Can't meet power requirment Solution:1. Correct NPM mode for L10A in all mode,Validated that no side effect on efficiency. 长期事宜： 1. Test case 增加休眠模式 2. 亮屏下用ADB 读取寄存器判定是否ok |  | 文亭 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-26 | 5.DVT1 | 3.Charging | 5.2 BB Test | S3 | Closed | Issue: DVT1B 火生1台机器不识别快充，需要分析。 clue： 1.关机一段时间后，再开机会回复正常。多次插拔充电器后，又fail 2.Fail 的时候，链接电脑，USB也不能正常链接（提示不正常的设备） Root Cause:1.AP not release USB Channel When QC 3.0 Lead to Pmic fail to intercommunicate with Charger. Solution:1.SW Update according to QC , Which is the same issue with QC3.0 issue under Power off Charging, SW Issue | link | 林峰 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-26 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | Issue: DVT1B high possibility Power off when ESD test Root Cause:1. Jtag signal affected Solution:1.DVT1B Jtag shielded with Copper and isolation film，Evaluated Pass. DVT2A PCB Has been modified . Same Issue with : DVT1 some user feedback auto power off。IKSWP-55128,IKSWP-56795,IKSWP-58803,IKSWP-54896,IKSWP-56798 | link | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-12-26 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | Issue: DVT1B ESD Evaluate, BT Drop clue： 1.Change SW no affect Root Cause:1.Side Key Fixing Clip Discharge by ESD2.Grounding on Sidekey FPC not Stable 3.Key Signal Affected 4.BT Signal Affected Solution:1.Isolate Side key grounding pad with Clip. Validate OK 。DVT1B test ok （2 round） Action:DVT2A增加绝缘膜贴在侧键FPC上，已通知结构备料 ，DVT2B发板需要将FPC 按键面的露铜去掉。 | link | 吉吉 |  |  | 2.PCB | 2.Stingray
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:WH111665 1.After +10KV air discharge at zone 6(Aging10),P sensor and light sensor no function,restart recovery. Clue: 点胶和封胶 是否没做好，直接打到P-sensor本体了？ （点胶不完整，打击P-sensor区域，会出现软性失效） RootCause: 1.P-Sensor Affected by ESD Solution:1. SW recovery ,RD Validate Pass 。 |  | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-16 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S3]Issue: Factory feedback SOL LED too dark & sometimes no function Clue: Factory mode & CQA mode with different Lightness . |  | 文亭 | 林峰 |  | 4.Parameter | 2.Stingray
2018-12-12 | 5.DVT1 | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT1A WH111559 Tumbler 200 times , D1 &D4 front &Rear camera can not work Clue：1.SDA wire open （SCL ok） D1 &D4 2. NFC IRQ，ANT_cap_sensor_CS1_N & REF _cap_sensor_CS1_N,wire open. 3. CPU shielding case seem lift up and SH118 seem lift up too. 4.Press CPU shielding case can recover Root Cause:1. Layer 10 CPU shielding case separate from PCB cause Layer 9 wire open. 2.High Strain on PCB Neck and shielding case Solution:1. enhance Layer 1 shielding case SH118 SMT ,in DVT1B V05 PCB 2:change the layout within this area ,will change in DVT2A V06 PCB 3.Add Foam on Bridge，Validate improved,Import in DVT2A and validate. | link | 文亭 | 芳梅 |  | 2.PCB | 2.Stingray
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue: 1.Zone 11(Aging10) proximity sensor no function then unable to enter system after reboot,recovered after reset(fastboot -w). 2.Light sensor and proximity sensor no function，recovered after reboot:D5(contact 6KV) 3.+8KV contact discharge at zone 14(Aging10), Vibration no function then unable to enter system after reboot,recover after reset(fastboot -w). 4. -8KV air discharge at zone7(Aging10), Phone unable to enter system after automatically reboot,recovered after reset(fastboot -w). RootCause:1.SW Bug , not happen in latest 2 ESD Test Solution:1.SW Update. Validate Pass |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:Unit 1 +15KV air discharge at zone 6/zone 9/8&10 (Aging10),The phone lock up,recovered after long pressed power key to reboot. Clue:1.System Halt 2.Reproduce ,Log 3.AP or Display Driver? RootCause:Proposal:TX Error? Solution:1.Jtag Removed,Validate Pass. |  | 吉吉 |  |  | 2.PCB | 2.Stingray
2018-12-05 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | Issue:Unexpected auto power off During ALT Drop Test ,CR IKSWP-42633 DVT1A NA SKU ALT(WH111516)(PA/PSA Anyone） A3(1):Drop right side DVT1A NA SKU ALT(WH111848)(total 9units） A3(1),B4(1):drop back side A4(1):drop left side Root Cause:1.JTAG Short with Edge of Back Housing Hole on bottom. Experiment:DVT1A LATAM L15 Isolate Jtag with film and validate , Pass 12/14 Solution:1.Remove JTAG Connector,monitor DVT1B Validate Pass Same Issue with : DVT1 some user feedback auto power off。 | link | 文亭 |  |  | 6.No Change | 2.Stingray
2018-12-05 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:The phone automatically reboot,then recovered:D1(contact 4KV) The bluetooth no function, recovered after reboot:D1(contact 4/6KV) Clue: 1.Unplug Side Key FPC and Pull out, ESD Pass 2.Unplug Side Key FPC and Keep in the original Position, ESD Fail 3.ESD Spark found on Key FPC Clip 4.Grounding PCB Bridge ,Shielding Key FPC,ESD Fail 5.Put Film on PCB Bridge,Isolate Key FPC ,ESD Fail 6.Internal Wire? Root Cause: 1.Proposal:WIFI/BT Antenna Strike by ESD ,Verify Fail. 2.Proposal:Varistor may not provide enough Anti-ESD performance, Verify Double Varistor Fail. 3.Proposal:In 03A PCB board, the wire from Anttena is connected to capacitor, but not Varistor first. V04 Modified, Validate Failed. 4.ESD on Power,and Key - lead to fail 5.Side Key FPC Solution:1.Grounding FPC Stiffiner Steel 2. Isolate Key Clip with FPC,Evaluate Pass. | Link | 吉吉 |  |  | 2.PCB | 2.Stingray
2018-12-05 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:The phone drop call,recovered after call again:D1(Air 8KV) Clue: 1.HandFree Confirmed 2.Proposal:Log Analysis 3.RF Tranceiverin bottom 4.Proposal:Frequency? +2 unit1 Root Cause:1.if Hand Free, TP Ghost Point Issue Solution:TP FW update,Validate OK |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-04 | 5.DVT1 | 11.Thermal | 4.Build | S3 | Closed | [S3]issue: RT516 damaged in DVT1A assembly, fail rate 0.53%= 4/750 Root cause:1.RT516 Crashed When lockdown Side FPC 2.Conflict with Fixture,No Issue after Optimize Fixture in DVT1B Solution:1.Optimize Fixture, DVT1B Validate Pass. 2.Reserve DVT2A Add 2 0402 capacitors to protect RT516,DNP |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-04 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]issue: In TCC ESD test, touch screen no function with large probability,recovered after pressed power key. Clue: Issues appeared when the Display panel faced down, and ESD dischaged on the back frame. 2.Proposal:Touch Screen OK withough ESD? Root cause: 1. TP IC might be interfered by ESD coupling. 2. TP IC is alive when TP no function. 3. TP IC calibration meets problem after ESD test. 4. This issue might be solved by Goodix calibration algorithm. Solution:1.Optimize TP Algorithm |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-12-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]WH111662 A3 ALT Loop2 Drop on left side , P-Sensor No Function. 12/12 Root Cause:1.FPC wire open on strain corner lead 2.FPC foldered in abnormal state Solution: Change FPC GND and Open Area，on-going |  | 小熊 | 文亭 |  | 2.PCB | 2.Stingray
2018-12-02 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]issue:on Dec/2 WH111848 ALT Loop2 B2:After drop top left corner,P sensor is always in enable status,light sensor is always in dark status, recovered after reboot Clue:Plan :1.PI Get log and check what the status CR IKSWP-44583. 2. Follow up the Loop 3~5 3. tear down the B2 after ALT test 4.SW check how to dump the Register when ALS/PS fail Root Cause:1.SW Bug and Fixed Solution:SW update |  | 小熊 | 李果 | CR link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-11-29 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]issue:WH111516_B4_NNBA120190 After loop2 drop right side,1 units' P sensor&Light sensor have no funciton,but restart can be recover Clue:Plan :1.LOG in CR IKSWP-43026 2. CTP not assembly good 3.Proposal:Try to Reproduce，Can't Reproduce，Monitor others Root Cause:1.suspect assembly issue ：CTP not assembly good may cause rubber moved and cover the sensor . Solution:Monitor Loop 3~5 result,No Issue |  | 小熊 | 敏敏 | CR link | 6.No Change | 2.Stingray
2018-11-26 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:ALT WH111516 ESD C1 样机Standby模式，+8KV空气放电 ，打TP Lens底部缝隙区域（Zone 3），CQA模式下检查指纹发现Fail，手动关机后不能再开机 Root Cause: 9008 state ，No HW dameged. Not a real issue |  | 吉吉 | 李果 |  | 6.No Change | 2.Stingray
2018-11-26 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S2]Risk:Mods Factory test plan: DVT1A dont start mods test Root Cause:SW not ready Solution:Inform SW*NPI |  | 邦邦 |  |  | 6.No Change | 2.Stingray
2018-11-16 | 4.EVT | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]Issue:[Jira iDART] (IKSWP-40058) Can not charge, shows discharging when connecting charger(1user,often)连接充电器无法充电 B2GID:304434411 Clue:14号，ppf29.10版本启动了。目前硬件的相关的可能只有这个。连接了usb没有充电，拔插后拧一下插头才能识别到。另外fastboot 模式也出现识别不到，也是拧usb口才读的到。 Root Cause:usb-c connector 虚焊 Solution: Release FA to Factory&Component,They will follow. | Link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-11-13 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:Sleep Current Drain 27.5mA Root cause: 1.Max3108 6.5mA 2.Memory 6mA 3.Display 1.2mA 4.after SW Merge All upgrate: Base Current =7.2mA@3.8V,Gap:2.2mA 5.Moto Action&Maya: -1.5mA ->5.7@3.8V , Gap:0.7mA 6.Proposal:Boot up with BP-Tool Mode ->System Boot :-0.5mA ->5.2mA@3.8V 7.Proposal: Solution:1.After Fine tuned,5.1mA achieved on DVT1B. | Link | 李果 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-11-13 | 4.EVT | 8.Mods | 5.2 BB Test | S2 | Closed | [S2]Issue: Remove Max3108（I2C->Uart）,Current Drain reduce 6.5mA Clue:1.L19A 2.7V 1mA Root cause: 1.UART Mode Config as Hi-z，improve 6mA 2.Disable Internal PLL, improve 0.5mA Solution:1.Uart Mode Config -SW 2.Disable Internal PLL-SW | Here | 邦邦 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-11-08 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: 1. 1/6 unit D6 cannot boot, stuck at MOTO logo, current leak and heat, after ESD test. 2. 2/6 units D3,D4 cannot boot after ESD test. Root cause: 1.1 D6 Stuck on Moto Logo when boot Due to Cap Sensor Damaged Through CH1 Sensor on Top Left. 2.1 D3,D4 Can't Boot Up Duo to AP Damaged on VDD 1.8V due to Mods SPI CS Pin that Damaged by ESD. Solution: 1.Adding one TVS on this channel and approved by Antenna. Import and validate in DVT1A. 2.Series in 1kΩ Mods SPI CS pin to enhance protection. Import and validate in DVT1A. | Here | 吉吉 |  |  | 1.SCH | 2.Stingray
2018-10-22 | 4.EVT | 5.Camera | 5.4 ALT | S2 | Closed | [S2]Issue:1/7 unit Front camera fail after ALT WH110271 B2 Root Cause:1. 1. CAM_R_I2C_CLK in Layer 9 break 2. Shielding Case Corner Strain Solution:1.Proposal:Adding Foam - ME 2.Proposal:Solder Open limitation - BB/RF/ME 3.Proposal:Reserve Enhance Shielding Case on Bridge Corner Same Root Cause as A+G Fail, Combined with 1/8 unit A+G fail after ALT WH110272 B2,Closed | Here | 芳梅 |  |  | 2.PCB | 2.Stingray
2018-11-05 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S2]Issue: DISP_VIO change from L13A to L15A,SW Downward Compatibility ok? Root Cause:1. Camera IOVDD need separate from DISP_VIO 2. Solution:1. follow HW ID to detect EVT and DVT1,L13A change to L15A Compatibility is ok DVT1 a CHECK OK . CLOSE |  | 敏敏 | 芳梅 |  | 6.No Change | 2.Stingray
2018-10-30 | 4.EVT | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue: Black Screen with 3/15 times during boot up Clue: 1.Reproduce when Assembly in phone ，No issue when place display plat, Found issue on Plat place too. 2.Issue Follow Dedicated Display 3.Hardly reproduce when insert converter FPC. 4.MIPI Test Pass. - new update 5.Proposal:Display Recovery lead to Reboot, Exp:Remove Recovery, No Display when boot sometime. 6.Remove Recovery Machanism，if Boot Up,No Issue. 7.Fix FPC using bandage with Converter FPC, 40 times no issue. - 2018-11-13 8.Assembly back into Phone with good assembly on Display FPC. 20 times no issue. 9. Root Cause: Why Boot up No Display on this display? 1.FPC Slip off Connector lead to Black Screen when shake 2.Proposal:Display Damaged ,Sent 1 Display to Samsung. Should get report in this week. 3.DSI Read Error ，Using TE Recovery instead of Dsi Read Recovery ，No Issue Solution: 1.Adapt TE Recovery ,Validate ok 2.Correct Display Power Down -Validate ok |  | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-30 | 4.EVT | 4.Audio | 5.2 BB Test | S2 | Closed | [S2]Issue:Receiver TDD Noise failed. Clue: 1.Codec affected, RootCause:1.Mic Side Tone Coupling Solution:1.Proposal:Resolve Mic up link Tdd Issue 2.Side Tone Coefficient Adjust |  | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-24 | 4.EVT | 6.Display/Touch | 5.4 ALT | S2 | Closed | [S2]Issue:1/4 after EVT MXC06 200times WH110432 D4,Display can not work 2/8 after EVT MXC06 200times WH110726 D3,D4 ,Display can not work 1/1 after EVT MXC06 200times WH109891 D3,Display can not work Root Cause:1. Disp_Sctrl Net open , PCB issue 2. Shielding Case Corner Strain Solution:1. Avoid Layer 2 Routing 2.Solder Mask Removed on corner | link | 芳梅 |  |  | 2.PCB | 2.Stingray
2018-10-24 | 4.EVT | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue:CH1 get stuck when wifi OFF Clue:1.Not occur when WIFI ON 2. Average value getting bigger gradually when WIFI off RootCause:1.CH1 not share the ANT with RF, and no capacitor to Gnd. so Gnd is independent from the system. Solution 1.CH1 add a 39PF capacitor to Gnd , RD evaluate ok, DVT1 validate. | here | 小熊 |  |  | 1.SCH | 2.Stingray
2018-10-22 | 4.EVT | 5.Camera | 5.1 Bring up | S3 | Closed | [s3]Issue:Rear & Front camera halt sometimes when preview Root Cause: Proposal:SW Issue.1. dvt1a sw OK |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-22 | 4.EVT | 3.Charging | 5.1 Bring up | S2 | Closed | [S2]Issue:Fuel Gauge,No Charging Current Detected Root Cause:1.Proposal:Current Register Mismatch - SW On-Going SW update display config file ,Solved. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-22 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue: 1 of 8 unit P sensor not found in QsensorTest after ALT WH110272 B1. Clue: 1. Change FPC, P sensor still not found 2. Updated software, P sensor still not found 3. P sensor Connector is soldered ok to the mainboard 4. Signal resistor test in P sensor connector on mainboard show normal 5. Test the connection between FPC connector and the bottom of mainboard Root Cause: 1.Why happened? SENS_I2C_SCL in inner layer crack under shielding case corner because of strain Solution: 1.PCB layout to change the force of BB shielding Same Root Cause with A+G fail after ALT，Closed | here | 小熊 |  |  | 2.PCB | 2.Stingray
2018-10-22 | 4.EVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2]Issue:1/8 unit A+G fail after ALT WH110272 B2 Root Cause:1.SPI_CLK in Layer 9 break 2.Shielding Case Corner Strain Solution: 1.Enhance Shielding Case on Bridge Corner ， DVT1B action According to DVT1A S1 result 2.Solder Open limitation - BB/RF/ME DVT1A Proposal 3.Adding Foam - ME DVT1A | here | 小熊 | 吉吉 |  | 2.PCB | 2.Stingray
2018-10-22 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]Issue:MIC TDD Noise -40dB >-71dB failed. Root Cause: 1.poor Cirrus Mic Anti-TDD , 1.1 Validate ACC+ Shielding Case pass; 1.2 Proposal:Estimate Knowles Mic. Exp: Interposer FPC Sampling to verify. 2.Near field power strength- Antenna 2.1 Proposal:validate Antena Energy Field Modification Solution: 1.Change to AAC Mic in DVT1A, AAC+3Walls Shielding Case 67dB@850MHz ，72dB@900MHz; Cirrus+3Walls Shielding Case 58dB@850MHz 2.Import Mic Shielding Case in DVT1A,Done | here | 院长 |  |  | 1.SCH | 2.Stingray
2018-10-22 | 4.EVT | 3.Charging | 5.3 EE DVT | S2 | Closed | [S3]Issue:1/4 units Surge Test Fail on 50V Clue: 1. no turn on，PMIC U2000 damaged，vbat leakage current 80mA，USB_IN leakage current 120mA 2. D500 damaged that had 110mA leakage current ， caused PMIC wasn't under protecting when surge test. 3. Surge test wouldn’t cause PTVS18VU1UPA damaged (After 400V, PTVS18VU1UPA was ok), so this D500 damaged may caused by other sources. 4. 4 pcs retest,all pass. Root Cause： D1 reused after edu16 OVP test，D500 damaged by OVP extreme test. NTF issue. Solution： NA Conclusion: NTF issue. | here | 林峰 |  |  | 6.No Change | 2.Stingray
2018-10-11 | 4.EVT | 3.Charging | 5.2 BB Test | S3 | Closed | [S3]Issue: Charging current 1.3A sometimes which should be 3A , Clue： 1. USB on PC can not work when 1.3A charging 2.Connector USB to PC and power on ，it always ok（test 10+ times） Root Cause: 1.SW issue --on going haijian Solution： 1.Fixed by the latest SW version。 | here | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-11 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]Issue: front camera preview fixed on +6KV ESD CD on Receiver Deco Root Cause: 1. Receiver Deco Grounding problem ,Need further check with ME Solution 1.Receiver Deco Short to Metal Housing, RD Evaluate ok,DVT1 Validate Pass. | here | 浦喆 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-11 | 4.EVT | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]Issue: system reboot in camera preview mode on +6KV ESD CD on Rear Camera&Mods Connector&Deco Root Cause: 1.display te affected（solved by adding 2K Resistor） 2.LCM Grounding not good . Greatly improved by optimized GND. 3.Recovery not feasible Solution: 1.reserve 100pf cap on te and reset,Serial in 2K in TE -Verification ,Screen Freezed ocasionaly and recover after 2s. 2.LCD Grouding Design Optimization 3.Optimize Recovery,Shift DSI Read check to TE Check,RD Evaluate ok. | here | 吉吉 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-11 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: ALT WH10272 Loop1 Drop top side 2units B2(1),A4(1) P-sensor no function ， Clue：1.No Gromet on P-Sensor incase LCD impact. Root Cause:1 .temp ALT units（ME ALT for Display glue verification） No Gromet ，not match design Plan: not ture issue for BB . |  | 文亭 | 小熊 | RPA analysis report link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-10-11 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3]Issue: WH109872 DVT EDu04 Eval - Reverse Polarity fail Root Cause:1.Shotkey Diode Don't Reserved after 3902 Removed. Solution:1.Adding Shotkey Diode - Lab Unit Modification - on-going 2.BB internal Test pass by jump wire 3. the solution had been changed in 48M-V03, will test in DVT1 DVT1A Test pass ：WH111518 ，close | here | 林峰 |  |  | 3.BOM | 2.Stingray
2018-10-11 | 4.EVT | 2.Power | 5.4 ALT | S2 | Closed | [S2]Issue: WH109891 MXc06 滚筒 D3 200次后 cannot not power on（可以开机有电流反应，初判主板导致无显示 ） Root Cause:Proposal 1.Display&Camera Signal in Layer3 around Screw Hole Open. 2.Can't dig further due to unit broken Solution:1.Re route affected signal to keep far away screw - Done Plan:-ME arrange EVT2 2 unit verification ,Monitor | link | 敏敏 | 文亭 |  | 2.PCB | 2.Stingray
2018-09-04 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S2 | Closed | [S2]Issue:Display Bringup not complete. ELVSS Keep -4.0V Root Cause:1.Proposal: PM6150A not correctly config Solution:1.SW Resolved. | here | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-09-04 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S2 | Closed | [S2]Issue:Display Bringup not complete. AVDD over voltage. Root Cause:1.PM6150A not correctly config , Solution:re configuration PM6150A,Verification Pass | here | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-09-04 | 4.EVT | 8.Mods | 5.1 Bring up | S3 | Closed | [S3]Issue: NFC I2C probe fail Clue: 1.NFC I2C is OK when remove MAX3108, MAX3108’s RST pin is low. 2.MAX3108 VCC has no power supply.LDOEN pin is low. 3.External supply 2.5V to VCC and Pull LDOEN to high,NFC I2C work. Root Cause: 1.Max3108 Hold I2C Bus 2.No VCC power supply for Max3108, Solution:Initial Power Max3108 correctly | link | 邦邦 |  |  | 1.SCH | 2.Stingray
2018-09-04 | 4.EVT | 9.Memory | 5.1 Bring up | S3 | Closed | [S2]Issue: 1. EVT with umcp cannot download Root Cause:1: There is no LUN in Blank umcp, ufs needs to be provisioned before download. Solution:provision UFS First | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-07-31 | 2.PCL | 4.Audio | 1.4 Solution | NA | Closed | [na]If QUP config to UART,Stingray will have not enough AP SPI for Audio codec. Root Cause: SM6150 not enough AP SPI Solution: 1.use LPI SPI (LPI Qup2)for Audio codec Firmware download , Update 8/8 ,SW can’t realize bridge AP to ADSP. Drop 2.Using I2C instead of SPI to Codec,Update 8/8:need 6.8S loading AOV code.Drop 3.QUP Config to SPI instead of UART. Update 8/8:Mainstream Solution. Plan:Closed. | Link | 院长 | 文亭 |  | 6.No Change | 2.Stingray
2018-08-31 | 4.EVT | 2.Power | 4.Build | S3 | Closed | [S2]Issue: EVT SCH&PCB design battery connector with 5CA9A6MXRG ,but the correct one should be 28014040001 Root Cause: Component Team Not align with ME Team,In-consistence between the PartNumber Solution:1. Carding the Component Selection Flow During Component&ME , Closed. | Here | 李果 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-09-04 | 4.EVT | 9.Memory | 5.1 Bring up | S3 | Closed | Issue2:Phone enter 9008(EDL) after download images. QC case number: 03648171 Root Cause:Download issue, miss some download file. Solution:Use moto baseline download tool. | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-08-27 | 4.EVT | 7.Sensor | 5.1 Bring up | S3 | Closed | [S2]Issue:I2C fail to read again sometimes (would happen in 1 hours ,sometimes just in 10 minutes ) Root Cause: SW I2C control issue. Detail need SW update Solution:1. QC feedback some Cord change link Plan： 1. 2 units Stress test 19 hours ok. 2. SW check how this change can solve the Issue | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 2.Stingray
2018-08-08 | 2.PCL | 1.Platform | 1.4 Solution | S3 | Closed | [S3]Issue:Not Enough Uart with Flow Control in AP for Mods APBA. RootCause:1.SM6150 AP QUP Limitation Solution:1.I2C Uart Bridge Using Max3108 ， update 8/28 SW Bringup on Demo Pass. 2.I2C Uart Bridge Using FPGA 3.USB Uart Bridge IC CP2102/FTD234 Plan:1.Manage in EVT bring up. Close | here | 邦邦 | 院长 |  | 1.SCH | 2.Stingray
2018-07-31 | 2.PCL | 8.Mods | 1.4 Solution | S3 | Closed | [s3]Issue:No SPI Port for Mods Root Cause: SM6150 not enough AP SPI Solution: add 1 Switch to solve it Action：Done. Already designed in Stingray and completed development. Update the design diagram here. | here | 邦邦 | 文亭 |  | 1.SCH | 2.Stingray
2018-05-07 | 1.Concept | 7.Sensor | 1.4 Solution | S3 | Closed | [S3]Risk:Als Design,No Feasible Place for Ambiant Light Sensor on Front Side. Root Cause:Full Display Solution:1.Place ALS on Edge ,2. turn to ALS under OLED ，under evaluation by SME team plan： 8/1 check use AVAGO9307 or AMS 3701 。 9/30 check if we can go with s2？ | here | 文亭 | 文亭 |  | 1.SCH | 2.Stingray
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [s2]Risk：Stingray P-sensor design ESD Risk Root Cause:P-sensor ESD Risk is high for the current Solution Solution: 1.Non-Conductive Grommet Around P-Sensor 2.Conductive Grommet Around P-Sensor- Update 0.3$,Further investigate Low Cost Conductive Grommet. 3.FPC Grounding Around P-Sensor 4.Folded Copper Shielding refer to Rio-M Plan: 1.Test Non-Conductive Grommet in EVT 2.Test Conductive Grommet In EVT EVT1 test ok ，close it | here | 吉吉 | 文亭 |  | 6.No Change | 2.Stingray
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S3]Risk:ESD May Damage USB-C on revised shorter metal shell Clarification:1.EVT Validate 2.Pin anti-ESD capability validate on shelby. Only D+/D- Pin have risk while other pins have good ESD durability. Solution:1.Keep Shelby Solution on D+/D- Protection Plan:1.Keep Shelby Solution ,EVT Monitor,Closed. | here | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S3]Risk:ESD May Damage Mods Pin Clarification:1.EVT Validate 2.ESD failure mode analysis Plan:1.Bettery Layout Protection 2.Better TVS with big capacitor and lower clamp voltage | here | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-07-23 | 3.PEL | 12.EMC | 2.Design | S3 | Closed | [S2]Risk:ESD May Damage Speaker Audio Amp and cause system halt. Clarification:1.EVT Validate 2.ESD failure mode analysis Solution：Add Varistor near the SPK pad and double check if the TVS due to this issue Plan:1. Add varistor near the SPK pad and test the ESD | here | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-05-07 | 1.Concept | 7.Sensor | 1.4 Solution | S3 | Closed | [S3]Issue:Proximity Design,No Feasible Place for P-Sensor Clue:Stowed Mode RootCause:Full Display Lead to No Space for P/ALS Sensor Solution:1.ME Manage to place it on Front Camera Conclusion:1.Turn to NUD Mangement，Closed | here | 文亭 |  |  | 6.No Change | 2.Stingray
2018-05-07 | 1.Concept | 1.Platform | 1.4 Solution | NA | Closed | [S1]Risk:Buttonless Design are not mature enough to introduce to Product | here | 嘉琨 |  |  | 6.No Change | 2.Stingray
2018-04-19 | 1.Concept | 1.Platform | 1.4 Solution | S3 | Closed | [S2->S3] Issue:1.Qualcomm feedback SM6150 Reference Design on 8/13, Update 8/17：Qualcomm Upload on Create Point on 8/17 Root Cause：1.Qualcomm Design Spec Release not follow Schedule, Solution：1.Follow up Qualcomm | here | 文亭 |  |  | 6.No Change | 2.Stingray
2018-04-20 | 1.Concept | 2.Power | 3.Review/Simulation | NA | Closed | [S2]Chiron BSP 24.2Hours/Latam UMTS, 21.6Hours in China UMTS on 7.0 User Mode on 3300mah. Solution:1.3600 maH now | here | 李果 |  |  | 6.No Change | 2.Stingray
2018-07-02 | 1.Concept | 12.EMC | 5.5 Certification | S2 | Closed | [S2]Issue:CE FM mode CS/RS (EN55035) test Fail Clue: Root Cause:FM IC demodulate the AM radio Solution:1. Conclusion:Sportan cancel the test item.Closed | here | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-07-02 | 1.Concept | 12.EMC | 1.4 Solution | S3 | Closed | [S3]Risk:CE ESD Usb Link Fail Verification:on-going EVT pretess ok | here | 吉吉 |  |  | 6.No Change | 2.Stingray
2018-07-10 | 1.Concept | 8.Mods | 1.4 Solution | S2 | Closed | [S2]Issue: SM6150 Can’t support Mods Projector on Original Architecture Root Cause: 1.SM6150 Only Deploy 1 X4 Lane DSI Solution: 1.Lattice ICE FPGA DP ->My DP Convert Solution - Will Verify on 10/20 if SW ready. 2.Discrete Solution without Lattice ICE,Principle Verified on Demo Pass.Reserve Solution in EVB. -Will Verify on 10/20 if SW ready | here | 邦邦 |  |  | 1.SCH | 2.Stingray
2018-07-12 | 1.Concept | 2.Power | 3.Review/Simulation | S3 | Closed | [S3]Issue:BSP 7.0 Simulation Shows 23.9Hrs on Latam UMTS Root Cause: 1.No Space on Y+ for Battery because of Camera 2.No Space on Y- for battery because of Mods&CPU+Memory Solution: Narrow down PCB Bridge and expand battery on X+ by 1.3mm 1.Put some low speed Signal on bottom Surface Layer 2.Attach 1 Copper on this layer to shield Value: Benefit 70mA increase up to 3570mah,Cost up $0.04. BSP on Target achieve all day life. | here | 李果 |  |  | 6.No Change | 2.Stingray
2020-02-26 | B.PVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3] TOF&NFC do not work sometimes on sofia+ B2B SKU Clue: 1. TOF&NFC share same I2C ，and SCL or SDA hold LOW when issue reproduce 2. issue happen after NFC reset (found by our reproduce)，also found on normal read operation（SW Reproduce） 3. Racer have Same issue . Root cause: 1. NFC FW Issue Solution: 1. Correct NFC FW | link | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-12-03 | 5.DVT1 | 7.Sensor | 6.Issue | NA | NA | [S2] DVT1B Sofia ALS-PS wheel test fail sometimes IKSWQ-39589 IKSWQ-39294 Clue: 1. 90 degree report 103 (device 3 ) & 241 (device 2)while it should be 5000+ Root cause: 1. Solution: 1. | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-11-15 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]PVT sofia NA Display missing pixels,unable to recover. Clue: 1. -15kV AD on FPS area, with display panel facing coupling plate. 2. Not appeared in all of sofia na and sofia plus EDU03 tests before. fial rate 1/68. 3. There is display issue in sofia row, with the same phenomenon. Root cause: 1. maybe display driver IC damaged, waiting founder FA. Monitor PVT 2nd source test |  | 吉吉 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-10-31 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S2] DVT2 Sofia NA ALS-PS no function after ESD ESU03 Clue:1. sensor damaged. INT pin =26R &500R VS normal xMR 2.check with ME the Glue width maybe different with Normal one 3. Root cause: 1. proposal :Glue width is too small . --ME is checking with Factory Solution: 1. proposal :improve the Glue width ,change to the width similar to DVT1 or sofia plus PVT: 2nd source pass. close | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-10-31 | 7.DVT2 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3] WH120786 DVT2 (2 fail/6 units), WH121714(2 fail/4 units) PVT Sofia Plus unit cannot power on after ESD @15KV Air Clue:1.Unit always enter 9008 mode; cannot recover . 2. According to UART log, boot config error 3.CPU bootconfig pins （SPK & REC Smart PA INT 2 pins） Diode parameter abnormal （Fail unit 0.4V VS normal unit 0.6~0.7V ） 4. CPU GPIO_118 short to GND，TOF_RST . checked EDU03 D1&D2 ,same fail. Root cause: 1. Boot Fail due to boot config error that because of CPU GPIO_118(TOF_RST_N) short to GND 2.1 Camera lens deposit is conductive in DVT2, making ESD reach TOF IC unit. exp:Change conductive deposit to non-conductive in PVT,fail. 2.2 Gap exit between lens and lens holder. exp:Red-dye immersion observed. conclusion: The interference between TOF rubber and camera lens is 0.27mm. The Elastic force of TOF rubber is greater than adhesion of clue. 3.1 anti-esd of Camera lens Double-sided adhesive become weak after temperature shock exp:RD Evaluate 2 units. Result:No issue before temp shock but both have issue after temp shock. exp: TCC Evaluate 3 units(factory pressure maintaining units). Result:No issue before temp shock but 1 unit has issue after temp shock. exp:Change adhesive with good temperature performance(PET->PSA).fail. exp:expand lens double- sided adhesive,0.6mm->0.9mm, Result:Rd evaluate fail exp:PET->PSA ; widen adhesive 0.6->0.9mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm , RD evaluate pass. TCC test pass 6/6 units. 2 units ESD fail before thermal shock. These 2 units have been tested MDu52(Environmental / Chemical Susceptibility), which influenced the clue performance. 3.2 Speculation: TOF Rubber too hard? Exp:PET; widen adhesive 0.6->1.1mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm; 60' hardness;RD evaluate pass. camera lens lift up 0.01~0.02mm. Exp:PET; widen adhesive 0.6->1.1mm; expand lens double-sided adhesive thickness,0.15mm->0.2mm; 50' hardness(softer); RD evaluate pass. camera lens does not lift up. Solution: 1. -adhesive change from PET to PSA ； -widen Camera lens double -sided adhesive , 0.6mm->0.9mm； -and thickness change from 0.15mm to 0.2mm； TCC test pass 6/6 units. 2. -PET adhesive(lower cost than PSA)-Lower Cost -widen Camera lens double -sided adhesive , 0.6mm->1.1mm； -thickness change from 0.15mm to 0.2mm； -reduce hardness of TOF rubber, 60 -> 50, running change. RD test pass 4/4 units.(45min 75'C thermal shock, 10 times). TCC test pass, 4 1st sourcing units, 4 2nd sourcing units. | Link | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-10-23 | 7.DVT2 | 3.Charging | 5.6 User Feedback | S3 | Closed | [S3]sofia some 3rd part charger can not charge(not standard QC 2.0 or QC 3.0 Charger) Clue: 1. waveform check charger output 12V in QC3.0 Authentication process （which should be 5V in normal charger). 2. External OVP open when Vbus get 10.3V ，and the charge drop(PMIC can not get the OVP information) 3. no problem on moto standard QC 2.0 & QC 3.0 charger Root Cause: this 3rd part charger is not standard QC 2.0 or QC 3.0 Charger.it output 12V when phone is doing QC3.0 authentication . Solution: 1. HW：External OVP change to 13.2V from 10.3V (PMIC can get OVP information when Vbus go above 10V.and it can protect >16V Vbus too,which would make PMIC damaged.). HW solution Import from Sofia+ DVT2 and sofia PVT . 2. SW : workaround ：when PMIC get OVP ,SW retry with no QC2.0 or 3.0 support . and charger will out 5V all the time. (New SW can work with New HW units) Other projects impact : it impact platforms with PMI632 or other low OVP PMIC which require external OVP IC. have synced the HW change to Sofia ROW yet . | link | 文亭 |  |  | 4.Parameter | 4.1.Sofia NA
2019-10-23 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: After +8KV air discharge at zone16 (Aging 10 ), fingerprint reader no function,recovered after reboot. Clue: Root cause: Egis sensor dead-loop after ESD. Solution:1. Enhance GND; PVT TCC test Pass |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-10-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH119393 EDU03 In final EIS test, LTE band5,band12,band13 div antenna degradation exceeds 3db, and TIS value is also out of spec. Root cause: 1. ANT DIV tuner damaged. 2. Layout is not the best design. Varistor + 0ohm. DVT2 optimize and monitor. 3. Inlay clue shifts down 0.15mm, making DIV ANT outside. DVT2 optimize and monitor. 4. If still fail in DVT2, change back to TVS128. Low risk No change ,monitor PVT test |  | 吉吉 |  |  | 6.No Change | 4.1.Sofia NA
2019-10-12 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | "[S3]Issue: DVT2 bulit CQA test SX9338 function abnormal: CH0/2 always triggers, CH1 never triggers Clue: 1. Factory SW works well for SX9338 units in Xiamen 2. Function ok when change back to SX9331. 3. Samples for factory and Xiamen download firmware in different way 4. Recheck firmware of SX9338 sent to factory 5. Root Cause: 1. Firmware download wrong because of upgrade fixture in Semtech work abnormally. 2. Solution: 1. Replace the wrong ones to right SX9338 " |  |  |  |  | 6.No Change | 4.1.Sofia NA
2019-10-10 | 5.DVT1 | 2.Power | 5.3 EE DVT | S3 | NA | [S3]Issue: DVT EDu13 - Battery Performance at Various Temperature WH119426 D1 auto power off after 1 hour -10C discharging(run Auto Cycle), the voltage is 3.66V Clue: The discharge time is judged according to the log time, but it fails due to the dislocation of the log time. The actual battery capacity is reasonable. Root Cause: The log time of the software is out of place, which causes the result to fail. Solution: Retest result pass |  | 李果 |  |  | 6.No Change | 4.1.Sofia NA
2019-10-10 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | NA | "[S2]Issue: WH119836 ALT light sensor and P-sensor no function B3( 5） Clue: Root Cause: P-Sensor fall off Solution: ME own further analysis |  | 小熊 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-10-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: WH119393 EDU03 light sensor and P-sensor no function,unable to recover.D3( +8KV air Zone10, left side of unit) Clue: 1. Not reproducible on other 2 units, with 100 times 15kV AD on zone10 and in calling mode. 2. P/L sensor shares the same voltage source with SAR sensor. Sar sensor functions well. 3. P/L sensor shares the same I2C wires with M sensor and A+G sensor. M sensor and A+G sensor funcion well. 4. No Relative Issue on Previous 6 Edu03 5. Re-Work P-Sensor Sample? Root Cause: 1.P/L sensor fail after cross validation. MB is well funtioning. 2. P/L sensor INT resistence is 98 ohm. Normal one's is infinity. 3.Speculation:Re-worked P/ALS-Sensor?- ESD protection device damage in INT pin Solution: |  | 吉吉 | 小熊 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-29 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]WH119444 Sofia NA SS DVT1B ALT B3(4) Weak vibration. WH119693 sofia +AT&T D8(400) Clue: 1. Fail follow PCBA 2. waveform check it should be inductor PL6502 issue 3. open shielding case and found inductor is glued on shielding case inside. and PL6502 broken Root Cause: Underfill operation problem cause inductor PL6502 broken suggest :ME check glue with BB Solution: 1. change Underfill operation to avoid glue on Inductor PL6502 | link | 院长 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-29 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: WH119444 Sofia NA SS DVT1B ALT A5(4) A5:Drop bottom left corner Volume + button no function. Clue: 1. check Sidekey FPC , press V- ,net open to gnd. FPC issue 2.FPC Wire crack (check finger to SMT pad open) 3. 2nd source Helitai FPC. Root Cause: 1. ME own further analysis Solution: 1. ME own further analysis |  | 吉吉 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-29 | 5.DVT1 | 10.USB-C | 5.4 ALT | S3 | Closed | [S3]Issue: WH119444 Sofia NA SS DVT1B ALT B3:After TH/TC USB charging is normal, but fail to connect computer. Clue: 1. can not power on when get the phone . 2.plug in USB and press V- can go into Fastboot mode. But not usb port found. 3. Failure follow FPCA . FPCA issue 4.2nd source Helitai FPC. Root Cause: 1. ME own further analysis,monitor Solution: 1. ME own further analysis,monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-18 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia NA cannot read SIM after DVT1B Tumble Test WH119323 D5(275) Clue: 1. SIM_RESET wire broken.(remove CPU) Root Cause: 1.Inner Layer PCB Delaminated 2.1 Proposal :RF Shielding case pseudo soldering 2.2 High PCB Strain on Shielding Corner. Solution: 1. Proposal : Shielding case SMT improve--SMT Engineer checked SMT is ok. No need change. 2. ME change cpu thermal copper to thermal grease to reduce PCB Strain .monitor test(sofia+ DVT1B )---ME 3. change USIM1_reset wire width to 0.15mm from 0.05 mm in DVT2 V05 PCB--BB-done | link | 李果 | 文亭 |  | 2.PCB | 4.1.Sofia NA
2019-09-25 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue:Sofia + NA FPS no function after DVT1B ALT WH119628，A2(5),A5(5) Sofia NA FPS no function after DVT1B ATT Drop WH119363，D10(54) Clue: 1. issue unit & good FPS module, FPS no function; issue FPS module & good unit, normal FPS function. Bad MB! 2. A2 :SPI_CS open to GND, A5:SPI_CS pin R is not stable. D10: SPI_CS open to GND 3.Remove CPU and check :A5 ,SPI_CS wire crack 4.Cross section : BB shielding case right bottom corn :A2 &D10 Via 2-4 crack ;A5 Layer 2 wire crack ; Root Cause: 1.Inner Layer PCB Delaminated 2.High PCB Strain on Shielding Corner. Solution: 1.Remove sensitive line under the shielding corner on DVT2 PCB V05.-done | link | 文亭 | 李果 |  | 2.PCB | 4.1.Sofia NA
2019-09-18 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia NA FPS no function after DVT1B Tumble Test WH119323 D7(150)，WH119323 D5（300） Clue: 1. issue unit & good FPS module, FPS no function; issue FPS module & good unit, nomal FPS function. Bad MB! 2. D7 MISO,MOSI,INT, 3 signal pins on MB BTB connector, no diode character and open to GND. Route broken? 3. D5 MISO, 1 signal pin on MB BTB connector, no diode character and open to GND. 4. remove CPU and check if wires are broken?--- wire broken. Root Cause: 1.Inner Layer PCB Delaminated 2.High PCB Strain on Shielding Corner. Solution: 1.Remove sensitive line under the shielding corner on DVT2 PCB V05. -done | link | 吉吉 | 文亭 |  | 2.PCB | 4.1.Sofia NA
2019-09-17 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ DVT1 DVT MXc03 - Power Cuts Impact Test ,WH118750 D2 , WH118615 D2 ,after right 2500 times:Gyroscope sensor fails Parametric test Clue: 1.WH118750 D2 Gyroscope-sensor channal 0&1 ok , channal dont change. 2. Sofia NA no such failure found so far. Root cause: 1.IC Broken Exp1.1 change a A+G on ok PCBA to WH118750 D2 ,D2 ok . Exp1.2 " Fail IC " on ok PCBA ，fail . So failure follow " Fail IC " 2.1 Speculation:Outer Force Crack? Z Axis not enough air gap 0.17mm? Exp2.1 check if there is some crack on fail IC Result:No Crack Observed , Conclusion:na Exp2.2 Adding more air gap on Z axis. and retest. - guilin/dengling ,date :09/23 2.2 Speculation: IC Issue? sent " Fail IC " to Vendor for further analysis---shengnan Result:No Crack Observed , Conclusion:na Solution: 1. |  | 小熊 | 吉吉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-17 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: Sofia DVT1 build P-sensor some units CT too high ,data? 2/ ? DVT1A, 4/? DVT1B ?/? DVT2 Clue: 1. Re Assembly Display,Disapear 2. Is it a real Issue? Check 6Sigma Distrubution Range.-Xiong 3. Some DVT2B units with high CT really has problem, such as P sensor shielded by glue, FPC gloden finger hided Root cause: 1. speculation: exp3.1: CT high limits units were real abnormal. exp3.2: collect all the test data, limits adjust. Solution: 1. it's not a real issue, CT distribution is a range, and should be adjusted according to the collected data. 2. Real abnormal ones should be reworked. | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-06 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: Sofia+ 2 pcs stylus stylus detected as plug out when full insertion during CQA. Clue: fail follow FPC Root cause:1pcs FPC ，no hall IC on FPC ，FPC Vendor hongxin issue . the other one check :seems same issue now Solution:FPC Vendor hongxin fix this issue |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-06 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [S3]Issue: Sofia+ 3 pcs/50pcs stylus detected as plug out when full insertion during CQA. Clue: 1. issue follow stylus 2. X-ray show magnet distance deviation 0.16MM /-0.15MM compare with normal one 3. 7mm insertion detect, 5mm normally Root cause: 1. speculation: stylus torllerance beyong spec? exp1.1: measure defect unit, result:by 9/9 conclusion:TBD 2. speculation: angular magnet assembly ME own 3. speculation: magnet field strength over spec exp3.1: compare Teslameter reading between normal and defect Solution: 1.WorkAround(9/6 ME Change Dead line),Y+ add more 1.5mm Spacing, Now 2.81mm between Magnet & Hor。Need change Sidekey FPC,FPC Change Confirmed. |  | 小熊 | 艳红 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-09-04 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ unexpected auto power off after ESD(8kV CD) on camera deco. Clue: 1. Flash LED and TOF are high risk component, which are nearest with camera deco. 2. remove Flash spr, issue could still be reproduced. 3. remove TOF and reserve interposer, issue could not be reproduced. 4. Discharge on TOF I2C pins directly(4kV AD), issue could be reproduced, with same fail logs, while could not on RST/INT. Root cause: 1. Camera deco discharge on TOF unit, causing I2C interferred Exp1.1:Adding TVS on I2C,Pass. Exp1.2:change TVS to 18pF or 33pF cap, fail Exp1.3:Series in Resistor 100R, DVT2 Verify Solution :1.Add 2 TVS on I2C ,04B PCB . pass 2.Remove Conductive Camera Deco |  | 吉吉 |  |  | 1.SCH | 4.1.Sofia NA
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118735) :Unable to power on A5(1),B2(1),B3(1) A5,B2,B3:drop back side. Root cause: 1.PMIC Crack，all of 3. Solution:Feedback to ME |  | 李果 |  |  | 2.PCB | 4.1.Sofia NA
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118493) :Unable to power on.A5(4) (Unexpected auto power off first A5:drop back side ,and then after drop right side,can not power on) Root cause: Solder Crack Solution:Feedback to ME，ME Follow |  | 李果 |  |  | 2.PCB | 4.1.Sofia NA
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA (WH118794) :Unable to power on.B1(2) Root cause: 1.Pmic Crack Vertically Solution:Feedback to ME，ME Follow |  | 李果 |  |  | 2.PCB | 4.1.Sofia NA
2019-09-02 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Soifa NA TMO drop(WH118494) FVCT11 Sofia NA:Unable to power on.D10(28) Root cause: 1. PMIC Crack Solution:ME Follow Action: |  | 李果 |  |  | 2.PCB | 4.1.Sofia NA
2019-08-31 | 5.DVT1 | 8.PCB | 1.4 Solution | S3 | Closed | [s3] why sofia na using 3+4+3 PCB Layers while sofia row using 2+6+2 which lead to cost up 0.4$-0.5$? clue:Sofia NA PCB design is compatible with Sofia+ NA/row clue:NSMD on Memory and CPU in Sofia Row RootCause:1) PI/SI Simulation not Pass 2)SMD |  | 川叔 |  |  | 6.No Change | 4.1.Sofia NA
2019-08-31 | 5.DVT1 | 8.PCB | 1.4 Solution | S3 | Closed | [S3] Sofia NA 54 Pin VS Sofia Row 40 Pin Root Cause:1.FM+Audio Jack 2.1ME : Ensure Audio Second SPKer on top 2.2 Proposal:PCB Compact Design 3. Sofia Row Reference Sofa NA ,Have some Improvement later. Solution: 0.006$ |  | 李果 |  |  | 6.No Change | 4.1.Sofia NA
20190830 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+Unable to power on- WH118591, B3(5)"B3:after shaker back side." Clue: 1. AVDD of PM6125 is reducing,off current is 0.13mA 2.Press PM6125 ,AVD hold at 1.8V ,and can power on Root cause: 1. PM6125 solder crack 2. ME stress to high on PM6125 Solution : 1. ME use thermal Grease(Old solution is 9X11) on CPU to reduce stress on PM6125 2. Backup : add underfill on PM6125 |  | 敏敏 |  |  | 2.PCB | 4.1.Sofia NA
20190830 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia+ Unexpected auto power cycle on- WH118591, A3(4),B1(4),B3(5)"A3:drop back side.B1:drop right side.B3:after shaker back side." Clue:1.check with log，shows XVDD_SHUT down，maybe battery is absence or VBAT or B_PLUS short to GND 2.Press all shield case of PCBA with great strength ,not reproduce auto power cycle on 3.Drop the phone from 1.5m height for 20 times,not reproduce auto power cycle on 4.No issue found from DVT1B Root cause: 1.Speculation: Solder Crack Exp1.1:Red-Dye PMIC , Result:No issue found on PM6125 Solution:1. No reproduce . severity low . close |  | 敏敏 | 艳红 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
20190815 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [S3]Issue: Sofia+ headset abnoraml when used 02b sub board Clue:1. The mic which striked form sub board is ok 2. The mic hold on the pcb is Root cause: proposal 1 ,ME design no buffer with Audio BOX in EVT causing D501 crack Solution:1. DVT1 ME check gap between Audio BOX and D501 is ok. Action:TCC resubmit 2 D501 ok units double check ----1A pass ，2A fail and D501 damaged . |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
20190815 | 4.EVT | 4.Audio | 6.Issue | S3 | Closed | [S3]Issue: Soifa+ uplink no signal on headset mode used 02b sub board Clue: The mic which tear down from board is ok. Root cause: The mic hold on the 02b sub pcb is blocked off, PCB vender process error. | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: EVT ESD Sofia NA(WH117724) 1）didn't test front side since easy to auto power off while testing it except display area 2）unexpected auto power off：D4(+8KV Air Zone16） Root cause: 1. JTAG is interfered by ESD. In detail, a loop made up of JTAG wire on Layer 9 and Layer 2 is interfered. Exp1.1:Cut JTAG Wire in Layer9 and Test. Result:No Issue. Conclusion:R1 Confirmed. Solution: 1. remove JTAG in Sofia+ DVT1A BR37327, monitor in TCC test. Test pass | Link | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-08-26 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: TP no function after ESD. Clue: 1. +8kV AD on TP IC area, and -15kV AD on FPS area, with TP facing down. 2. NO INT signal to AP when touching. SPI is well functioning. Root cause: 1. TP enter big palm mode, and filtering any input outside. Solution: Updating TP firmware to V06. Verify ok. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-08-06 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [S3]Issue: Edu04 Reverse Polarity Test Fail in EVT WH117718 Clue:1. fail units D501 crack 2.RD units test pass Root cause: proposal 1 ,ME design no buffer with Audio BOX in EVT causing D501 crack Solution:1. DVT1 ME check gap between Audio BOX and D501 is ok. Action:TCC resubmit 2 D501 ok units double check ----1A pass ，2A fail and D501 damaged . | link | 林峰 | 文亭 |  | 6.No Change | 4.1.Sofia NA
2020-06-18 | D.SHIP | 5.Camera | 6.Issue | S3 | Closed | [S2]Issue: can not open flash led during test in the factory sometimes Clue:1. when the issue happens, need to take off the battery. Root , power off b no help 2. Usb_in_mid voltage is 5V ok (VDD_flash),but Flash_led1 0V，no output Root cause: 1. proposal: Sw check the logs 6/21 Exp: SW update ,Result: No SW error find ,Conclusion: May hw issue 2. proposal: PMI632 SW or HW issue ,need Qualcomm support 6/23 Exp: SW update ,Result: 0xd308 shows OVLO Conclusion: May usb-in_mid >5.5V 3. proposal: check usb_in_mid voltage 6/23 Exp: SW update ,Result: max 5.1V Conclusion: may Pmi632 mis-trigger 4. proposal: modify OVLO threshold to 6V 6/24 Exp: Flash ok ,Result: flash led function ok Conclusion: internal comparator mis-trigger 5. proposal: adb shipmode to cut off B_plus ，try to repair NG phone 6/28 Exp: can fix the issue ,Result: no help Conclusion: may PMI632 Vbat circuit error 6. proposal: May PMI632 Vdd_Gen issue which leads to VIB & flash no function ,try to check sleep leakage 7/3 Exp: ,Result: 1 poweroff leakage 103mA，1 poweroff leakage104mA Conclusion:PMIC VBAT current leakage 103mA,Qualcomm make sure it's VDD_Gen issue Solution: 1. 产线操作方法管控降低不良率： 组装电池完成后，扣上电池连接器，然后完全拔掉，过1s后，再重新扣合上电池连接器 昨天产线实验数据： BE17线Sofia+ 1750Pcs，不良2Pcs，F/R:0.11% BE02线 sofia na， 1000pcs，不良0Pcs，F/R: 0% 从数据上看有挺大的改善。 2. 简化不良机修复方案： 不良机可以通过放电到自动关机后，再放置2小时，使电池过放保护，达到VBAT断电，之后再充电，开机。这种方案不用拆机，减少人力和物料消耗。 怀玉这边有安排试了 7台不良机如上操作，闪光灯可以恢复正常。 短期方案如上，请车间从成本和人力上选择最合适的方案，建议是2种方案搭配用。谢谢了。 | LINK | 芳梅 | 怀玉 |  |  | 4.1.Sofia NA
2019-07-29 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S2]Issue: Unexpected auto power off- Sofia+(WH117750）B3(1) Clue:1. It can be turned on normally.but Display abnormal 2. The log shows can't read the ID of display, and advise me to update SW Root cause: 1. proposal: update SW to the new version Exp:SW update ,Result:OK ,Conclusion:Maybe SW issue Solution: SW ,Closed | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
20190830 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Sofia auto power power off 1 time , WH118417 D4,D10 （TMO Drop） ，top side drop Clue:1. Can not reproduce Root cause: Solution:1. Action: |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-29 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: Unable to power on-WH117715 (sofia na) A6（4） post shaker inspection. IKSWQ-4345 Clue:1. always Auto power cycle ,check by chenwt 8/1 .SW checking log (power about 28S and then power cycle) Root cause: 1.Speculation modem or wifi block problem EXP1: SW erase modem and can power up 100+s ,and then power cycle . It should modem block problem 2 Speculation:Solder Crack. Exp2. Red-Dye done ,but no issue found .PCBA damaged. Solution: Action follow DVT1A ALT . DVT1A ALT no such issue found | link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-08-01 | 4.EVT | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue: Loudspeaker noisy. Sofia Na EVT ALT WH117715 ,B1(1) B1(1)： Root cause: 1.Audio AMP Boost Broken(because of damaged boost inductor). 2.Boost Inductor laminated duo to partially glue between inductor surface and shielding case in drop test. Solution: 1.Feedback to ME to Check Glue Process. done B2(1)： Root cause: 1.Audio AMP Boost Broken(because of damaged boost inductor). 2.Boost Inductor laminated duo to partially glue between inductor surface and shielding case in drop test. Solution: 1.Feedback to ME to Check Glue Process. done | link | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3] Issue1: Front & rear main camera no image (Display Blank,unstable) ALT WH117715B1(3),B2(4) ,A1(5) Issue2: Front & rear main camera no image (Display Blank,unstable) ALT WH117750(sofia+)：A2(4) after drop Clue:B1:(N2SR010084) ,A1:(N2SR010083),A2:(N2PZ080020),B2: Not in hand Clue: Front & rear main camera reuse a mipi switch U5000. Clue:Reproduce by Frozen U5000 Root cause: 1.Proposal:U5000- CSI2 MIPI Solder Crack/U5000 VREG_L12A Solder Crack EXP1.1: Reflow B1-U5000 ,can not reproduce by now. EXP1.2: Reflow A1-U5000 ,can not reproduce by now. Exp1.3:Cross Section Sofia+ A2 :F6 pin solder crack ,E6,A6 Partitial crack. Solution: 1. Sofia+ Glue U5000 ,Sofia NA TBD ,DVT2 no glue tracking 2.ME:Add Groove in Shielding Case---recheck WH18735,A4(5), U5000 solder crack . --solution2 can not solve Sofia+ issue. Sofia NA TBD ,waiting for DVT1B test | link | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: L-sensor no function after ALT EVT ALT Sofia NA(WH117715)，A1(5),B1(5) A1：Can not reproduce Clue: LCD module is tilted Root cause: Solution: B1：reproduce Clue: ALS can work, but reading data in Qsensortest is very small. The reading in office is only 10lux and the normal ones are 300lux. Root cause: ALS area is covered by rubber Solution: 1.ME confirm no LCD module tilted issue in DVT1A 2.ME Evaluating not use rubber |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue: P-sensor no function after ALT EVT ALT Sofia NA(WH117715) ，B 3（5），B4（5） B3：Can not reproduce Action： TCC for red dye test,unit broken，close. B4： Can not reproduce Clue:LCD module is tilted(checked by ME Guilin) Root cause: Solution: 1.ME confirm no LCD module tilted issue in DVT1A |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3] Issue: rear main camera not work after EVT Tumble Test WH11717, D4 Clue: 1. Main Camera I2C resistor abnormal. Should be wire crack Rootcause： 1.rear Camera can't work duo to I2C_SCL crack in inner layer under shielding case corner because of pcb strain Solution： 1.Remove L9 wires in this area ,Sofia Plus DVT1A Verify 2.Change L9 wires in this area to Width no less than 0.3mm,Sofia Plus DVT1A Verify 3.Feedback to ME if any approach to reduce pcb strain，Done | link | 邦邦 | 艳红 |  | 2.PCB | 4.1.Sofia NA
2019-07-31 | 4.EVT | 5.Camera | 5.3 EE DVT | S3 | Closed | [S3] Issue: wide& rear main camera not work after EVT Tumble Test WH11717, D5 Clue: 1. Main Camera I2C resistor abnormal. Should be wire crack Rootcause： 1.rear Camera can't work duo to I2C_SCL crack in inner layer under shielding case corner because of pcb strain Solution： 1.Proposal:Modify Layout ：remove L9 wires in this area ,by 8/5 2.Proposal:Modify Layout ：change L9 wires in this area to Width no less than 0.3mm,by 8/5 Duplicate with WH11717,D4,Closed | link | 邦邦 |  |  | 2.PCB | 4.1.Sofia NA
2019-07-31 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S2] Clue: Front & rear main camera reuse a mipi switch U5000. Root cause: 1.Proposal:U5000- CSI2 MIPI Solder Crack/U5000 VREG_L12A Solder Crack Action： Cross section will be done ，Plan TBD Solution: 1.Proposal:Glue U5000 2.Proposal:Reduce PCB Strain Duplicate of Issue1: Front & rear main camera no image (Display Blank,unstable) ALT WH117715B1(3),B2(4) ,A1(5),Merged &Closed | link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-31 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [S3]7/31 TDD Noise Found in EVT Root Cause: 1.SPK Coil Couple by Electro Megnetic Interference Exp:Isolate and Loop Back SPK Coil P/N and Test . Result:Noise heard. Conclusion:R1 Confirmed. Exp:Move SPK out of Phone, and Observe .Result:No Noise . Conclusion:R1 Confirmed. 2.1 Long Distance from Battery GND to PA Exp:Modify GND Sink Point closed to PA. Result:Pass ;Conclusion:R2.2 Confirmed. 2.2 Proposal:GND around SPK Exp:Eliminate GND Around SPK , Cancel Due to R2.2 Solution: 1.Change GND Sink Point closed to PA.RD Validated Pass. Monitor TDD Test on Sofia Plus DVT1A Units. (V03a PCB) | Link | 院长 | 川叔 |  | 2.PCB | 4.1.Sofia NA
2019-07-30 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: EVB test , phone shoutdown when test ,face up ,Without charging Clue: 1.can not reproduce With charging 2.face down ok Root cause: ESD couple through Jtag connector with ground plan because a backhousing hole. EXP: cover this hole ,RD retest pass. Solution:DVT1A there will be not a hole above the Jtag . |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-29 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: Unexpected auto power off-WH117750 (Sofia plus NA) ：B3(1),A4(2) Clue: https://idart.mot.com/browse/IKSWQ-3900 B3:drop right side. Units broken for TCC other test,can not try to reproduce. Clue:1.SW log check ：1 user power off found , but No useful log found.(very little log add in the SW now) Root cause:Proposal 1.SW issue Solution: 1.Waiting for Android Q SW and recheck in DVT1A A4:drop top side.Units broken for TCC other test,can not try to reproduce. Clue:1.SW log check ：1 user power off found , but No useful log found.(very little log add in the SW now) Root cause: Proposal 1.SW issue Solution:1.Waiting for Android Q SW and recheck in DVT1A |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-30 | 4.EVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: Unable to power on- WH117750(Sofia plus NA) A6(1),B6(1),A5(3)after drop Issue1：B6:drop left side. Root cause: 1.Internal Reference Voltage Regulator AVDD Abnormal which lead to unable power on 2.PM6125 Crack observed duo to PCB Strain Solution: 1.ME Follow Issue2：A5: drop Top side. N2PZ080004 can be power on, not reproduce 8/1 by chenwt Can't Reproduce. Issue3：A6:drop back side. Root cause: 1.PM6125 Crack duo to PCB Strain Solution: 1.ME Follow | link | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-26 | 4.EVT | 6.Display/Touch | 4.Build | S3 | Closed | [S3]Issue: EVT build sofiaNA found 4pcs Display abnormal ,failure follow Main PCBA Clue: 1. Blacklight Driver inductor Or Diode damaged (3pcs inductor ,1 pcs diode ) 2. Check Backlight circuit: 1).The inductor PL5300 1.1A typical, 1.3A max, The inductor choose is oK 2). sofia can't support display module hot-plug, if battery on , then plug display module, may lead LEDA(VBAT) short to GND, there will be a very big current, damage inductor or diode 3). poweron without display, the power VSP 5.5V /VSN -5.5V/VIO 1.8V/LEDA 24V etc are always on, then plug display module, more power signal may short .need SW to modify 4) Check Blacklight Driver setting : 5) LM3697 has OCP( set at 1 A (typical). it'a hardware action. But it's not useful for the short of Vout_LEDA to GND 6）LED String （LED_K1 /K2/K3）short Detection is not work , the short decection can't report active， need sw to check, it may occupy system resources 7. RD found 1pcs fail in assembly display module when unit power on . ---Longhai Root cause: 1. Proposal:Display Abnormal due to PL2500; PL5300&D5300 Damaged. 2.Proposal:Power Supply Grounding lead to big current 3.Proposal:Power Supply Grounding due to Hot-plug with battery Solution: 1 .Proposal:产线管控,拒绝带电插拔 ,Factory Informed. DVT1A Monitor 2.Proposal:SW update,shut off power supply to display, when without a display module.(DVT1A cost down display LDO , L9A can't close),SW Imported.DVT1A Monitor 3.Diode PMEG4005AESF 0.5A typical /0.71 max，Change the Diode to Rohm RB161QS-40， 1A typical. PMEG4005AESF 0.5A typical is not enough for HBM mode ,DVT1A Import and Monitor No more fail found ，close | LINK | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-24 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: Phone auto power off after ESD at rec deco Clue: 1. There are 3 parts that could be affected by rec deo second ESD: P sensor, LCD, receiver. 2. After removing P sensor, issue reproduced. 3. LCD recovery well fuctioned. 4. Receiver not GND to MB or middle frame. 5. Add conductive foam to enhance recevier GND, issue not reproduced. 6. This part of GND design is involved in EVB, but not be carried on in EVT. Root cause: Receiver not GND to MB or middle frame. Solution: Add conductive foam to enhance recevier GND. rework test ok . import in DVT1A monitor |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-22 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: P sensor no function(permanent) after ESD at rec deco Root cause: rec deco sencond discharge on P sensor IC Solution: Proposal 1: cut rec deco edge to keep away from P sensor IC; add discharge tip to LCD metal plate. Validate Pass. but will cost up too much . ME go with Proposal 2 Proposal 2:cut rec deco edge to keep away from P sensor IC; add discharge tip near LCD metal plate.(0.5mm shorter than proposal 1 ) Risk :can not rework ,just can retest in DVT1A . Test pass | Link | 吉吉 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-07-12 | 3.PEL | 11.Thermal | 5.2 BB Test | S3 | Closed | [S2]Issue: EVB ：When in charging mode ,Battery NTC report about 45 degree ，but Battery module real temp is 30 degree. Clue: Vbus OVP heat when charging , maybe impact NTC detect. Root Cause: 1. Vbus OVP heat when charging impact NTC temperature Solution: 1. change Vusb OVP IC to main board from DVT1 ----chenwt Battery NTC close to battery cell actual temperature. | Link | 林峰 | 文亭 |  | 1.SCH | 4.1.Sofia NA
2019-07-12 | 3.PEL | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue: There is noise on the board when Display on,EVB board+EVB Display module Clue:1. remove Display ,no noise. It maybe Bias current working noise. or Backlight driver noise. 2.The noise only exist when use 2p8s panel,when use 3p6s panel is ok. Root Cause: 2.SW setting is wrong for 2p8s panel:OVP set to 24V,which leads TI LM3697 output some noise (5Khz to 10+Khz ,not fixed) . (TI LM3697) . issue in EVB Display module , not real issue Solution: 1. No need to change , sofia display module is 3P6S , the voltage of LEDA is 18V , 24V OVP is ok waiting for an analysis link and then close---chang fangmei Done | LINK | 芳梅 | 院长 |  | 6.No Change | 4.1.Sofia NA
2019-07-02 | 2.PCL | 1.Platform | 1.4 Solution | S3 | Closed | [S3]Issue: Sofia NA Cost VS Sofia Row,8$ Gap. Passive,Dll 0.56$, Sensor Gap 0.1$,PCB Gap:1.77$ RootCause: Passive ,DLL Gap 0.56$ 1.1 Cap Sensor LDO, -0.0176$ 1.2 FPS LDO ,-0.0176$ 1.3 Cap Selection(BB), -0.087$ 1.3 Buck Boost ，-0.1$ 1.4 Total Gap left : 0.34$ 1.5 Proposal:RF Cap: 100pf , etc ? 1.6 Proposal:RF Bead , ? 1.7 Proposal: RF Cap Sensor Gap 0.1$ 2.1 M-Sensor & A+G , Same Solution ,0$ 2.2 Cap sensor: A96T346($0.25) vs SX9331($0.43) (Gap: +$0.18); 2.3 Psensor:MN58406($0.3)+26005($0.29) vs VCNL36866A($0.32) (Gap: -$0.27); Sensor Gap Should be -0.09$, GCM Issue PCB Gap: 3.1 Design Gap Proposal:PCB Mainboard 10层2阶 - -20% ， -0.3$ , Drop Due to NA+Row more Complexity 3.2.1 GCM Negociation Gap 3.2.2 Vendor Selection 3.1.Main PCB $1.13 $1.96 $0.83 3.1.1 Jack on MainBoard 3.1.2 27W Turbo 3.1.3 3.2 Main Flex $0.26 $0.71 $0.45 3.2.1 3.2.2 40 Pin VS 54 Pin ,1pin/1 cents 3.2.3 Same Vendor , Vendor Price . 3.2.4 3.3 Prox sensor FPCA $0.00 $0.25 $0.25 3.3.1 Need Confirm. 3.4 SIM/SD Flex VA $0.05 $0.00 -$0.05 3.4.1 3.5 Side Key FPC $0.00 $0.44 $0.44 3.6 PCBs AND FLEXES, OTHER $0.25 $0.09 -$0.16 Solution: | Link | 李果 | 小范 |  | 1.SCH | 4.1.Sofia NA
2019-06-26 | 3.PEL | 12.EMC | 5.1 Bring up | S3 | Closed | [S3]Issue: EVB SIM can not work: RootCause:1. No VSIM 2.NFC power supply design issue cause no Vsim output to SIM card Solution: 1.NFC change 2. Reserve 0R for Vsim because there maybe not NFC in some sku. (will be done by RF) |  | 李果 |  |  | 1.SCH | 4.1.Sofia NA
2019-06-26 | 3.PEL | 12.EMC | 3.Review/Simulation | S3 | Closed | [S2]Solution Risk: Doha DVT issue: GPIO97 config to INT function will cause CPU can not sleep . QC case：04068560 RootCause: QC SM6125 problem ,QC reply other Designer face the same problem , No solution From QC by 6/27 Solution: change AUD_DSP_IRQ_N From GPIO97 to GPIO 45 before Sofia NA EVT Gerber out. |  | 文亭 | 院长 | change link | 1.SCH | 4.1.Sofia NA
2019-06-26 | 3.PEL | 12.EMC | 3.Review/Simulation | S3 | Closed | [S3]Solution Risk: USB OVP 2 ball input and output , 3A charging current ok? Solution:check with Vendor ， the test data show it is ok . |  | 林峰 | 院长 |  | 6.No Change | 4.1.Sofia NA
2019-05-29 | 2.PCL | 4.Audio | 1.4 Solution | S2 | Closed | [S2]Design Risk: Nomad Uplink performance . Clue:Nomad=4.3 >4.0 , Test Pass. No Risk. RootCause: 1.Mic Uplink noise lead to nomand loss Exp1.1: Rioh test result 2.1 Audio Codec Ground and Earphone GND Voltage Level difference Exp2.1:RIO-H Nomad Failure Issue FuPan ， Result: 82nH Inductor connect to Noisy GND , Conclusion: Noisy Audio GND lead to fail. EXP2.2: A40 Grounding design check , Result:EarPhone GND loop back to Mainboard. Conclusion:Audio GND and Earphone GND should be the same voltage. 2.2 Proposal: TDD noise algorithm duo to high TDD Issue 2.3 Floor Noise due to Sub PCB design Solution: 1.Separate Audio Ground ,Validate Pass,No Risk. | link | 院长 | 文亭 |  | 6.No Change | 4.1.Sofia NA
2019-05-15 | 3.PEL | 9.Memory | 2.Design | S3 | Closed | [S3]Design Risk:Upper limitation and low margin in DDR Routing Impedance Clue:Micon 4+64 Pass Simulation Root Cause: 1.Impedance control can't be with good margin due to distance between layers. 2.Thickness Locked to 0.716mm duo to Cost Balance. Solution: 1.DDr Eye-Diagram to validate -BB/SW 2.QC SI Simulation -BB/QC 3.EVB H/L T Stress Test. - BB 4.QC Can Fine Tune 1p by SW DDR REG Fine tune. if failed. waiting for recheck and then close---Dongjiakun |  | 嘉琨 | 院长 |  | 6.No Change | 4.1.Sofia NA
2019-05-17 | 2.PCL | 2.Power | 1.4 Solution | S3 | Closed | [S2] Solution Issue: PM prefer Sofia NA BSP Target=72Hours@50th but currently Sofia BSP=56.1 @50th Root Cause: 1.BSP Output Solution: 1.PM Sync the Actual BSP. |  | 李果 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 4.1.Sofia NA
2019-05-29 | 2.PCL | 12.EMC | 1.4 Solution | S3 | Closed | [S2]Solution Risk: Pesnsor/REC Deco ESD RootCause: 1.Rec Deco Floating 2.P-sensor Closed to Deco Solution: 1.Proposal:Extend Rec Deco GND more close to Display Shielding Can. EVT Verify. EVT test fail ，new issue list，DVT1A go with reserved solution |  | 吉吉 | 李果 |  | 6.No Change | 4.1.Sofia NA
2019-05-17 | 2.PCL | 7.Sensor | 1.4 Solution | S2 | Closed | [S2]Solution Issue: Use I3C A+G that cost up 0.2$ Root Cause: 1.No SPI Interface support in SM6125 lead to use I3C 2.HIFI AR Core Require High Speed Data Bus. 3.Moto G Support HIFI AR Core Requirement to support Google App. Solution: 1.Keep I3C Design | Link | 小熊 | 李果 |  | 1.SCH | 4.1.Sofia NA
2019-05-17 | 2.PCL | 7.Sensor | 1.4 Solution | S3 | Closed | [S2]Solution Issue: Discrete P-Sensor Solution totally Cost up 0.5$ Root Cause: 1.Discrete P-Sensor Cost up 0.3$, CTP Cost up 0.2$ 2.Narrow Gap on the forehead suggest by ME&SME 3.Normal 3in1 P-Sensor Can't Fit. 4.FPC Can't Afford enough space. Solution: 1.Using Laser Hole through 2 Layers , Meet Requirment. |  | 小熊 | 李果 |  | 1.SCH | 4.1.Sofia NA
2019-05-17 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [S3] Issue: EVB build always enter 9008 mode Clue:9008 can blank flash ,but can not enter fastboot mode root cause: GPIO118 pull high to L9A ,cause the Boot mode incorrect. solution:1. DNP R5006 for EVB build -done 2. EVT sch delete R5006--done |  | 文亭 | 邦邦 | SCH change link | 1.SCH | 4.1.Sofia NA
[6 empty] | [S3] 1.4 pin 版与2 pin 版的利用率 （方正使用2pin可以提高） 2.打孔的数量 3.贴片效率 4.打板的数量，华为4次，oppo 2次 ， 影响他的交付， 5.混搭大板和小板 5.阻抗线低于40um的，LDK，355D，射频要求45um以上，285. | [5 empty] | 4.1.Sofia NA
2020-08-20 | D.SHIP | 1.Platform | 5.6 User Feedback | S3 | Closed | [S2]Issue:Game performance, Asphalt 9 high quality Display setting, FPS=22fps ,VS 30FPS of Redmi K30 Clue:1.CPU big core almost not work ,just Small core working. Vs Redmi K30 Big core working more. 2. GPU working with full Frequence and usage . Vs Redmi K30 not full frequence . 3.Display module resolution:Nairobi ：2520*1080；Racer 5G：2340*1080 ；Realme X50：2400x1080 ；Redmi K30 ： 2400x1080 suspect: 1. CPU block the performance exp1：lock CPU CLKto higest always ，no improvement 2.GPU get too much work to do and too heavy .can not work well exp2：change Display setting 2.1 Use Sofia Display , issue gone . 2.2 setting Nairobi display resolution to 1920*864 on SW , issue gone . Root cause：SW didnot set Display Physical size ,and then Game make too much loading to GPU ,lead to FPS drop. solution: Temp ：Set Display Physical size to 67*157mm in SW platform code , issue gone |  | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-28 | C.RAMP | 9.Memory | 5.6 User Feedback | S3 | Closed | [S3]Issue:Second Vendor Micron 6+64, TombStone Issue found on 1 DVT1 unit from DFer. clue: 1.Total 661 pcs produced in 3T , Plan on 7/20 shipping request 2K. Hynix is first vendor . 2.Memory FW 106 Root Cause: 1.UFS communication issue found through Log. Same symptom on Racer. 2.Micron confirm that FW 106 has one ufs timing compatible bug with QC SM7250(Though meet JEDEC）, fixed in FW 109 and verified workable. 2.1 Shift Back this unit from BJ for furthur FA. 2.2 SW judge the severity . 6/30 Solution:1:Using new FW 109 Memory in the following production . |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-22 | B.PVT | 7.Sensor | 4.Build | NA | NA | Issue: Build PROX_SENSOR_UNCOVERED_RADIO :CT too large ,over SPEC Clue: 1. CT OVER SPEC issue follow LDA module (front housing+p-sensor+CTP) 2. 1 unit component Vendor checked component is ok. Root Cause: suspect 1 : assembly issue. Solution ： | link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-17 | 7.DVT2 | 11.Thermal | 5.5 Certification | NA | NA | Issue: Thermal ,RF power limited in certification. Clue: 1.High temp test fail （should be Thermal config limited RF power) Root Cause: Solution 1： |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-22 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | Issue:ESD，PVT ATT SKU WH127075 ，D2 1：The charging LED is always on after 15KV air discharge:1台 Zone 13 Clue: 1. Zone 13 ：face down ，upside 2. SOL_LED work sync with it Power input VREG_BOB. suspect PM7150L damaged Root Cause: PM7150L damaged . Solution ： ME follow the glue quantity between front rim and front housing |  | 文亭 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-22 | B.PVT | 12.EMC | 5.3 EE DVT | S2 | Closed | Issue:ESD，PVT ATT SKU WH127075 2：unable to power on after 15KV air discharge：1台 Zone1 Clue: 1. a Root Cause: P-sensor power(L10A) abnormal impedance（ 660R） Solution ： ME follow the glue quantity between front rim and front housing |  | 敏敏 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-06-19 | 7.DVT2 | 4.Audio | 5.5 Certification | NA | Closed | Issue: VZW ,EN55035 ,CS fail Clue: Root Cause: Solution 1： change Volume. changed by adb and retest pass |  | 院长 | 李果 |  | 4.Parameter | 5.Nairobi
2020-06-17 | 5.DVT1 | 7.Sensor | 5.5 Certification | NA | Closed | Issue: DVT1 AR Core certification fail: calibration fail. Clue: 1.calibration including camera & A+G sensor 2.A+G sensor should be Invensence (2nd source which only build in DVT1 unit) 3.Depth camera change in DVT1, the test phone are with old depth camera. Root Cause: Over limit, need calibration to decrease raw_data into threshold (Same as Racer) Solution ： Use adb command to calibrate A+G before AR Core test. | link | 小熊 | 邦邦 |  | 4.Parameter | 5.Nairobi
2020-06-10 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: PVT EDu03【WH127058】 light and proximity sensor no function:D1(NNIE430147) (15KV, Zone1） Root Cause:P-sensor INT abnormal ，Component damaged Solution 1：ME follow the glue quantity ( 0.33mm->0.5mm) | LINK | 小熊 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-23 | 5.DVT1 | 9.Memory | 4.Build | NA | Closed | [s3] Issue:Factory rework Umcp &CPU ,PCBA go into 9008 dirrectly and can not download （3 pcs in 3pcs） clue:1.Blankflash tool log show UFS initial fail ;2.uMCP is KM5V8001DM-B622 （didnt rework other memory） 3. AB swap(uMCP )， fail follow uMCP; 4. rework 1unit with hynix MEMORY，not reproduce （ODYSSEY use） 5. non-secure phone，IFlash No Bonding with CPU and Memory ; 6.FW Status latest ;7.new ic ，while racer used too but not qualified Root Cause: -Why Memory Can't Download after Blank Flash? 1.1 Memory Damaged? Conclusion: Exp1.1: Failed Memory ReBalling and Welding back to Original Board and another new Board ; Result:Both Failed Exp1.2：Samsung FA ; Result：FW OK,User Data UECC Error, Redownloading and Aging Test Pass. Exp1.3 :Verify Issued Memory that sent back from Samsung; Result:Test Pass. 1.2 Welding Issue？Conclusion1.2:TBD Exp1.2.1 Cross Section,TBD; Exp1.2.2 Remove CPU,and Measure Impedence of each Memory Net on Failed Memory,TBD Exp1.2.3 X-Ray ;Result:No cross welding Exp1.2.5 Reballing Failure Unit and Reflow Oven,TBD 2.1 Over Temperature during Maintain Lead to Damage? Exp2.1 Check Temperature and Duration During Maintain if over Spec;Result: No Feasible Repairing Heating Temperature of Memory in industry. Exp2.2: Check IF Station Data,Result:No Issue Exp2.3:Flash Bootloader ;Result:Pass with Memory Issue reported Exp2.4.1:good unit,Heat and remove Shielding Case;Result:Failed. Exp2.4.2:Re-Flash and Boot Successfully.Welding Back Shielding Case,Result:Boot OK. Exp2.5:Good Unit.Heat and remove shielding Case,Result:OK Exp2.5.Heat Memory directly for 100°C-320°C@50~100°C Step @<30S ;Result:OK Solution:1.Heating Temerature Control , 320°C ，<30S 2.Factory Evaluate MVA increase 0.041RMB | link | 嘉琨 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-25 | 7.DVT2 | 11.Thermal | 5.2 BB Test | S3 | Closed | [Monitor]Risk:Nairobi Thermal on 5G Scenario Clue:Heat Feedback on WeChat Video Talk and Teams Meeting etc.when 5G working on both Downlink and UpLink,5W+.Over 45°C when long time used. Clue:Mdu30 Pass ,Except 5G Scenario duo to lack of 5G Environment in WuHan TCC. Potential Root Cause:1.No 5G Thermal Standard &Lack of 5G Environment in WuHan TCC 2.Raw Thermal Config without 5G mitigation Precaution Measure: 1.5G SW mitigation , Solution confirmed,fine tune done on 5/28,Monitor |  | 林峰 |  |  | 4.Parameter | 5.Nairobi
2020-05-20 | 5.DVT1 | 6.Display/Touch | 4.Build | S3 | Closed | [Closed] Risk:liberty Backlight damaged issue Clue:DVT1-DVT2 no Issue feedback. Run in 100 units，No Issue. Clue:Exp: PVT Run in 1000 , Monitor 6/? Potential Root Cause: 1.Temperature,Over Heating on PM7150L or Switching Inductor? Exp:Run in on 50 °C and Low brightness/High Brightness Switch stress test, Result:No Issue 2.OVP &OCP when Mode Switching? Exp:Signal Measure,Result:OVP Set 38.5V,OCP 1.75A,Vsw=58V,0.5S@30V,Function Normal@several Times ,Will Keep More Stress Test. 3.4X5 Leds VS 3X6 Leds？ Exp:After 1,2, Than Verify 3X6 , Result:TBD 5/26 4. Isat of Inductor？ Exp:Nairobi Inductor 1.2A, Current Drain=0.8A@Full brightness of Display ,Result:Meet Requirement Cost: Murata 280% > Samsung 200% > MicroGate 100%(1.1 Cent) Precaution Measure:1.SW Import Soft Start both on Power on and Wake up , 2.Set OVP 20.5V,OCP 1.05A ,RD Verified OK RD Verified Pass. DVT&PVT&MP Run in 2595pcs ,CQA Verified Pass, No Risk & Closed. | LINK | 芳梅 |  | liberty tech review link | 6.No Change | 5.Nairobi
2020-05-25 | 7.DVT2 | 10.USB-C | 5.6 User Feedback | NA | NA | [S3]issue: Nairobi Thunderbolt USB port detect fail issue(SM7250) 。 具体issue：Nairobi 5G项目，在部分电脑 雷电口可以识别USB， 部分电脑 雷电口不能识别USB。（目前测试 Lenovo 2台T470S ，还有1台T480电脑， 都有问题。 只有1台T490 电脑ok.） SW QC CR：Case Number 04621321 Clue: 1. SM7250平台的Racer 5G 同样的表现 2. SM7250平台竞品手机情况： realme X50 ，readme K30 ，发现同样fail的问题， 故障波形一致。 3.有台T480电脑（liuyc20的电脑）原来不能识别，更新电脑的雷电口驱动后可以识别。 Rootcause： SM7250 平台性 和 电脑 雷电口 的兼容性问题 solution: 待QC分析 | link | 文亭 |  |  |  | 5.Nairobi
2020-05-15 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [Monitor]Issue: Adaptive brightness mode，brightness shows 0%,screen flash sometime Clue： 1. Backlight current=(hal/4095)*CABC duty circle*25mA，brightness 0%,hal=19，Cabc duty=79% ,backlight flash. hal=19, backlight current= 0.0916mA/sink， hal=34, backlight current= 0.166mA/sink， 2.enable CABC(0x1D951=0x1), set 0x19D49=0x0c(PMIC Digital Accumulator bit-width selection14 bit to 15bit) and 0x1D952=0x0, set CABC=79%, hal19/34 ok , but Hal=29/48/67/72/91 backlight duty not stable, screen flash Root Cause:1.Limitation of PM7150L under Low driving current with CABC , Exp:find which parameter leads backlight flash : when backlight flash, cabc duty circle stable(test the waveform from display and use signal generator set CABC), hal value stable(adb log hal value per 10ms and adb set hal value ), but the backlight wled duty not stable ,it means the current changes。 CABC duty circle change to 96% or disable CABC ,backlight duty is stable hal=19/34. 2.CABC Compatibility Limitation of PM7150L? Exp:Check with QC, QC confirmed known issue on PM7150, Solution:1.Set 0x19D49=0x0c(PMIC Digital Accumulator bit-width selection14 bit to 15bit) and Disable CABC on Low brightness<=200, SW Work around ,Version effected | LINK | 芳梅 |  |  | 4.Parameter | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03[WH124614]Kernel panic;D3(15KV zone6） Clue：1.Cap-Sensor No Function 2.Duplicated Root Cause: 1.Cap sensor ATVS VR100 damaged duo to EOS . 2.Speculation:ATVS Rated Voltage Margin not enough Exp:Change a Stronger Part,DVT2 Imported and Test Pass. Solution ： VR100 change to LXES03AAA1-193(Rated Voltage: DC 4V,AC+/-25V ->DC 6.3V AC +/- 80V) , DVT2 Imported,DVT2 EDU03 WH125964 pass | link | 李果 | 小熊 |  | 3.BOM | 5.Nairobi
2020-05-11 | 7.DVT2 | 7.Sensor | 4.Build | NA | Closed | [Monitor] Issue: Build found some M-sensor surface scratches monitor SMT process from5/11 by NPI | link | 小熊 | 怀玉 |  |  | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03【WH124662】 light and proximity sensor no function:D4(15KV, Zone3） Root Cause:P-sensor INT abnormal （35R to GND） ，Component damaged Solution 1：ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，DVT2 EDU03 WH125964 pass |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-15 | 7.DVT2 | 7.Sensor | 5.4 ALT | NA | Closed | Issue: DVT2 ALT WH125967 D4,D5 P/L sensor no function Clue： 1.CQA Psensor can not enter, Lsensor no data Root Cause: 1.Speculation: P/L sensor crack issue.(same AS issue found in DVT1).ME follow |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-15 | 7.DVT2 | 7.Sensor | 5.3 ME DVT | NA | Closed | Issue: DVT2 ATT WH125966 D2 cap sensor no function Clue： 1.CQA All channel unknow ,reboot can not recovery Root Cause: SW issue Solution ： Fixed ,from 5/15 |  | 小熊 | 文亭 |  | 3.BOM | 5.Nairobi
2020-05-15 | 7.DVT2 | 4.Audio | 5.3 ME DVT | NA | Closed | Issue: DVT2 ATT WH125967 D4 headset no function Clue： 1. report checked All MIC no function with headset 2. MIC analysis show ALL mic ok . SO it is headset downlink issue. Root Cause: Sub board crack (area near headset jack) Solution ： ME follow |  | 院长 | 文亭 |  | 3.BOM | 5.Nairobi
2020-04-29 | 5.DVT1 | 3.Charging | 4.Build | NA | Closed | [s3] Issue: Build BrdTest Station,"TURBO_CHARGE_CONNECTED" Test Fail, Retry pass,NTF. Fail Rate:10%? CR: IKSWQ-90483,SW: QPN30.13 Clue：1. most of fail PCBAs are VZW SKU. Exp：Stress test with 2PCBA to check if it can be reproduce--Can not reproduce by 0507 chenhy4 2.Fail log:charging type SDP,Pass should be DCP Exp：check USB D+/- waveform when issue reproduce 3.retry pass without shutdown power or moving the board Root Cause: 1. Speculation:Contact issue? Can not reproduce in DVT2 so far ,monitor DVT2 VZW build （FROM 5/14） By 0515 no issue found ，close | link | 文亭 | 怀玉 | https://idart.mot.com/browse/IKSWQ-90483 | 6.No Change | 5.Nairobi
2020-05-08 | 5.DVT1 | 4.Audio | 5.6 User Feedback | S3 | Closed | [Monitor] Issue: Background Noise observed on V07 PCB during Car Audio charging & Aux in mode ， Clue :1. follow up Main PCBA. V06 No Issue. Root Cause: 1.HS_REF is ground well but still was Affected by MainGround that mainly used as Vbus Power Return Ground. 2.HS_REF was Shift to Layer5 from Layer 7 duo to R&L Crosstalk Audio Ground Optimization Solution:1.Recover Audio Routing as V06 Version on PVT&Risk Buy, done 5/9 | Link | 院长 |  |  | 2.PCB | 5.Nairobi
2020-05-06 | 5.DVT1 | 4.Audio | 5.2 BB Test | S3 | Closed | [Monitor] Issue: HeadSet Downlink TDD Background Noise observed on V07 PCB Clue :1. follow up Main PCBA.V06 No Issue. Root Cause: 1.HS_REF is ground well but still was Affected by Layer 4 MainGround that mainly used as RF GSM PA Power Return Ground. EXP1.1 Connect HS_REF to GND on sub board and recheck issue gone. 2.HS_REF was Shift to Layer5 from Layer 7 duo to R&L Crosstalk Audio Ground Optimization Solution:1.Recover Audio Routing as V06 Version on PVT&Risk Buy, done 5/9 | Link | 院长 |  |  | 2.PCB | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue: DVT1 EDu03【WH124642】[NNIA1C0043 /D4] 2. -15KV air discharge at zone15(Aging 10),Cap sensor CH0 unknown Clue：1.直接用ROOT权限操作CAP SENSOR IC，IC可以正常输出各实际状态 2.自测碰到三个通道都unknown的状态，应该是权限问题(Permission)导致 3.在同平台smith在4月29日有修改权限配置，应该是HAL层不同导致。但之前的项目Sofia等都不需要配权限 Root Cause: Linux访问文件都是需要配置好权限的，目前这些节点都是root用户权限，对于上层进程而言，这个权限比较苛刻 Solution 2：SW更新，让它们属于同一个group就可以了，同group的就没有这个权限问题 | link | 小熊 | 李果 |  | 3.BOM | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue:DVT1 EDu03【WH124642】[NNIA1C0043 /D4] 1. +15KV air discharge at zone13(Aging 10),proximity sensor/light sensor no function,unable to recovery Root Cause: 1.proximity sensor/light sensor INT abnormal （100R to GND），Component damaged 1.1 glue quantity too low? Solution 1：ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，monitor duplicated to EDu03【WH124662】P-sensor issue |  | 李果 | 小熊 |  | 3.BOM | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] Issue: DVT1 EDu03[WH124614]Kernel panic;D2(15KV zone6） Clue：1)P-Sensor no Function 2)Cap-Sensor No Function Root Cause: 1.Kernel panic and P-sensor/cap-sensor no function duo to VCC of P-sensor shorted 2.P-Sensor Damaged by ESD duo to glue width under spec(0.38mm observed <0.5mm Spec) Solution: ME follow the glue quantity ( 0.38mm->0.5mm)，DVT2 import ，monitor reproduce in EDu03【WH124662】. duplicated to EDu03【WH124662】P-sensor issue |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-15 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [Monitor] DVT1 Issue:Edu03 ESD Test，cap sensor function normally on D4(NNIE130086) on 4/15, but no function after reboot Clue： 1.Remove VR100 on CH2 and the cap-sensor returns to normal Root Cause: 1.Cap Sensor CH2/Addr affected by VR100(ATVS LXES03AAA1-154 abnormal impedance), Sending to XiaMen & Later to Murata Japan for further FA (zto:640106156044) 4/16 Exp 1.1:Stress Test 800 Times @Zone13@2Units, Can't Reproduce. Exp1.2:Try Infineon TVS ESD103, Result: TBD Exp1.3:V/I Test Shows Leakage Resistance ~79Ω Exp1.4:Stress Test 600 Times on ANT Directly,Can't Reproduce. Monitor. 2.Cap Sensor Enter RD Debug Mode when Pull Down Exp2.1:Reproduced on Semtech DemoBoard @Pull Down 20K , Semtech America explain It is RD Debug Mode Entry. Exp2.2:Isolate ANT by spraying Paint，Result:TBD Solution:1.According to Result of Exp1.1 and Exp1.3，Exp1.4，Turn to Monitor reproduced ，EDu03[WH124614] ,duplicated to EDu03[WH124614] capsensor issue | link | 李果 | 小熊 |  | 4.Parameter | 5.Nairobi
2020-05-07 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3] MDu30[WH124618] FVC E1D，QPN30.19 ,20W 充电器,无热管,Speaker位置增加散热膜，display 2nd IC display 90HZ 场景验证（充电下,wifi streaming 手动设置） 1）Camera photo front 42：44.6 2）LTE data call at Max power front 38：39.7 3）Game with charging back plastic 42:51.6 4) Processor loading front 40：42.8 Toot cause ，Thermal config issue ，correct from 5/13 |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-11 | 7.DVT2 | 7.Sensor | 4.Build | NA | Closed | [s3] Issue: Build TEST L2AR Station,M-sensor fail，DVT2 10% (13/130)，NTF Clue：1. can not reproduce with manually test (6 in 6,By huaiyu & Online ME Liuxiang) 2. other sensor NTF too. 3. When issue happen the USB port is connected but Network &ADB can not work. 4.L2AR test with Vbus power but not Vbat. change to power by Vbat ,issue gone Root cause：suspect Vbus power not enouth for the test. solution :change to power by Vbat from 5/12 . monitor | link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-06 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3] Issue: EDu03【WH124662】 1）the phone lock-up,restart to recover：D1(6KV contact，zone7） Root Cause: should be ramdump issue. monitor in New SW from 30.23 |  | 李果 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-05-06 | 5.DVT1 | 2.Power | 4.Build | NA | Closed | [s2] Issue: Build CQA1,In CQA app, check battery information, find battery level jump,CR: IKSWQ-91703 Clue：1. NNIA1C0039 issue ,other can not reproduce 2.Fail log:temperature jump too .t=25,-40,39 in one second! 3. Fail log:Battery remove and then Battery inserted after 2 second! Root Cause: 1. NNIA1C0039 1 unit issue, not common issue. reassembly sub board and recovery . should be connector assembly issue. | link | 李果 | 文亭 |  | 6.No Change | 5.Nairobi
2020-04-26 | 5.DVT1 | 2.Power | 5.4 ALT | NA | Closed | [s3] Issue: WH125660 A5，B1 auto poweroff 1 time Clue：Ramdump show it not poweroff but ramdump too Root cause ：same as IKSWQ-89850，a QC bug . found in ESD test too IKSWQ-85825 Solution:fixed in SW 30.22 . monitor |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-26 | 5.DVT1 | 2.Power | 5.3 EE DVT | NA | Closed | [s3] Issue:EDU13 WH124523 Power ：battery performace Run local video less than 5 hours （~=2.7 hrs） Clue：1.sofia plus more than 5 hours 2. Nairobi power log show average current is 1.8A.3.Battery capacity checked no problem（70% of 25 degree）. 4. Problem ： D1 NNIA110016 standby current is about 0.2~1.2A，abnormal Root Cause: 1. D1 unit current abnormal(+0.2~1.2A） ,RF calibration parameters lost and the modem has been restarted 2. Recalibrate RF parameters and the current is normal Solution: 1.Recalibrate RF Parameter |  | 李果 | 敏敏 |  | 6.No Change | 5.Nairobi
2020-04-24 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3] RISK:WH124577 ESD :In final TIS test, LTE band7 main antenna degradation exceeds 3db, and TIS value is also out of spec on D4(NNIV120109) on 4/24, Clue： Root Cause: Sending to XiaMen ANT for further FA 4/24 ，Will Open after Ant Check 针对这台B7的问题，ANT暗室同样可以复现。 结论如下： 1． 我们提供工厂的TuneCode都是偏TX的，所以RX相对差。 2． 我们提供tunecode都是基于EVT机器，和DVT1的机器比，天线性能偏移掉了。 在问题机上，我们update新的code以后有源和无源数据都是合理的 |  | 李果 | 林峰 |  | 6.No Change | 5.Nairobi
2020-04-26 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | NA | Closed | [s3] Issue:Thermal WH124559 Game with charging plastic 42:59 Clue：Stale data，NA & Close Root Cause: |  | 林峰 |  |  | 6.No Change | 5.Nairobi
2020-04-13 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:DVT1-1 P sensor CQA test can enter but no reading 4/40pcs Clue: 1.log show phone in FAR(0) state 2. restart phone, test ok 3.can reproduce sometimes 4.Seperated I2C . 5.Reproduced once on Stress Test on 1 unit @Stay Still@Change Light Frequently@overnight. Root Cause: 1.Interupt keep low by P/ALS through Log lead to Test Fail 2.P/Als missed receive Int Flag Read duo to ADSP didn't Pull Up in first few mili seconds in sleep mode. 3.Why ADSP Missed Few Seconds Pull Up，Coworking with Qualcomm Exp3.1:Register Comparison , Result: Canceled Solution:1.Workaround 1,ADD Int Flag read when phone wake up . Drop According to S2，S3 2.Workaround 2,ADD INT flag read and do ISR in ESD recovery loop (1 time per 8S), Imported 3.Workaround 3,Add External Pull Up Resistor ，Done on DVT2 ,Monitor | link | 小熊 | 文亭 |  | 3.BOM | 5.Nairobi
2020-04-23 | 5.DVT1 | 2.Power | 5.2 BB Test | NA | Closed | [s3] Issue: sleep current abnormal （25mA）after open and close camera APP clue:1. remove all the camera module ，PCBA sleep current is 25mA too Root Cause: 1. AXI port Resource Request，No Vote Mechanism to exit and Continually Occupy resource which lead to AP can't enter Sleep mode. Solution: 1. Adding Vote Temporarily。Verified OK-SW 2.Furtherly Check with QC |  | 邦邦 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-23 | 5.DVT1 | 1.Platform | 5.6 User Feedback | NA | Closed | [s3] Issue: 2 PCBAs go into 9008 always ,From RF debug clue: 1. have current leakage (1#100 mA ,2#300mA) 2. can blankflash but go into 9008 again 3.S4A impendence abnormal. 1#=13R ,2#=4R 4.remove CPU and S4A impendence ok 5.S4A is close to Vbus on main connector Root Cause: 1.CPU (related to S4A part )damaged. 2.suspect: connect Main fpc to Main board when main FPC and sub board connector toPC already(with 5V power) cause short the S4A to vbus. Solution: connect the Main FPC to Main Board when sub board not connect to PC or chareger. | link | 文亭 |  |  | 6.No Change | 5.Nairobi
2020-04-13 | 5.DVT1 | 12.EMC | 5.2 BB Test | S2 | Closed | [S2]4/12 DVT D1 After +15KV air discharge at zone 13(Aging4),No Main display 1.Grounding OK. Root Cause:1.Display Affected. Sending to XiaMen for further FA 4/14 Solution:1.Dispaly damage, and KP further FA |  | 芳梅 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-17 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue: CQA P-sensor No Value，ALS Stuck，Restart ok Root Cause: Share Same Root Cause with Intrupt hung. Solution: SW Fix |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-17 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: Factory SW FB :NAIRO_IFLASH_DVT1_005_894.xml.zip PS can not enter . Clue:SW poblem,NAIRO_IFLASH_DVT1_004.xml.zip is ok. Root Cause: SW Power config issue Solution:SW change https://gerrit.mot.com/#/c/1536341/ |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-15 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: L2站点有发现，ALS/PS rawdata偏小， 重启后依然fail Root Cause:麦拉遮挡PS 孔--by Huaiyu Solution:Factory own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-15 | 5.DVT1 | 7.Sensor | 4.Build | NA | Closed | [S3]Issue: CQA PS 正常，ALS 一直dark，不变化， 重启后依然fail Root Cause:ALS 校准bug有关(重新刷机可以解决)--by Huaiyu Solution:SW own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-13 | 5.DVT1 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]DVT1-1 ALT(WH12455) A6(5) Magnetometer no function Root Cause:1.M-sensor crack 2.M-sensor too close to board edge Solution:1.V07 PCB change M-sensor far away from board edge ,done。 monitor | link | 小熊 |  |  | 2.PCB | 5.Nairobi
2020-04-10 | 4.EVT | 12.EMC | 5.3 EE DVT | S3 | Closed | [S3]Issue:EVT EDU14 WH124347，surge test fail ，D1 &D2 Vbus At 150V&100V fail（unexpected auto power off at plug in the power） clue： 1.first project to use Will TVS for surge. other project use NXP TVS for surge Rootcause: 1.New Part WILL SF68C56226 Edu14 surge Test Verified failed. solution: Change back to NXP 48014320001（Used in all in-house project） 1. BOM change done 2.DVT2 SCH change done. 3.DVT2 and PVT material ok. further Project Action：parameter test ：WILL fail unit VS WILL OK unit VS NXP unit （sub board test wave ），done 。 Will D18 performance is similar to NXP 18 ， verity it in TCC and D18 pass . | link | 文亭 | 林峰 |  | 3.BOM | 5.Nairobi
2020-04-13 | 5.DVT1 | 7.Sensor | 6.Issue | S3 | Closed | [S3]DVT1-A(V07) Magnetometer placement change cause SW parameter update Root Cause:1.M-sensor crack 2.M-sensor move from BOT to TOP on mainboard Solution:1.SW parameter compatible by HWID。 2. HW of Japan SKU reserve 2 placements for M sensor to make SW compatible. | link | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-03 | 4.EVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3] Issue:EVT CE CS Pre-test Failed, Over 15dB@4.5MHz@UpLink Root Cause: 1.CS Uplink failed due to Audio Ref Signal not balanced and Echo Suppression Algorithm Take Effect. Solution: 1.Fine tune Coupling Capacitor and inductor on Ref on newest audio configuration. RD Validated Pass. Sporton validated Pass |  | 院长 | 李果 |  | 1.SCH | 5.Nairobi
2020-04-06 | 4.EVT | 11.Thermal | 3.Review/Simulation | S3 | Closed | [S3]Overheating risk are on speaker Root Cause:1.SPK Heating Solution:1.Add Graphite on SPK Box.Test Pass. ~0.15￥，No Volume loss |  | 林峰 |  |  | 4.Parameter | 5.Nairobi
2020-04-14 | 4.EVT | 1.Platform | 5.2 BB Test | S3 | Closed | [S3] 1 unit NNIV040046 can not power on sometimes. unstable clue: 1.SW check it is related to a SW debug function D+ short to gnd will run EDL mode ，then release D+ will enter 9008 2.test R between D+and GND it is ok sometimes 3.copper for mmw ANT cover USB test point 4.remove the copper can not reproduce for 5 times test. Root Cause:1.thermal copper for mmW ANT cover USB test point causing D+ short to GND . 5. Impact VZW SKU(with mmW) Solution:1.change copper ? 2.add a glue to cover the USB test point?(checked can not move the test point) ME tracking | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-04-07 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [na]Issue:EVT CQA Report Rear Camera Record Stuck,FR：4/53=8%（IKSWQ-80124） Clue： 1.Follow Mainboard 2.Only happen in RF connector SMT in wrong direction 3.when in flymode there is no issue Root cause：1.MCLK Signal dispear after few seconds when camera start up. 2. Multiple invoked in Clock module and Modem module on GPIO25/MCLK 3.GPIO25 Detection invoked when RF Calibration Fail duo to Connector wrong direction 4.Modem Code share Racer 5G GPIOI25 Config which is not used in nairobi Solution:SW Re-Config GPIO25 - Verified Pass. | link | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343， A6(1) Flashled always on ， including power off mode. clue：1.Light unstable when knock the phone around Flash LED. Rootcause： 1.Flash LED on due to spring M1811( Flash LED2+) and M1813(WLED_CAM) short which caused by cracked registration mast 2. ME furtherly analysis solution: ME Follow 1.ALT after 4/20 remove the registration mast. 2. change registration mast to bigger from DVT2 | link | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，No Turn On ,A1 Clue:1.Turn on after changing Display. but PCBA cannot power on when unit arrive in XM 2. Main FPC： B to B pin deformed，can not assembly well ，may cause pins short when press B to B （will heatup when plug in charger）,when connect main fpc ,can not power on ,disassembly main fpc,it can power on . 3. Main FPC change to a good PCBA , 1 time it can not charge and heat up on the connector,1time it can not power on . So the Main FPC should be damaged physically Rootcause：1.Display module Broke（but it should be broken when disassembly） 2.Main board VREG_S4A_1P8=0.8V,Resistance of VREG_S4A_1P8=1.2Ω,normal value is 2.1KΩ ,suspect charging with the damaged main FPC cause Main board damaged. 3. Main FPC damaged when assembly 4. ME ：FPC didnt assembly well cause main FPC damaged. ( B to B pin deformed) Solution: ME tracking DVT1 build if the FPC assembly bad. BB monitor | link | 敏敏 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-30 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop5，Display DIM:B6(1) Rootcause：4/2ME can not reproduce，waiting for KP check |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-31 | 4.EVT | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue：EVT WH124356 ATT11+WH124357 ATT12 ，D1 ，not turn on（when unit arrived XM ME） Clue：1.enter fastboot mode but shut down within 5 sec. 2.can Blankflash ,and enter fastboot mode and not poweroff ,but when flashall,phone reboot ,it will reproduce failure again. 3. it show low battery voltage in charging mode. Rootcause： check the Battery Voltage=0 . swap a good battery it it ok. move to KP for battery analysis DVT1 ：ATT11 WH124550 D10 & ATT12 WH124551 D10 same fail ，battery issue |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-17 | 4.EVT | 7.Sensor | 5.4 ALT | NA | Closed | [S3]Issue：EVT RD ALT*2round evaluation，ALS/ps fail 3 in 6 (including 2 in 6 sol LED fail too) Rootcause： ME middle housing deformed causing P-sensor component damaged and LED damaged too. solution: ME own. ME action 1. ：enhance housing strength by adding metal at the corner, will implement in DVT1 white color build； ME action 2. move P-sensor up 0.2mm |  | 小熊 | 文亭 | test result | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-31 | 4.EVT | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [S3]Issue：Nairobi 目前的SW 关机状态下，短按开机键 屏幕会闪一下,CR(IKSWQ-79283) Clue： 时序测试：现短按开机键时，mipi输出后，背光亮起的时间有差异。短按是mipi数据输出60ms后，背光开始输出，长按开机键，mipi数据输出500ms后，背光开始输出. 希望SW 分析 Rootcause：SW reply 结合代码走查，发现了个code的BUG,预计解决 by 4/2 check ok with SW 4/8 |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，No Turn On ,A1 Clue:Main FPC connector deformed. Rootcause： assembly issue Solution: ME Own 1.correct Allsmbly in DVT1. 2. checking if need to change Main FPC for better Allsmbly |  | 文亭 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop1，Cannot enter front camera mode:A2(1) Rootcause：ME FA B2B Issue ，should be assembly cause connector damaged 4/2 | link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ATT drop WH124356， Proximity sensor and light sensor no function:D1(27,T,1.25m),D3(12,B,1m),D4(45,T,1.5m) Rootcause：ME middle housing deformed causing P-sensor component damaged,same as ME evalution test. ME own the issue tracking | Photo link | 小熊 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 5.Camera | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ATT drop WH124356， Cannot enter rear 4 camera mode：D1(3,F,1m),D3(21,F,1.25m) Rootcause：Macro camera fail. B to B connector dissasembly.ME own the issue tracking | Photo link | 邦邦 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，loop2，unable to power on after top right corner drop:A1(2) Rootcause：DISPLAY FPC在近主板B2B的弯折区有严重变形，并且display module的B2B 边框区域有明显塌陷，图片已上传GD 主板没有问题，更换display module后可以正常开机。ME&KP own the issue tracking | Photo link | 林峰 | 怀玉 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]Issue：EVT ALT WH124343，loop2， P/L sensor no function after top side drop:A1(2),B5(2) Rootcause：-sensor component damaged,same as ME evalution test. ME own the issue tracking | photo link | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-26 | 4.EVT | 5.Camera | 3.Review/Simulation | S3 | Closed | [S3] Risk：Ringlight driver hotplug risk when assembly rear hoursing. Clue:Ringlight driver always output Vbat -0.3V on WLED_CAM . it may short to Flash LED2+ when assembly. will it be a issue? Evaluation: 1. Very Low chance to misassembly rear hoursing .we can not reproduce. 2. Eval Test Vbat=3.8V , manually make WLED_CAM short to Flash LED2+ ,LED current <500mA， Driver ok. Risk close . No change needed for this item |  | 院长 | 文亭 |  | 6.No Change | 5.Nairobi
2020-03-26 | 4.EVT | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue：EVT ALT WH124343，B1(1) No display Clue:1.手机可以开机，无显示 2.拆解后，没有发现明显Display B2B翘起，在重新扣合B2B后，显示恢复正常 目前看到的2台机器，FPC弯折区都有明显往一个角度弯折 Rootcause： suspect Display module issue , KP own the further analysis |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-17 | 4.EVT | 10.USB-C | 5.2 BB Test | S3 | Closed | [S3]issue: 10.1.1 Nairobi EVB USB 2.0 eye test fail Clue:USB phy tuning have 4* 8 bit register X0,X1,X2,X3 QC default parameter :0xA1,0x43,0x2E,0x03 solution: parameter tuning to: 0xA1,0x03,0x27,0x03 .Test pass . SWchange parameter from 03/17 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-03-05 | 4.EVT | 8.PCB | 3.Review/Simulation | S3 | Closed | [S3] Issue：V03 FPC outline not match ME requirement ，found by FPC vendor Rootcause： 1.get wrong V02 PCB 2. didnt complete ME check process before gerber out Solution: 1.Update V03 FPCgerber lesson learn :1.Need CAD update the Milestone PCB if it is updated. 2.need ME check before gerber out |  | 邦邦 | 艳红 |  | 2.PCB | 5.Nairobi
2020-03-05 | 4.EVT | 8.PCB | 3.Review/Simulation | S3 | Closed | [S3] Issue：V03 sub ，panel and audio jack overlap （0.09mm*0.05mm） Rootcause：Panel check before Audio jack change done. Solution: EVT build :push audio jack before reflow ,and 100% check smt status after reflow DVT1 :Panel change before Gerber out (V04) lesson learn : 1.audio jack PCB liberry design with panel cut out . it can cut the overlap area berfor gerberout automaticly. 2. Panel check must be completed after all PCB change done. |  | 艳红 |  |  | 2.PCB | 5.Nairobi
2020-03-05 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Issue： Camera control pin on PM7250 Voltage =3.8V ,not 1.8V (total 5 pins) Rootcause：PMIC MV GPIOs can config to hight voltage ot low voltage (1.8V) Solution: SW change PMIC MV GPIOs setting to Low voltage -done |  | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-02-27 | 4.EVT | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3] Issue：Receiver Pads placement do not match ME LDS design Rootcause：1.Recierver Pads placement do not match ME LDS design 2.why review and design not match? TBD---zhihao Solution: PCB04&05 Phone :PCBA remove GND spring , ME add a copper to connect REC pin.--ME own PCB06 change Pad placement to match ME design. -done |  | 院长 |  |  | 2.PCB | 5.Nairobi
2020-02-26 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | [S3] Issue：Deepsleep current =20mA+ @ 3.8V,over spec about 15mA on EVB-B V01 PCB Rootcause： 1.VREG_S4A_1P8=14.6mA @ 3.8V,over spec 12.73mA due to mmW config. not ready 1.1 after calibration,VREG_S4A_1P8 down to 2.1mA 1.2 flash SW which add mmW config.,VREG_S4A_1P8 down to 3.8mA 2.VREG_BOB=1.8mA @ 3.8V, over spec 1.3mA due to cap sensor not enter sleep mode. 3.VREG_S4C_S5C_0P75=2mA @ 3.8V,over spec 0.5mA,this is power for an on-chip memory of SM7250 Solution: 1.SW optimize 2.Deepsleep current of V04 PCBA=5.05mA @ 3.8V(all sensor disable),meet target |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-01-10 | 4.EVT | 1.Platform | 5.4 ALT | NA | Closed | [S2]issue: EVB WH123730 MDu66-Eval Product Bend Test not power on ,D4 Clue: WH123730 D4: 1.Vbat=3.79V, can not charge up, with a power supplier no big current, 23 mA with powerkey pressed . 2. PMIC shielding case seems been reworked 3. reheat PM7250&PM7250B by Chenbang ,no improve. Root cause: 1. SMT issue ，fail board before assembly Solution: 1. None | link | 林峰 | 文亭 |  | 6.No Change | 5.Nairobi
2020-01-10 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]issue: EVB ALT WH123729 not power on A3 (Loop3). Other units fail too after some days. Clue: A3: 1.Vbat=2.78V ,can not charge up, can power on with a Good Battery ,but suspect no charging current into Vbat（Can detect turbo charging） . No IC crack found. 2.testmode check Battery temp=-40 degree C，suspect NTC problem Root cause: 1. NTC dropped （same as other fail units） 2.NTC ME design issue Solution: 1. Change NTC placement in EVT，ME Confirmed | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2020-01-10 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Risk: FPS soft fail after ESD. Clue: Because of ME design limit, FPS module GND is very weak, and no metal deco. Probable Cause: 1. FPS driver deadlock after ESD, cannnot response to AP's command. Precautionary Measures: 1. Add 100ohm series resistace on FPS signal routes. Verify ok on sofia. 2. Independent LDO power for FPS. When AP knows the FPS ESD error, auto power cycle the FPS module. Verify ok on sofia. EVT ESD test tracking |  | 小熊 |  |  | 6.No Change | 5.Nairobi
2020-01-10 | 4.EVT | 12.EMC | 5.4 ALT | NA | Closed | [S1]Risk: No solution for ANT ESD protection. Clue: 1. ANT is exposed at the gap of inlay. 2.Murata A-TVS ESD protection performance is weak. 3. Infenion's TVS has better ESD protection performance, but with large harmonic. ESD128 -20dB, ESD 103 -40dB. Root cause: ANT tuner and SP4T will be damaged because of no protection. Solution: 1.ATVS EOL on 2021.9 | Link | 李果 |  |  | 6.No Change | 5.Nairobi
2020-01-07 | 3.PEL | 1.Platform | 3.Review/Simulation | S3 | Closed | [S3]Issue: Jtag pin wrong Root cause: copy racer sch but replace connector with sofia parts Solution: 1. EVB-B wire out for bringup---done ，bringup ok 2.EVT change SCH refer to sofia sch---done 20200313 V04 PCB checked ok by Wangxf14 |  | 吉吉 | 文亭 |  | 1.SCH | 5.Nairobi
2020-01-07 | 3.PEL | 5.Camera | 5.1 Bring up | S3 | Closed | [S3]Issue: Macro camera bringup fail Root cause: Mipi design, CSI3 Lane0 P/N swapped. Solution: 1. rework to swap Lane0 P/N by flywire for bringup ok 2. Correct connection in EVT sch 20200312 V04 checkedok | Link | 邦邦 |  |  | 1.SCH | 5.Nairobi
2020-01-07 | 3.PEL | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3]Issue: A+G 上电时有个51mA VDD脉冲电流 Clue：MISO 和 电流脉冲有周期性出现，可能有关系 Root cause: PIN2/3(connected to GND) sink current Solution: PIN2/3 connected to VDD/VDD set to NPM mode at power up | LINK | 小熊 |  |  | 6.No Change | 5.Nairobi
2019-12-03 | 3.PEL | 4.Audio | 5.1 Bring up | S3 | Closed | [S3]Issue: 1.1.1 Nairobi Fastboot fail after Blankflash in EVB-B build，about 50% units fail SW QC CR ：04388408 ，ongoing ---王小峰 Clue:1. 按开机键后VBAT 电流从几十mA到200+mA变化，未掉电 2. log ：fail after QSEE load ，可能安全建制部分有问题导致系统触发reset 3. log ：PM: OCP Occured: PMIC: 2; LDO: 8 推断可能 Vreg_L8C有问题 Analysis： 1.memory power ok ，没有看到掉电 ---学敏 2.bootconfig ok，去除所有bootconfig相连器件，依然fail--chenwt 3.加焊CPU和memory 1pcs，依然fail--chenwt 4.测量系统复位信号： PS hold 维持1.8V，没有低电平输出. SDM_RESIN_N 这个一直有信号输出在reset CPU的样子，570ms一次。--chenwt 5.check Vreg_L8C ，U4504 M-sensor ，U4503 barometer，U4502 A+G--chenwt 5.1 remove A+G ok 5.2 Vreg_L8C 外加1.8V 可以起来。 电源6705B上看到最大瞬间电流在 26mA左右。 Root cause: Vreg_L8C is in LPM mode. but A+G cause a bigger current rush Solution: 1.Sw check Vreg_L8C config is in LPM mode ， change to NPM mode. Done by 1/2 2. check A+G current when power up.----shengnan xiong 后续分析借鉴：不开机相关log可以查看关键字OCP看是否有线索。 | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 5.Nairobi
2019-12-03 | 3.PEL | 4.Audio | 3.Review/Simulation | S3 | Closed | [S3] case ：From Chicago John Gorsica： in talking to CTO audio team (Marley integration), have learned that Qualcomm's software implementation expects a separate bus for the EC (echo canceller) reference signal. Our original plan was to use I2S TDM mode to send this data over a single I2S bus. This team has requested that a second I2S bus be routed from LPI GPIO121-124 to AIF3 on Marley. Action：EVB，no change ； change into EVT with Racer solution --SCH change done |  | 文亭 | 院长 |  | 1.SCH | 5.Nairobi
2019-12-03 | 3.PEL | 4.Audio | 3.Review/Simulation | NA | Closed | [S2] QC BB review：Recommend use normal GPIO MI2S instead of LPI MI2S for 3rd party codec. LPI MI2S may met jitter issue for 3rd party codec. We have CR2547793 for LPI MI2S 48kHz jitter issue, pls check with audio sw for CR status. QC SW answer： will solve the problem in about 2 months. Action： no change. Close . reopen it if there is issue found |  | 文亭 | 院长 |  | 6.No Change | 5.Nairobi
5.Nairobi
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 试用机PVT ，wangqifu的机器，试用一段时间后，OTA SW 然后发现有时候充电慢。 售后一台机器报功耗高，暂时合并分析（接口信号异常了，qifu的机器概率性测试到异常，售后的一直测试到异常） Tahoe power consumption abnormal （After sale），IMEI 354001150843951 Analysis Clue:1. Vbus ，USB D+ ，CC1，CC2，SBU output are abnormal. This cause AP can not sleep always ,it sleep out too often. Clue2：R between CC1& USB D+ =900+R when plug in type-C cable(no charger connected ) Root Cause: suspect PM8150B damaged EXP1：sent the phone to Wuhan factory and replace PM8150B with a new one ,then check if it is ok ? have sent out the phone | link | 文亭 | 敏敏 |  |  | 6.Tahoe
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 售后2台故障机报充电自动重启和充电慢问题 clue: 1.354001150743953 充电时自动重启，插电脑检测不到手机 D+:827Ω，D-:398Ω； 354001151119179 有时偏慢，有时充不进电，有时电量无变化 D+:372KΩ，D-:820Ω； 2.怀玉 在武汉拆机分析发现CPU端阻抗异常，TVS 阻抗也异常 Action：EOS测试失效的机器，TVS 和CPU 也都坏了，比较拟合，EOS？ Solution: | TCC 摸底测试link | 文亭 |  |  |  | 6.Tahoe
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s2]Issue: 售后1台故障机报充电速度慢 clue: 1. USB D+和D- 插入充电器时没波形。 关机测量对地阻抗异常，在1K R 以下 。正常是几百KR 2. 拆机直接测试主板测试点对地阻抗，D- =2.2R ，D+ =800+R ，异常 3. 测试小板D+、D-对地阻抗，10KR左右， 也是异常的。而线路上对地只有TVS器件。推测TVS器件也异常了。 Root Cause: 怀疑是EOS导致。 那EOS来源是什么？机器的防浪涌能力如何？ Action：TCC 增加 tahoe 对USB2.0和CC pin 的防浪涌能力摸底测试 ，60V fail，很高的抗性。EOS测试失效的机器，TVS 和CPU 也都坏了，比较拟合。 为什么还是会坏？有啥改进机会？ Solution: | TCC 摸底测试link | 文亭 |  |  |  | 6.Tahoe
2021-03-15 | D.SHIP | 3.Charging | 5.6 User Feedback | NA | Closed | [s3]Issue: Linxee claim 2 pcs new devices freeze and reset during charging. clue: 1. Linxee 借用试产机 及 购买量产机器用来做DP to HDMI cable 产线测试，一台手机会和上千条cable 适配。 2.有2台新购买手机（总共买3台），第一次测试，测试到没电后，插充电器充电，然后开机发现就死机重启。 机器走售后流程中。 3.试产机器也有1台出现问题，故障机USB无法认到，Bug2go log 分析应该是USB识别不到导致的 watchdog 重启。 建议分析硬件USB相关，转寄XM机器。 HW 分析：故障同上，USB2.0的主板段 D+ D- 阻抗异常，而且推断是CPU端异常；小板段也是异常，推测是TVS也异常。 Root Cause: 怀疑是EOS导致。 那EOS来源是什么？机器的防浪涌能力如何？ Action：TCC 增加 tahoe 对USB2.0和CC pin 的防浪涌能力摸底测试 Solution: | CR IKSWR-55445 | 文亭 |  |  |  | 6.Tahoe
2021-03-01 | D.SHIP | 2.Power | 4.Build | NA | Closed | Tahoe： 原始issue：Tahoe EVT板级测试 test 出现概率漏电流异常，800uA左右 。 正常关机没有复现issue。 分析：非正常关机导致，漏电流电源确认是PM7150L的AVDD电源（内部电源），提case 给QC ，QC答复是PM7150L（或者PM6150L）申请 系统19.2M时钟后没有正常关闭导致一直耗电 。----RD Wu Xuemin，NJ SW xuwei9 解决： QC 给了个patch，尝试在我们这种工厂关机流程中去关闭19.2M时钟的申请，然后DVT1 SW ok了（包含了QC给的patch），之后产线测试都没有再反馈了。该问题close。 扩展Issue：整机端是否有类似问题？ （Ibiza项目板级有问题，暂时没解决，直接扩展整机摸底测试，发现也有类似问题。） 整机测试：发现整机端也有这个问题。 （当然整机端和BT端，SW不太一样，开机程度也不太一样。）-----来源 ：SW MFG Luguo，RD Wu Xuemin Tahoe项目回退确认BT 情况：发现QC给的patch 集成之前的版本，10/12 就已经问题不复现了。 而9/29的EVT版本有问题。 中间的变更可能是解决BT 测试 漏电流问题的关键。（反推可能patch并没起作用）-----来源 ：SW MFG Luguo Ibiza 和 Denver ： Issue：测试一直都有这个概率漏电问题（早期EVT还有板子漏电问题，可能覆盖了一个试产阶段，DVT解决板子漏电问题） 后来原来以为参考tahoe增加patch 后就ok ，但是一直没有办法清除，一直怀疑是patch 及修改方法不对。 但从目前结果看，这个patch 有可能并不能解决这个问题。 Action： 1. Ibiza 不同SW修改方案的再次验证（可能是QC会重新给patch？可以也扩展到tahoe看下效果）。---- SW，SW MFG 2.寻找 Tahoe 9/29~ 10/12这段时间 factory SW版本的变更点，用来找解决这个case 的重要线索。----NJ SW，SW MFG 扩展涉及范围：今天增加测试的结果 PM8150L tahoe （测试结果：故障概率复现） PM7150L Nairobi （测试结果：故障概率复现） PM6150L Denver，ibiza ，Kiev（测试结果：故障概率复现） PMI632 的 Sofia NA和 PM6150A 的 Quattro ，（测试结果：故障不复现） 所以初步总结：LCD背光用到QC PMxxxxL 方案的机型应该都有同样问题。 Solution： SW 更改产线的下电时序，保障LCD来得及关闭 背光部分。避免该问题。 导入截止由SW 和 PQM 决定。 |  | 敏敏 | 文亭 |  |  | 6.Tahoe
2020-12-17 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | CR：IKSWR-35501 photo mode-The flash is on to take pictures, and the phone is automatically turned off Clue：Low voltage battery+DP+Camera+Flash ，auto power off Rootcause solution：change Flash current from 2.4A to 1.5A ，recheck ok | link | 芳梅 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-12-17 | B.PVT | 6.Display/Touch | 5.6 User Feedback | NA | Closed | DP compatible issues | collection | 邦邦 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-12-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [s3]Risk: ALT ESD C1 +15KV Zone3/4/6/7/8 auto power off，adn enters the system crash interface. recovered after pressing power key clue: 1. Root Cause: Solution:not reproduce |  | 李果 |  |  | 6.No Change | 6.Tahoe
2020-12-02 | 5.DVT1 | 1.Platform | 5.6 User Feedback | NA | Closed | [s3]Issue: there are some phone freeze and dark screen problem inDF clue: 1. Root Cause: SW Solution: | link | 嘉琨 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-11-23 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | [s3]Issue: Mdu30 , 1.LTE data call fail clue: 1. Pass last test, Retest Pass. Root Cause: Solution:PVT Retest Pass. |  | 林峰 |  |  | 6.No Change | 6.Tahoe
2020-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | "[s3]Issue:Edu03 , DVT1 test WH132624 ,D4,After +8KV air discharge at zone6 (Aging10),the phone drop call(2020/11/20 11:02) Clue: 1. zone6 is upper side 2. just happen 1 time in DVT1 total 4 round test. (16 units) 3. real net phone call Root Cause: Solution:can not reproduce ,monitor PVT。 PVT not reproduce |  | 李果 | 韩凯 |  | 6.No Change | 6.Tahoe
2020-11-23 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | "[NA]RISK:Edu03 , VT1 test WH132624 ,D1&D2 After -8KV contact discharge at zone18 (Aging10),the phone Unexpected auto power off Clue: 1. zone18 is camera deco ,middle 2 cameras (upper 2 cameras is Zone17) 2. D1 Rear camera(and Rear flash) is ON , D2 Front camera(and Front flash) is ON 3.WH133310 have same issue too . (total is pass ,because it is high voltage test and recoverable issue) Root Cause: Deco 的接地不好导致 Solution: 1. 主板上有预留加强接地方案，但基于目前属于软性可接受范围，故综合cost平衡，暂时不导入增加导电布方案。 PVT Retest Pass. |  | 李果 | 韩凯 |  | 6.No Change | 6.Tahoe
2020-11-23 | 5.DVT1 | 11.Thermal | 5.3 EE DVT | S3 | Closed | "[s3]Issue: Mdu30 ,SPK 最大功率fail 。 Root Cause: 1. SPK 石墨偏上贴了。2.石墨片偏小些 Solution: 1. SPK 石墨往下贴一些，并且石墨片加大。 手工验证 往下贴 改善1.5度，再加大后总的改善2.7度。 PVT导入 PVT test pass |  | 林峰 |  |  | 3.BOM | 6.Tahoe
2020-12-10 | 5.DVT1 | 1.Platform | 5.2 BB Test | NA | Closed | [na]AnTuTu Performance- 1.Tahoe Total Score 60W （61.5W Best ） VS IQOO5 Pro 66W - @12/2 2. Tahoe GPU 24W+ VS IQOO5 Pro GPU Score 27W RootCause: 1.CPU/GPU Config to Performance Mode, increased to 63W . - SW 2.Speculation:GPU Optimize , Supposed to increase 3W . Exp:Consulting QC for help.- Result：GPU OverClocking only effective on AA chipset.Not fitful on AB/AC due to fuse. QC is not willing to provide OverClocking Patch . 3. more power CPU and bigger DDR5 and bigger UFS 3.1 Memory, 12+256 Memory + SM8250-AC Exp:Build 4 pcs for testing. 12/21 Solution: 1.Set CPU/GPU to Performance Mode Score ： 630000 （Best） 2. Set GPU supper performance forSM8250-AC，mode ，Score ：670000（Best） |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-23 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [na]Issue:Audio headset Downlink TDD Noise was audible. Root Cause: 1.1 Href Signal in layer 7 Affected by Grounding Layer 6&8 in which Big Current Pass through 1.2 Big Current Path on Layer6&8 duo to different Grounding Via placement in Whole PCB Layers compare with Nairobi. 2. Audio Signal in the surface side of Battery in which big Power Noise exit. 3.Href in MainFPC route on the side of L Channel. Exp:change Href in the middle of L&R, RD Validated ok. Solution: 1.seperate Href Signal from main RF PA power path, DVT1 import and verify 1.1 Optimize Layer 11 Grounding 1.2 Switch Audio Signal Fan out Position on Connector to far away from Battery Connector. 2.back up Href signal routing on Layer 2, DVT1 import and verify 3.Put Audio signal on the other side of FPC. DVT1 import and verify 4.Swap Audo_L&HREF in Main_FPC ,PVT Unit validated Pass.uplink:-75dB (Spec -71dB) ,Downlink:No Noise. PVT test pass | LINK | 院长 |  |  | 1.SCH | 6.Tahoe
2020-11-23 | 5.DVT1 | 1.Platform | 5.2 BB Test | NA | Closed | "[s3]Task: Tahoe Antutu Score test SM8250-AA =58W;SM8250-AB =59.6W;SM8250-AC =61W 竞品 : SDM865 Android R 的竞品就看到 1+的机型 8T，SM8250-AA （从CPU主频信息倒推）memory 是 12GB+256GB，跑分59W pass 提升机会：Android Q 竞品 IQOO5 跑到66W，GPU到达27W VS tahoe的 23W+ ，有一定提升机会。 SW 寻求提升方法中 | link | 文亭 | 林峰 |  | 6.No Change | 6.Tahoe
2020-11-23 | 5.DVT1 | 7.Sensor | 1.1 OD | NA | Closed | "[s3]Risk: Tahoe Add 1 Dock which may impact M-sensor Evaluation: M-sensor simulation checked pass. can accaptable. Tahoe+ need more check for this case, Risk(maybe tahoe+ need this Dock too?) |  | 小熊 | 文亭 |  | 6.No Change | 6.Tahoe
2020-09-27 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3] Issue: DVT EPr02 Eval - eCompass WH131414 测试结果为 10°，目标是5°，暂停，等待确认结果 Root Cause:1.parameter related Solution: tune done,RD self test pass .TCC DVT test pass WH132626 |  | 小熊 |  |  | 4.Parameter | 6.Tahoe
2020-11-10 | 5.DVT1 | 12.EMC | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 ,2nd round test , 2units can not power on Clue: D3 failed point is near P-sensor&SOL_LED ,D4 failed on the chin. D3： Root Cause: 1.SOL_LED of PM8150L short to GND which lead to fail to power on. 2.Sol_LED Strike by ESD through 0.5mm width Glue Area Solution: 1.Add one TVS on Sol_LED,BOM Changed. RD Validated OK. TCC Validate ok WH133310&WH132624 D4: Root Cause: 1. LEDA of PM8150L Damaged which lead to power cycle issue. 2.LEDA Strike by ESD through Display Edge. Solution: 1.Add one high voltage TVS on LEDA ,BOM Changed. RD Validated OK. TCC Validate ok WH133310&WH132624 | link | 李果 | 韩凯 |  | 3.BOM | 6.Tahoe
2020-10-09 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 2/8 units unexpected power off, recovered after rebooting Root Cause: 1.System auto power off due to FPS Striked by ESD. Exp1.1:Disconnect FPS Con, Result:Not Reproduce. 2.CPU Affected by ESD Through SPI of FPS Exp2.1:Disconnect SPI Signal one by one. Result:MOSI&MISO Matters. Exp2.2:Replace ESD Block Resistor 100R with 1K. Result:Pass. Exp2.3:Replace ESD Block Resistor 470R on SPI MISO &MOSI line and import in DVT 1build Solution: 1.Replace ESD Block Resistor 470R on SPI MISO &MOSI line and import in build. monitor 2. replace ESD Block Resistor 1K on RSR,CS,INT line. in DVT1B BR 40462 ,Test pass | link | 李果 |  |  | 3.BOM | 6.Tahoe
2020-10-29 | 4.EVT | 10.USB-C | 6.Issue | NA | Closed | [s3]Issue: SW test ，Connect Jiewang（500G） mobile hard drive to the OTG cable phone does not recognize,IKSWR-11737 clue: 1.change This OTG cable to a hub ,it it ok 2.Racer turbo(SM8250) can not recognize too. but other projects can recognize 3. test by our OTG and hub + our 1T&2T hard drive ,they are ok,can not reproduce. 4.both USB 2.0 &3.0 OTG header test fail on this mobile hard drive Jiewang（500G） Root Cause:no signal issue found. Action 1.1: SW analysis no result Action 2: HW, eye diagram test (host mode ) USB2.0 pass， USB3.0 host fail at 5G Far End Total Jitter at BER-12 (CTLE ON) -5.9 %. Solution:keep current status. no change . |  | 文亭 |  | IKSWR-11737 | 6.No Change | 6.Tahoe
2020-10-22 | 4.EVT | 2.Power | 5.3 EE DVT | NA | Closed | [s3]Issue:sleep current 8.6mA , can we lowdown it? clue:高通的参考数据4.7-6.7，我们现在关闭sensor后8.6mA Root Cause: 1.Action 1: RRT31.13 版本分解各个模块耗电 2.breakdown 数据看，除Memory 容量差异样（6G VS 8G），主要在VREG_S4A_1P8 上存在3.3mA Gap，QC上的数据应该只测了单路SM8250 PX3， Solution: VREG_S4A_1P8 功耗相对其他平台看，数据接近的，属于正常范围，将修正BSP target | Link | 敏敏 |  |  | 6.No Change | 6.Tahoe
2020-10-29 | 4.EVT | 5.Camera | 4.Build | S3 | Closed | [s3]Issue: Tahoe TOF calibration fail issue 2%~3% clue:ToF I2C probe failed Root Cause: Power on frequence dont meet Spec Solution: SW change Power on frequence to 5ms delay , temp SW check ok, import in SW mainline with 5ms delay from 11/02 lesson learn： add power and I2C frequence check in TOF BB test。 need to provide a design With margin | Link | 邦邦 |  | IKSWR-12689 | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-27 | 4.EVT | 2.Power | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 1/8 unit can't power on ,15KV Air Discharge on chin. clue1:PMU Damage 2:leakage current of AVDD of PM8150L is 340uA,normal is 1.5uA 3:press power key,REF_BYP of PM8150L no output 4:AVDD leakage current and REF_BYP output of PM8250 is all normal Root Cause: 1.PM8150L Damaged 2.Speculation:Floating VDD_BOB Affected by ESD which lead to PMIC Damage. Exp:Test more 2 unit on SubBoard but not reproduced. Solution: 1. Add 1 cap on VDD_BOB Terminal. - Done 2.Reserver 1 Resistor on Mainboard in next version. DVT1A test pass |  | 李果 |  |  | 1.SCH | 6.Tahoe
2020-10-09 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3]Issue:Edu03 15KV Air Discharge at MIC3 ,System auto power off clue 1: 6 units (2units TCC+4units new drivers) 15KV +200 times/unit ,Result :Pass Root Cause: 1. SW issue Solution: 1.Monitor DVT1 TCC test pass |  | 李果 |  |  | 6.No Change | 6.Tahoe
2020-09-27 | 4.EVT | 2.Power | 4.Build | NA | Closed | [na] Issue: BT test ，IKSWR-6070，[BRDTEST] BATTERY_OFF_CURRENT_BOARD_1 Fail ，800ua VS target 300uA ,Retest Pass，NTF。9/21, 11.9%; 9/22, 14.1% Clue1:Attaching Display and Power Cycle 100 times. No Issue. 2:open kernal uart log and remove display ,power cycle over 100 times,no issue 3:leakage current is from AVDD_BYP of PM8150L,640uA Root Cause: 1. Speculation: Device Config and initialization issue solution：SW change . import in DVT1 SW . close . can reopen it if it reproduce. |  | 敏敏 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-27 | 4.EVT | 9.Memory | 5.4 ALT | S3 | Closed | [s3] Issue: ALT WH131408，B6 ，unable to read memory card initial and recovers after TH/TC in loop2 but the same failure repeats after TH/TC in loop5. A4(5), B3(5) Loop5 can not read memory card. A2(0) unable to read memory card initial and recovers after TH/TC in loop2 Clue1: Tear down B6,No SD Card solder issue found. Clue2:2 initial failure found, but recover Clue3:SD Strace <60mm. Root Cause: 1. SW analysis log ，https://idart.mot.com/browse/IKSWR-6840, ---log invalid（时间不匹配） EPr03 - Memory Card Compatibility Testing pass，including 21 different Tcards close 。will reopen it if it reproduce |  | 嘉琨 | 李果 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-10-10 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [NA]Issue: some LPD mis triggered isuse found ， clue 1: no issue in Without redriver boards Root Cause: 1.should be Redriver impact it EXP1:remove redriver and checked ok: EXP2:ADD pulldown R on SBU to check LPD limit :300~400KR . EXP3:check Redriver Aux on Hi_z config : 80~160KR. lower than LPD limit ,causing the issue. Solution: 1.remove LPD function on SW |  | 文亭 | 院长 |  | 1.SCH | 6.Tahoe
2020-09-23 | 4.EVT | 6.Display/Touch | 5.2 BB Test | NA | Closed | [na]Risk:DP Signal eye height 98.6mV in worst case(850mV and 3.5dB Pre-emphasis , not meet 104mV spec in No Redriver Solution. Clue1:with Redriver,Eye Height=145mV(Cost Up0.8$). 2:with 1.6m extension cable,DP link ok in No Redriver Solution Root Cause:1.Insertion loss of FPC and PCB Routing with 5.9dB loss Exp1:Test More Display ,9/29 Exp2:Measure the accurate Swing Voltage between 600mV and 850mV to detemine the margin. Solution:1.Sub Board using No Redriver go first and keep verify the risk level in the following. Product Team raise PCMCR to add USB3.1 and DP1.4 , Need Add Back Redriver. Closed. | Link | 芳梅 | 邦邦 |  | 4.Parameter | 6.Tahoe
2020-09-27 | 4.EVT | 7.Sensor | 5.3 EE DVT | S3 | Closed | [s3] Issue: DVT EPr04 WH131416 After making a call, the screen turn off,cannot recovered by itself root cause: parameter related ,need tuning by 9/30 ,not blocking PCB solution:SW change . done . self receck ok by 10/13 |  | 小熊 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-23 | 4.EVT | 11.Thermal | 4.Build | S3 | Closed | [s3] Issue:thermal ，在正常CQA 闪光灯打开时温度过高 ,手在靠近闪光灯的时候烫手，请怀玉帮忙看一下是否可以调整 Root Cause: 默认电流300mA.超过标准的200mA左右。 Solution:1. SW tuning torch current setting |  | 林峰 |  |  | 4.Parameter | 6.Tahoe
2020-09-23 | 4.EVT | 11.Thermal | 4.Build | NA | Closed | [s3] Issue:thermal ，在正常CQA检验过程中手机温度会比其他项目温度高 Root Cause: 1. can not sleep .more power . SW not very stable , will refer to TCC thermal test data |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-27 | 4.EVT | 10.USB-C | 5.2 BB Test | NA | Closed | [S3]Task: USB 2.0 eye test ， devices mode test done and pass | link | 文亭 |  |  | 6.No Change | 6.Tahoe
2020-09-23 | 4.EVT | 6.Display/Touch | 5.2 BB Test | NA | Closed | [s3] Issue: DP Audio no function Root Cause: Audio get information that it is HDMI ，so audio output with HDMI. config it to DP output ,it will ok. need to find out why HDMI information report to Aduio. Solution:1. SW workaround changed ,and SW checked ok. mainline SW check pass 9/27 |  | 芳梅 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-23 | 4.EVT | 10.USB-C | 5.2 BB Test | S3 | Closed | [s3] Issue: OTG output 1.6A loading ，有0.7V的纹波，频率160KHz左右。 1A 时是400mV左右，和其他机器类似。还可以接受。 Root Cause: Solution:1. |  | 文亭 |  |  | 6.No Change | 6.Tahoe
2020-08-20 | 3.PEL | 5.Camera | 2.Design | NA | Closed | [s3]Risk ：TOF FPC上 Xshut pin 直连到VDD（2.8V），是否有风险 Root Cause: 结构空间只够5个弹片，Xshut 评估有机会FPC上直接拉高来省掉一个pin，达到5个pin的目标。但是FPC上没有留上拉电阻，而是直接接到2.8V。后来追查结构上空间也非常有限，很难加 电阻在FPC上，除非万不得已 实验:1. ST L3 demo 板上直连Xshut 和VDD ，接2.8V电源，发现只有5UA漏电，可以认为没有漏电问题，可以接受 2.裸片IC单独2.8V供电，对地电流约为0.7mA，Xshut对VDD短接后，对地电流为微安级，在可接受范围内，风险等级低 solution： keep design |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-06-08 | 1.Concept | 11.Thermal | 2.Design | NA | Closed | [s3] Issue:thermal ，目前布局热管对不上POP 的CPU。 需要确认下如何处理。 Root Cause: -受结构限制问题 （特别是中框件不能动） Solution:1. 布局或结构中框调整，让热管尽量靠近CPU热源 风险低 | ME link | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-16 | 4.EVT | 1.Platform | 5.1 Bring up | NA | Closed | [S3]Issue:SIM2 不识别 Clue:1.SIM2通道有正常信号访问 Root Cause: 1.软件采用的初始NV 数据直接参考Racer，导致无法识别. Solution：1.SW调整NV ， 可以识别. |  | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
2020-09-10 | 4.EVT | 1.Platform | 5.1 Bring up | NA | Closed | [S3]Issue:无法Provision Root Cause: 1.SW直接采用Racer上的UFS3.0，Memory Type 设置不对，我们使用的是UFS3.1 Solution: 1.SW正确配置Memory Type |  | 嘉琨 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 6.Tahoe
6.Tahoe
2019-01-17 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | Closed | Issue:Can't Power On with Leakage Current in After Sale ,12/20 units of not power on . 0.0x% RootCause: 1.USB_CC;PM660 ,Pin27 ;VOL_UP;PM660A,Pin97 2.USB Vbus(5V) Closed to CC1,CC2 3.CC1,CC2 Maximum Voltage =6V Solution: 1.Accept the failure rate. 2.SM6150 CC1,CC2 upgrade to 22V 3.TCC Evaluate More units - 2019/4/30 |  | 敏敏 | 吉吉 |  | 6.No Change | 1.Shelby
2018-07-17 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2] Shelby P-sensor :can not power on when LED current set to 150mA Clue: RootCause: 1.LDO OCP 2.Wrong Configuration Solution:1.Right Configuration | link | 敏敏 | 小熊 |  | 4.Parameter | 1.Shelby
2018-07-05 | D.SHIP | 7.Sensor | 5.6 User Feedback | S2 | Closed | [S2]Issue:User Feedback that Black screen when talk RootCause: 1.P-Sensor TMD2725 has bug on calibration, It occurs when IR of Sunlight transition when Calibrate. 2.Easier triggered on high gain 4X ，Normal 100mA,2X,or 1X is ok on golden eagle,houdini Solution: 1.SW Work around to void negative P Value. 2.Change Gain to1x for better margin（LED current from 20mA to 80mA to match performance requirement） | link | 文亭 | 小熊 |  | 4.Parameter | 1.Shelby
2018-06-26 | D.SHIP | 2.Power | 5.6 User Feedback | S3 | NA | "[S3]Power users roam to China and found Shelby had a short battery life. Clue: 1.Using VRZ Sim 2.Ask another Power User who are roaming to china,Battery Life is normal,He closed the data link. 3.Houdini also have GMS issue Root Cause: 1.Proposal:4G connecting not stable because of the compatibility of network service. -Try 3G manually and try. -Observing the Signal connecting status 2.Proposal: VPN was blocked because of Chinese Government Policy Issue,GMS(Google Service) keep trying connect to Google Service and cause extra 7 Hours battery life dropped which is found in Houdini too due to WakeLock Service don’t release . -setting ->battery->Slider down to check if GMS have abnormal battery drain percentage 3.Proposal:VPN Usage will cause extra 10 Hours Battery life Dropped which can be reproduced. -setting ->battery->Slider down to check if VPN activated 4.Proposal:other APP that keep connecting -setting ->battery->Slider down to check if some APP have abnormal battery drain percentage 5.Proposal:User in low signal strength Area which cause searching with maximum power,maybe low possibility in china -Observing the Signal connecting status Solution: 1.Normal issue 2.Normal Issue 3.Normal Issue 4.Normal Issue 5.Normal Issue. Closed |  | 李果 |  | BB Analysis | 6.No Change | 1.Shelby
2018-04-27 | C.RAMP | 7.Sensor | 4.Build | S3 | Closed | [S3]Als no function Clue:Connetion Bad RootCause:Spring Contact Issue,ME Analysis OK2Ramp Pass，Closed |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-04-27 | C.RAMP | 8.Mods | 4.Build | S3 | Closed | [S3]1 unit found Missing Pixel with Mods Projector Clue:1.BT Pass,2.With Projector Mods Fail Root Cause:1.Solder Joint on AP DSI4&5 |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-04-14 | B.PVT | 7.Sensor | 5.4 ALT | S2 | Closed | [S2] Issue:ALT WH105378 A5 loop2 Magnetometer sensor no function Root cause: 1.M-Sensors Crack by cutting force Observed on FPCA 2.M-Sensor was cut by Sharp Edge in the Slot 3.M-Sensor need glue more Solution 1.Expand Glue on M-Sensor 2.ME Expand Slot 3.Proposal：SOP Improvement Merge to 2018-3-29 Edu02 Issue ,Close | link | 小熊 |  | ME Analysis | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-03-29 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Issue:DVT3 Edu02 Magnetometer sensor no function Clue: 1.Magnetometer Sensor no function also found during Assembly 2.EDu02 on FPCA samples 10pcs checked Pass by Hongflex. 3.PVT IQC Sort FPCA,No Failure Found. Root cause: 1.FPCA Damaged. Nothing to do with Edu02 2.Some 3 of 5 M-Sensors Crack Observed on FPCA 3.Proposal:M-Sensor Crashed with the Pocket Edge during Abnormal Assembling: -Owner:NPI liuyulong Solution: 1.Proposal：Assembly SOP Improvement –Owner：NPI Liuyulong 2.Proposal：Enlarge the M-Senosr Pocket as below for more space for M-Sensor–ME Ethan 3.M-Sensor need glue more Plan: 1.Assembly Issue Analysis，Focus on Side FPCA Assembly in PVT, To see if failure found in JOT –Owner:NPI ，On-Going 2. Enlarge the M-Senosr Pocket more space for M-Sensor –ME Ethan ，Done，Solution Run in Change in MP directly. 3.Glue M-Sensor - ME Ethan/BB | link | 小熊 |  | BB Analysis | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-03-28 | 7.DVT2 | 5.Camera | 5.6 User Feedback | S1 | Closed | [S3]issue：Media volume maximum, when rear camera take picture ,there are some vertical line. clue：Audio smart pa and rear camera avdd 2.8v ldo use the same B_plus power supply, Root Cause:1.Smart pa consumes large current , so B_plus voltage has a big drop which belows 2.8V， AVDD ldo putout is not stable ,this causes the issue happen Solution: 1.Cirrus Enable Surge Current Threshold，Verify Pass，SW imported | Link | 院长 |  |  | 4.Parameter | 1.Shelby
2018-03-08 | 7.DVT2 | 8.Mods | 5.1 Bring up | S3 | Closed | [S3]MyDP I2S Bring up SW Own |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-03-15 | 7.DVT2 | 9.Memory | 5.6 User Feedback | S3 | Closed | [S3]QC CR：03374129 moto CR：IKSWO-65523 issue： Kernel panic while streaming music and using BT headset B2GID:301816190 1 time clue： QC log analysis show： This issue is happening due to memory corruption. issue is only once so far. Lets keep this in monitoring state. moved the case to h/w CE to help further as device needs for PTE/foundry team investigation. QC reply ，BT issue ，RF take this issue。 |  | 威姐 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-03-15 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]CR IKSWO-71285 One Unit Haptic feedback has stopped working / Audio Lost B2GID:301980855 Clue:1.Log show I2C issue,new type 2.Re-Boot OK 2.DVT2a HW Version Root Cause: Solution: Plan:1.NTF,Monitor |  | 院长 |  |  | 6.No Change | 1.Shelby
2018-03-12 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Samsung Display White after ESD Zone 16 Clue:1. RootCause:1.EMI Conductive Fabric on LCD Driver Area Introduce the ESD Energy 2. ESD Energy Flow Through Sensitive Area of LCD Driver Solution:1.Better conductive EMI Conductive Fabric to GND 2. Using Anti-Static Film to Block the ESD Energy through Sensitive Area ,DVT3 Validation Pass. |  | 靓仔 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-03-09 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [s3]Soft ESD Failure on Second Vendor TianMa D6 Unit,Reboot OK （8KV Air discharge） Clue:1.Zone1- P-Sensor/SPK no function ,Reboot OK 2.Zone1 -System Halt ,Reboot OK. Root Cause:1.Codec Affected by ESD through SPK Solution:1.Move TVS Position to the SPK Terminal, Evaluation Pass. Antenna Eval Pass DVT3 Validation Fail， Keep Original Design |  | 靓仔 |  |  | 3.BOM | 1.Shelby
2018-02-26 | 7.DVT2 | 8.Mods | 5.6 User Feedback | S3 | Closed | [s3]DTV app shows signal low when inserts usb with wall adaptor. Clue:1. Root Cause:1.Charger Detection Invoke USB while it is used for Video Steam Solution:1.Disable USB Invokation in these scenario Plan: Support SW, SW solve it | Link | 邦邦 | 文亭 & 李果 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-02-26 | 7.DVT2 | 8.Mods | 4.Build | S3 | Closed | [s3]60% HDK Projector test Fail on DVT2B Clue:1.Projector Mods OK 2.Slim Port Routing is ok 3.Eye diagram OK 4.DP Link error ok 5.Fine Tune Drive Strength ，No Improvement Root Cause:1.DSI MIPI Lanes Set to 2 ,It should be 4 Lane. 2.Some Cable can't supoort 1080P stablly. Solution:SW Lead 1.Configure right 2.Config to 480p Plan:1.Validation with other Factory in Brazil | Link | 邦邦 | 院长 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-02-12 | 7.DVT2 | 9.Memory | 4.Build | S2 | Closed | [S2]Issue:1. Shelby_IF_QBOOT_BLANK_FLASH_01_true fail In DVT2A EMEA &Brazil SKU . Clue:1.Erase DDR ,Can't reproduce 2.heat Unit 1 memory about 100，200,300 degree，can't recover 3.heat memory up to 400 degree ，Recovered 4.Found Dirt under memory after Take it Down，Re solder the same memory ,recovered. 5.Heat Unit 2,Can't recover 6.Red dye 1 unit no abnormal found 6.Detached Memory,Check Signal ,one CPU Address line open Root Cause： 1.CPU Address line Solder open 2.Why solder open,SMT investigate Solution: 1.SMT investigate Plan: 1.Cross Section Unit 2 . 2.investigate other 2 units 3.Raise SW SR to Qualcomm | Link | 威姐 | 邦邦 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-02-12 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3]Epr04 test fail in DVT2A Root Cause: P-sensor gain is too high Solution:1.change gain PLDRIVE to 20,build a new config (tested in XM ok) Plan:1. retest in Wuhan TCC with new config by2/24 Verification：1. new WH104491 test pass at 2/23. will check with SW chaoyi change into: OCW28.41-BECKHAM-SHA1 |  | 文亭 |  |  | 4.Parameter | 1.Shelby
2018-02-12 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]-6KV contact discharge at zone 16(Aging 10),Mods function intermittently, recover after restart. -6KV contact discharge at zone 16(Aging 10),Mods function intermittently, recover after restart. Root Cause:1. CC pin ESD Suppression Not enough Solution:1.change CC pin TVS to larger capacitance and retest with improvement. Evaluation Pass.DVT3B Validation Pass Plan:1.DVT3B Validation |  | 靓仔 |  |  | 3.BOM | 1.Shelby
2018-02-09 | 7.DVT2 | 6.Display/Touch | 4.Build | S2 | Closed | [S2]Power off when Import TianMa LCM Root Cause:1.Power sequence mismatch between First Vendor Samsung and Second vendor TianMa Solution:1.Fine tune Power Sequence to meet both of them Plan:Verifing |  | 芳梅 | 院长 |  | 4.Parameter | 1.Shelby
2018-02-12 | 7.DVT2 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Risk:Cap Sensor I2C Risk Root Cause: Solution:1.Reset SCL When Error Found Plan:1.SW arrange Pressure Test |  | 院长 |  |  | 6.No Change | 1.Shelby
2018-02-11 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S3] 1.Some Unit Cap Sensor function not stable 2. CQA Test Cap Sensor Fail Clue:1.Happend when Wifi Scaning each 70S. Root Cause:1.Wifi Scaning Mode 2.Cypress FW filter Solution:1.Cypress improve filter,Far away need 6S Response time，DVT3 validation Pass | link | 小熊 |  |  | 4.Parameter | 1.Shelby
2018-02-11 | 7.DVT2 | 8.Mods | 4.Build | S3 | Closed | [S3] DVT2A,3/2600, Mods Projectors still can't work Clue:1.1 Unit can’t reproduce 2.Change Anx7805,can’t recover Root Cause:1.ANX7805 I2C error .2.ANX7805 Reset Sequence issue 3.U5041 C4&C5 Solder Joint by X-ray Solution:SMT Lead-Solder Paste Resize ,DVT2b No defect found Plan: | Link | 邦邦 | 院长 | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-01-08 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | [S2]Issue:1.Cap Sensor Detection distance cannot match ANT SAR requirement in DVT1B units Root Cause：1.Cypress Solution may not meet requirement 2.Antenna Pad Too Small,3.loading capacitor too big 4.FW Parameter need fine tune Solution:1.Reduce Loading Capacitor-Done 2.Proposal:Increase Ant Area ,Dropped because of schedule impact . 3. Fireware Parameter fine tune. Best Performance now.but not stable. 4.Using Psensor to resolve Front Detection 5.Back side set as 10mm | link | 小熊 | 森森 | link | 4.Parameter | 1.Shelby
2018-01-18 | 5.DVT1 | 8.Mods | 5.1 Bring up | S3 | Closed | [S2]Issue: Harsu Mods can't work Root Cause:1.CSI2 P/N Swap ，DVT2A Revised 2.SW do not ready Plan:1.Support Jon Bring up 2.Pressure test. | Link | 邦邦 |  | Link | 1.SCH | 1.Shelby
2018-02-03 | 5.DVT1 | 1.Platform | 4.Build | S3 | Closed | [S2]U5040 Solder joint Root Cause:1.Proposal:Soler Paste Over Volume Solution:1.Fine Grain Stencil Plan:Give Advice to SMT on Stencil Grain | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-01-15 | 5.DVT1 | 9.Memory | 4.Build | S3 | Closed | [S3]Issue:1.DVT1B Second Vendor 4+64&4+32 Hynix memory build . 17pcs can not flash in IF . clue:1.Blankflash Success , 2.Fastboot mode failed , Root Cause:1.Qualcomm SW Driver Issue Solution:1.4G Weak DQS Pull Up Patch-SW | Link | 威姐 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-01-04 | 5.DVT1 | 11.Thermal | 5.4 ALT | S3 | Closed | [S3]DVT2a Tianma display compare result in Max brightness，+2.5℃ > samsung display Clue:1.Decrease Brightness ineffective RootCause:The power consumption of Tianma is higher than that of Samsung Solution:1.Adding Graphite under Driver IC Plan: control the power consumption of Tianma display,DVT2B tracking--onwer: KeyPart | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-12-18 | 5.DVT1 | 3.Charging | 4.Build | S3 | Closed | [S3]Issue:Remove the Charge,charge icon not disappear Clue:1.Only happen on AICL Closed Root Cause:1. PM660 Issue 2.Same as 98 Solution:1.Qualcomm feedback no solution except enable AICL mode. | Link | 林峰 |  | Link | 6.No Change | 1.Shelby
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Usb Fail 3 units D2：After ±8KV air discharge,The computer can not identify the UUT,can not recover. D3,D4：After -15kv air discharge,The computer can not identify the UUT,can not recover. Root Cause:1.D2-D4 Usb Analog Switch Damaged 2.Rohm 1pF TVS request by purchase team can't meet Requirement 3.Easy to striked by ESD due to Type C Connector tongue piece protrude Solution:1.Using Better TVS on DM/DP,Eval 10pF Pass，Verify on DVT1B，DVT1B Pass-2018-1-12 ，ALT Fail 1 unit -2018-1-16 2.Reserve Additional TVS closed to USB-C Pin on DVT2 3.Reserve 2 0R Resistor on DM/DP Done 3.TVS Closed to USB Port 4.2 TVS （Switch+Port） | link | 靓仔 |  | link | 3.BOM | 1.Shelby
2018-01-08 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S3]Issue: can't boot in low temperature environment (-10C°） Clue:1.battery capacity drop to 0%, so can't boot up 2.Sencond Vendor Battery is OK. Root Cause：1.Qualcomm Fuel gauge Algorithm issue,ESR+Rslow>2ohm under -10°C Solution:1.Fine tune ESR coefficienct,Evaluate OK Plan:1.Gathering Battery Discharge data and to check with Qualcomm to possition the issue. | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-01-29 | 7.DVT2 | 8.Mods | 4.Build | S2 | Closed | [S2]Issue:1.DVT2A Build Projector Failed Root Cause:1.I2C read 0X42,and then Fail to Write 0X02 due to clk bit halt on 6th bit due to I2C Arbitary mode 2.The Rising of V1.0 Power of Anx7805 affect the CLK during 1us. Solution:1.Retry Reading IO expander-Verify Pass. 2.Initial IO expander first, Presure Test on Projector Open Scenario ,Focus on Vibrator and Audio.- Pass | Link | 院长 | 敏敏 | Link | 4.Parameter | 1.Shelby
2018-01-17 | 5.DVT1 | 12.EMC | 5.5 Certification | S2 | Closed | [S2]Issue:CE ESD Usb Link Fail Clue: Root Cause:Usb Data Transfer interrupt by GND voltage drop when ESD Solution:1.Proposal:Separate Signal & Changing GND with Shielding GND 2.Proposal:Separate Shielding GND with Cable 3.Better TVS with bigger Capacitor- Sporton Verify Pass Plan：1.import S3 in dvt2a and monitor Closed |  | 靓仔 | 森森 |  | 3.BOM | 1.Shelby
2017-12-25 | 5.DVT1 | 4.Audio | 5.4 ALT | S3 | Closed | [S3]Issue:Vibration/Earpiece speaker/Alert speaker function intermittently during ALT Root Cause:1.I2C Abnormal lead to Function intermittently 2.Anx7805 I2C Abnormal lead to this issue. 3.I2C abnormal when Anx7805 Pown Down and V1.0 Power Supply exit. Solution:1.Using independent GPIO to control An7805 1.0V Power 2.Modify Power on/off Sequence to avoid Power down and V1.0 Power supply exit at the same time. 3.Reset IO expander U5401 when I2C crash. Plan: 1.Monitor in DVT2A | Link | 院长 |  | Link | 1.SCH | 1.Shelby
2018-01-16 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue:Alt test after ESD,GamePad Mods keypad no input Clue: RootCause:1.ANX7805 Usb Port Damaged 2.ESD Proect May not enough Solution:1.Optimize ESD Protection，DVT2A imported Plan:Monitor DVT2A Test Status | Link | 靓仔 | 邦邦 | Link | 2.PCB | 1.Shelby
2018-01-08 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S3] NTF BT ：DVT1B AMPS_MSMGPIO14_INITIAL_LOW_STATE fail Clue： Root Cause：1.Power Sequence Issue Solution：1.Initial C-Wire first，and start to test Plan：Verify on DVT2A | Link | 邦邦 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2018-01-08 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S2]DVT1a 2 units（total 1500pcs） JOT AMPS_NO_LOAD_CALIBRATION_STATUS fail clue：1.SN: NS9A110077 change U710/U711 to a new one retest pass by liguoa 2.SN: NS9C120127 is under analysis by Xianhua 3.No Signal When Calibrate 1A 4.Same Issue on Houdini RootCause:1.276 ,280 exceed 1-255 range Solution:Replace 220K compensation Resistor with 620K Plan:1.Replace 220k compensate Resistor with 620K , 2.Verify in DVT2A | Link | 李果 |  | Link | 3.BOM | 1.Shelby
2018-01-08 | 5.DVT1 | 2.Power | 5.2 BB Test | S3 | Closed | [S3]Issue:DVT1A Power Consumption exceed 2mA,Failed at Standby Mode (6mA while BT/WiFi is on) Clue: Root Cause：1.Mods Anx7805 IC 1.0V Power Supply is not shut down. 2.This IC share the same Power Source with WIFI/BT,Enable Pin share the 3.3V Power Supply on Anx7805 Solution:1.Using Seperated GPIO as Enable. Plan:1.Import Solution1 in DVT2A and verify | Link | 敏敏 |  | Link | 1.SCH | 1.Shelby
2017-12-25 | 5.DVT1 | 1.Platform | 4.Build | S2 | Closed | [S3]Issue:1.DVT1a U5040,U5041 Solder open issue ，SMT suffered failure rate of 0.5% Root Cause:1.Cold Pad Design lead to Solder Open Solution:1.Expand Solder Paste 2.using cold pad design 2.Reseve Glue Design on this IC by fine adjustment hole on shielding case Plan: 1.DVT2A Verify | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-11-15 | 4.EVT | 7.Sensor | 5.4 ALT | S3 | Closed | [S2]Issue: Ps/ALS sometimes not work after 1.2M drop . reboot ok . Clue:1. ME found that Position Over limit Root Cause:pop pin connect shortly open when drop ,recover after a short time. cause p-sensor work abnormal Solution：Proposal 1. ME check design Proposal 2. SW evaluate recover method at same time. Plan: 1.Follow up ALT DVT test result 2.Push Software Insert Recovery Mechanism 3.Push ME Analysis or Improve Spring Contact Stability DVT1A ，1st ALT ok ，follow up DVT1A 2nd ALT | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-06-20 | 4.EVT | 9.Memory | 5.2 BB Test | S3 | Closed | [S3]Risk:SD trace is too long (130mm length,More than limitation 77mm) Conclusion: keep good pcb layout，protect the signal, keep equal tace length. Verification:EVT Test, 1.4ns, 0.96ns , Risk Turn to Issue. Issue:SD card Interface Signal Integrity Fail, 200M Mode ;Clk,Data,CMD Rising Time/Falling Time Exceed 1.4nS,Creteria <0.96nS. Clue:1.200M Sandisk sd card ,SDR104 ,No Speed affection 2.100M （No Brand）Copy fail temporarily,Signal Integraty OK,low down clk to 50M ok. 3.Modify IO Driver Capability,can't meet. Root-Cause:Trace too long Solution:1.Optimize Routing,Less Gounding to lower down parasitic capacitance 2.Lower Down Clk when Data Error rate like P2,or Houdini | link | 威姐 |  | link | 6.No Change | 1.Shelby
2017-12-27 | 5.DVT1 | 8.Mods | 5.4 ALT | S3 | Closed | [S3]Issue:ALT WH103118 B1 can not power on with turbo charge mods. RootCause:1.Analog Mux Damaged lead to can't power on 2.Proposal:maybe caused by ESD/EOS Solution:1.Optimize Mods Pin ESD Routing in DVT2. Plan:1.Monitor | Link | 邦邦 |  | Link | 2.PCB | 1.Shelby
2017-12-27 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:Edu16 Charger Overvoltage Test 1/2 Fail Clue:1.D2, After 11V Charger Overvoltage test, the charge current changed to 1.5A（Initial 500mA ），can be recovered by restart, the test stop Root Cause: 1.It is not a OVP Issue,2.Why Trigger 1.5A Charging Mode is a SW Issue Plan:Support SW to Analysis. | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Unable to power on D1：After -15KV air discharge,power off,unable to power on Root Cause:1.LCD Damaged lead to fail to power on 2.Wrong Grounding Foam Position lead to ESD Damaged(Conclusion by Display zhuanghuajun) Solution:1.Enlarge Conductive Foam and Graphite Keep out Area ,Verify 1 unit evaluation pass Plan:1.Evaluation Thermal Side Effect. | link | 靓仔 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-12-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:DVT1A ESD Test Display Missing Pixels D5：After-15KV air discharge,display missing pixels. Root Cause:1.Wrong Grounding Foam Position lead to ESD Damaged(Conclusion by Display zhuanghuajun) Solution:1.Enlarge Conductive Foam and Graphite Keep out Area ,Verify 1 unit evaluation pass Plan:1.Evaluation Thermal Side Effect. | link | 靓仔 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-12-12 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:Cap Sensor Sensing Fail Clue:1.2 Channel Fail,Value 2000-5000 ,Normal value is 0. Root Cause:1.Antenna Switch output capacitance affection lead to sensing failure Solution:1.Add 82nH Inductor to cancel this affection Plan:1.Antena confirm the inductor affection,2.NA Sku keep run for data. 3.Latam Sku add 82nH inductor.4.Reserved inductor in DVT1B,Will determine the final solution after solution verification pass. | Link | 小熊 |  | Link | 1.SCH | 1.Shelby
2017-12-04 | 4.EVT | 8.Mods | 5.2 BB Test | S3 | Closed | Issue:The eyes height is fail, compare with Eagle it is fail too. Rootcause:1.Maybe due to the MDK to increase the length of lines. Plan:1. Check if there are some opportunity to improve the pcb layout. 2.Check if can test without MDK 3, Refer to the Mydp test result which using the same lines. | Link | 威姐 |  | Link | 6.No Change | 1.Shelby
2017-11-22 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue：4 units boot up failure after ALT Root Cause: 1 VREG_OLEDB Abnormal result in Boot Failure 2 OLEDB_EN Abnormal result in VREG_OLEDB Abnormal 3 PCB delamination under Mods result in OLEDB_EN crack Solution&Verification： Solution 1:Wires on 9th Layer Keep away from Mods Conn Verification 1=DVT1B Verify Plan： 1.Mods Connector Changed to original version,Low risk | link | 文亭 |  | link | 2.PCB | 1.Shelby
2017-12-03 | 4.EVT | 3.Charging | 5.6 User Feedback | S3 | Closed | [S2]Issue:Shelby EVT2 can't compliant with Xiaomi 10W Type-C Charger. Clue:1.Factory Software 2.Moto 30W Charger is ok . 3.Verify Xiaomi 10W Charger OK(Include Low Voltage) 4.Compliance test is ok Root-Cause:Need issue confirmed Plan:1.Need to reproduce issue ,Proposal 1):Using 4X Extended USB Cable 2).Using repeater 3)Using USB Cable without D+,D- | Link | 林峰 |  | Link | 6.No Change | 1.Shelby
2017-11-27 | 4.EVT | 5.Camera | 5.2 BB Test | S3 | Closed | [S3]Risk: Flash Thermal Evaluation fail at 1.5A which exceed LED's Junction Temperature , and will damage flash led Clue: 1.factory flash calibration set flash current 1.5A(cool)+0A(warm)/ 0A(cool)+1.5A(warm) 2.Ibis use the same LED Flash,No defect in Factory,After sale 2.Thermal Evaluation result: Flash can work at 1.2A(cool)+0A(warm)/0A (cool)+1.2A(warm)/0.75A(cool)+0.75A(warm) Root Cause:1. Solution :1. Flash positive add vias 2. Flash positive enlarge copper paving Plan:1.Verify on DVT1A Same AS Ibis（simulation data） ，monitor | LINK | 芳梅 |  | LINK | 2.PCB | 1.Shelby
2017-12-01 | 4.EVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:WH102567 ESD Fail，Unit Can't Power On Clue：1.Restart Fail 2.disassembly and find no grounding for display module. Rootcause:1.Display damaged Plan:1.KP zhuanghuajun Analysis. 2. grounding display module in DVT1A . | Link | 靓仔 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-12-25 | 5.DVT1 | 12.EMC | 5.5 Certification | S3 | Closed | [S3]Issue: EN301489 RS Pre-test fail Clue：With this solution 1，#8#9Failed, Using Letv cable Pass -2018-1-13 Root Cause:1.Mic Bead cause the unbalanced which easily affected by RS 2. Solution:1.Remove Mic Bead, Pass ，2.Add 2 1.5nF Capacitor on Mic Channel and R&L to System GND,Pass | Link | 院长 |  | Link | 3.BOM | 1.Shelby
2017-12-29 | 5.DVT1 | 1.Platform | 5.6 User Feedback | S3 | Closed | [S3]Issue:Vibration/Earpiece speaker/Alert speaker not work sometimes (function intermittently at 12/28) ,found by SW Yongbin. more units were found Clue:1. Log show I2C fail. 2.SMT suffered Solder open failure rate of 0.5% on U5040,U5041 Root Cause：1.Anx7805 cause I2C Abnormal 2.according to A5 cross section ,it should not related SMT issue Solution:1.Refer to <[S3]Issue:Vibration/Earpiece speaker/Alert speaker function intermittently during ALT> Plan:1.Same issue with another one ,combinate | link | 文亭 |  | link | 1.SCH | 1.Shelby
2017-11-15 | 4.EVT | 3.Charging | 5.4 ALT | S2 | Closed | Issue:EDU04 WH102186 fail Root Cause: 1. U550 Damaged by MosFET breakdown in over reversed polarity Voltage. 2. U550 reversed polarity Voltage SPEC is -0.5v/2A, and measured Voltage is -0.382V/1A ,-0.432V/2A in SPEC. 3. TCC retest 5PCS ,all pass. The design is available,only 1 PCS damage maybe cause by other reason.(etc. wrong test condition/ component single defect） Monitor in the next test. DVT1A pass | Link | 林峰 |  | Link | 6.No Change | 1.Shelby
2017-11-09 | 5.DVT1 | 7.Sensor | 5.2 BB Test | S2 | Closed | Issue:Synaptics Need 3.45V LDO Root Cause: SPEC requirement Solution：1. 3.45V LDO use On 2. change power input of 3.45V LDO from VBAT to OTG power 5V boost . Done 3. Choose 3.5V LDO for second source availible Plan:DVT1 Verify NO FOD in shelby | Link | 礼森 |  | Link | 1.SCH | 1.Shelby
2017-11-27 | 4.EVT | 12.EMC | 5.4 ALT | S2 | Closed | Issue:DVT EDu03 Eval - ESD Certification Test After +10KV air discharge at left side crevice in zone 16（Aging 10），Cannot open rear and front camera and vibrator no function,can't recover. Clue:1.LCD Grounding is not good Root Cause:Cap sensor damaged . No ESD protection now. (ANT TVS DNP in EVT because no sample) Solution&Verification:1.Mount ANT TVS，DVT1 Vefify Pass Plan：Monitor |  | 靓仔 |  |  | 3.BOM | 1.Shelby
2017-11-13 | 4.EVT | 1.Platform | 5.4 ALT | S3 | Closed | Issue:Unable to power on Clue:A3(1),A5(1),B1(1),B5(2) Root Cause:battery plug incorrectly Action： Factory correct it in coming build monitor 2nd ALT test result ME own | Link | 文亭 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-11-22 | 4.EVT | 10.USB-C | 4.Build | S2 | Closed | Issue:EvT2 can not recognize network in xiamen enginner lab Clue:1.Wuhan Fixture OK but Xiamen Fail 2 ADB can't Connect 3.EVT1 OK Root Cause:Limited Margin due to TVS used in USB D+,D- are 10pF Solution：Using New TVS with 1pF Capacitance |  | 威姐 |  |  | 3.BOM | 1.Shelby
2017-11-13 | 4.EVT | 3.Charging | 5.4 ALT | S3 | Closed | Issue:EVT1st ALT Charging abnormal Clue:A4(3),B2(3) RootCause:Cause by Low Temperature, Analysis:Log Provide to SW for analysis； Battery Power low to 50% easy to cause power off in -10℃ Solution： 1. charge to 100% and make sure battery >50% during ALT test ,verified ok. | Link | 林峰 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-11-10 | 4.EVT | 5.Camera | 5.1 Bring up | S2 | Closed | Issue:Andriod CTS Camera test item PIP(picture in picture) Failed Root Cause:1.Rear Camera & Front Camera Using the same CSI0 Data Channel 2.Share Same Reset Signal Solution:SW Disable parallel cameras for CTS test， NO need to change HW CSI design | Link | 芳梅 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-11-09 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | Issue:Noise when insert type-c earphones Root Cause: 1.Mic Bias 25Hz Switch Solution:1.Mic Bias constant open,Evalation OK Plan：DVT1A verify, Verify: OK | link | 院长 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-11-08 | 4.EVT | 9.Memory | 5.2 BB Test | S3 | Closed | [S3]Issue: Alternate Operation Fail Root cause:1.Variant BOM can’t invoke Alternate Part 2.Alternate Part need same Symbol and Cells name. Solution:1.Develop tool to solve it . |  | 芳梅 |  |  | 6.No Change | 1.Shelby
2017-10-23 | 4.EVT | 8.Mods | 5.2 BB Test | S3 | Closed | Issue:Mods I2S Tx no out RootCause:I2S Tx ，Rx Switched in front of MUX input Solution: 1. Short TX,RX, -liguoa---I2S verified OK 2.Switch TX ,RX on EVT-2 -liguoa - Done Verification:Verify on EVT2 | Link | 李果 |  | Link | 1.SCH | 1.Shelby
2017-12-21 | 5.DVT1 | 3.Charging | 5.4 ALT | S3 | Closed | [S1]Issue:With the charger can't turn it off,Will be automatically power on Clue: Root Cause:Mobile phone input ALT special instruction(fastboot oem off-mode-charge 0) Solution:Eliminate the instruction( fastboot oem off-mode-charge) | link | 李果 |  | link | 6.No Change | 1.Shelby
2017-12-16 | 5.DVT1 | 8.Mods | 4.Build | S3 | Closed | [S3]Issue:SDA Pin of a MOD connector short to GND Clue: Root Cause: The mod connector short circuit Solution:DVT2 will change the old connector Plan: | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-10-27 | 4.EVT | 2.Power | 5.2 BB Test | S3 | Closed | Issue：Power Consumption Airphone :29mA RootCause: 1.Mods ANX7805 :20 mA 2. Cap-sensor :1.1mA 3. TP: 4mA Solution： 1.10/25 SW has been modified---weiweij 2.Because there is no firmware version cause, need to get the phone debug. Will follow blaine cap-sensor solution.-----caoyi 3. wil be optimization when get the formal TP ----liguo/yongbin Update Airplane 4.1mA 10/27 | Link | 李果 |  | Link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-10-12 | 4.EVT | 6.Display/Touch | 5.1 Bring up | S3 | Closed | Issue：金手指厚度做成0.3mm，Spec is 0.2+/-0.02mm RootCause：some DFM mistake confirmation between CAD & Hongflex Solution： 1.grinding thinner 10pcs by hand- fanlf/liujjg 10/13 done 2.Hongflex re make the sample (10/12) chenwt |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 1.Shelby
2017-10-12 | 4.EVT | 7.Sensor | 4.Build | S3 | Closed | Issue：There is not U6160 in BOM(FPC2050 ,side FPS driver IC) RootCause：SCH Variant BOM affected by old Info Solution：1.EVT board only not SMT U6160. chenwt Done 10/12 2.Soler FPC2050 by hand for SW bring up . Chenwt 10/16 3.update BOM generation process,adding variant review step .fangmei 10/16 | Link | 芳梅 |  | Link | 3.BOM | 1.Shelby
2017-06-16 | 3.PEL | 8.Mods | 5.2 BB Test | S3 | Closed | Issue：EVB Mods Bringup suffer much RootCause：1.Clock&CS of SPI Swapped 2. M-PHY I2S Rx Missing 3.SPI Switch Signal LPI can't work Solution：1.Swap clock&cs 2.jumper wire 3.replace LPI-GPIO with GPIO | Link | 李果 |  | Link | 1.SCH | 1.Shelby
2017-06-16 | 2.PCL | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk: SAR sensor design， Cap sensor can support 3 ANT？（1 up +2 down）？How to design it？ Evaluation:Change IC from SX9310 to SX9324. More compatible for High Path capacitor（From 100pf to 200pf，same cost）？ Conclusion:1 Cap sensor can support 3 ANT （3 Bottom ANT） | link | 小熊 |  | link | 6.No Change | 1.Shelby
2017-07-25 | 2.PCL | 3.Charging | 5.2 BB Test | S2 | Closed | OVP design check,Moto has added OVP IC, Keep monitor |  | 靓仔 |  |  | 1.SCH | 1.Shelby
2017-08-15 | 3.PEL | 10.USB-C | 5.2 BB Test | S2 | Closed | Risk：Usb Eye diagram may fail because of Type-C connector on FPC | Link | 威姐 |  | Link | 6.No Change | 1.Shelby
2017-08-01 | 1.Concept | 10.USB-C | 5.2 BB Test | NA | Closed | Risk：IBIS Swiwming Water Proof Fail 2017-8-28：IP68 Canceled on NPI，turn NA Solution：Reserved ADC on CC1 for anti-water research ,Research it on EVT | Link | 威姐 |  | Link | 6.No Change | 1.Shelby
2017-06-20 | 1.Concept | 11.Thermal | 5.2 BB Test | S3 | Closed | Risk: Thermal design check . there should be high thermal Risk ,need further check Evaluation: Conclusion：It is fine according to the latest Thermal Simulation | link | 林峰 |  | link | 6.No Change | 1.Shelby
| 1.Concept | 1.Platform | 5.2 BB Test | S1 | Closed | Design：Key Design to compatible with Option C1，Option C2，Option D，Option E before 9/5 Conclusion: Design Changed | Link | 森森 |  | Link | 2.PCB | 1.Shelby
2017-08-28 | 3.PEL | 1.Platform | 5.2 BB Test | S1 | Closed | Issue：LPI GPIO can't use，Need xx more GPIO conclusion: Add IO Expander | Link | 文亭 |  | Link | 1.SCH | 1.Shelby
2017-06-16 | 1.Concept | 8.Mods | 5.2 BB Test | S2 | Closed | Risk:NEW MODs connector SMT RISK( Can pass Build and can pass ALT) Conclusion: here | here | 李果 |  | here | 6.No Change | 1.Shelby
2017-07-03 | 1.Concept | 10.USB-C | 5.2 BB Test | S2 | Closed | Risk:Type C ，switch control logic is correct？ Conclusion: It is ok | link | 威姐 |  | link | 6.No Change | 1.Shelby
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S3 | Closed | Risk:M-sensor placed on side of battery ,some Assembly risk Evaluation: 1. check with AKM porformance . 2. can we put it on main PCB?（base on new stacking） Conclusion:Place in the middle of Side Key FPC | link | 小熊 |  | link | 2.PCB | 1.Shelby
2017-06-20 | 1.Concept | 3.Charging | 5.2 BB Test | S2 | Closed | Product Design:Charging solution 20W？27W ？ charing IC solution is？(Impact thermal and placement) Conclusion: 27W Adpater +20W charging rate (not big switch solution) . Thermal risk is high. Any chance change to 20W Big switch solution？ Charging Solution back to 15W because of cost - 2017-8-1 |  | 林峰 |  |  | 6.No Change | 1.Shelby
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk:Barometer design ：ME requirement is for IP68？ Conclusion:check with Bosh that no IP68 phone MP with Bosh Barometer .Barometer can not work because the air can not go into the phone. Next Action: Any solution for air to go into phone but water can not go into it? Cost? IP68 Cancel on NPI -2017-8-23 | link | 小熊 |  | link | 6.No Change | 1.Shelby
2017-06-16 | 1.Concept | 7.Sensor | 5.2 BB Test | S2 | Closed | Risk:P-sensor ，How to design it in Notch phone？ Conclusion:Camera+SPK+P-sensor+camera,P-sensor on Flex ,now is ok. needed further tracking if there is any change | link | 文亭 |  | link | 6.No Change | 1.Shelby
2017-08-02 | 1.Concept | 10.USB-C | 5.2 BB Test | NA | Closed | Risk：FPS option 2-3 may have ESD risk Evaluation： Conclusion：Solution Canceled | Link | 靓仔 |  | Link | 6.No Change | 1.Shelby
2017-06-16 | 1.Concept | 4.Audio | 5.2 BB Test | NA | Closed | Risk:Use typeC For earphone interface，How to design FM（ANT） ？ Action:1.Inform Risk to RF,RF Own -Done 6/16 | link | 院长 |  | link | 6.No Change | 1.Shelby
2019-12-16 | D.SHIP | 9.Memory | 6.Issue | S2 | Monitor | [S2]Risk:WDC Memory may exceed erase endurance specification which may lead to no turn on Clue1:Roburst2 have several No Turn on issue in EWG and DF due to UFS issue Clue2:P/E Cycle(Programing or Erase Cycle) limitation should under 1M, For Roburst2 UFS, Low Risk under 200K ;Mid-Risk <-250K; High Risk <=300K Estimated Average P/E Cycle=P/E Cycle Counter+71%x Initialization Counter ≈ 71% Initialization Clue3:For UMCP， the initialization Counter Coefficient should be low than 71% duo to bisc4 INAND New Generation Tech. WDC will feedback the coef by 12/20(CHN) Clue4:For Stingray,Initial Assessment P/E Cycle≈ 154K ( From 2 Stingray and 2 quattro Power Cycle Data).More data with more accurate estimate on-going ,12/20(CHN) The risk is true,we still need more data to have a more clear view. Root Cause： Why no turn on? 1.All Free SLC Block used for improve write operation was wrongly erased after initialization by Firmware due to they are wrongly recognized as "Not Erased" even for erased block,After exceeded endurance Specification,it will lead to no turn on . From WDC FA on R2. Why those opeartion issued? 2.1 Those operation will be triggered after VCCQ Power Down in Sleep mode or HW Reset issued. From WDC FA ,It is known issue 2 months ago in WDC. 2.2 Why Free Block was recognized as "not Erased"? UFS FW Design Logic error issue Solution: 1. Correct memory FW 1.without erased all free block operation; 2.enable a new SLC(6% memory capacity consumed) and update,by OTA or by service center , WDC will release solution by 12.23 |  |  |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-07-22 | C.RAMP | 2.Power | 4.Build | S2 | Closed | [S2]Issue:Display Flicker during Charging after Patched for Flicker when Loud Speak. Clue:Only when Battery Fully Charged Root Cause: Why Display Flicker when Charging? 1.Input Charging Voltage Ripple 200mV Observed and ELVDD 120mV Ripple observed when Charging to Full battery Capacity, TianMa Display Need 5mV . 2.ELVDD Enter Force Boost Only (0xDE70=0x80) ,No Issue under Charging with Original setting 0x00(Boost Only Mode and Boost+LDO mode Dynamic Switching) duo to when input Voltage Transient over 200mV-300mV， Pmic Will Enter Boost+LDO Mode with low ripple(7mV). . Why ELVDD Force Boost Only（0x80）? To solve issue when Loud Speak(0.7% Failure Rate) 3.0x00(Dynamic Boost&LDO mode) have issue Switching when Voltage Transient over 200mV-300mV that happen during Loud Speak which lead to over 5mV Ripple 4.1 TianMa Display Only Accept 5mV Ripple, SDC Display accept 50mV due to AVC Tech. 4.2 0x81 mode consume extra 20mA Power current. Solution: 1.When Charging , Set 0xDE70 as 0x81（Force Boost +LDO mode，Extra 20mA Power Consumption,Acceptable under Charing） When not Charging , Set 0xDE70 as 0x80 (Force Boost Mode, No Extra Power Consumption) HW Validate OK. SW Release 7/26 | Link | 敏敏 | 芳梅 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-07-05 | C.RAMP | 2.Power | 5.6 User Feedback | S3 | Closed | [S3]Issue: 7/5 SW summary User Feedback that Shut Off Suddenly when using DouYin, Camera Capture with Music Background or Duo in Low Battery Status. Clue:Stingray 4.6A, Quattro 29.59 6A, Quattro 29.45 5.5A RootCause: 1. Shut Off Due to Supply 2.8V over 3ms on PMIC. Exp:VBAT_L2=2600mV(deglitch=8mS) or IBAT_L1=6000mA(deglitch=8mS), it will trigger BF fault and cause BATFET open. 2. 2.8V over 3ms on PMIC duo to High Power Consumption in Audio Smart PA.Over 7.5A maximum Current Observed in DouYin APP. 3.1 BCL Setting From 5.5A to 4.5A. 3.2 High Audio Smart PA Gain Setting. 30% bigger Current Drain than Stingray. 29.59 have 9% Bigger Current Drain Than 29.45 Solution: 1.Enable Smart PA Low Voltage Protection, 50ms or 5ms Release time, HW Verify OK. KP Audio team check 5mS not impact audio performance , SW will merge this change . by 7/10 Under Pressure Test and DFer Validation | link | 敏敏 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-07-05 | C.RAMP | 5.Camera | 5.6 User Feedback | S3 | Closed | [S3]Issue:29.59-2 Thermal Camera Test, 1°C Higher than 29.49 ,but in test Tolerance. Clue1:59-2 : 42.9°C @15Min ; 29.49 41.9°C@15Min ，39.6°C@10Min Clue2:Camera Power 3% increased observed. Root Cause:1. Power Consumption 900mA+@Camera Preview, While Z6 Pro with Same 48M only 600mA 2.Camera Team investigate. Solution:Monitor. |  | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-06-14 | C.RAMP | 10.USB-C | 5.2 BB Test | S3 | Closed | [S3] Issue: Quattro Compatibility Test with M14（ThinkVision new generation Display）10% Display Low Resolution 640X480， about 1-2/10 Failure rate. Clue: 1080p normally Clue:External Adaptor with M14, No Issue Clue:Change Another Cable , No Issue. Root Cause: Why Low Resolution? 1.EDID Read error Exp:Log Analysis. Result:EDID Read Error . Conclusion:Phone side can't read EDID. Why EDID Read Error? 2.Aux P/N Signal Transaction Affected by OTG Vbus Sink Current Exp2.1: Observe Vbus Waveform, Result: Aux Read Time slot in VBUS Sink Current. Conclusion: Aux P/N Affected by Vbus sink current. Exp2.2:Delay Aux Reading by 5S , Result:No Issue , Conclusion: Aux Reading avoid Big Current can resolve issue. Why Aux P/N Signal Affected 3.1 Aux P/N in Cable Bad Common mode rejection Exp3.1.1:Verify Black Cable and white cable on differential interference. Result:Aux P and Aux N have different differential interference. Conclusion: Cable Matters. Exp3.1.2: Compare Black Cable with Standard Cable. Result:Aux N is more close to Vbus than Aux P which lead to different Common Mode Rejection. 3.2 OTG Output big Ripple duo to Vbus Power Exp3.2: Measure WaveForm,Using External Loading . Result: 0.65V Ripple@200KHz (Target <0.5V Ripple) when Current drain greater than 900mA (OTG enter PFM Mode) Observed. Conclusion: Big Ripple Observed when Current great than 900mA. Why Big Ripple? 4.OTG of PM6150A Enter PFM Mode and unstable Exp4.1: Switching WaveForm Observation Result:Big ripple when enter PFM mode. Conclusion: PFM mode Alter lead to big ripple. Exp4.2:Change 4.7UF to 10uF on MID_CHG, Result: 0.2V Ripple@800K ,Acceptable. Conclusion: Increase capacitor on Mid_CHG can solved this issue. Solution: 1.Set EDID Read Fail retry Delay to 4S -SW Need CR - Recommend 2.Modify Type-C Cable, Twisted-pair Aux P&Aux N. - ThinkVision Team - Not Recommend 3. Change C2412 to 10uF ， Cost Up $0.003 - Baseband - Recommend , Bom Changed | Link | 芳梅 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-06-14 | B.PVT | 6.Display/Touch | 5.4 ALT | S3 | NA | [S3] Issue: Display Missing Pixel after ALT Drop Estimate to drop this issue ,Due to wrong Test Method-Tear Down Crack Display cause Abnormal PCB Strain. |  | 芳梅 |  |  | 6.No Change | 3.Quattro
2019-06-14 | B.PVT | 12.EMC | 5.4 ALT | S3 | Closed | [S3] Issue: Display FOD visible after ESD Clue: ESD at zone15, LOGO LIGHT area. Recovered after 2 minutes automaticly. Clue: Root cause: 1.LHBM Reg Affected, 1. Panel Abnormal , TE Lost, Panel Recovery Triggered and Recovered. Solution: 1.SW recovered and NTF 2.Close LHBM 1.Close LHBM |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-06-14 | B.PVT | 12.EMC | 5.3 EE DVT | S3 | Closed | Issue:[S3] 1.P sensor no function after ESD, with permanent damage. （EDU03） WH116676 1 unit fail 1/6 Clue: 1. ESD at zone 1, front camera area. ME Status OK. 2. In 8 TCC tests, 42 units in total before PVT, no this issue. 3. 8 more PVT units Zone1 ESD pass .then these 8 PVT units stress test pass(100 times +15kV AD and 100 times -15kV AD on zone 1), 5 times strengthen test. Root Cause: 1.P sensor IC VDD is damaged, with low impedance. With about 100mA current, IC heats. 2. Receiver deco 2nd discharge. Solution: 1.Low Risk :Accept 2.modify Grounding conductive fabric （make a path for Receiver deco 2nd discharge）,ANT Approved, Runing Change. | Link | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-06-04 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2] Issue 2: [Quattro] [Factory] [CQA1] test result:P-sensor is at Near status all time. Rootcause： 1.Near status caused by high CT due to Rubber cover the IR LED cause reflection 2. DVT2B Rubber dimensions：Out of tolerance 3. Wrong Rubber Design due to incorrect Vendor Spec Solution： 1. use MP tooling Rubber that within tolerance ---PVT import 2. change the rubber design ,here ---Pilot Import 3. change threshold to increase 50% margin.---PVT import | link | 文亭 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-05-31 | 7.DVT2 | 7.Sensor | 5.6 User Feedback | S3 | Closed | [S3] Issue: sometimes Motoaction can not work outdoors IKSWP-89083 clue：1. When the IR channel data is too high，Pdata will increase and fluctuate. Root cause： 1.Moto Action suspend due to P-Sensor report Near status(Pocket Mode),Observed from Log. 2.Low Threshold observed as a result of low noise calibration which triggered by wrong P-Sensor Data under normal crosstalk value. 3.Innormal P-Sensor Data reproduced after P-Sensor quit sunlight Mode. (Sunlight Mode is to solve correct response under outdoor IR enviroment,by setting Pdata=0 and Report Far Status). 4.Why P-Sensor output a wrong data when quiting sunlight mode? Can not reproduce by Vendor RD. Solution： SW Working Around. 1.Optimize Low Noise calibration :using Average data without Peak and Valey data to calibrate. 2.Optimize Low Noise calibration : Do not calibrate when IR channel is higher than 1oooo 3.Debounce Trigger ,Only when 4 continuesly valid data compare to originally 1 . validated on temp patch. 4.Set lower sunlight mode to level 1 which is easier to enter (original is level3) , validated on temp patch. 5.Low Down 5mm detection distance(20mm Near,25mm Far) to increase threshold to 180,120（MPS=2）. DF Validate Pass. | link | 文亭 | 小熊 |  | 4.Parameter | 3.Quattro
2019-05-31 | 7.DVT2 | 3.Charging | 5.3 EE DVT | S3 | Closed | [S2]Issue: 40℃高温关机充电4 hours，充入电量未达标准3.9V Clue1:从log分析，高温充电下，充电thermal机制启动，充电电流降到300mA，Quattro 电池4000mAh，电量大，充电速度太低无法满足需求. Clue2:thermal config 调整，最低充电电流提到700mA，自测Pass，实验室测试临界pass，与预期不符，从log分析，充电误进USB模式，导致充电电流只有500mA Clue3：经过实验室压力测试，关机状态下，常温或高温下，都有概率会进入USB模式，开机不会 出现fail的概率和USB cable线插入的速度有关，慢速插入时复现概率高 Clue4：测量fail时出现的波形，关机下，系统先进bootloader，再进kernel，初始化完成后，亮屏充电，发现在bootloader下做充电状态识别时，会有异常波形出现，导致无法进入BC1.2之后的QC3.0协议，在后续的kernel mode 继续以异常的状态持续充电 Root Cause: 1.bootloader模式下，充电状态识别容易出现异常（尤其是慢速插入时），而开机状态，充电识别初始化在kernel层完成，在kernel层的充电识别初始化，未发现问题 2.Proposal:Moto Bootloader solution： 在进入Kernel后重新做一次充电状态识别，可以有效排除慢插的影响，确保系统识别正确的充电类型 经多次压力测试，OK | Link | 林峰 | 院长 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-05-29 | 7.DVT2 | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: DVT2A unable to power on after ALT complete Clue: 1. leak current: 15ma when power off 2. the voltage of DVDD(PM6150) is 1.5v ,the normal voltage is 1.8v 3. B_PLUS is 1.654V,the normal voltage is colse to vbat voltage. root cause: 1.PM6150 is damaged after ALT 2.The corner chipping already propagate to the active circuitry area, so it do affect the function 3.High PCB Stain due to abnormal Test Method that Tear Down Display. Solution: 1.Monitor next ALT. | here | 敏敏 | 院长 |  | 6.No Change | 3.Quattro
2019-05-16 | 7.DVT2 | 11.Thermal | 5.3 EE DVT | S2 | Closed | [S2]Issue: DVT2A Quattro Thermal Failed 4.3℃ on Camera Photo Clue: 1.DVT2B re-test on camera 43.1°C,improve 1.2°C. Root Cause： 1.Camera Fine Tune Not Fixed and power consumes more 2.Thermal config Triggered but failed to mitigate the surface temperature. Solution： 1. HW: CPU heat spreader Expand 2. Active photo off @Back Therm>40°C 3. MAX backlight 100%->95% @ Quiet therm>45℃ 4. turn off log 5.Turn off WMP(Thermal Log APK) PVT Validate Pass | here | 林峰 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-29 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3]Issue: standby U510( USB DP ss mux) current leakage 0.6mA Root Cause: U510 pin 18 EN is pulled up to L7C which is always on , when EN=H，U510 active current is 0.6mA. solution： Change the power supply to L17A which is used for USB PD. L17A could be powered off if there is no usb or dp device. |  | 芳梅 | 李果 |  | 1.SCH | 3.Quattro
2019-04-29 | 7.DVT2 | 7.Sensor | 5.2 BB Test | S3 | Closed | [S2]Issue: DVT2A ALS Angular in Y axis is only 25 degree(Standard=33 Degree?) Clue: 1. Test in Vishay show ALS angle in Y axis only 25 degree 2. if no silicone case, 27 degree in Y axis solution： By adjust LCD brightness response curve | here | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-06-07 | B.PVT | 2.Power | 5.4 ALT | S3 | Closed | [S2]Issue: Quattro No turn on issue after ALT drop-Link Clue1： U2400 Pin solder Crack in DVT1B & DVT2A Clue2： U1600 Pin solder Crack in DVT2B Clue3 : all no turn on issues happened after display crack. Clue4:No issue in Tumbling Test. Root Cause： 1.U2400/U1600 issue Exp 1.1: current observation. Result: Conclusion: U2400 abnormal 2.U2400/U1600 solder crack Exp 2.1: red dye test. Result:U2400 solder Crack found by red dye test.Conclusion: U2400 solder crack. 3.U2400/U1600 weak solder joint. Drop Exp 3.1 Cross section failed one .Result: by 6/18 Exp3.2 Cross section normal one. Result:Solder Joint Normal .Conclusion: No Issue. 4.Proposal: ME change lead to high PCB Strain Exp 4.1: Harder Thermal Pad . Result: Failed too . Conclusion:Harder Thermal Pad also failed. Exp4.2: .TBD 5. No Sealess Assembly display in position lead to high PCB Strain after display crack and removed for analysis. Exp 5.1: keep original display until ALT drop finish(loop 5) result:Function and Red-dye no Issue . Conclusion:Drop test without Sealed Display lead to Extreme High PCB Strain that cause Memory and Pmic Solder Crack. Solution： 1.add underfill in U2400 & u1600,optimizing underfill cost . 2.Remove underfill | Link | 林峰 |  |  | 6.No Change | 3.Quattro
2019-05-06 | 7.DVT2 | 12.EMC | 5.4 ALT | S3 | NA | [S3]Issue: FOD self test fail, but can recover withou rebooting Clue:1. -15KV air discharge at zone 11(Aging 10),Fingerprint Self Test fail, then return to the previous menu,after executing the “Fingerprint performance Test“ test item,then run "Fingerprint Self Test" item.it can be pass 2. Sensor is alive. AP SPI port is well functioning. Solution: 1. SW asked vendor for help. 2. Update SW, PPH 29.29 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-27 | 7.DVT2 | 11.Thermal | 5.6 User Feedback | NA | Closed | [S3]Issue:User Feedback Quattro Got Hot using 65W Type-C Charger（T480 Note Book） Clue:Test 65W , Issue Can't Reproduce in XM SW,XM HW,BJ Thermal Root Cause: Need confirm Issue first. |  | 林峰 |  |  | 6.No Change | 3.Quattro
2019-04-29 | 7.DVT2 | 7.Sensor | 4.Build | S3 | Closed | [S2]Issue: DVT2A P-sensor TCMD unstable Clue:1. JOT Fixture may impact the test result ----ENG chen Huaiyu /WWTE Tang Muzong 2. SW DVT2A_04 get the data different per test , should be some problem ---SW Huangjq9 solution： SW&WWTE Own |  | 小熊 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-29 | 5.DVT1 | 10.USB-C | 5.4 ALT | S2 | Closed | [S2]Issue: DVT1B ALT-WH115686 ， A1(3) A1:TH/TC,USB charging is normal, but fail to connect computer. Clue： DM,DP common mode filter open , replace it and remove TVS on DP ,it is ok. Root Cause: -Why TVS&CMF Damaged? 1.External High Voltage on DP Exp1:Apply 9V on TVS with 1A Discharge Current. Result:TVS Damaged Observed. Conclusion:TVS and CMF damaged on DP duo to High Voltage over 9V Exp2:Draw Vbus Log and Pivot out. Result: Continues Voltage over 9V found . MAX=12V 2.Proposal: SW Issue? Drop Exp:Observe Normal One VBUS. Result:Under 5.5V . Conclusion: Not SW Issue. -Why over 9V voltage on DP? 1.Vbus short to DP due to Bad USB Cable or Bad Charger or Water Ingression Exp2:Mark ALT USB Cable and Charger , Observe the following ALT Test. Monitor if new failure. Result:the third failure happend Exp:Using Charging Monitor test the Calbe and Charger. Result: Heat found between Cable and Charging Monitor. Conclusion: Charger Broken duo to USB Cable Short found. -Why Over 9V on Vbus ? 1.Proposal:Charger supply Over 9V duo to D+Or D- short to Vbus Exp3:Short D+/D- with tweezers . Result:Vbus go 10V-12V. Conclusion: NA -Why USB Cable Short? Artifical USB and Plug Plastic perished and all fallen off. Bad cable solution： 1. Using New Cable & Charger in latest ALT of Quattro. 2. Discuss with TCC Lab to use reliable USB Cable in ALT Test. | link | 文亭 | 林峰 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-10 | 5.DVT1 | 1.Platform | 4.Build | S2 | Closed | [S2]Issue: Factory IF QBlank Flash Issue ，1-3% NTF (Unknown Device,) Root Cause: 1.Soft Reset After Provision lead to multiple channel conflict. Solution: 1.SW Optimize Soft Reset by Adding 1S Delay between Provision and Bootloader Flashing. | here | 文亭 | 小范 | here | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-22 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S2]Issue: DVT1B ALT WH115309 ，Not turn on after ALT loop 5 (6 in 12) Clue：Cross section， not abnormal found between DVT1A & DVT1B Root Cause: 1.U2400 PM6150A Solder Crack Found , Confirmed by MDU44 2.High PCB Strain Lead to Solder Crack Exp:Add Bucket Holder ,Result:6/12 Failure -> 1/10 Failure ，Conclusion:Significant Improved. Exp:Add Harder Thermal Pad on U2400,DVT2A Validate Pass Exp:Under Fill U2400,Result:DVT1A Validate Pass. solution： 1.Add Bucket Holder 2.Add Harder Thermal Pad 3.Backup:Underfill U2400, DVT1B ALT Pass. | link | 林峰 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | NA | [S3]Issue: TP no fuction - recoverable Clue: 1. +8V air discharge at zone 3(Aging 10),touch screen no function,press the power key 10s times later power off,press the power key to reboot recovered.(4/15 10:55)(Front camera(and Front flash) is ON ) 2. Zone 3 is the bottom side of display. Root cause: TP keypart own |  | 吉吉 |  |  | 6.No Change | 3.Quattro
2019-04-10 | 5.DVT1 | 1.Platform | 4.Build | NA | NA | [S2]Issue: Factory IF QBlank Flash Issue ，1-3% NTF (Unknown Device) Root Cause: 1.Proposal: Moto Multi-Downloading Tools +USB3.0 Issue? (No Issue feed back from other vendor of QC SM6150) Exp1:Using Qualcomm Multi-Downloading Tools + USB2.0 Tools Resource:PI Align with SW on requirement -IMG include UFS provision,reset and blank flash in PBL mode Solution: NPI own ，BB monitor and support |  | 文亭 | 小范 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-24 | 5.DVT1 | 5.Camera | 5.2 BB Test | S2 | Closed | [S3]Issue:DVT1A Quattro tele camera OIS_VDD and GRO_VDD are swapped Root cause: OIS_VDD and GRO_VDD are swapped in camera module 2D drawing. Impact: All units before DVT1B Tele camera OIS cannot work（Not including DVT2A）. Solution: change the OIS_VDD and GRO_VDD in DVT2A sch Action : 1.Notice PI & HPM DVT1a&DVT1B units Tele camera OIS cannot work 2. rework units for china team bringup OIS 3. mail how to rework the units for chicago team . 4.optimize 2D drawing Lesson learn : optimize 2D drawing requirement with Camera Module Vendor . Such as add power voltage requirement in 2D mapping ,Add current requirement for each power in 2D Drawing . etc | link | 邦邦 |  |  | 1.SCH | 3.Quattro
2019-04-25 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3] Issue: P sensor no fuction after ESD, recover after reboot Clue: 1. SW version is 29.15 2. P sensor could get no fuction without ESD, just covered by finger. Root cause: 1. P sensor fuction bugs in SW 29.15 2. ESD recovery works well in SW 29.16. 3. TCC re-test P sensor fuction after update SW 29.19. No issue this time. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-22 | 5.DVT1 | 7.Sensor | 6.Issue | S2 | Closed | [S2]Issue: DVT1B, NqTL1Q0095, fail to open every camera Clue: No data read from A+G sensor in CQA test Root cause: 1. Camera software combines A+G sensor in its algorithm, if sensor is inactive, camera will fail to be launched. 2.Question:Why A+G Failed? persist.img data have been erased, sensor can't download their parameter and stop starting. Reflash persist make sensors all work normally | link | 小熊 | 邦邦 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: Phone drop call after ESD Clue: 1. +8KV air discharge at zone 12(Aging 10),Dropped call.(4/15.14:25-14:35)(In a call) 2. zone12 is bottom side of battery door. Root cause: Unreproduciable after 200 times +-15kV AD, with phone keypad hidden Unreproduciable in DVT1B 2nd EDU03 test, WH115370 |  | 吉吉 |  |  | 6.No Change | 3.Quattro
2019-04-17 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue: System stucked after ESD Clue: 1. +8KV air discharge at zone 11(Aging 10),Picture jammed,press the power key 10s times later power off,press the power key to reboot recovered.(4/15 10:55-11:05)(Rear camera(and Rear flash) is ON ) 2. Zone 11 is the right side of battery door. Root cause: Unreporducible after 200 times +-15kV AD Unreproduciable in DVT1B 2nd EDU03 test, WH115370 |  | 吉吉 |  |  | 6.No Change | 3.Quattro
2019-04-10 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S2]Issue: DVT1B +8KV air discharge at zone 10(Aging 6),Drop call,picture jammed,restart cannot be recovered, Re-pair Bluetooth headset recovery Clue: 1. zone 10 includes cap sensor ant, div ant and bluetooth ant. 2. From DVT1A to DVT1B, bluetooth ant's GND inductor(2.7nH) is removed. 3. Another new unit could reproduce this issue. Root cause: SW Issue, IKSWP-79280 |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-24 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:DVT1B Display go black when calling with DVT1B ，7 pcs Root cause:1.P-sensor Rubber change in DVT1B Exp:Temp parameter check ok by 4/4 ,Done Solution: 1.Provide BAT to update new Parameter. 2.SW ready by 4/8 PPH29.9 Lesson learn : need to follow up Change impact .P-sensor Rubber change impact Factory build and TCC test ，when the change was confirmed need to change SW in time for them .（for User too） | link | 小熊 | 文亭 |  | 4.Parameter | 3.Quattro
2019-04-05 | 5.DVT1 | 5.Camera | 5.4 ALT | S3 | Closed | Issue:Quattro DVT1A FVC L1A MXC06（WH114507）D3, alt camera no flash RootCause:Proposal: Proposal:1.48M （rear main camera）Connector Release， Lead to CQA rear 1 viewfinder torch on flash ledTest Failure 软件逻辑上用camera id识别camera关系，48M的camera id正常为0，连接器松动，初始化失败，id 0被分配给其他的Camera。所以在rear 1 viewfinder torchon中看到的是其他camera的图像。 经验证，该机器flash LED自身功能正常。 2.Why Connetor Loose？ Solution: 1.ME Own |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-24 | 5.DVT1 | 5.Camera | 5.2 BB Test | NA | Closed | [S3]Issue:Quattro DVDD Ripple when work，（哪个camera？什么情况下面出现） Root cause:Camera Current Drain Solution: DVT2A Reserve 1 LDO. | link | 邦邦 |  |  | 1.SCH | 3.Quattro
2019-03-24 | 5.DVT1 | 12.EMC | 5.4 ALT | S3 | Closed | [S3]Issue:The video was stucked(Picture jammed) during ESD testing Root cause: 1. SW bug(IKSWP-73588) Solution: SW version update |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-25 | 5.DVT1 | 6.Display/Touch | 5.2 BB Test | S2 | Closed | [S2]Issue: DVT1A Tianma Display Flicker found under gray Scale. Root Cause: 1.Tianma Display can't endure 5mV dynamic ripple of ELVDD. 2.ELVDD Power Ripple 5mV when Power Mode Switching on non PSRR mode. Solution:1.SW set 0xde70 register to 0x80,force ELVDD circuit work at boost only mode. | Link | 敏敏 | 院长 |  | 4.Parameter | 3.Quattro
2019-03-20 | 5.DVT1 | 2.Power | 5.4 ALT | S3 | Closed | [S3]Issue: DVTA ALT WH114449 A1 ，Auto power off 1time in loop3(1 in 12) clue: 1.after Loop4 ，it always power off after drop 2.Press Top PM6150 Shielding case ，Reproduce case 3.remove rear housing ，reproduce （so it is PCBA issue） 4. remove PM6150A Shielding case ，Reproduce 5.remove PM6150 Shielding case ，can not power on 6. this ALT units were built with temp shielding case ，which can not protect PCBA well. 7.Measure power (primary power Vreg_BOB=0V ,So PM6150A do not work completely ) Root Cause: 1.U2400 PM6150A Solder Crack Found , Confirmed by MDU44 2.Temp shielding case have weak protection Solution： 1. Update New shielding Case , 2nd ALT Test good , Mdu44 for double check pass too 2. Backup solution:underfill for DVT1B 2nd ALT&tumbler ---linfenga | link | 文亭 | 敏敏 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-19 | 5.DVT1 | 1.Platform | 5.4 ALT | S3 | Closed | [S3]Issue: DVT1A Not turn on after tumbler test WH114467,D1&D2 （2 in 5） Clue: 1.D1 &D2 Power on current 110~130mA ,can go into 9008 mode with V+ key,but can not download. (should be memory issue) 2.found Shield case is too weak ,and more than 25% unsolder 3. D 1 press U1600 then can turn on Root Cause: 1.U1600 Memory Solder Crack due to Tumbling, Confirmed by Mdu44 2.Temp shielding case have weak protection Solution: 1. Update New shielding Case , 2nd tumbler test(With correct shielding case) pass 2. Backup solution:underfill for DVT1B 2nd ALT&tumbler ---linfenga | link | 文亭 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-19 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: Front camera preview fixed after ESD test. Recovered after reopen camera app. Root cause: 1.No GND for front camera 2.After grounding, issue not reproduce. Solution: Add Grounding area. After enhancing GND, this issue is not reproducible in DVT1A 2nd ESD test. |  | 吉吉 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-19 | 5.DVT1 | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue: P sensor no function after ESD test. Recovered after reboot. Root cause: 1. Air gap around P sensor IC. Solution: 1. need SW recovery ,Tracking 2. ESD recovery works well in WH115318 |  | 吉吉 | 小熊 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-18 | 5.DVT1 | 7.Sensor | 4.Build | S3 | Closed | [S3]Issue:P-sensor no function Clue: Root Cause: Rubber skewed ME will be in charge of this issue. |  | 小熊 |  | link | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-01-09 | 3.PEL | 1.Platform | 3.Review/Simulation | S3 | Closed | [na]Simulation:High Strain on BGA4 0.43%,BGA3 0.58%（pixworks&Audio codec ） Root Cause: 1.PCB Strain 2.Drop Crash Solution:1.Monitor DVT1 ALT ， Red-Dye Data & tumbler test result 2.Reserved DVT1B underfill ，need to check how to build DVT1B | here | 林峰 |  | Simulation | 6.No Change | 3.Quattro
2019-03-01 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [s3]DP over Usb-c didn't work on AR Prototype of nReal（若太科技） Clue:1.Work on DP Display RootCause: 1.USB SS&DP Coexistance Config? Exp:Get USB+DP Hub to verify the co-existance 2.Not Fit with This AR(Need Customization) |  | 芳梅 | 邦邦 |  | 6.No Change | 3.Quattro
2019-03-20 | 5.DVT1 | 10.USB-C | 4.Build | S3 | Closed | [S3]Issue: DVTA Factory IF 9008 and fastboot mode can not get USB3.0 clue:it is ok when board Power on Root Cause:Switch power L7C not turn yet in Fastboot mode and 9008 . Plan: 9008 mode ：not support USB 3.0 on Quattro Fastboot mode ：SW issue ,Yuecai solve it at 3/21 ,will submit into DVT1B SW by 3/26 |  | 邦邦 | 文亭 |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-03-18 | 5.DVT1 | 6.Display/Touch | 5.4 ALT | S3 | Closed | [S3]Issue:No Main display after Shaker right (WH114449 B3 loop1) Clue: Root Cause: 1. can't turn on caused by side-key FPC Dome invalid. ME will be in charge of this issue. |  | 芳梅 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-02-27 | 4.EVT | 6.Display/Touch | 5.2 BB Test | S3 | Closed | [S3]Issue:Display blink some time ，Worse with Adaptor FPC Clue: change mipi 1.09 G from 1.14G ,improved . but fail too with Adaptor FPC Root Cause: Pw8368 insertion loss 1.EMI filter impact? Exp1:Replace EMI with 0R Resistor 2/28 No improvement 2. Pixelworks Insertion Loss? Exp2-1:works under normal mode is ok with Adaptor FPC, but the hardware bypass mode fail. 2/28 Exp2-2: Compare the mipi signal Waveforms，hardware bypass mode is much worse than normal mode 3/1 Exp2-3: mipi Impedance in the px8368wm =100 ± 20%Ohm, but the mainboard PCB and display panel mipi = 85 ± 20%Ohm Exp2-4: Pixelworks Vendor can't putout the Insertion loss data Exp2-5: Compare the MIPI waveforms before and after Pw8368, the loss makes the MIPI quality bad 3.SW Configuration on MIPI Signal Integraty, Exp3-1:.MIPI Drive Strength Increase to 0xFF(default 0x88) ，no improvement 3/1 Product Team Reject this feature due to MEMC not remarkable |  | 芳梅 |  |  | 1.SCH | 3.Quattro
2019-02-27 | 4.EVT | 12.EMC | 5.2 BB Test | S3 | Closed | [S3]Issue：Board ESD Evaluation Display easy to go dark Clue: The system is well functioned. Root Cause: 1. No ESD recover strategy in current SW version. 2. No TE signal after screen blanked. Panel IC died. Solution: Pixelworks FAE may provide ESD recover version if possible. Product Team Reject Pixel Work due to MEMC not Remarkable. No this issue in DVT1A PCBA, but need to sheild JTAG connector. |  | 吉吉 |  |  | 1.SCH | 3.Quattro
2019-02-27 | 4.EVT | 10.USB-C | 5.1 Bring up | S3 | Closed | [S3]Issue：USB 3.0 SS ，flip test fail ( 1 side can work ) RootCause: SW Config Solution:SW re-Config |  | 邦邦 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2019-05-16 | 7.DVT2 | 3.Charging | 4.Build | S3 | Closed | [S2]Issue: 40℃高温关机充电4 hours，充入电量未达标准3.9V Clue1:从log分析，高温充电下，充电thermal机制启动，充电电流降到300mA，Quattro 电池4000mAh，电量大，充电速度太低无法满足需求. Clue2:thermal config 调整，最低充电电流提到700mA，自测Pass，实验室测试临界pass，与预期不符，从log分析，充电误进USB模式，导致充电电流只有500mA Clue3：经过实验室压力测试，关机状态下，常温或高温下，都有概率会进入USB模式，开机不会 出现fail的概率和USB cable线插入的速度有关，慢速插入时复现概率高 Clue4：测量fail时出现的波形，关机下，系统先进bootloader，再进kernel，初始化完成后，亮屏充电，发现在bootloader下做充电状态识别时，会有异常波形出现，导致无法进入BC1.2之后的QC3.0协议，在后续的kernel mode 继续以异常的状态持续充电 Root Cause: 1.bootloader模式下，充电状态识别容易出现异常（尤其是慢速插入时），而开机状态，充电识别初始化在kernel层完成，在kernel层的充电识别初始化，未发现问题 2.Proposal:Moto Bootloader solution： 在进入Kernel后重新做一次充电状态识别，可以有效排除慢插的影响，确保系统识别正确的充电类型 经多次压力测试，OK | here | 林峰 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 3.Quattro
2017-12-21 | C.RAMP | 12.EMC | 5.6 User Feedback | S1 | Closed | [S1]Issue：SPK Degrade Clue:1. Root Cause:1.Cause by ESD? Solution&Verification: Plan: FuPan: |  | Yangwla |  |  | 6.No Change | 0.Andy NA
2017-04-24 | C.RAMP | 12.EMC | 5.4 ALT | NA | Closed | [NA] OK2Pilot ESD Fail,SPK Noise Issue:ESD Fail on Zone1 -15KV on Alt ,1/2. Root Cause:Find that Conduct Foam Grounding not good ,100Ω，out of spec 3Ω Solution:Press Conduct Foam on FPC to ensure the grounding，and then Assembly on back Housing. Verificaion: Verify ESD 4 pcs on 4/27：WH100063-Pass Research 1:Further Diving on Bead Effect -yangwla Research 2:ESD TVS Part Near by Contact Pin Research - yangwla | here | Yangwla |  |  | 3.BOM | 0.Andy NA
2017-03-22 | 7.DVT2 | 11.Thermal | 5.5 Certification | NA | Closed | [NA]Issue:TMO Thermal Pre-Test Fail ,Gap 5°C Root Cause:Can't Meet TMO Standard Solution: Waiver With TMO Plan: 1.TAM Dialog with TMO on this case by TBD | here | Liguoa |  |  | 6.No Change | 0.Andy NA
2017-04-13 | B.PVT | 12.EMC | 5.5 Certification | S3 | Closed | [S3]Issue:Sku2 EUT with second source Charger,CE 301489 RE test has 2.1dB margin,FCC 15B RE has >3dB margin Root Cause:Andy NA EUT Dvt2 A ,Assemble parts mix with first and second source,impact the RE Level Solution:Use the First source assemble parts Plan: Andy NA EUT must guarantee that has no Mix and Match of the first and second source of assemble parts | here | Yangwla |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 0.Andy NA
2017-02-27 | 7.DVT2 | 7.Sensor | 5.4 ALT | S3 | Closed | [S3] Sensor No Function found in ALT . Issue: Andy NA DVT2B Alt 2pcs fail:Sensor no Function Root Cause: P-Sensor Solder Short between IC & interposer board Solution:PE Lead (eminent change SMT line which with SPI ) Plan:PVT SKU2&3 use new samples for control run . | here | Chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 0.Andy NA
2017-02-17 | 7.DVT2 | 12.EMC | 5.3 EE DVT | NA | Closed | After +15KV discharged at zone9(camera&flash&MIC2),Mic 2 no function:C2 | here | Yangwla |  |  | 2.PCB | 0.Andy NA
2016-01-03 | 5.DVT1 | 12.EMC | 5.3 EE DVT | NA | Closed | [S1] ESD Fail,SPK Degrade Issue:ESD Fail on Zone1 -15KV on Alt ,1/2. | here | Yangwla |  |  | 1.SCH | 0.Andy NA
2016-01-05 | 5.DVT1 | 7.Sensor | 5.3 EE DVT | NA | Closed | P - sensor anti-fog test, at the same time arranged SKU1 and SKU3 SKU1 fail, but SKU3 pass | here | huangls |  |  | 4.Parameter | 0.Andy NA
2016-12-29 | 5.DVT1 | 8.PCB | 5.4 ALT | NA | Closed | ALT/AT&T -Boot up Failed | here | Liguoa |  |  | 2.PCB | 0.Andy NA
2017-01-23 | 5.DVT1 | 12.EMC | 5.5 Certification | NA | Closed | Andy CE Certification RE Test Failed | here | yangwla |  |  | 3.BOM | 0.Andy NA
2017-01-11 | 5.DVT1 | 3.Charging | 5.2 BB Test | NA | Closed | Bad 5W（1A)） charger issue. change SW and pass | here | wuxm5/Chenwt |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | 0.Andy NA
2016-11-22 | 4.EVT | 12.EMC | 5.2 BB Test | NA | Closed | Issue:RF Buzz Noise Condition:NS Cancel ，Mic_GND Connect to Pmic_GND Result: -46dBV/-48dBV | here | Xiaozh1 |  |  | 2.PCB | 0.Andy NA
2016-11-29 | 4.EVT | 12.EMC | 5.2 BB Test | NA | Closed | EVT ESD Fail,P-Sensor No Function | here | yangwla |  |  | 2.PCB | 0.Andy NA
2016-11-29 | 4.EVT | 12.EMC | 5.3 EE DVT | NA | Closed | Andy EVT Edu14 surge Failed | here | Xiaozh1 |  |  | 1.SCH | 0.Andy NA
2017-05-31 | B.PVT |  | 4.ALT/DVT | S3 | Closed | [S3]Issue:psensor no function in ALT loop5 -Chenwt RootCause: PAD crack were found on Both PCB & Module .There may be some crash during assembling since silicon rubber case assembled well and no obvious deformation observed. Solution: Monitor to see if it happened twicely. | here | chenwt/Lvgl |  |  |  | 0.George NA
2017-05-31 | B.PVT |  | 4.ALT/DVT | NA | Closed | [S2] DVT2b ESD Fail,Headset Pop Noise Issue:ESD Fail on Zone15, PVTA&PVTBEval Pass Root Cause:1.Codec Damaged by ESD through SPK Solution:1.Move TVS closed to Signal Pin Plan: Update ESD Design Rule with high priority -yangwla | here | yangwla |  |  |  | 0.George NA
2017-05-20 | 7.DVT2 |  | 4.ALT/DVT | S2 | Closed | [S2] DVT2b ESD Fail,SPK Noise Issue:ESD Fail on Zone1, PVTA Eval Pass but PVTB Re-Test Fail 1/4. Root Cause:1.Codec Damaged by ESD through SPK Solution:1.Add 2 TVS on SPK Channel 2.Switch Semtech Part nearby contact Pin with will part ,Eval 4 pcs with Pressure Test Pass Verificaion: Verify ESD 4 pcs on 6/1 ,Pass | here | yangwla |  |  |  | 0.George NA
2017-04-28 | 7.DVT2 |  | 2.Build | NA | Closed | [NA]Issue: Cap Sensor Detection Partially Fail on BT Root Cause: 1.No update issue belongs to CQA Software Issue .2 No output issue need to furtherly Analysis Solution: Update Cap Sensor Configure Data Avoiding Trensient Response Pending Verification:Pass | here | xiongsn1 |  |  |  | 0.George NA
2017-04-28 | 7.DVT2 |  | 5.Certification | S3 | Closed | [S3] Issue:EN301489 ESD Failed on Data Link(Phone to PC) -Yangwla Root Cause: PC Side USB Module Affected. Cable shielding Issue.Andriod big version update on usb Data transformation which cause the data verification capability S3 down and the procedure easily affected by ESD. Solution: 1. Improve Cable Shielding ,Cert Pass | here | yangwla |  |  |  | 0.George NA
2017-04-20 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] George NA DVT2A MDu30 Thermal Test,game+charge,Front side 44.2℃ VS 42℃ Issue: Pass B standard(45℃） but fail in A standard（42℃），quality update a stricter request and block it. Root Cause: cost down solution cause 1℃ up （42.9℃ DVT1B），and charge current mitigation not available for DVT2A test (44.2℃） Solution: update SW mitigation solution by controlling charging current. Plan: Self test pass，and submit to test on 4/26，test result will output on 4/28 | here | Linfenga |  |  |  | 0.George NA
2017-04-20 | 7.DVT2 |  | 4.ALT/DVT | S3 | Closed | [S3] George NA DVT2A XM99620 1pcs(Loop5) no turn on Issue: no turn on Root Cause: PM8940 U1205 Joint Crack by Strain, Solution: Under Fill U1205 Verification: Pass | here | chenwt |  |  |  | 0.George NA
2017-04-19 | 7.DVT2 |  | 4.ALT/DVT | S3 | Closed | [S1] after ALT(for EDU06) ( loop3 1pcs D2,Loop5 1pcs D10) No signal Issue: LTE No Camp Root Cause: U5500&U5600 Solder Crack Solution: 1.Glue U5500&U5600 2. Single strech Shielding Case Plan: https://docs.google.com/spreadsheets/d/11us2BUCEQluIthHAMDMPdh_TdoCEyoipaotpBndCfr8/edit#gid=0 | here | chenwt |  |  |  | 0.George NA
2017-04-17 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] Can not power on after ALT(for EDU06) ( loop4 TH/TC done ) D7 Issue: VPH_PWR short to GND. C2110 component issue. remove it and the phone ok. Root Cause: PE lead the fail analysis Solution: PE lead Plan: TBD | here | chenwt |  |  |  | 0.George NA
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Issue:ALT DTF test ,3*Loop5 ，1 pcs no power on Analysis/RootCause:From cross-selection Analysis,U1205(pm8940) had cracked on the board side of solder joints Solution/Verificaiton:ALT and tumbler test were pass until now. Plan:FolS3 up the next ALT and tumbler test,if the same failure happen, add underfil is the available backup solution. | here | Linfenga |  |  |  | 0.George NA
2017-03-25 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Thermal materials cost down solutions risk Issue:Decrease half size of copper could cost down ￥0.2，the temperature should rise 0.5-1℃； Analysis/RootCause: LTE Data call(15dB） fail，RF correct the measure method after align with TCC because the wrong measure method cause big different data between DVT1A and DVT1B. Solution：the retest result was pass after update measure，and the cost down solutions could been accepted. Plan: DVT2A had imported the cost down solution which could save $0.27. | Link | Linfenga |  |  |  | 0.George NA
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Red Dye test After ALT, Found MCP functional solder had partial crack but function was ok Verification:ALT and tumbler test were pass until now. Follow up the next ALT and tumbler test,if the same failure happen, add underfil is the available backup solution. | here | Linfenga |  |  |  | 0.George NA
2017-04-17 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] MSM_therm not correct (EDU08) Issue: MSM_therm too S1t . more than CPU Root Cause: R1208 not mount Solution: R1208 change to 0R from DNP Plan: change From DVT2B ,done. Retest with rework units by chenwei ,ongoing.WH99980 ,pass | here | chenwt |  |  |  | 0.George NA
2017-04-13 | 7.DVT2 |  | 4.ALT/DVT | NA | Closed | [NA] LCD damaged Flickering after ALT ESD here Issue:1/2sets Zone 3: air discharge -15KV fourth times, top display flickering, and can not recover.LCD damage. Root Cause: housing resistance, the value is 21.6ohm, while spec should less than 1ohm.ME checked that this lot housing resistance abnormal while in the process Solution: OK housing lead in. And built in DVT2A Golden units and latest Black units. Plan: ESD test will be done in XM99841(golden,4/16) and XM99784 (black,4/20) update:XM99841 Pass and XM99784 Pass | here | pengsp/chenwt |  |  |  | 0.George NA
2017-03-15 | 5.DVT1 |  | 2.Build | NA | Closed |  | here | chenwt |  |  |  | 0.George NA
2017-03-07 | 5.DVT1 |  | 4.ALT/DVT | NA | Closed | [NA]Thermal DVT1a failed Issue:1.WCDMA Voice Call 1.2 °C while no charging 2.Wifi Stream (Front 0.9°C ，Back 1.2°C) while charging ,here Solution：1.Decrease PA Power 2.Charging Rhythm Modification Verification：Dvt1b Pass | here | Linfenga |  |  |  | 0.George NA
2017-03-15 | 5.DVT1 |  | 2.Build | NA | Closed | [NA]Isuse:sensor Vision test limit need update Solution:Delta limit need to change from 580 to 300( refer to Andy),and folS3 up DVT2A test DVT2A check ok ，close | here | chenwt |  |  |  | 0.George NA
2017-03-07 | 5.DVT1 |  | 3.BB Test | NA | Closed | Cap sensor noise Place Cap Sensor IC as Closed as Possible to Sensor PAD,Shielding Sensor Line Ant had confirmed performance is ok . DVT1B PCB change：Place Cap Sensor IC as Closed as Possible to Sensor PAD,Shielding Sensor Line | here | Linfenga |  |  |  | 0.George NA
2017-01-16 | 4.EVT |  | 3.BB Test | NA | Closed | discharge on low voltage battery the sample don't charging on low voltage battery，but normal voltage battery is ok sw problem,charge is ok after sw update charge is ok after sw update |  | wuxm5 |  |  |  | 0.George NA
2017-01-16 | 4.EVT |  | 4.ALT/DVT | NA | Closed | ALT issue: After loop2 post drop inspection, phone heat up: B2 1.off current more than 500mA 2.EOS problem.Not happened then in the next ALT test. | here | chenwei24 |  |  |  | 0.George NA
2017-01-13 | 4.EVT |  | 2.Build | NA | Closed | Board Test Issue:2 PCS Board Fail 1.Vr1421 TVS damaged;（0.5mA current increase） EOS damage from FA report of vendor: 2.U1205 PM8940 chipset damaged;(MPP2 pin damage) 3.Not happened then in DVT1 build need vendor analysis report. | here | FAE |  |  |  | 0.George NA
行 | 值 | [10 empty] | #N/A
| 列 | [10 empty] | #N/A
行 | 值 | [10 empty] | #N/A
Issue Count @Change=SCH/PCB/BOM/Parameter | [11 empty] | #N/A
| 列 | [10 empty] | #N/A
行 | 值 | [10 empty] | #N/A
2022-08-15 | C.RAMP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [s3]Issue: DFer Report 2 units black screen for 1s observed and recovered , 1 or 2 times each day when use whats app browser. Clue:1.No relative black screen issue found in edu04 during 3T test. Clue:2.ESD Test on failed unit, 12kV 500 times and 15kV 500 times Clue:3.Check all DFers to see if any other same issue. Result:no extra found Clue:4. Increase issue reproduce rate. Root Cause: 1.ESD Recovery Triggered duo to read operation error when Check Display Reg each 8s. Exp 1.1 Check Log , Result: DSI Error Notified . Exp 1.2:Check Host Status. Result:read operation the status is 0x13(0001 0011), BTA_BUSY, DSI host side didn’t receive the BTA from the panel side , Conclusion:Display may in suspend mode. 2.Read operation error duo to Display driver mipi in Suspend mode Exp 2.1: Remove ESD Recovery Code and reproduced. Result:Display Freezed, no dsi error found, no black screen observed. Exp 2.1.1: Only Reset Display and check if recovery . Result: Drop duo to feasibility Exp 2.1.2:Only Reset Host MIPI to check if not recovery. Result: Display Freeze not recover. Conclusion: Display Suspend Exp 2.2: When Display Freezed, Set brightness of Display through Write operation. Result:No response. Exp 2.3:After 2.2, perform read operation, Result: Dsi error occur,same with exp1.1 Conclusion:Display Suspend Exp 2.4: Press Power Key and Press again to awake. Result: Display Frozen Recovered. Exp 2.5: ESD recovery just reset AP DSI, not reset panel， Result: can’t recovery panel 8/24 conclusion: which shows panel error Exp 2.6: ESD recovery just reset panel, not reset AP Result : wait SW version 8/30 Why Display Driver in suspend mode? 3.1 Display Driver have decode issue with MIPI @220mV . MIPI Compliance Spec:140mV-270mV. Exp:3.4 Fly wire on MIPI Dn/Dp，Result:Not reproducable. Exp:3.5 Set MIPI HS Voltage to 0X88. 220mV -> 180mV . Result:Not reproduce in Brazil . Exp 3.1: Check working status of display driver. Result:drop Exp 3.2:Capture WaveForm in when Display Reset Triggered. Result:No reproduced for both unit Exp 3.3:ABA Test. Result:Send Reproducible Unit to XiaMen ,can't reproduce once. 3.2 Proposal:Bus control Conflict lead to Display Suspend?- Drop duo to not relative. Exp:Extend TA get time for 5 clk to 10 clk and verify . Result: Drop duo to not relative. 3.3 Maximum WIFI Power and check. Result: Not reproduced on fly wired unit. 3.4 BTB Connector Check ,Result: No connector issue observed. 3.5 Display Driver Instruction Explanation error? Exp 3.5.1: Display Driver Instruction Explanation change to LP Mode instead of CMD Mode ,Result:reproduced Exp 3.5.2: Display Driver Instruction Explanation change to HS Mode instead of CMD Mode ,Result:user reject test 3.6 MIPI compliance can’t meet mipi spec? Exp 3.6.1 MIPI Compliance Test. Result:Pass. Exp 3.6.2 Nova FAE test MIPI AC timing include BTA timing on NG Unit, result ： Pass 3.7 Set driver ic MIPI error flag to check MIPI RX/TX state+ MIPI D0P/N fly wires Result:can’t reproduce Why can’t reproduce? Exp3.7.1 MIPI fly wires influence fall time or raise time or other timing？ Exp3.7.2 SW change leads the result? Release version to DF user on 8/26, DF user not yet test 8/30 3.8 Does the MIPI Resistance meet 90±10% Exp 3.8.1 Test NG unit MB & MIPI Res Solution: 1.low down MIPI driver strength ,0X66. | LINK | 芳梅 |  |  |  | C.Miami
2022-07-15 | B.PVT | 12.EMC | 6.Issue | NA | NA | Issue: 6k contact discharge ,flash light unexpected off,recoverd after triggering on/off button again Root Cause:1.FA Solution:1.Accept |  | 韩凯 |  |  |  | C.Miami
2022-06-23 | 7.DVT2 | 4.Audio | 6.Issue | S2 | Closed | Issue: sound become lower on headset mode clue: 1. FAS4480 (audio switch ) change to wrong path switch which connect mic to gnd, gnd to mic. Root cause: 1. PD report typec_accessory_mode 4 when headset is working and that make FSA4480 to switch wrong path. | LInk | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor | C.Miami
2022-08-17 | C.RAMP | 3.Charging | 4.Build | NA | Closed | Issue: Miami Ramp 2 units CQA test wireless charge no function （2pcs in 15000pcs） Clue：1. Facotry ABA analysis check the fail follow U2750（MEP：CPS4019， wireless charge IC ， SC98D48834 ，Vendor： CPS） 2. when test CPS4019 GP2 ( RXN ) with multimeter ，the issue gone Root Cause: suspect when Vbus no power supply， CPS4019 GP2 ( RXN ) detect high and disable CPS4019 output power （normally Vbus no power supply CPS4019 GP2 ( RXN ) should detect low and output power . when Vbus with power supply ，CPS4019 GP2 ( RXN ) should detect high and disable output power） Solution: 1. CQA more unit and monitor . 2. Change FW：change CPS4019 GP2 ( RXN )to pull down 100K when detection and change to ADC mode but not GPIO mode .set high threshold with 0.75 V （with 100ms high debounce）， Low threshold with 0.5V . New SW import form 8/26 | link | 文亭 |  | CR |  | C.Miami
2022-06-22 | 7.DVT2 | 1.Platform | 4.Build | S3 | Closed | [s3]Issue: NIAR220212 CQA test : wireless charge disconnect and connect repeatedly Clue：1. Facotry ABA analysis check the fail follow U2750 （CPS4019 wireless charge IC） 2.after one day this unit report CQA unstable ， wireless out coil ,it fail sometimes . 3.after one more day change a U2750 again ,it show ok now. will change back the 2#fail IC 4 .Jot test pass ,can not cover this fail. Root Cause: action 1. fail IC 1# analysis , Factory will send IC to Vendor at 6/22 SF1148791576550 IC check pass fixture test by CPS. send a phone to recheck IC on our phone.@ 6/28 ,SF1144696625060 action 2. fail unit reproduce in Xiamen ,get tx log and check tx CE timeout ,send this fail unit to Shanghai CPS for further analysis . when CPS4019 Vout output V， RXN_WLC pull to 1.8V(45ms MAX) and close CPS4019 Vout. Solution: 1. action PVT CQA all units and monitor . 2. Change FW to 0xb : close Vout when RXN high over 100ms . Temp FW recheck pass with fail unit. | link | 文亭 |  |  |  | C.Miami
2022-05-14 | 5.DVT1 | 1.Platform | 4.Build | NA | Closed | [s3]Issue: DVT1 some Board IF fail Clue：SW log 手机会在开机阶段，GPIO01会拉低，检测到上键被按到，如果设置了factory mode,会进入fastboot mode的问题 Root Cause: Solution: 1. temp：SW config GPIO01 of PMR735A （V+） 在判断key之前，先把gpio01设置为pull up | link | 文亭 |  |  |  | C.Miami
2022-05-12 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [s3]Issue:WH152361 ,EDU 14 ,D 3 200V fail on Vbat test point Root Cause: 2nd source main charge IC SC89890H .(refor to Rodhe 4G project analysis) Solution: 1. SC89890H IC improve ,sample will ready 6/10 ,DVT2 . will verify in DVT2 2.backup 2 * 0603 10UF 2V capacity on Vbat that can improve it , DNI . Import in DVT2 gerber out.-done | link | 文亭 |  |  |  | C.Miami
2022-05-05 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | [s3]Issue:WH150848 EVT EDU03 Test, D4 Cap-sensor CH3 no function(15KV) Root Cause: ANT C303 short circuit by ESD Solution: 1.ANT 3 add TVS |  | 小熊 | 韩凯 |  |  | C.Miami
2022-04-25 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:TDD Noise Found in EVT Root Cause:1.Reciever Affected by Magnetic Field of GSM-PA Ground Path to two spacing Battery Connectors. 2.1 Two spacing Battery connector duo to charging thermal request Solution: 1.accept the result on 33dBm. 2.backup audio switch design for optimization validation |  | 院长 |  |  |  | C.Miami
2022-04-25 | 4.EVT | 3.Charging | 4.Build | S3 | Closed | [s3] Issue: factory BT fail in 2nd charge IC SC89890H build Clue：1.Factory use SDP port for BT test 2.SDP that need rerun BC1.2 by charge IC(ignore the 1st BC1.2 result） . 3.can not get rerun INT (from Log ). 4.waveform test checked there is not rerun BC1.2 waveform most time. link 5.waveform test checked there is 1 int after 1st BC1.2 INT sometimes and it can connect to SDP. link Rootcause：suspect SC89890H rerun BC1.2 function need some delay after first BC1.2 INT solution：Delay 100mS after first BC1.2 INT when rerun BC1.2 （Temp SW test pass） | LINK | 文亭 |  |  |  | C.Miami
2022-03-30 | 3.PEL | 4.Audio | 5.1 Bring up | S3 | Closed | [s3] Issue: power off current =8mA .vs 0.2xA target rootcause：Audio switch current leakage solution：change Audio switch power from VPH_PWR to LDO （not on when power off ） | LINK | 院长 |  |  |  | C.Miami
2022-03-30 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，SIM detection can not work Clue： Miami Sub Board is designed based on dubai+ NA Sub。 INT does not need external pull-up resistance on MTK platform, QC platform requires external pull-up resistance. Root Cause: SIM INThas no pull-up resistance Solution: 1.EVB rework sub PCBA is OK. 2. Change MB PCB for EVT. done 3. | link | 李果 |  |  |  | C.Miami
2022-03-30 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，charging type detection can not work Root Cause: USB connection to charging IC incorrect Solution: 1. change PCB for EVT. done 2.EVB rework PCBA for charging related case bringup | link | 文亭 |  |  |  | C.Miami
2022-03-30 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，Wireless charge can not work on power off mode Root Cause: AP GPIO49 pull down FlangN when power off ，cause RXN high to stop wireless charge Solution: 1. add a Nmos on GPIO49 |  | 文亭 |  |  |  | C.Miami
[6 empty] | #REF! | [5 empty] | C.Miami
[6 empty] | #REF! | [5 empty] | C.Miami
[6 empty] | No Highlight Issue | [5 empty] | C.Miami

## Summary Status
Issue Count@Overall
用于“Issue”的 COUNTA | Phase
Project | 1.Concept | 2.PCL | 3.PEL | 4.EVT | 5.DVT1 | 7.DVT2 | B.PVT | C.RAMP | D.SHIP
0.Copperfield |  |  |  |  | 1 | 7 | 2 | 1
1.Shelby |  |  |  | 4 | 21 | 17 | 1 | 2 | 3
2.Stingray | 9 | 3 | 4 | 31 | 29 | 13 | 4 | 3 | 13
4.1.Sofia NA |  | 6 | 7 | 20 | 27 | 4 | 2 |  | 1
5.Nairobi |  |  | 6 | 29 | 30 | 9 | 4 | 1 | 1
6.Tahoe | 1 |  | 1 | 20 | 10 |  | 2 |  | 5
7.Denver |  | 1 |  | 6 | 3 | 2 | 2
8.Sierra |  |  | 4 | 3 | 14 | 5 | 3 | 1 | 1
9.Yukon |  |  |  | 11 | 5 | 8 | 8
A.Milan 5G |  |  | 4 | 9 | 11 | 3 | 1 |  | 1
B.Dubai+ NA |  |  | 4 | 5 | 8 | 10 | 3 | 4 | 1
D.Geneva NA |  |  | 2 | 9 | 3 | 10 | 7 | 4 | 1
E.London NA |  |  |  | 9 | 17 | 7 | 7 | 1 | 1
F.Manaus Row |  |  |  | 4 | 6 | 3 | 3 |  | 1
G.Manaus NA |  |  |  | 2 | 4 | 1 |  | 4
H.Boston |  |  |  | 14 | 7 | 5 | 2 | 2 | 1
J.Wrangler |  |  | 1 | 6 | 9 | 4 | 2 |  | 1
K.Houston |  | 1 |  | 17 | 12 | 7 |  | 1
L.Prado |  |  | 2 | 4 | 9 | 1 | 1 | 1
Issue Count @Change=SCH/PCB/BOM/Parameter
用于“Issue”的 COUNTA | Phase
Project | 1.Concept | 2.PCL | 3.PEL | 4.EVT | 5.DVT1 | 7.DVT2 | B.PVT | C.RAMP
2.Stingray | 2 | 2 |  | 10 | 12 | 3 | 1
4.1.Sofia NA |  | 3 | 4 | 3 | 9 | 1
5.Nairobi |  |  |  | 3 | 10 | 4
7.Denver |  |  |  | 2 | 1
8.Sierra |  |  | 4 |  | 3 | 1
9.Yukon |  |  |  | 7 | 2 |  | 1
A.Milan 5G |  |  | 2 | 2
B.Dubai+ NA |  |  | 1 | 4 | 3 | 2 |  | 1
D.Geneva NA |  |  | 2 | 4 | 1 | 5 | 1
E.London NA |  |  |  | 4 | 5 | 2 | 3
F.Manaus Row |  |  |  | 2 | 2 | 2 | 1
G.Manaus NA |  |  |  |  | 1
H.Boston |  |  |  | 5 | 3 | 2 | 2
J.Wrangler |  |  | 1 | 4 | 2
K.Houston |  |  |  | 3 | 4
L.Prado |  |  | 1 | 3 | 3

## Miami
Report date | Phase | Block | Source | Severity | Status | Issue | Doc | Owner | Assistant | Sheet | Change?
2022-08-15 | C.RAMP | 6.Display/Touch | 5.6 User Feedback | S3 | Closed | [s3]Issue: DFer Report 2 units black screen for 1s observed and recovered , 1 or 2 times each day when use whats app browser. Clue:1.No relative black screen issue found in edu04 during 3T test. Clue:2.ESD Test on failed unit, 12kV 500 times and 15kV 500 times Clue:3.Check all DFers to see if any other same issue. Result:no extra found Clue:4. Increase issue reproduce rate. Root Cause: 1.ESD Recovery Triggered duo to read operation error when Check Display Reg each 8s. Exp 1.1 Check Log , Result: DSI Error Notified . Exp 1.2:Check Host Status. Result:read operation the status is 0x13(0001 0011), BTA_BUSY, DSI host side didn’t receive the BTA from the panel side , Conclusion:Display may in suspend mode. 2.Read operation error duo to Display driver mipi in Suspend mode Exp 2.1: Remove ESD Recovery Code and reproduced. Result:Display Freezed, no dsi error found, no black screen observed. Exp 2.1.1: Only Reset Display and check if recovery . Result: Drop duo to feasibility Exp 2.1.2:Only Reset Host MIPI to check if not recovery. Result: Display Freeze not recover. Conclusion: Display Suspend Exp 2.2: When Display Freezed, Set brightness of Display through Write operation. Result:No response. Exp 2.3:After 2.2, perform read operation, Result: Dsi error occur,same with exp1.1 Conclusion:Display Suspend Exp 2.4: Press Power Key and Press again to awake. Result: Display Frozen Recovered. Exp 2.5: ESD recovery just reset AP DSI, not reset panel， Result: can’t recovery panel 8/24 conclusion: which shows panel error Exp 2.6: ESD recovery just reset panel, not reset AP Result : wait SW version 8/30 Why Display Driver in suspend mode? 3.1 Display Driver have decode issue with MIPI @220mV . MIPI Compliance Spec:140mV-270mV. Exp:3.4 Fly wire on MIPI Dn/Dp，Result:Not reproducable. Exp:3.5 Set MIPI HS Voltage to 0X88. 220mV -> 180mV . Result:Not reproduce in Brazil . Exp 3.1: Check working status of display driver. Result:drop Exp 3.2:Capture WaveForm in when Display Reset Triggered. Result:No reproduced for both unit Exp 3.3:ABA Test. Result:Send Reproducible Unit to XiaMen ,can't reproduce once. 3.2 Proposal:Bus control Conflict lead to Display Suspend?- Drop duo to not relative. Exp:Extend TA get time for 5 clk to 10 clk and verify . Result: Drop duo to not relative. 3.3 Maximum WIFI Power and check. Result: Not reproduced on fly wired unit. 3.4 BTB Connector Check ,Result: No connector issue observed. 3.5 Display Driver Instruction Explanation error? Exp 3.5.1: Display Driver Instruction Explanation change to LP Mode instead of CMD Mode ,Result:reproduced Exp 3.5.2: Display Driver Instruction Explanation change to HS Mode instead of CMD Mode ,Result:user reject test 3.6 MIPI compliance can’t meet mipi spec? Exp 3.6.1 MIPI Compliance Test. Result:Pass. Exp 3.6.2 Nova FAE test MIPI AC timing include BTA timing on NG Unit, result ： Pass 3.7 Set driver ic MIPI error flag to check MIPI RX/TX state+ MIPI D0P/N fly wires Result:can’t reproduce Why can’t reproduce? Exp3.7.1 MIPI fly wires influence fall time or raise time or other timing？ Exp3.7.2 SW change leads the result? Release version to DF user on 8/26, DF user not yet test 8/30 3.8 Does the MIPI Resistance meet 90±10% Exp 3.8.1 Test NG unit MB & MIPI Res Solution: 1.low down MIPI driver strength ,0X66. | LINK | 芳梅
2022-07-15 | B.PVT | 12.EMC | 6.Issue | NA | NA | Issue: 6k contact discharge ,flash light unexpected off,recoverd after triggering on/off button again Root Cause:1.FA Solution:1.Accept |  | 韩凯
2022-06-23 | 7.DVT2 | 4.Audio | 6.Issue | S2 | Closed | Issue: sound become lower on headset mode clue: 1. FAS4480 (audio switch ) change to wrong path switch which connect mic to gnd, gnd to mic. Root cause: 1. PD report typec_accessory_mode 4 when headset is working and that make FSA4480 to switch wrong path. | LInk | 院长 |  |  | 5.SW/ME/RF/ANT/Component/MFG/Vendor
2022-08-17 | C.RAMP | 3.Charging | 4.Build | NA | Closed | Issue: Miami Ramp 2 units CQA test wireless charge no function （2pcs in 15000pcs） Clue：1. Facotry ABA analysis check the fail follow U2750（MEP：CPS4019， wireless charge IC ， SC98D48834 ，Vendor： CPS） 2. when test CPS4019 GP2 ( RXN ) with multimeter ，the issue gone Root Cause: suspect when Vbus no power supply， CPS4019 GP2 ( RXN ) detect high and disable CPS4019 output power （normally Vbus no power supply CPS4019 GP2 ( RXN ) should detect low and output power . when Vbus with power supply ，CPS4019 GP2 ( RXN ) should detect high and disable output power） Solution: 1. CQA more unit and monitor . 2. Change FW：change CPS4019 GP2 ( RXN )to pull down 100K when detection and change to ADC mode but not GPIO mode .set high threshold with 0.75 V （with 100ms high debounce）， Low threshold with 0.5V . New SW import form 8/26 | link | 文亭 |  | CR
2022-06-22 | 7.DVT2 | 1.Platform | 4.Build | S3 | Closed | [s3]Issue: NIAR220212 CQA test : wireless charge disconnect and connect repeatedly Clue：1. Facotry ABA analysis check the fail follow U2750 （CPS4019 wireless charge IC） 2.after one day this unit report CQA unstable ， wireless out coil ,it fail sometimes . 3.after one more day change a U2750 again ,it show ok now. will change back the 2#fail IC 4 .Jot test pass ,can not cover this fail. Root Cause: action 1. fail IC 1# analysis , Factory will send IC to Vendor at 6/22 SF1148791576550 IC check pass fixture test by CPS. send a phone to recheck IC on our phone.@ 6/28 ,SF1144696625060 action 2. fail unit reproduce in Xiamen ,get tx log and check tx CE timeout ,send this fail unit to Shanghai CPS for further analysis . when CPS4019 Vout output V， RXN_WLC pull to 1.8V(45ms MAX) and close CPS4019 Vout. Solution: 1. action PVT CQA all units and monitor . 2. Change FW to 0xb : close Vout when RXN high over 100ms . Temp FW recheck pass with fail unit. | link | 文亭
2022-05-14 | 5.DVT1 | 1.Platform | 4.Build | NA | Closed | [s3]Issue: DVT1 some Board IF fail Clue：SW log 手机会在开机阶段，GPIO01会拉低，检测到上键被按到，如果设置了factory mode,会进入fastboot mode的问题 Root Cause: Solution: 1. temp：SW config GPIO01 of PMR735A （V+） 在判断key之前，先把gpio01设置为pull up | link | 文亭
2022-05-12 | 4.EVT | 3.Charging | 5.3 EE DVT | S3 | Closed | [s3]Issue:WH152361 ,EDU 14 ,D 3 200V fail on Vbat test point Root Cause: 2nd source main charge IC SC89890H .(refor to Rodhe 4G project analysis) Solution: 1. SC89890H IC improve ,sample will ready 6/10 ,DVT2 . will verify in DVT2 2.backup 2 * 0603 10UF 2V capacity on Vbat that can improve it , DNI . Import in DVT2 gerber out.-done | link | 文亭
2022-05-05 | 4.EVT | 7.Sensor | 5.2 BB Test | S3 | Closed | [s3]Issue:WH150848 EVT EDU03 Test, D4 Cap-sensor CH3 no function(15KV) Root Cause: ANT C303 short circuit by ESD Solution: 1.ANT 3 add TVS |  | 小熊 | 韩凯
2022-04-25 | 4.EVT | 4.Audio | 5.2 BB Test | S3 | Closed | [s3]Issue:TDD Noise Found in EVT Root Cause:1.Reciever Affected by Magnetic Field of GSM-PA Ground Path to two spacing Battery Connectors. 2.1 Two spacing Battery connector duo to charging thermal request Solution: 1.accept the result on 33dBm. 2.backup audio switch design for optimization validation |  | 院长
2022-04-25 | 4.EVT | 3.Charging | 4.Build | S3 | Closed | [s3] Issue: factory BT fail in 2nd charge IC SC89890H build Clue：1.Factory use SDP port for BT test 2.SDP that need rerun BC1.2 by charge IC(ignore the 1st BC1.2 result） . 3.can not get rerun INT (from Log ). 4.waveform test checked there is not rerun BC1.2 waveform most time. link 5.waveform test checked there is 1 int after 1st BC1.2 INT sometimes and it can connect to SDP. link Rootcause：suspect SC89890H rerun BC1.2 function need some delay after first BC1.2 INT solution：Delay 100mS after first BC1.2 INT when rerun BC1.2 （Temp SW test pass） | LINK | 文亭
2022-03-30 | 3.PEL | 4.Audio | 5.1 Bring up | S3 | Closed | [s3] Issue: power off current =8mA .vs 0.2xA target rootcause：Audio switch current leakage solution：change Audio switch power from VPH_PWR to LDO （not on when power off ） | LINK | 院长
2022-03-30 | 3.PEL | 1.Platform | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，SIM detection can not work Clue： Miami Sub Board is designed based on dubai+ NA Sub。 INT does not need external pull-up resistance on MTK platform, QC platform requires external pull-up resistance. Root Cause: SIM INThas no pull-up resistance Solution: 1.EVB rework sub PCBA is OK. 2. Change MB PCB for EVT. done 3. | link | 李果
2022-03-30 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，charging type detection can not work Root Cause: USB connection to charging IC incorrect Solution: 1. change PCB for EVT. done 2.EVB rework PCBA for charging related case bringup | link | 文亭
2022-03-30 | 3.PEL | 3.Charging | 5.1 Bring up | S3 | Closed | [s3] Issue: Bringup ，Wireless charge can not work on power off mode Root Cause: AP GPIO49 pull down FlangN when power off ，cause RXN high to stop wireless charge Solution: 1. add a Nmos on GPIO49 |  | 文亭
No Highlight Issue